## Area Wise Spread - DB 2 (hidden)
Number of CEMs | 95
Row Labels | Sum of Total H.P | Sum of Customers According to % (Market Share) | Sum of HP Based on completion - Realistic
Abbottabad | 1864 | 745.6 | 745.6
Gulfam Town_Mera Muzzafar | 450 | 180 | 180
Malikpura | 714 | 285.6 | 285.6
Salhad | 700 | 280 | 280
Abbottabad Ph2 | 1826 | 730.4 | 730.4
Al Mansoor Town Ext. | 440 | 176 | 176
Jhangi Qazian | 420 | 168 | 168
Jhangi Saeedan Extension | 482 | 192.8 | 192.8
Kaghan Colony Extension | 302 | 120.8 | 120.8
Kareenpura Extension | 182 | 72.8 | 72.8
Al Hafeez Garden & Tariq Garden | 5502 | 2200.8
Al Hafeez Garden Ph-5 | 1450 | 580
Al Hafeez Gdn Ph-2 | 1404 | 561.6
Al Raheem Gdn Ph-2 Extn. | 1150 | 460
Tariq Garden | 1498 | 599.2
Al Jalil & Al khalil LHE | 17546 | 7018.4 | 7018.4
Al Hamra | 424 | 169.6 | 169.6
Al Jalil Housing P2 | 2232 | 892.8 | 892.8
Al Jalil Housing P3 | 2210 | 884 | 884
Al Jalil Housing P4 | 2106 | 842.4 | 842.4
Al Kabeer Ph-2-Pk1 | 2268 | 907.2 | 907.2
Al Kabeer Ph-2-Pk2 | 3086 | 1234.4 | 1234.4
Al Kabeer Ph-2-Pk3 | 776 | 310.4 | 310.4
Al Kabeer Town Ph-1 | 512 | 204.8 | 204.8
Central Park Housing-P1 | 1526 | 610.4 | 610.4
Central Park Housing-P2 | 1200 | 480 | 480
Central Park Housing-P3 | 1206 | 482.4 | 482.4
Askari (1-6) Karachi | 19448 | 9724 | 9724
Akari-1 | 320 | 160 | 160
Akari-2 | 240 | 120 | 120
Akari-3 | 970 | 485 | 485
Askari-4 | 1612 | 806 | 806
Askari-5 P1 | 728 | 364 | 364
Askari-5 P2 | 3460 | 1730 | 1730
Askari-5G | 282 | 141 | 141
Askari-5H | 216 | 108 | 108
Askari-5J | 1300 | 650 | 650
Askari-6 Sec 01 | 566 | 283 | 283
Askari-6 Sec 02 | 470 | 235 | 235
Askari-6 Sec 03 | 1040 | 520 | 520
Askari-6 Sec 04 | 936 | 468 | 468
Askari-6 Sec 05 | 540 | 270 | 270
Askari-6 Sec 06 | 1080 | 540 | 540
Askari-6 Sec 07 | 1080 | 540 | 540
Askari-6 Sec 08 | 1224 | 612 | 612
Askari-6 Sec 09 | 1224 | 612 | 612
Askari-6 Sec 10 | 1224 | 612 | 612
Askari-6 Sec 11 | 936 | 468 | 468
Askari Lahore | 11408 | 4563.2 | 4520
Askari-1 | 720 | 288 | 288
Askari-10 P1 | 3018 | 1207.2 | 1207.2
Askari-10 P2 | 1734 | 693.6 | 693.6
Askari-10 Sec-S | 216 | 86.4 | 43.2
Askari-11 P1 | 972 | 388.8 | 388.8
Askari-11 P2 | 1628 | 651.2 | 651.2
Askari-11 P3 | 960 | 384 | 384
Askari-2 | 228 | 91.2 | 91.2
Askari-5 | 1104 | 441.6 | 441.6
Askari-9 | 828 | 331.2 | 331.2
Askari Multan | 980 | 392 | 392
Askari-1 | 182 | 72.8 | 72.8
Askari-2 | 292 | 116.8 | 116.8
Askari-3 | 506 | 202.4 | 202.4
Askari RWP (4-7-10) | 4054 | 1621.6 | 1621.6
Askari-10 | 372 | 148.8 | 148.8
Askari-4 | 864 | 345.6 | 345.6
Askari-7 P1 | 472 | 188.8 | 188.8
Askari-7 P2 | 964 | 385.6 | 385.6
Nazeer Apt. | 54 | 21.6 | 21.6
Willoughby Road appartments | 1328 | 531.2 | 531.2
Askari Sialkot | 772 | 463.2 | 463.2
Askari-I | 272 | 163.2 | 163.2
Askari-II | 500 | 300 | 300
Bahadurabad (KTTC) | 2446 | 978.4 | 978.4
Bahadurabad & Sharfabad | 2446 | 978.4 | 978.4
Bahawalpur | 486 | 243 | 243
Japan Town | 486 | 243 | 243
Bahawalpur (P3) | 3358 | 1343.2 | 1343.2
Asif & Hassan Town | 1740 | 696 | 696
Cheema Town Ph-2 | 700 | 280 | 280
Japan Town | 486 | 194.4 | 194.4
Medical Colony | 432 | 172.8 | 172.8
Bahwalpur (P2)-B | 25116 | 10046.4 | 10046.4
3 Marla Scheme | 1730 | 692 | 692
Alibad_Colony | 278 | 111.2 | 111.2
AlNoor Exct-Haram-Garden Ph-4 | 298 | 119.2 | 119.2
Al-Rahim Garden & Crystal Homes | 484 | 193.6 | 193.6
Anwarabad Colony | 332 | 132.8 | 132.8
Askari | 108 | 43.2 | 43.2
Band Road Extension & Makhdumpu | 2086 | 834.4 | 834.4
Fauji Basti | 1206 | 482.4 | 482.4
Green and Al-hafeez Town | 1886 | 754.4 | 754.4
Habib Colony | 518 | 207.2 | 207.2
Haseeb Town,Fahad Colony & Dila | 3180 | 1272 | 1272
Islamia Colony PK1 | 1158 | 463.2 | 463.2
Islamia Colony PK2 | 2030 | 812 | 812
Islamia Colony PK3 | 1498 | 599.2 | 599.2
Khakwani Colony | 708 | 283.2 | 283.2
Model Town C Extension | 750 | 300 | 300
Mohallah Aam Khass and Noor Sha | 830 | 332 | 332
New_Muslim town | 892 | 356.8 | 356.8
Paragon Ideal Homes | 824 | 329.6 | 329.6
Safari Garden Phase 1 | 204 | 81.6 | 81.6
Safari Garden Phase 2 | 308 | 123.2 | 123.2
Shahdara & Habib Colony | 1746 | 698.4 | 698.4
Small Industrial Estate | 700 | 280 | 280
State and Middle Town | 934 | 373.6 | 373.6
Taha Town | 428 | 171.2 | 171.2
Buffer Zone Khi | 36884 | 11065.2 | 5532.6
P1 | 4492 | 1347.6 | 673.8
P2 | 3760 | 1128 | 564
P3 | 3548 | 1064.4 | 532.2
P4 | 6488 | 1946.4 | 973.2
P5 | 12000 | 3600 | 1800
P6 | 6596 | 1978.8 | 989.4
Chinar Bagh Lahore | 13310 | 5324 | 5324
Chinar_Bagh_P01 | 694 | 277.6 | 277.6
Chinar_Bagh_P02 | 962 | 384.8 | 384.8
Chinar_Bagh_P03 | 898 | 359.2 | 359.2
Eden Lane Villas 2 | 814 | 325.6 | 325.6
Rehman Garden-2 Pk-1 | 2366 | 946.4 | 946.4
Rehman Garden-2 Pk-2 | 1540 | 616 | 616
Rehman Garden-2 Pk-3 | 1118 | 447.2 | 447.2
Rehman Garden-2 Pk-4 | 824 | 329.6 | 329.6
Rehman Garden-2 Pk-5 | 1320 | 528 | 528
Rehman Garden-2 Pk-6 | 984 | 393.6 | 393.6
Rehman Garden-2 Pk-7 | 846 | 338.4 | 338.4
Rehman Garden-2 Pk-8 | 944 | 377.6 | 377.6
Chitral Ph1 | 3832 | 1532.8 | 909.2
Bakarabad & Jughoor | 714 | 285.6 | 285.6
Chitral City | 3118 | 1247.2 | 623.6
CTC Lahore | 3870 | 1548 | 1548
Ali Park & Nadirabad P1 | 1424 | 569.6 | 569.6
Ali Park & Nadirabad P2 | 1512 | 604.8 | 604.8
Gulshan e Ali | 934 | 373.6 | 373.6
Darussalam_LucknowSociety_DadabhoyTown | 3058 | 1223.2
Darussalam Society | 1074 | 429.6
Lucknow Society | 1322 | 528.8
Dadabhoy Town | 662 | 264.8
Daska | 21078 | 8431.2 | 8431.2
Barkat Town | 592 | 236.8 | 236.8
Bhatti Colony | 536 | 214.4 | 214.4
Civil Lines | 598 | 239.2 | 239.2
Faisal_Town | 320 | 128 | 128
Garden Town | 1288 | 515.2 | 515.2
Ghalotian Mor | 456 | 182.4 | 182.4
Gulistan_town | 1100 | 440 | 440
Gulshan Colony | 752 | 300.8 | 300.8
Habibpura | 778 | 311.2 | 311.2
Islampura | 1132 | 452.8 | 452.8
Model Town | 556 | 222.4 | 222.4
Punjab Small Ind. Estate | 196 | 78.4 | 78.4
Qazi Town | 460 | 184 | 184
Rehmanpura | 652 | 260.8 | 260.8
Sambrial_Road | 256 | 102.4 | 102.4
Shahabpura | 946 | 378.4 | 378.4
Unknown Society _ 4 | 528 | 211.2 | 211.2
Unknown Society _ 5 | 288 | 115.2 | 115.2
Unknown Society _3 | 508 | 203.2 | 203.2
Unknown Society 10 | 664 | 265.6 | 265.6
Unknown Society 13 | 362 | 144.8 | 144.8
Unknown Society 14-P1 | 124 | 49.6 | 49.6
Unknown Society 14-P2 | 874 | 349.6 | 349.6
Unknown Society 14-P3 | 462 | 184.8 | 184.8
Unknown Society 14-P4 | 464 | 185.6 | 185.6
Unknown Society 20 | 424 | 169.6 | 169.6
Unknown Society 21 | 128 | 51.2 | 51.2
Unknown Society 9 | 408 | 163.2 | 163.2
Unknown Society_11 | 522 | 208.8 | 208.8
Unknown Society_12 | 244 | 97.6 | 97.6
Unknown Society_22 | 418 | 167.2 | 167.2
Unknown Society_23 | 956 | 382.4 | 382.4
Unkown Society 1 | 300 | 120 | 120
Unkown Society 15 | 246 | 98.4 | 98.4
Unkown Society 16 | 102 | 40.8 | 40.8
Unkown Society 17 | 208 | 83.2 | 83.2
Unkown Society 18 | 154 | 61.6 | 61.6
Unkown Society 19 | 94 | 37.6 | 37.6
Unkown Society 2 | 338 | 135.2 | 135.2
Unkown Society 24 | 66 | 26.4 | 26.4
Unkown Society 6 | 372 | 148.8 | 148.8
Unkown Society 7 | 876 | 350.4 | 350.4
Unkown Society 8 | 330 | 132 | 132
DG Khan | 23218 | 10448.1 | 10448.1
Adam Housing-P1 | 554 | 249.3 | 249.3
Adam Housing-P2 | 428 | 192.6 | 192.6
Al Hussain Garden | 228 | 102.6 | 102.6
Al Inam Gardens | 316 | 142.2 | 142.2
Al Rasool Town | 310 | 139.5 | 139.5
Canal View | 582 | 261.9 | 261.9
CPC Colony | 346 | 155.7 | 155.7
Dream City | 532 | 239.4 | 239.4
Ejaz Town | 690 | 310.5 | 310.5
Garden Town | 488 | 219.6 | 219.6
Gul zameen Colony | 196 | 88.2 | 88.2
Gulberg housing Society | 1166 | 524.7 | 524.7
Indus Smart City | 148 | 66.6 | 66.6
K Gaardens | 360 | 162 | 162
Khayaban e Sarwar | 1110 | 499.5 | 499.5
Khayaban i Abid | 242 | 108.9 | 108.9
Main Area P1 | 3176 | 1429.2 | 1429.2
Main Area P2 | 3656 | 1645.2 | 1645.2
Main Area P3 | 1776 | 799.2 | 799.2
Model Town | 1012 | 455.4 | 455.4
New Defence | 930 | 418.5 | 418.5
New Model Town | 398 | 179.1 | 179.1
NMC Colony 1 | 296 | 133.2 | 133.2
Part of New Defence | 262 | 117.9 | 117.9
Railway Civil Lines P1 | 596 | 268.2 | 268.2
Railway Civil Lines P2 | 570 | 256.5 | 256.5
Royal city | 166 | 74.7 | 74.7
Royal Pearl Enclave | 1768 | 795.6 | 795.6
Sana Valley | 424 | 190.8 | 190.8
Usmania Village | 230 | 103.5 | 103.5
Zam Zam City | 262 | 117.9 | 117.9
DHA Gujranwala | 528 | 264
DHA Sector A ( Villas ) | 528 | 264
DHA KHI - Common Corridor Project | 19009 | 7603.6 | 7603.6
DKTCC (Remaining Areas) | 19009 | 7603.6 | 7603.6
DHA Multan | 9298 | 5578.8 | 5578.8
Additional Cost | 0 | 0 | 0
Block M | 2576 | 1545.6 | 1545.6
Block Q | 2914 | 1748.4 | 1748.4
Block R | 2466 | 1479.6 | 1479.6
DHA Rumanza-P1 | 724 | 434.4 | 434.4
DHA Villas | 618 | 370.8 | 370.8
DHA PH 1-5 | 5458 | 2729 | 2729
DHA PH-4 KK | 1106 | 553 | 553
DHA PH-5 M | 926 | 463 | 463
Ph-1 G & H Block | 930 | 465 | 465
Ph-1 K Block | 252 | 126 | 126
Ph-2 Q Block | 286 | 143 | 143
Ph-2 T Block | 234 | 117 | 117
Ph-3 XX Block | 162 | 81 | 81
Ph-3 Y & Z Block | 700 | 350 | 350
Ph-4 K Commercial | 580 | 290 | 290
Ph-5 K Commercial | 282 | 141 | 141
DHA PH 7-8 | 37684 | 18842 | 18842
PH-7-P1 | 4170 | 2085 | 2085
PH-7-P2 | 3496 | 1748 | 1748
PH-7-P3 | 6980 | 3490 | 3490
PH-7-P5 | 5536 | 2768 | 2768
Ph-8-IVY-P1 | 2918 | 1459 | 1459
Ph-8-IVY-P2 | 3820 | 1910 | 1910
PH-8-P1 | 1992 | 996 | 996
PH-8-P2 | 2412 | 1206 | 1206
PH-8-P3 | 1386 | 693 | 693
PH-8-P4 | 1420 | 710 | 710
PH-8-P5 | 930 | 465 | 465
PH-8-P6 | 842 | 421 | 421
PH-8-P7 | 980 | 490 | 490
PH-8-P8 | 802 | 401 | 401
Faisalabad | 168 | 67.2 | 67.2
Fesco Abdullahpur | 50 | 20 | 20
Fesco Colony 132 KV | 24 | 9.6 | 9.6
NAYAB Colony Directors Residencies | 4 | 1.6 | 1.6
Officers Colony Canal Road | 90 | 36 | 36
Faisalabad Citi Hosuing Extension | 3312 | 1987.2
P4-Citi Housing | 2926 | 1755.6
P1, Extended Part | 386 | 231.6
Faisalabad Misc Areas | 5240 | 2620 | 2620
CITI Housing PH-2_Main | 2620 | 1310 | 1310
Eden Orchards | 1778 | 889 | 889
Kaleem Shaheed Colony-2 | 842 | 421 | 421
Faisalabad Ph4 | 28822 | 11528.8 | 11528.8
Al Barkat Villas | 190 | 76 | 76
Al Rehmat Villa | 228 | 91.2 | 91.2
Bilal City | 170 | 68 | 68
Canal Burg | 206 | 82.4 | 82.4
Canal Garden_Canal Rd | 342 | 136.8 | 136.8
Canal Park | 140 | 56 | 56
CITI Housing D Block | 524 | 209.6 | 209.6
Eden Villas | 1088 | 435.2 | 435.2
FDA City_P1 | 3278 | 1311.2 | 1311.2
FDA City_P2 | 3476 | 1390.4 | 1390.4
FDA City_P3 | 5098 | 2039.2 | 2039.2
Green Village | 60 | 24 | 24
Gulshan e Haram-II | 346 | 138.4 | 138.4
Gulshan e Makkah | 460 | 184 | 184
Haneef Garden | 78 | 31.2 | 31.2
Iqbal Stadium Comm.Area | 106 | 42.4 | 42.4
Jalvi Market | 524 | 209.6 | 209.6
Khy-e-Manzoor | 432 | 172.8 | 172.8
Layllpur Garden | 482 | 192.8 | 192.8
M3-Ind.Estate_P1 | 322 | 128.8 | 128.8
M3-Ind.Estate_P2 | 298 | 119.2 | 119.2
Madina Town | 2346 | 938.4 | 938.4
Meadows_I | 144 | 57.6 | 57.6
Mujahid Town_Ali Town | 334 | 133.6 | 133.6
Naimat Colony | 1434 | 573.6 | 573.6
Nawab City | 350 | 140 | 140
Royal Villas EXT. | 298 | 119.2 | 119.2
Samanabad | 2792 | 1116.8 | 1116.8
Satellite Town | 1610 | 644 | 644
Shehzad Colony | 414 | 165.6 | 165.6
Wapda Town | 710 | 284 | 284
Younas Town | 148 | 59.2 | 59.2
Zuabir Colony | 394 | 157.6 | 157.6
Gujranwala | 970 | 388 | 388
Tariq Garden & Makki Road Area | 970 | 388 | 388
Gujranwala Makki Road | 13348 | 5339.2
PK-01 | 5402 | 2160.8
PK-02 | 7946 | 3178.4
Gujranwala Ph2 | 76772 | 30708.8 | 30708.8
Al mansoorah colony | 492 | 196.8 | 196.8
Aman Society | 96 | 38.4 | 38.4
Aurangzaib Town | 594 | 237.6 | 237.6
Civil Lines | 1248 | 499.2 | 499.2
DC Colony ext.PK_1 | 1230 | 492 | 492
DC Colony ext.PK_2 | 722 | 288.8 | 288.8
G magnolia Remaining Part | 1520 | 608 | 608
Garjakh Road | 3480 | 1392 | 1392
Ghordor Road P1 | 3824 | 1529.6 | 1529.6
Ghordor Road P2 | 4278 | 1711.2 | 1711.2
Ghordor Road P3 | 3376 | 1350.4 | 1350.4
Ghordor Road P4 | 2012 | 804.8 | 804.8
Green Valley Ph-6 | 442 | 176.8 | 176.8
Gulshan Aziz Colony | 388 | 155.2 | 155.2
Hafizabad Road | 4144 | 1657.6 | 1657.6
Jalil Town | 1492 | 596.8 | 596.8
Jinnah Road | 6232 | 2492.8 | 2492.8
Jinnah Road 2 | 3502 | 1400.8 | 1400.8
Kashmir Colony 1 & 2 | 2096 | 838.4 | 838.4
Master Citi Pk-1 | 1678 | 671.2 | 671.2
Master Citi Pk-2 | 3232 | 1292.8 | 1292.8
Master Citi Pk-3 | 2608 | 1043.2 | 1043.2
Nowshehra Road | 3950 | 1580 | 1580
Nowshehra Sansi Road | 2714 | 1085.6 | 1085.6
P1 muslim town | 636 | 254.4 | 254.4
P2 muslim town | 440 | 176 | 176
Qasim Town | 1774 | 709.6 | 709.6
Shalimar Town | 598 | 239.2 | 239.2
Sialkot By Pass | 1586 | 634.4 | 634.4
Sialkot Road | 3022 | 1208.8 | 1208.8
Sui Gas Road Pk1 | 3292 | 1316.8 | 1316.8
Sui Gas Road Pk2 | 1706 | 682.4 | 682.4
University Town | 278 | 111.2 | 111.2
Wafay Citi GG Block | 4322 | 1728.8 | 1728.8
Waffay Block Rem.Area | 3768 | 1507.2 | 1507.2
Gujranwala Ph3 | 44336 | 17734.4 | 17734.4
Ajwa City_P1 | 2202 | 880.8 | 880.8
Ajwa City_P2 | 3046 | 1218.4 | 1218.4
Civil Line Area BOQ | 1728 | 691.2 | 691.2
Civil lines Lower End | 280 | 112 | 112
Disposal Road | 814 | 325.6 | 325.6
Fazal Town | 544 | 217.6 | 217.6
Garden Town_P1 | 2208 | 883.2 | 883.2
Garden Town_P2 | 892 | 356.8 | 356.8
Garden Town_P3 | 1132 | 452.8 | 452.8
Ghorrdo Road | 1276 | 510.4 | 510.4
GT Rd Pocket 06 | 636 | 254.4 | 254.4
GT Rd Pocket 07 | 1006 | 402.4 | 402.4
GT Rd Pocket 08 | 980 | 392 | 392
GT Rd Pocket 09 | 1388 | 555.2 | 555.2
GT Rd Pocket 10 | 1400 | 560 | 560
GT Rd Pocket 11 | 1466 | 586.4 | 586.4
GT Rd Pocket 12 | 1084 | 433.6 | 433.6
Hafizabad Road | 234 | 93.6 | 93.6
Khokhar k_BOQ | 1920 | 768 | 768
Parao Road | 2006 | 802.4 | 802.4
Pasrur Rd & Skt Bypass | 3576 | 1430.4 | 1430.4
SKT Rd Pocket 01 | 1660 | 664 | 664
SKT Rd Pocket 02 | 3386 | 1354.4 | 1354.4
SKT Rd Pocket 03 | 986 | 394.4 | 394.4
SKT Rd Pocket 04 | 750 | 300 | 300
SKT Rd Pocket 05 | 424 | 169.6 | 169.6
Sui Gas Road | 5620 | 2248 | 2248
Tanveer Town & Ratta Rd | 1692 | 676.8 | 676.8
Gulshan-e-Maymar | 9282 | 3712.8 | 3712.8
Sector P, U, V & SPECHS | 1262 | 504.8 | 504.8
Sector Q | 204 | 81.6 | 81.6
Sector R | 1036 | 414.4 | 414.4
Sector S | 172 | 68.8 | 68.8
Sector T | 382 | 152.8 | 152.8
Sector W, ZA & Colonies | 1912 | 764.8 | 764.8
Sector X | 2072 | 828.8 | 828.8
Sector Y | 598 | 239.2 | 239.2
Sector Z | 1644 | 657.6 | 657.6
Hafizabad | 27226 | 12251.7 | 12251.7
Akhtar Town & Tarrar Road | 1390 | 625.5 | 625.5
Al Kareem City | 1606 | 722.7 | 722.7
Alipur Chatta Road Pocket 1 | 666 | 299.7 | 299.7
Alipur Chatta Road Pocket 2 | 1622 | 729.9 | 729.9
Anarkali Bazar | 362 | 162.9 | 162.9
Azam Garden | 446 | 200.7 | 200.7
Canal & Officer & Faisal | 1310 | 589.5 | 589.5
Defence Colony | 996 | 448.2 | 448.2
Gulberg | 210 | 94.5 | 94.5
Hassan Town | 2056 | 925.2 | 925.2
HVTR & MB & POR & JBR | 2656 | 1195.2 | 1195.2
Iqbal Garden | 372 | 167.4 | 167.4
Kassoki Road P1 | 1050 | 472.5 | 472.5
Kassoki Road P2 | 1096 | 493.2 | 493.2
Kot Hashmat 1 & Kot Hashmat 2 | 920 | 414 | 414
Madina Town | 238 | 107.1 | 107.1
Makkah Town & Ali Town | 2248 | 1011.6 | 1011.6
Qazipura_Qadirabad Srndg Area | 806 | 362.7 | 362.7
Sattellite Town | 512 | 230.4 | 230.4
Shalimar_Al Hamra Town | 540 | 243 | 243
Sukheke Hafizabad Road | 2214 | 996.3 | 996.3
Sultan Residencia Park | 464 | 208.8 | 208.8
Sunny Garden | 580 | 261 | 261
Tulip City | 908 | 408.6 | 408.6
Unknown Society 2 & Iqbal Town | 296 | 133.2 | 133.2
Unknown Society 5 | 500 | 225 | 225
Zahoor Orchard | 426 | 191.7 | 191.7
Zahoor Orchard Town | 736 | 331.2 | 331.2
Haripur Hazara | 1744 | 697.6 | 697.6
Makhan_Malikyar_Kalas | 350 | 140 | 140
Roshan_Noor ext._Madina_Uni | 680 | 272 | 272
Sarai Saleh | 714 | 285.6 | 285.6
Haripur Ph2 | 7928 | 3171.2 | 3171.2
Darvesh P1 | 300 | 120 | 120
Darvesh P2 | 684 | 273.6 | 273.6
Gulzar Colony & Main Rd | 424 | 169.6 | 169.6
Kangra Colony P1 | 978 | 391.2 | 391.2
Kangra Colony P2 | 1168 | 467.2 | 467.2
Main KKH & Lari Adda | 782 | 312.8 | 312.8
Model Town | 398 | 159.2 | 159.2
Noor Colony | 846 | 338.4 | 338.4
Pak China Phosphate Colony | 200 | 80 | 80
Roshanabad | 208 | 83.2 | 83.2
T & T Colony | 726 | 290.4 | 290.4
TIP Housing | 1214 | 485.6 | 485.6
Hyderabad | 15510 | 6204 | 5946.36
Abdullah Sports Tower Ext | 96 | 38.4 | 38.4
Barrage Colony | 608 | 243.2 | 243.2
Barrage Officer Colony | 114 | 45.6 | 45.6
Bismillah City & Ext | 1042 | 416.8 | 416.8
Fazal Sun City | 3446 | 1378.4 | 1378.4
Gulshan e Bakhtawar Ext | 502 | 200.8 | 50.2
Hyd Cantt P01 | 190 | 76 | 76
Hyd Cantt P02 | 368 | 147.2 | 147.2
Hyd Cantt P03 | 56 | 22.4 | 22.4
Ink City 02 P01 | 174 | 69.6 | 69.6
Ink City 02 P02 | 90 | 36 | 36
Ink City 02 P03 | 216 | 86.4 | 86.4
Khursheed Town | 300 | 120 | 120
Latifabad No 04 | 888 | 355.2 | 355.2
Latifabad No 09 | 1316 | 526.4 | 526.4
Latifabad No 10 | 1912 | 764.8 | 764.8
Marvi Town & Marvi Garden | 592 | 236.8 | 236.8
MB Shora Colony | 902 | 360.8 | 288.64
New Wahdat Colony | 706 | 282.4 | 282.4
Saima Down Town | 436 | 174.4 | 139.52
Sarfaraz Colony | 242 | 96.8 | 96.8
Site Area & Shanghai Tower | 270 | 108 | 108
SSGC Housing | 370 | 148 | 148
Wapda Colony | 674 | 269.6 | 269.6
Hyderabad Misc Areas | 1692 | 676.8 | 676.8
Fortune Arcade | 46 | 18.4 | 18.4
Indus Society | 212 | 84.8 | 84.8
Palm Village | 1248 | 499.2 | 499.2
Shah Nawaz Grand City | 186 | 74.4 | 74.4
ISB DHA Ph4 | 4120 | 1648 | 1648
DHA Ph-4 P1 | 2138 | 855.2 | 855.2
DHA Ph-4 P2 | 1982 | 792.8 | 792.8
ISB DHA Ph-5 | 4528 | 1811.2 | 1721.92
P1 | 598 | 239.2 | 239.2
P2 | 816 | 326.4 | 326.4
P3 | 1148 | 459.2 | 459.2
P4 | 850 | 340 | 340
P5 | 1116 | 446.4 | 357.12
ISB-BT-Ph-8 | 13642 | 5456.8 | 5456.8
Bahria P10 | 2892 | 1156.8 | 1156.8
Bahria P25 | 1092 | 436.8 | 436.8
Bahria P26 | 2298 | 919.2 | 919.2
Bahria P3 | 994 | 397.6 | 397.6
Bahria P6 | 1910 | 764 | 764
Bahria P8 | 2144 | 857.6 | 857.6
Bahria P9 | 2312 | 924.8 | 924.8
Islamabad | 26612 | 10644.8 | 10165.76
G-11 P1 | 1444 | 577.6 | 577.6
G-11 P2 | 1944 | 777.6 | 777.6
G-11 P3 | 2684 | 1073.6 | 1073.6
G-11 P4 | 3684 | 1473.6 | 1473.6
H13_Mainly Hostels | 908 | 363.2 | 363.2
Mumtaz City P1 | 2016 | 806.4 | 806.4
Mumtaz City P2 | 1100 | 440 | 440
N.Blue Ar. & Other Buildings | 2404 | 961.6 | 961.6
PAF Tarnol-P1 | 1550 | 620 | 372
PAF Tarnol-P2 | 1444 | 577.6 | 346.56
PHA G-11 & I12 | 4674 | 1869.6 | 1869.6
University Town P1 | 1232 | 492.8 | 492.8
University Town P2 | 1528 | 611.2 | 611.2
Islamabad DHA Ph1 | 3300 | 1320 | 1320
DHA_Ph-1_P1 | 930 | 372 | 372
DHA_Ph-1_P2 | 1258 | 503.2 | 503.2
DHA_Ph-1_P3 | 1112 | 444.8 | 444.8
Islamabad Misc Areas | 14990 | 7495 | 7495
CTD_ANF_Police Lines_H11 | 522 | 261 | 261
E-16 | 726 | 363 | 363
Hostel City | 394 | 197 | 197
I-10 P1 | 1220 | 610 | 610
I-10 P2 | 812 | 406 | 406
I-10 P3 | 1192 | 596 | 596
I-10 P4 | 1810 | 905 | 905
I-10 P5 | 2218 | 1109 | 1109
I-11 Aerial | 418 | 209 | 209
I-11P1 | 570 | 285 | 285
I-11P2 | 1504 | 752 | 752
I-9 P1 | 1222 | 611 | 611
I-9 P2 | 794 | 397 | 397
I-9 P3 | 752 | 376 | 376
I-9 P4 | 836 | 418 | 418
Islamabad Ph3 (P2) | 23944 | 9577.6 | 9577.6
B-17 Blk-D extn | 588 | 235.2 | 235.2
B-17 BlockD | 1124 | 449.6 | 449.6
B-17 BlockF-P1 | 1978 | 791.2 | 791.2
B-17 BlockF-P2 | 2512 | 1004.8 | 1004.8
E-17 | 876 | 350.4 | 350.4
Emaar P1 | 324 | 129.6 | 129.6
Emaar P2 | 356 | 142.4 | 142.4
Emaar P3 | 462 | 184.8 | 184.8
Faisal Town P2 | 1516 | 606.4 | 606.4
Faisal Town P3 | 2208 | 883.2 | 883.2
Faisal Town P4 | 1434 | 573.6 | 573.6
FMC_Partial | 3146 | 1258.4 | 1258.4
Hostel City_Extn | 278 | 111.2 | 111.2
I-14-P1 | 1978 | 791.2 | 791.2
I-14-P2 | 1606 | 642.4 | 642.4
I-14-P3 | 1710 | 684 | 684
I-14-P4 | 1848 | 739.2 | 739.2
Jhang | 17360 | 7812 | 7812
Al Karam City Phase 1 | 602 | 270.9 | 270.9
Ali Town | 1610 | 724.5 | 724.5
Chaudary Colony | 1020 | 459 | 459
Civil Lines | 950 | 427.5 | 427.5
Ghaziabad | 2296 | 1033.2 | 1033.2
Gulshan Colony | 1372 | 617.4 | 617.4
Khokar Colony | 244 | 109.8 | 109.8
Lalazar Colony | 532 | 239.4 | 239.4
Madina Colony | 814 | 366.3 | 366.3
Officers Colony | 330 | 148.5 | 148.5
Paradise City | 602 | 270.9 | 270.9
Samanabad | 1302 | 585.9 | 585.9
Satellite Town_PK1 | 1770 | 796.5 | 796.5
Satellite Town_PK2 | 920 | 414 | 414
Satellite Town_PK3 | 746 | 335.7 | 335.7
Shadab Colony | 490 | 220.5 | 220.5
Shah Block | 270 | 121.5 | 121.5
Sultan Colony | 630 | 283.5 | 283.5
Unknown Society 3 | 266 | 119.7 | 119.7
Unknown-1 | 270 | 121.5 | 121.5
Unknown-2 | 324 | 145.8 | 145.8
Jhelum (P4) | 6664 | 2665.6
Bagga | 228 | 91.2
Chitan | 294 | 117.6
Eid Gah | 206 | 82.4
Gharmala | 202 | 80.8
Gujjar pur | 126 | 50.4
Kantrila | 238 | 95.2
Kantrili | 208 | 83.2
Kotli Allahyar | 266 | 106.4
Saeela | 694 | 277.6
Gharmala Monan | 132 | 52.8
Jahangir | 214 | 85.6
Jhakkarr | 448 | 179.2
Chak Hafizan | 168 | 67.2
Chak Doulat | 154 | 61.6
Ranjha Mahira | 532 | 212.8
Muftian | 130 | 52
Chak Akka | 1976 | 790.4
Thatti Gujran & Mughlan | 448 | 179.2
Jhelum- Kala Gojran | 1102 | 440.8 | 440.8
Kala Gujran_P1 | 680 | 272 | 272
Kala Gujran_P2 | 422 | 168.8 | 168.8
Jhelum Ph2 | 4800 | 1920 | 1920
Bagh Mohalla & Naya Mohallla | 1252 | 500.8 | 500.8
Bala Gujjran | 246 | 98.4 | 98.4
Chal Jamal | 312 | 124.8 | 124.8
Citi Housing Block D_E_F Extn. | 1426 | 570.4 | 570.4
Kharala | 640 | 256 | 256
Makhdoomabad | 726 | 290.4 | 290.4
Shamas Pur | 198 | 79.2 | 79.2
Karachi Misc Areas | 6372 | 3186 | 3186
Falaknaz Pebbles | 108 | 54 | 54
FB Area Block-22 | 326 | 163 | 163
Gulshan Block-19 | 768 | 384 | 384
MBCHS | 720 | 360 | 360
Model Colony | 1302 | 651 | 651
Muslim Khatri CHS | 352 | 176 | 176
PIB Colony | 2248 | 1124 | 1124
Soomra Society | 548 | 274 | 274
Karachi Ph5 | 29092 | 11636.8 | 11311.6
AbrazulMinal_KingsBridgeView | 1400 | 560 | 560
AFOHS PK-1 | 984 | 393.6 | 393.6
AFOHS PK-2 | 478 | 191.2 | 191.2
AFOHS PK-3 | 1256 | 502.4 | 502.4
Al Rahim City Ph-1 | 488 | 195.2 | 195.2
Al Rahim City Ph-2 | 480 | 192 | 192
Amynabad | 290 | 116 | 116
Callachi Society | 1626 | 650.4 | 325.2
Chandni Chowk | 1390 | 556 | 556
Custom Preventive CHS | 258 | 103.2 | 103.2
Diamond City_Wasi Country Park | 1154 | 461.6 | 461.6
F.B Area Block-21 | 2160 | 864 | 864
Gulshan Block-4A | 580 | 232 | 232
Khayaban-e-Patni CHS | 212 | 84.8 | 84.8
Kings_ASF_ Tower_P01 | 2016 | 806.4 | 806.4
Kings_ASF_ Tower_P02 | 2016 | 806.4 | 806.4
Kokan CHS | 346 | 138.4 | 138.4
Madras CHS | 734 | 293.6 | 293.6
NIPA Society | 284 | 113.6 | 113.6
Oasis Park Residencia | 346 | 138.4 | 138.4
Pak Ideal CHS P1 | 452 | 180.8 | 180.8
Pak Ideal CHS P2 | 448 | 179.2 | 179.2
PiliBheet Society | 728 | 291.2 | 291.2
Pioneer Fountain_KHI UNI | 262 | 104.8 | 104.8
Redline | 310 | 124 | 124
Sadabad Society | 348 | 139.2 | 139.2
Saima Villas | 1342 | 536.8 | 536.8
Scheme33_MalirCantt_MDU_P01 | 2356 | 942.4 | 942.4
Scheme33_MalirCantt_MDU_P02 | 1320 | 528 | 528
Scheme33_MalirCantt_MDU_P03 | 1238 | 495.2 | 495.2
Scheme33_MalirCantt_MDU_P04 | 1104 | 441.6 | 441.6
Sum Sum Tower | 384 | 153.6 | 153.6
Water Board Society | 120 | 48 | 48
Ya Rehman Society | 182 | 72.8 | 72.8
Kasur | 38704 | 15481.6 | 15481.6
Abdul Khaliq Colony | 82 | 32.8 | 32.8
Ali Ahmed Shah Colony | 712 | 284.8 | 284.8
Al-Kareem Garden | 440 | 176 | 176
Al-Majeed Housing Scheme | 460 | 184 | 184
Azhar Colony Khara Road and Bas | 1660 | 664 | 664
Defence Colony | 632 | 252.8 | 252.8
Dhorr Kot Road & Kot Fateh Din | 2180 | 872 | 872
Gulberg | 1394 | 557.6 | 557.6
Haji Park Bypass | 328 | 131.2 | 131.2
Haji Park Commercial | 114 | 45.6 | 45.6
Haji Park Phase 1 | 390 | 156 | 156
Hamza Town | 204 | 81.6 | 81.6
Ideal Garden Housing | 388 | 155.2 | 155.2
Kasur Raiwand Road | 902 | 360.8 | 360.8
Khara Road | 1968 | 787.2 | 787.2
Khara Road and Nafees Colony | 2524 | 1009.6 | 1009.6
Madina Town | 136 | 54.4 | 54.4
Main Kasur P-1 | 2010 | 804 | 804
Main Kasur P-2 | 3350 | 1340 | 1340
Main Kasur P-3 | 424 | 169.6 | 169.6
Main Kasur P-4 | 1954 | 781.6 | 781.6
Main Kasur P-5 | 1158 | 463.2 | 463.2
Maqbool Town | 126 | 50.4 | 50.4
Munir Shaheed Colony | 682 | 272.8 | 272.8
Mustafa Park | 186 | 74.4 | 74.4
Nadeem Park | 354 | 141.6 | 141.6
New City | 940 | 376 | 376
Officer Colony | 204 | 81.6 | 81.6
Peeru wala Road | 1370 | 548 | 548
Qadirabad , NoorShah Wali and K | 4836 | 1934.4 | 1934.4
Road Kot | 1406 | 562.4 | 562.4
Saeedabad | 2064 | 825.6 | 825.6
Saif City | 376 | 150.4 | 150.4
Saleem Town Ph-1 | 1420 | 568 | 568
Tariq Colony | 1330 | 532 | 532
Khyban-e-Amin, High court & Al Rehman PH4 | 14734 | 5893.6
PK01 | 4706 | 1882.4
PK02 | 938 | 375.2
PK03 | 2990 | 1196
PK04 | 2590 | 1036
PK05 | 1756 | 702.4
High Court Society | 776 | 310.4
Al Rehman Garden 4 | 978 | 391.2
Lahore Misc Areas | 12550 | 6275 | 6275
Al-Hamd Society | 264 | 132 | 132
Al-Raheems Homes | 120 | 60 | 60
BOR | 788 | 394 | 394
Cavalry Ext Aerial | 1792 | 896 | 896
Cavalry Ext Hybrid | 1792 | 896 | 896
Dream Avenue | 506 | 253 | 253
Fazaiya Society P1 | 1470 | 735 | 735
Fazaiya Society P2 | 1492 | 746 | 746
Judicial Colony Ph 2 | 466 | 233 | 233
Mansoora | 140 | 70 | 70
Misc. Areas | 400 | 200 | 200
Sultan Town | 494 | 247 | 247
Wafaqi Colony | 2678 | 1339 | 1339
Wocland | 148 | 74 | 74
Lahore Ph5 | 46192 | 18476.8 | 18386
Abid Market | 656 | 262.4 | 262.4
Etihad Town | 2606 | 1042.4 | 1042.4
Ferozpur Road | 2278 | 911.2 | 911.2
Ilyas Colony | 616 | 246.4 | 246.4
Jail Road Bird Wood & Waris Co | 454 | 181.6 | 90.8
Jinnah Colony Aerial | 216 | 86.4 | 86.4
Lawarance Road & China Road | 372 | 148.8 | 148.8
LC_P1 | 1818 | 727.2 | 727.2
LC_P2 | 742 | 296.8 | 296.8
LC_P3 | 790 | 316 | 316
LC_P4 | 828 | 331.2 | 331.2
LC_P5 | 862 | 344.8 | 344.8
LC_P6 | 1176 | 470.4 | 470.4
LC_P7 | 908 | 363.2 | 363.2
LDA_Ph-1 | 1956 | 782.4 | 782.4
LDA_Ph-2 | 1970 | 788 | 788
LDA_Ph-3 | 2082 | 832.8 | 832.8
Mall Road | 820 | 328 | 328
N LHR City P1 | 1940 | 776 | 776
N LHR City P2 | 1560 | 624 | 624
PAEC T.Buried | 1364 | 545.6 | 545.6
Park View_Hybrid_P1 | 1266 | 506.4 | 506.4
Park View_T.B_P2 | 2378 | 951.2 | 951.2
Park View_T.B_P3 | 1510 | 604 | 604
Park View_T.B_P4 | 3186 | 1274.4 | 1274.4
Rehan Gardens Ph 1&2 | 538 | 215.2 | 215.2
Sherwani_Shadab Hsng Scty | 1362 | 544.8 | 544.8
Township_A2_P01 | 1338 | 535.2 | 535.2
Township_A2_P02 | 2004 | 801.6 | 801.6
Township_B1_P01 | 766 | 306.4 | 306.4
Township_B1_P02 | 928 | 371.2 | 371.2
Township_B1_P03 | 1378 | 551.2 | 551.2
Township_B1_P04 | 1354 | 541.6 | 541.6
Township_B2_P01 | 434 | 173.6 | 173.6
Township_B2_P02 | 620 | 248 | 248
Township_C1_BL03 | 558 | 223.2 | 223.2
Township_C2_BL03 | 558 | 223.2 | 223.2
Lalamusa | 14988 | 6744.6 | 6744.6
Darbari, Qureshi Muhallah,Shad | 1678 | 755.1 | 755.1
Dhamah,Lalazar & Railway Colony | 532 | 239.4 | 239.4
Eid Gah, Rehmat Abbas,Kaira Muh | 2802 | 1260.9 | 1260.9
Gunjra Road,Bagh e Syedan & Bud | 1600 | 720 | 720
Karimpura, Hajipura, SabriMuhal | 1876 | 844.2 | 844.2
Mehar Muhallah,Weraowala,Sadiqa | 1454 | 654.3 | 654.3
Syda Gol,Faisalpur,Jogi&Qasbah& | 3950 | 1777.5 | 1777.5
Thirkian,Asghar Town,Ahmad Town | 1096 | 493.2 | 493.2
LHE - DHA Phase 6, EME, Rahbar | 7826 | 3130.4
Rahbr-Sec-1-P1 | 1190 | 476
Rahbr-Sec-1-P2 | 952 | 380.8
Rahbr-Sec-2-P1 | 2848 | 1139.2
Rahbr-Sec-2-P2 | 2836 | 1134.4
Lhr MW City & Al Hafeez Ph-1 | 14370 | 5748
Pocket-1 | 1948 | 779.2
Pocket-2 | 828 | 331.2
Pocket-3 | 2042 | 816.8
Pocket-4 | 2728 | 1091.2
Pocket-5 | 2654 | 1061.6
Pocket-6 | 986 | 394.4
Pocket-7 | 1778 | 711.2
Al Hafeez Garden Ph-1 | 1406 | 562.4
Mandi Bahauddin | 33480 | 15066 | 15066
Al-Rehman, Eiffel, Sultan Town | 1566 | 704.7 | 704.7
Arshad Town and Model Town | 2134 | 960.3 | 960.3
Bangali Town | 750 | 337.5 | 337.5
District Complex, Complex City | 250 | 112.5 | 112.5
Gillani Town,Tariqabad,Sufipura | 3164 | 1423.8 | 1423.8
Gulberg Town | 326 | 146.7 | 146.7
Gurrah Muhallah | 3690 | 1660.5 | 1660.5
Hajipura | 788 | 354.6 | 354.6
Hamza Ali town | 548 | 246.6 | 246.6
Jinnah City | 224 | 100.8 | 100.8
Kachehri Area | 2708 | 1218.6 | 1218.6
Manzoorabad | 412 | 185.4 | 185.4
Paradise Complex | 134 | 60.3 | 60.3
Qila Gujjran, Rehmanpura | 1708 | 768.6 | 768.6
Ranger Colony | 382 | 171.9 | 171.9
Royal Palm City | 312 | 140.4 | 140.4
Sattelite Town | 736 | 331.2 | 331.2
Shalimar City | 562 | 252.9 | 252.9
Sufi City Housing Scheme PK-1 | 1542 | 693.9 | 693.9
Sufi City Housing Scheme PK-2 | 2672 | 1202.4 | 1202.4
Tajpura, Shalimar & Amin Twn | 2636 | 1186.2 | 1186.2
Unkown Area 2 | 1338 | 602.1 | 602.1
Unkown Area 3 | 1152 | 518.4 | 518.4
Unkown Area 4 | 940 | 423 | 423
Unkown Area 6 | 2806 | 1262.7 | 1262.7
Mardan | 2522 | 1008.8 | 1008.8
Bismillah Town | 512 | 204.8 | 204.8
Gulberg Town | 552 | 220.8 | 220.8
Gulshan Town Ph1 | 376 | 150.4 | 150.4
Mohabatabad P1 | 340 | 136 | 136
Mohabatabad P2 | 456 | 182.4 | 182.4
Orchird Villas | 286 | 114.4 | 114.4
Mardan Ph2 | 12994 | 5197.6 | 5197.6
Abdullah Colony & Nawa Killy | 394 | 157.6 | 157.6
Bari Chum | 1134 | 453.6 | 453.6
Bicket Gunj | 654 | 261.6 | 261.6
Cantt | 314 | 125.6 | 125.6
Center Colony | 288 | 115.2 | 115.2
Daman & Kilo Town | 612 | 244.8 | 244.8
Defence Housing | 50 | 20 | 20
Gaju_Khaksar_Shams Gunj | 1262 | 504.8 | 504.8
Green Acres P1 | 966 | 386.4 | 386.4
Green Acres P2 | 500 | 200 | 200
Guli Bagh | 1122 | 448.8 | 448.8
Katcheri Road | 444 | 177.6 | 177.6
Labour Colony | 458 | 183.2 | 183.2
Maqam Mandi | 120 | 48 | 48
Muslimabad | 2262 | 904.8 | 904.8
New Bagh Colony | 524 | 209.6 | 209.6
New Surkh Dheri | 480 | 192 | 192
Pohan Colony | 460 | 184 | 184
Shamsi Rd | 462 | 184.8 | 184.8
Sharifabad | 300 | 120 | 120
VIP Housing | 188 | 75.2 | 75.2
Mingora | 15008 | 6003.2 | 6003.2
Between Fizaghat & Sangota | 62 | 24.8 | 24.8
Airport (Ghanshal village) P01 | 500 | 200 | 200
Ingaroderai-Takhtaband P01 | 2350 | 940 | 940
Ingaroderai-Takhtaband P02 | 1080 | 432 | 432
Ingaroderai-Takhtaband P03 | 946 | 378.4 | 378.4
Kabal P01 | 104 | 41.6 | 41.6
Kabal P02 | 132 | 52.8 | 52.8
Kabal P03 | 422 | 168.8 | 168.8
Kabal P04 | 150 | 60 | 60
Kabal P05 | 508 | 203.2 | 203.2
Kabal P06 | 162 | 64.8 | 64.8
Kabal P07 | 180 | 72 | 72
Kabal P08 | 462 | 184.8 | 184.8
Kabal P09 | 1228 | 491.2 | 491.2
Odigram P01 | 536 | 214.4 | 214.4
Odigram P02 | 1110 | 444 | 444
Odigram P03 | 1086 | 434.4 | 434.4
Odigram P04 | 426 | 170.4 | 170.4
Odigram P05 | 114 | 45.6 | 45.6
Odigram P06 | 764 | 305.6 | 305.6
Shagai & Akhon Baba P01 | 818 | 327.2 | 327.2
Shagai & Akhon Baba P02 | 704 | 281.6 | 281.6
Shia Bagh & BUH Qambar P01 | 714 | 285.6 | 285.6
Shia Bagh & BUH Qambar P02 | 450 | 180 | 180
Model Town_Sh Faisal_Faisal Cant | 29862 | 11944.8
Model Colony | 1302 | 520.8
SHFT Pocket-1 | 658 | 263.2
SHFT Pocket-2 | 1814 | 725.6
SHFT Pocket-3 | 1438 | 575.2
SHFT Pocket-4 | 810 | 324
SHFT Pocket-5 | 1628 | 651.2
TariqBinZayed | 1156 | 462.4
Gulshan-e-Rafi | 712 | 284.8
Salman Gardens | 382 | 152.8
Anwar-e-Ibrahim | 558 | 223.2
Rafi Gardens_Gulshan e Muneer | 890 | 356
M.Ali Shaheed Society_Maaz Town | 596 | 238.4
Punjabi Sodagran Society | 450 | 180
Shamsi Society | 1744 | 697.6
Bilal Town | 2212 | 884.8
Alfalah Society | 1330 | 532
Rafah-e-Aam Society | 834 | 333.6
Hansabad | 528 | 211.2
Bagh-e-Malir | 792 | 316.8
Gulshan-e-Tayyaba | 488 | 195.2
Gohar Green | 1906 | 762.4
Kazimabad | 1154 | 461.6
Surti_Humaira_Jami | 1516 | 606.4
Alamgir&Jannat ul Barkat | 1020 | 408
Pak Kausar Town | 1034 | 413.6
Darakhshan Society PK1 | 222 | 88.8
Darakhshan Society PK2 | 2078 | 831.2
Millat Garden | 610 | 244
Multan Misc. Areas | 29738 | 14869 | 14869
Al Khalil Housing Scheme | 140 | 70 | 70
Allabad, AliTown & IslamPura | 1024 | 512 | 512
AlQuresh Phase 1 | 1366 | 683 | 683
AlQuresh Phase 2 | 1420 | 710 | 710
Aslam, Mujtuba & Canal Colony | 1036 | 518 | 518
Bahadurpur | 1306 | 653 | 653
Bast Shor Kot | 508 | 254 | 254
Bilal Colony & Mukhtyar Town | 1444 | 722 | 722
Bodla Town | 1514 | 757 | 757
Bukhari Villas | 476 | 238 | 238
Canal Cantt Views | 1048 | 524 | 524
Chah Hadi Wala | 384 | 192 | 192
Citi Housing Sector A | 526 | 263 | 263
Citi Housing Sector B | 1082 | 541 | 541
Citi Housing Sector C | 1274 | 637 | 637
Defence Housing Society | 518 | 259 | 259
Defence villas | 272 | 136 | 136
Gulberg & New Gulberg | 1084 | 542 | 542
Gulistan-i-Ashar | 1012 | 506 | 506
Gulraiz Town | 720 | 360 | 360
Gulshan e Faiz | 1328 | 664 | 664
Gulshan e Iqbal | 216 | 108 | 108
Gulshen-i-Sardar | 228 | 114 | 114
Inam City | 148 | 74 | 74
Khan Village II | 454 | 227 | 227
Khayaban e Kubra | 170 | 85 | 85
Lasani Colony | 816 | 408 | 408
Mohsin Town & Rasheed Avenue | 428 | 214 | 214
Muslim Town | 502 | 251 | 251
New Naqshband Colony | 990 | 495 | 495
Qaiserabad | 944 | 472 | 472
Qasim Pur Colony | 996 | 498 | 498
Qasim Villas & Shams Colony | 452 | 226 | 226
Rehman Colony | 334 | 167 | 167
Sadiqabad latifabad Wahidabad | 2080 | 1040 | 1040
Shamsi Colony | 252 | 126 | 126
Unknown 01 | 84 | 42 | 42
Village garden | 148 | 74 | 74
Writers Colony | 574 | 287 | 287
Zakariya Villas | 440 | 220 | 220
Multan Ph3 | 30952 | 12380.8 | 12380.8
Adam Housing | 1130 | 452 | 452
Al Nawab Rehman Villas AlKareem | 1470 | 588 | 588
Ali Town | 1486 | 594.4 | 594.4
Bhutta Colony | 94 | 37.6 | 37.6
Buch Villas Extn. | 464 | 185.6 | 185.6
Canal View Multan | 564 | 225.6 | 225.6
Citi Housing Jinnah Block-P1 | 2128 | 851.2 | 851.2
Citi Housing Jinnah Block-P2 | 2024 | 809.6 | 809.6
Citi Housing Sector D | 1256 | 502.4 | 502.4
Dewan ka Bagh | 1598 | 639.2 | 639.2
Dream Valley | 118 | 47.2 | 47.2
Fatima Jinnah Town A | 940 | 376 | 376
Fatima Jinnah Town B | 1158 | 463.2 | 463.2
Fatima Jinnah Town C | 502 | 200.8 | 200.8
Fatima Jinnah Town D | 1472 | 588.8 | 588.8
Fatima Jinnah Town E | 716 | 286.4 | 286.4
Fatima Jinnah Town F | 928 | 371.2 | 371.2
Fatima Jinnah Town G | 650 | 260 | 260
Fatima Jinnah Town H | 1004 | 401.6 | 401.6
Fatima Jinnah Town J | 572 | 228.8 | 228.8
Green Fort Housing Society | 1094 | 437.6 | 437.6
Gulshan-i-Ghafoor | 108 | 43.2 | 43.2
Gulshen e Yousaf & Stadium | 1684 | 673.6 | 673.6
Ibrahim Garden | 174 | 69.6 | 69.6
Marhaba Canal View | 1078 | 431.2 | 431.2
Multan Golf City | 370 | 148 | 148
Nawab Bhatta Colony | 1050 | 420 | 420
Nayab Grace City | 554 | 221.6 | 221.6
Nayyab City & Extension | 1196 | 478.4 | 478.4
Posh AVenue | 68 | 27.2 | 27.2
Royal Residencia | 614 | 245.6 | 245.6
Sadiqabad latifabad Wahidabad | 2080 | 832 | 832
Sayyam City | 376 | 150.4 | 150.4
Western Fort | 232 | 92.8 | 92.8
Muridky, Kalasha Kako, Shadra | 210804 | 84321.6 | 84321.6
Ajnianwala | 1998 | 799.2 | 799.2
Bahrrian Wala | 698 | 279.2 | 279.2
Chalk no.12 | 1355 | 542 | 542
Feroz Wattowan-i | 1428 | 571.2 | 571.2
Ferozewala | 36000 | 14400 | 14400
Ghang | 1457 | 582.8 | 582.8
Jandiala Sher Khan | 1478 | 591.2 | 591.2
Jatri Kohna | 1428 | 571.2 | 571.2
Kala Shah Kaku | 11500 | 4600 | 4600
Kaloke | 2317 | 926.8 | 926.8
KOT Abdul Malik | 14800 | 5920 | 5920
Kot Sondha | 2463 | 985.2 | 985.2
Kurkle Androon | 573 | 229.2 | 229.2
Lahore Jaranwala Road | 16400 | 6560 | 6560
Mirza Virkan | 1264 | 505.6 | 505.6
Muradey Kalan | 460 | 184 | 184
Muridke | 32100 | 12840 | 12840
Nazri Lubana | 497 | 198.8 | 198.8
Nokhar | 1122 | 448.8 | 448.8
Rakh Hiran Minara | 4466 | 1786.4 | 1786.4
Safdarabad | 13000 | 5200 | 5200
Shahdara Town | 64000 | 25600 | 25600
Narowal | 32432 | 12972.8 | 12972.8
Abdullah City | 396 | 158.4 | 158.4
Al-Hamra City | 230 | 92 | 92
Al-Rafeh Garden | 248 | 99.2 | 99.2
Al-Raheem Residencia | 370 | 148 | 148
Al-Reheem Garden | 1060 | 424 | 424
Al-Rehmanpura and Zafarwal Road | 962 | 384.8 | 384.8
Bismilllah Society | 616 | 246.4 | 246.4
Circular Road | 2074 | 829.6 | 829.6
Civil Lines | 2220 | 888 | 888
Doctor's Colony | 1434 | 573.6 | 573.6
Garden Town | 582 | 232.8 | 232.8
Green City Park | 448 | 179.2 | 179.2
Habib Garden | 248 | 99.2 | 99.2
Hayat Town | 638 | 255.2 | 255.2
Katchery Road and Allama Iqbal | 888 | 355.2 | 355.2
Khayaban-e-Nawab | 562 | 224.8 | 224.8
Manik Road Mohala Hussainabad | 524 | 209.6 | 209.6
MOh Bijli Ghar | 970 | 388 | 388
Moh Meera Shah Hussain | 4458 | 1783.2 | 1783.2
Mohala Hajver Nagar Open Area | 762 | 304.8 | 304.8
Mushtaq Town | 1750 | 700 | 700
Narowal Bypass to Nawab Town (C | 1356 | 542.4 | 542.4
Nisari Muhallah & Muslim Town S | 1008 | 403.2 | 403.2
Pan peer Road Societies | 1868 | 747.2 | 747.2
Pasrur Bypass , City Commercial | 1348 | 539.2 | 539.2
Punjab Housing & NPS | 908 | 363.2 | 363.2
Rana Shami Town & Satellite Tow | 420 | 168 | 168
Sadeeqpura | 296 | 118.4 | 118.4
Samanabad-College Area | 3420 | 1368 | 1368
Usman Trade City | 368 | 147.2 | 147.2
Naval Anchorage and other Areas (ISB) | 4904 | 2452 | 2452
18_P1 | 888 | 444 | 444
18_P2 | 278 | 139 | 139
C-18 | 832 | 416 | 416
Naval ANchorage | 1726 | 863 | 863
Roshan Pakistan | 1180 | 590 | 590
Okara | 9462 | 3784.8 | 3784.8
1-4L | 708 | 283.2 | 283.2
Ayub Park | 1368 | 547.2 | 547.2
Bajwa Colony, Samad Pura Road,S | 2438 | 975.2 | 975.2
Dubai Town | 738 | 295.2 | 295.2
Farid Town | 2470 | 988 | 988
Karmawala | 30 | 12 | 12
Sher Rabbani Town & Ghaziabad | 1710 | 684 | 684
PAF Base Chaklala | 2830 | 1132 | 1132
PAF Base Chaklala | 2830 | 1132 | 1132
Palm City Lahore | 732 | 293
Palm City | 732 | 293
Peshawar (P2) | 9672 | 3868.8 | 3868.8
City Side P01 | 1048 | 419.2 | 419.2
City Side P02 | 976 | 390.4 | 390.4
City Side P03 | 1060 | 424 | 424
Misc.Areas Warsak | 1584 | 633.6 | 633.6
OPF Colony | 788 | 315.2 | 315.2
Warsak Rd Ext. P1 | 394 | 157.6 | 157.6
Warsak Rd Ext. P2 | 154 | 61.6 | 61.6
Warsak Rd Ext. P3 | 918 | 367.2 | 367.2
Warsak Rd Ext. P4 | 1006 | 402.4 | 402.4
Warsak Rd Ext. P5 | 616 | 246.4 | 246.4
Warsak Rd Ext. P6 | 350 | 140 | 140
Warsak Rd Ext. P7 | 778 | 311.2 | 311.2
Peshawar Misc Areas | 16258 | 8129 | 8129
Askari 01 | 214 | 107 | 107
Askari 02 | 364 | 182 | 182
Askari 03 | 52 | 26 | 26
Askari 04 | 84 | 42 | 42
Askari 05 | 142 | 71 | 71
Charkhana P01 | 4508 | 2254 | 2254
Charkhana P02 | 2780 | 1390 | 1390
Charkhana P03 | 2992 | 1496 | 1496
Officer & Professor Colony_PU | 336 | 168 | 168
OPF Colony | 788 | 394 | 394
Ring Road P01 | 2236 | 1118 | 1118
Tajabad P01 | 1262 | 631 | 631
Tajabad P02 | 500 | 250 | 250
Petaro Garrison, Hyderabad | 740 | 296
Petaro | 740 | 296
PSW to Torkham Border | 0 | 0 | 0
PSW to Torkham Border | 0 | 0 | 0
Quetta | 1200 | 480 | 480
Killi Payen | 400 | 160 | 160
Sabzal Road | 800 | 320 | 320
Quetta Cantt | 5825 | 2912.5 | 2912.5
Cantt_P1 | 1108 | 554 | 554
Cantt_P2 | 4717 | 2358.5 | 2358.5
RahimYar Khan Ph2 | 8486 | 3394.4 | 3268.64
ALi + Fort + Madina | 312 | 124.8 | 124.8
Atta Housing + Canal + Paradise | 786 | 314.4 | 188.64
Dastgeer Colony | 378 | 151.2 | 151.2
Fahad Town | 328 | 131.2 | 131.2
Gulberg+Ahmed+Air view | 576 | 230.4 | 230.4
Ittehad Garden P1 | 712 | 284.8 | 284.8
Ittehad Garden P2 | 1000 | 400 | 400
Ittehad Town & Other | 268 | 107.2 | 107.2
Niazi Colony | 2506 | 1002.4 | 1002.4
Rehmat Colony | 1620 | 648 | 648
Rawalpindi | 9032 | 3612.8 | 3612.8
Gulshanabad P01 | 1758 | 703.2 | 703.2
Gulshanabad P02 | 1470 | 588 | 588
Gulshanabad P03 | 916 | 366.4 | 366.4
Jhelum Road Buildings | 1082 | 432.8 | 432.8
Metro Homes | 528 | 211.2 | 211.2
Samarzar Housing Society | 1824 | 729.6 | 729.6
Sanobar City | 1454 | 581.6 | 581.6
Rawalpindi Misc Areas | 1444 | 722 | 722
Afzal Town Expansion(Aerial) | 1428 | 714 | 714
Ayub Park | 16 | 8 | 8
Royal Palm & Canal View | 8768 | 3507.2 | 3507.2
Canal View | 1950 | 780 | 780
P1 | 1030 | 412 | 412
P2 | 1566 | 626.4 | 626.4
P3 | 2314 | 925.6 | 925.6
P9 | 1908 | 763.2 | 763.2
Sadiqabad | 36784 | 14713.6 | 14713.6
Abid Colony | 474 | 189.6 | 189.6
Ajmal Town,Faisal Town | 1160 | 464 | 464
Akbar Town & Laghari Colony | 902 | 360.8 | 360.8
Al Haram City, Hamza City Overs | 378 | 151.2 | 151.2
Al Hassan, Jamal City, Al Noor | 460 | 184 | 184
Ali Tiown & New Ali Town | 348 | 139.2 | 139.2
Allama Iqbal Town, Aslam Town, | 1924 | 769.6 | 769.6
Amir Canal View, Canal Residenc | 262 | 104.8 | 104.8
Arif Town, Shahzad Colony | 1478 | 591.2 | 591.2
Awan Housing Society | 272 | 108.8 | 108.8
Azizabad | 508 | 203.2 | 203.2
Canal View | 168 | 67.2 | 67.2
Cheema Town, Permi Town | 766 | 306.4 | 306.4
Chief Residencia Housing Societ | 258 | 103.2 | 103.2
Commercial Area, Kothi Mohallah | 1296 | 518.4 | 518.4
Faiz Colony | 676 | 270.4 | 270.4
Gulshen I Azmat, Maqbool City | 332 | 132.8 | 132.8
Gulshen I Iqbal | 178 | 71.2 | 71.2
Haider Colony | 1446 | 578.4 | 578.4
Haq Town | 1116 | 446.4 | 446.4
Heaven City | 278 | 111.2 | 111.2
Hussainabad & Ghafoorabad | 1284 | 513.6 | 513.6
Indus Town | 2010 | 804 | 804
Izhar Enclave,Unknown1,Unknown2 | 362 | 144.8 | 144.8
Jinnah Town, Mohallah Islampura | 804 | 321.6 | 321.6
Mehar Farid Colony | 1034 | 413.6 | 413.6
Model Avenue | 644 | 257.6 | 257.6
Model City Housing | 746 | 298.4 | 298.4
Model Town, Arfat Town | 652 | 260.8 | 260.8
Muhajir Colony, Old Sadiqabad | 1126 | 450.4 | 450.4
Mujahid Colony, Tipu Sultan | 876 | 350.4 | 350.4
Muncipal Town, Illyas Colony, | 2052 | 820.8 | 820.8
Mustafa , Zafar, Bismillah, Kar | 1122 | 448.8 | 448.8
Noor Colony,Zamindara Housing | 970 | 388 | 388
Public Colony & Commercial Area | 594 | 237.6 | 237.6
Rao Town | 950 | 380 | 380
Rehman Avenue | 262 | 104.8 | 104.8
Rustam Colony & Mohallah | 686 | 274.4 | 274.4
Satellite Town, Aziz Town, Gill | 1360 | 544 | 544
Siraj Colony,Sukh Chain Housing | 304 | 121.6 | 121.6
Tibba Qadirabad | 1226 | 490.4 | 490.4
Warriach Town & Arian Colony | 1316 | 526.4 | 526.4
Zakria Garden,Unknown 3-4, | 1040 | 416 | 416
Zamzam Garden,Jeevan City | 684 | 273.6 | 273.6
Sahiwal (P2) | 5554 | 2221.6 | 2221.6
Golf City | 286 | 114.4 | 114.4
Montgomery Society | 188 | 75.2 | 75.2
Muhall Noor & Park Salamat Park | 916 | 366.4 | 366.4
Peoples & Bitholdi Colony | 2948 | 1179.2 | 1179.2
Razaq Royal Ph-3_P1 | 774 | 309.6 | 309.6
Razaq Royal Ph-3_P2 | 286 | 114.4 | 114.4
Sitara City | 156 | 62.4 | 62.4
Sahiwal Misc Areas | 2776 | 1388 | 1388
Bhutto Colony | 1860 | 930 | 930
Chak 89 | 916 | 458 | 458
Sargodha | 24198 | 10089.8 | 10089.8
Al Freed Garden Phase 1 | 480 | 192 | 192
Al Freed Garden Phase 2 | 670 | 268 | 268
Atta Muhammad Coloy HH To 47 Ch | 214 | 107 | 107
Awan Chowk To Gulberg City | 640 | 320 | 320
Aziz,Imran,Nawab,Gondl,Fjr,Srwr | 1432 | 572.8 | 572.8
Bajwa Colony | 340 | 136 | 136
Bashir,Chuna Bhati,Jamil | 1038 | 415.2 | 415.2
Chak 43 NB,Ali & Yousuf Park | 832 | 332.8 | 332.8
Factory_Area | 350 | 140 | 140
Fazil Town FDT To Khizar Masjio | 784 | 392 | 392
Ghani Park FDT To Steel Welding | 386 | 193 | 193
Govt Central Model School To Th | 688 | 344 | 344
Green valley | 288 | 115.2 | 115.2
Gulberg City | 792 | 316.8 | 316.8
Islampura | 2800 | 1120 | 1120
Istiqlalabad | 1800 | 720 | 720
Kachari Road To Awan Colony Dep | 220 | 110 | 110
Kacheela House To Gujjar House | 336 | 168 | 168
Liaquat Colony | 450 | 180 | 180
Milatabad | 766 | 306.4 | 306.4
New Raza Garden | 1128 | 451.2 | 451.2
Raza Gardan Phase 1 & 2 | 1116 | 446.4 | 446.4
Rehmanpura | 1800 | 720 | 720
Remount Depot | 206 | 82.4 | 82.4
RPO Office TO Session Court Roa | 252 | 126 | 126
Sabar Wall Colony | 1662 | 664.8 | 664.8
Salman Pura - Saleem Park | 622 | 248.8 | 248.8
SGD Bhalwal Road TO Fatima Jinn | 586 | 293 | 293
Z Block NST & Services Colony | 970 | 388 | 388
Zafar Colony | 550 | 220 | 220
Sialkot | 21922 | 8768.8 | 8768.8
Amir Street Cap Rd & Model Town | 210 | 84 | 84
Ayan Garden | 56 | 22.4 | 22.4
Bograh Ext | 528 | 211.2 | 211.2
Bonkan | 550 | 220 | 220
Camp Gujran | 556 | 222.4 | 222.4
Capital Rd & Model Town Ext | 358 | 143.2 | 143.2
Christian Town & Muslim Town | 868 | 347.2 | 347.2
Circular Road | 628 | 251.2 | 251.2
CITI Housing E_F_G | 1894 | 757.6 | 757.6
Citi Housing Sec-A_Sectn-1 | 1426 | 570.4 | 570.4
Diamond Citi P2 | 2282 | 912.8 | 912.8
Fatehgarh | 232 | 92.8 | 92.8
Fatehger Ext | 2120 | 848 | 848
Gohaddpur to Ghaniabad | 470 | 188 | 188
Hunterpura Ext | 534 | 213.6 | 213.6
Jallianwala | 620 | 248 | 248
Kashmir Rd Jani Shop st | 386 | 154.4 | 154.4
Kent Housing Ext. | 184 | 73.6 | 73.6
Khadim Ali Rd | 240 | 96 | 96
Marala Road & Muradpur | 604 | 241.6 | 241.6
Nihalchand & Greenwood St | 980 | 392 | 392
Peerwali | 978 | 391.2 | 391.2
Rangpura Road | 632 | 252.8 | 252.8
Rizwan Colony Deen Pura | 170 | 68 | 68
Roras Road | 1092 | 436.8 | 436.8
Shahabpura Main Rd | 440 | 176 | 176
Towards Chitti Sheikh | 404 | 161.6 | 161.6
Towards Ugoki Mor | 1078 | 431.2 | 431.2
Zafarwal | 434 | 173.6 | 173.6
Zahoor Elahi Road | 968 | 387.2 | 387.2
Sialkot Cantt | 3576 | 1788 | 1788
Cantt Commercial | 1382 | 691 | 691
Cantt.P_1 | 748 | 374 | 374
Cantt.P_2 | 884 | 442 | 442
Cantt.P_3 | 562 | 281 | 281
Sukkur | 18858 | 7543.2
Barrage Colony | 964 | 385.6
NewSukkurCityTownship | 762 | 304.8
Unknown 11 | 670 | 268
Sukkur Township Pocket 1 | 2046 | 818.4
Sukkur Township P-2_KingCrystl2 | 1516 | 606.4
Golimar Area | 292 | 116.8
Sachal Township_Kings Crystal | 1864 | 745.6
Shikarpur Rd | 1058 | 423.2
100 Feet Rd P1 | 1472 | 588.8
100 Feet Rd P2 | 2416 | 966.4
Sukkur Ind Area | 350 | 140
Unknonwn_1 | 402 | 160.8
Unknown 03 | 180 | 72
Main City P1 | 2372 | 948.8
Main City P2 | 2494 | 997.6
Swat | 3256 | 1302.4 | 1302.4
Derai P1 | 1032 | 412.8 | 412.8
Derai P2 | 848 | 339.2 | 339.2
Derai P3 | 512 | 204.8 | 204.8
Saidu Ext | 864 | 345.6 | 345.6
Swat Ph2 | 17592 | 7036.8 | 6699.68
Aman kot | 2538 | 1015.2 | 812.16
Gul Kada | 816 | 326.4 | 261.12
Kanju Road P01 | 758 | 303.2 | 303.2
Kanju Road P02 | 1222 | 488.8 | 488.8
Khwaja abad | 860 | 344 | 275.2
Landikas_Rang Mohalla | 3236 | 1294.4 | 1294.4
Main Bazar Mingora | 3102 | 1240.8 | 1240.8
Makan Bagh | 522 | 208.8 | 208.8
Rahimabad_Qambar | 1758 | 703.2 | 703.2
River Area_Hayatabad | 1394 | 557.6 | 557.6
Saidu Sharif P1 | 568 | 227.2 | 227.2
Saidu Sharif P2 | 818 | 327.2 | 327.2
Top City Islamabad | 7702 | 3851 | 3851
Block-A | 2270 | 1135 | 1135
Block-B | 1576 | 788 | 788
Block-C | 2308 | 1154 | 1154
Block-D | 1548 | 774 | 774
Wah Cant Misc Ares | 5152 | 2576 | 2576
Block N & O New City Ph2 | 1008 | 504 | 504
Block P New City Ph2 | 614 | 307 | 307
Block Q New City Ph2 | 304 | 152 | 152
Block R & S New City Ph2 | 1548 | 774 | 774
Block U & V New City Ph2 | 554 | 277 | 277
Block W & Y New City Ph2 | 570 | 285 | 285
Block Y & Z New City Ph2 | 554 | 277 | 277
Wah Cantt | 3196 | 1278.4 | 1278.4
Gulistan Colony | 1750 | 700 | 700
Gulshan e Anwar T.Buried | 730 | 292 | 292
Tameer e Hayat Colony | 716 | 286.4 | 286.4
Wahh Estate | 2156 | 862.4 | 862.4
Estate Area P2 | 618 | 247.2 | 247.2
Estate Area P3 | 1538 | 615.2 | 615.2
Grand Total | 1444140 | 600881.5 | 544448.26

## Arial, Hybrid, Buried (hidden)
Number of Total Areas | 4
Row Labels | Count of Area / Section / Pocket / Society (Original Name)
Arial | 93
Buried | 253
Hybrid | 804
Grand Total | 1150

## HP - Customer Network (hidden)
Home Passes - Total | 1444140 | 600881.5 | 544448.26 | 229830.1 | 557486
Row Labels | Sum of Total H.P | Sum of Customers According to % (Market Share) | Sum of HP Based on completion - Realistic | Sum of Sellable Capacity - E | Sum of Sellable Capacity - T
Abbottabad | 3690 | 1476 | 1476 | 1196 | 2990
Bahawalpur | 28960 | 11632.6 | 11632.6 | 3274.2 | 8064
Chitral | 3832 | 1532.8 | 909.2 | 623.6 | 3118
Daska | 21078 | 8431.2 | 8431.2 | 381.6 | 954
Dera Ghazi Khan | 23218 | 10448.1 | 10448.1 | 0 | 0
Faisalabad | 37542 | 16203.2 | 14216 | 13719.2 | 32988
Gujranwala | 144722 | 57941.6 | 52338.4 | 36427.2 | 91068
Hafizabad | 27226 | 12251.7 | 12251.7 | 0 | 0
Haripur | 9672 | 3868.8 | 3868.8 | 3212.8 | 8032
Hyderabad | 17942 | 7176.8 | 6623.16 | 4163.96 | 11054
Islamabad | 103742 | 44256.4 | 43688.08 | 26058.28 | 60594
Jhang | 17360 | 7812 | 7812 | 0 | 0
Jhelum | 12566 | 5026.4 | 2360.8 | 2342.4 | 5856
Karachi | 155453 | 61074.8 | 42049 | 28422.4 | 73079
Kasur | 38704 | 15481.6 | 15481.6 | 0 | 0
Lahore | 401986 | 166363.8 | 148964 | 26932 | 66672
Lalamusa | 14988 | 6744.6 | 6744.6 | 0 | 0
Mandi Bahauddin | 33480 | 15066 | 15066 | 0 | 0
Mardan | 15516 | 6206.4 | 6206.4 | 5509.6 | 13774
Multan | 70968 | 33220.6 | 33220.6 | 25328 | 56718
Narowal | 32432 | 12972.8 | 12972.8 | 0 | 0
Okara | 9462 | 3784.8 | 3784.8 | 3784.8 | 9462
Peshawar | 25930 | 11997.8 | 11997.8 | 10022.4 | 21152
Quetta | 7025 | 3392.5 | 3392.5 | 3072.5 | 6225
Rahim Yar Khan | 8486 | 3394.4 | 3268.64 | 2362.24 | 6220
Rawalpindi | 17360 | 7088.4 | 7088.4 | 2202 | 5144
Sadiqabad | 36784 | 14713.6 | 14713.6 | 0 | 0
Sahiwal | 8330 | 3609.6 | 3609.6 | 2642.4 | 5912
Sargodha | 24198 | 10089.8 | 10089.8 | 6721.8 | 15778
Sialkot | 26270 | 11020 | 11020 | 8332 | 19550
Swat | 35856 | 14342.4 | 14005.28 | 12559.52 | 31734
Torkhan Border | 0 | 0 | 0 | 0 | 0
Wahh | 10504 | 4716.8 | 4716.8 | 539.2 | 1348
Sukkur | 18858 | 7543.2 |  | 0 | 0
Grand Total | 1444140 | 600881.5 | 544448.26 | 229830.1 | 557486

## Budgets (hidden)
Number of Total Areas | 18581034211.0381 | 8480651043.2293 | 9519720397.1999
Row Labels | Sum of Allocated Budget | Sum of Revised Budget | Sum of Difference
Abbottabad | 46635361.121 | 4933262.6816 | 41702098.4394
Bahawalpur | 234720343.2277 | 78068026.9577 | 48751767.1897
Chitral | 107457482.0098 | 69955211.3372 | 37502270.6725
Daska | 238190943.4392 | 150040448.3198 | 88150495.1195
Dera Ghazi Khan | 415670312.3488 | 415670312.3488
Faisalabad | 715131057.0272 | 91398554.2358 | 567810727.1535
Gujranwala | 1642979885.176 | 591739195.3929 | 1015816807.0546
Hafizabad | 252576804.9885 | 252576804.9885
Haripur | 166186302.6104 | 37229959.821 | 128956342.7894
Hyderabad | 247184920.0797 | 62007415.8715 | 178992492.9772
Islamabad | 1899278927.2637 | 853745637.8312 | 1040417112.7484
Jhang | 190914712.4087 | 190914712.4087
Jhelum | 172926785.0482 | 71668192.8508 | 51090933.4386
Karachi | 2148258237.7282 | 912013069.8938 | 1144334678.187
Kasur | 277182368.4801 | 276278195.9401
Lahore | 4687149709.8115 | 2183279055.3426 | 2378935957.8479
Lalamusa | 151789539.3189 | 151789539.3189
Mandi Bahauddin | 303045745.7902 | 303045745.7902
Mardan | 198763325.656 | 27323021.716 | 171440303.94
Multan | 1277748684.2307 | 444024103.3454 | 806099668.7116
Narowal | 274744690.9635 | 274744690.9635
Okara | 102458798.3625 | 15368819.7544 | 87089978.6081
Peshawar | 307075969.798 | 99622299.7437 | 207453670.0543
Quetta | 135338960.1659 | 22356218.3999 | 112982741.7661
Rahim Yar Khan | 111071445.702 | 14964640.4864 | 96106805.2156
Rawalpindi | 177277562.8741 | 47104579.4838 | 130172983.3904
Sadiqabad | 350433922.1714 | 350433922.1714
Sahiwal | 85781337.1301 | 42199240.2089 | 39901741.9701
Sargodha | 193303052.3165 | 50749454.452 | 142553597.8645
Sialkot | 483284928.4537 | 141873994.0454 | 341410934.4083
Swat | 465926299.3645 | 93712460.2242 | 364292663.1616
Torkhan Border | 125214350 | 18782152.5 | 106432197.5
Wahh | 210791285.8799 | 19469858.8882 | 191321426.9917
Sukkur | 184540160.0914 | 121568245.515
Grand Total | 18581034211.0381 | 8480651043.2293 | 9519720397.1999

## Timeline Box (hidden)
Number of Total Areas | 9
Row Labels | Count of CEM Number | m | C
Apr-2026 | 61 | 2026-04-01 | 61
Feedback Awaited | 45 | 2026-07-01 | 33
Jul-2026 | 33 | 2026-06-01 | 64
Jun-2026 | 64 | 2026-03-01 | 37
Mar-2026 | 37 | 2026-05-01 | 26
May-2026 | 26 | 2026-10-01 | 292
Oct-2026 | 292
Timeline not applicable | 592
Grand Total | 1150

## Table of Contents
Table of Content
Dashboard - Summary
Dashboard - Feasibility
Dashboard - Financials
Data Bank
Timeline Box
Standardized Comments
HP - Customer Network
Arial, Buried, Hybrid
City Names
Budgets
Swap Details
Actuals
Feasibilities
Area
Live/Not Live

## Data Bank
[15 empty] | Feeder | 50% | 100%
[15 empty] | 100% Live | 15% |  | 7805702.1861 | 1170855.3279
1990454.0575
[5 empty] | 1444140 | 600881.5 | [8 empty] | 22095709754.6035 | 10815617066.9371 |  |  |  |  | 7192974.7153 | #REF! | [19 empty] | 0 |  |  |  |  | ßßßßßßß
[16 empty] | 48.95% | [14 empty] | AZ
CEM Number | CEM Initiation Date | City Name | Fesibility Name | Area / Section / Pocket / Society (Original Name) | Total H.P | Customers According to % (Market Share) | New Customers | Terminated | Active | Not Active | Remarks - Actuals | Customers based on completion | HP% based on Live % ( Work Progress) | HP Based on completion - Realistic | Allocated Budget | Revised Budget | Difference | Costing Efficiency | Area / Section / Pocket / Society (Revised Name) | Customers Take up %age (Key Factor) | Total Civil works - Buried | Total Civil works - Arial | Originally Approved on: Arial, Buried, Hybrid | Allocation Percentage | Current Status (Live/Not Live) | Live on (Arial,Buried, Hybrid) | % of Completion of Work Done | Compeltion % not % | Start Date.. | Start Date OffSet | Duration | Days Remaining | Status | Timeline | Timeline - Monthwise | Remarks by ODN | Remarks Grouped | Std Remarks | Additional Remarks (5-6M) | Additional Remarks (5-6M)2 | Swapped With - | Swapped/Removal Budget | HP - Revised | 71 vs 26 | 72 vs 26
I250212 | 2024-09-14 | Swat | Mingora | Between Fizaghat & Sangota | 62 | 24.8 |  |  |  |  | NOC and Civil work pending | NOT LIVE - RETAIN BUDGET | 0% | 24.8 | 5376147.3012 | 5376147.3012 | 0 | -1 |  | 0.4 | 1617 | 3172.945 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250212 | 2026-06-01
I260296 | No Initiation Date | Sukkur | Sukkur | 100 Feet Rd P1 | 1472 | 588.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 70% |  | 22129453.0529 | 8962428.4864 |  |  |  |  | 5111.75 | 19417.6357 | Hybrid | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Crossing Pending and Other Civil Related work pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I260296 | No Initiation Date | Sukkur | Sukkur | 100 Feet Rd P2 | 2416 | 966.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 70% |  | 26522963.7375 | 10741800.3137 |  |  |  |  | 4135.4 | 30832.3465 | Hybrid | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Crossing Pending and Other Civil Related work pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I240683 | 2024-05-15 | Okara | Okara | 1-4L | 708 | 283.2 | 231 | 54 |  | 177 |  | LIVE - 100% Completed | 100% | 283.2 | 14710666.25 | 2206599.9375 | 12504066.3125 | -1 |  | 0.4 | 2849.7 | 18016.25 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240683 | Timeline not applicable
I240518 | 2024-02-27 | Islamabad | Naval Anchorage and other Areas (ISB) | 18_P1 | 888 | 444 | 14 |  | 2 | 12 |  | LIVE - 100% Completed | 100% | 444 | 5022290.1311 | 753343.5197 | 4268946.6114 | 0 |  | 0.5 | 1743.75 | 2788.9897 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240518 | Timeline not applicable
I240518 | 2024-02-27 | Islamabad | Naval Anchorage and other Areas (ISB) | 18_P2 | 278 | 139 | 0 |  |  |  |  | REMOVE BUDGET (T) | 0% | 139 | 4525188.2481 | 0 | 4525188.2481 | -1 |  | 0.5 | 1706.25 | 6137.5094 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | remove (after June) | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | I240518 | Timeline not applicable
I240701 | 2024-05-16 | Feeders/Transportations | Swat | 24F Cable | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 660000 | 330000 | 330000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240701 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | 3 Marla Scheme | 1730 | 692 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 85% | 692 | 8809572.4567 | 2444656.3567 |  |  |  |  | 1286.5177 | 9419.8009 | Hybrid | 85% | Not Live |  | 85% | 0.85 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Cable pulling pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Adam Housing-P1 | 554 | 249.3 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 249.3 | 16702835.75 | 16702835.75 |  |  |  | 0.45 | 8363.7 | 7443 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Adam Housing-P2 | 428 | 192.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 192.6 | 14769070.25 | 14769070.25 |  |  |  | 0.45 | 7360.65 | 6328.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Abdullah Colony & Nawa Killy | 394 | 157.6 | 394 | 13 | 12 | 1 | 0 |  | 100% | 157.6 | 7472398.9395 | 1120859.8409 | 6351539.0986 | -1 |  | 0.4 | 0 | 19592.5125 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Abdullah Sports Tower Ext | 96 | 38.4 | 58 | 0 |  |  |  | NOT LIVE - RETAIN BUDGET | 100% | 38.4 | 3652917.4793 | 547937.6219 | 3104979.8574 | -1 |  | 0.4 | 1375.8562 | 840.2976 | Buried | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 92 | 93 | 45 | Completed | 46174 | Jun-2026 | Civil work completed, but not live due to pending customer possession from the builder. | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240702 | 2026-06-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Al Hussain Garden | 228 | 102.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 102.6 | 6341933 | 6341933 |  |  |  | 0.45 | 3085.35 | 2785.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Abid Market | 656 | 262.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 80% | 262.4 | 7827127.336 | 2504680.7475 | 5322446.5885 | -1 |  | 0.4 | 874 | 2022.5 | Hybrid | 80% | NOT LIVE |  | 80% | 0.8 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46054 | Mar-2026 | Cable pulling pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240703 | 2026-03-01
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | AbrazulMinal_KingsBridgeView | 1400 | 560 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 560 | 4430148.0874 | 4430148.0874 | 0 | -0.833 |  | 0.4 | 415.1442 | 1275.481 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46204 | Apr-2026 | Permission Issue | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240705 | 2026-04-01
I240704 | 2024-05-15 | Multan | Multan Ph3 | Adam Housing | 1130 | 452 | 0 | 0 | 0 | 0 | Budget Shifted | LIVE - 100% Completed | 100% | 452 | 36999248.9 | 5549887.335 | 31449361.565 | #DIV/0! |  | 0.4 | 18159.3 | 13746 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Swapped with Manic Block Buch Villas | Swap Cases | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Al Inam Gardens | 316 | 142.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 142.2 | 10497664.75 | 10497664.75 |  |  |  | 0.45 | 5045.6 | 4503.7 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Al Rasool Town | 310 | 139.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 139.5 | 9129729 | 9129729 |  |  |  | 0.45 | 4880.9 | 4476 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Canal View | 582 | 261.9 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 261.9 | 5787365.7628 | 5787365.7628 |  |  |  | 0.45 | 998.4 | 4521.0697 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | AFOHS PK-1 | 984 | 393.6 | [5 empty] | LIVE - 100% Completed | 100% | 393.6 | 52832203.429 | 7924830.5143 | 44907372.9146 | -1 |  | 0.4 | 25051.5859 | 17445.469 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | AFOHS PK-2 | 478 | 191.2 | [5 empty] | LIVE - 100% Completed | 100% | 191.2 | 23923705.6889 | 3588555.8533 | 20335149.8356 | -0.765 |  | 0.4 | 11643.1568 | 9277.2194 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | AFOHS PK-3 | 1256 | 502.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 502.4 | 64454759.129 | 64454759.129 | 0 | -1 |  | 0.4 | 29179.3859 | 25756.0427 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240705 | 2026-06-01
INT-23-00445 | 2022-12-29 | Rawalpindi | Rawalpindi Misc Areas | Afzal Town Expansion(Aerial) | 1428 | 714 | 245 | 49 | 53 | 143 |  | LIVE - 100% Completed | 100% | 714 | 9210946.31 | 1381641.9465 | 7829304.3635 | #DIV/0! |  | 0.5 | 0 | 12237.876 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00445 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Airport (Ghanshal village) P01 | 266 | 106.4 | 121 | 107 | 9 | 5 |  | LIVE - 100% Completed | 100% | 106.4 | 2211881.4604 | 331782.2191 | 1880099.2413 | -1 |  | 0.4 | 0 | 2931.9471 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Airport (Ghanshal village) P01 | 234 | 93.6 | 108 | 95 | 6 | 7 |  | LIVE - 100% Completed | 100% | 93.6 | 1910813.0392 | 286621.9559 | 1624191.0833 | -0.85 |  | 0.4 | 0 | 3442.6945 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | CPC Colony | 346 | 155.7 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 155.7 | 6395179.5415 | 6395179.5415 |  |  |  | 0.45 | 1705.2 | 5519.602 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Dream City | 532 | 239.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 239.4 | 15928200.5 | 15928200.5 |  |  |  | 0.45 | 7953.9 | 7119 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Ajwa City_P1 | 2202 | 880.8 | [5 empty] | LIVE - 100% Completed | 100% | 880.8 | 60544035.8736 | 9081605.381 | 51462430.4925 | -1 |  | 0.4 | 33561.6461 | 26265.2554 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Ajwa City_P2 | 3046 | 1218.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 75% | 1218.4 | 74734284.6954 | 27091178.2021 | 47643106.4933 | 0 |  | 0.4 | 41664.3791 | 33270.9825 | Buried | 75% | NOT LIVE |  | 75% | 0.75 | 2026-03-01 | 31 | 32 | -16 | In Progress | 46113 | Apr-2026 | HHs placement in progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240700 | 2026-04-01
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Etihad Town | 2606 | 1042.4 | [5 empty] | LIVE - 100% Completed | 100% | 1042.4 | 35268957.3897 | 5290343.6085 | 29978613.7813 | -1 |  | 0.4 | 9645 | 5208.75 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Feeders/Transportations | Lahore Ph5 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 82640788 | 41320394 | 41320394 | -1 |  |  | 26448 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Ferozpur Road | 2278 | 911.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 10% | 911.2 | 29293628.758 | 26803670.3136 | 2489958.4444 | -1 |  | 0.4 | 4462 | 11277 | Hybrid | 10% | NOT LIVE |  | 10% | 0.1 | 2026-03-01 | 31 | 32 | -16 | In Progress | 46113 | Apr-2026 | Civil Work hold by TEPA/LDA | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240703 | 2026-04-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Ejaz Town | 690 | 310.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 310.5 | 8524660.3935 | 8524660.3935 |  |  |  | 0.45 | 2365.55 | 8636.0911 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Feeders/Transportations | DG Khan | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 93527861.2 | 93527861.2 |  |  |  |  | 30856.1 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Al Barkat Villas | 190 | 76 |  | 0 | 0 | 0 | Yet not active | SWAPPED | 0% | 76 | 3623949.247 | 0 | 3623949.247 | -1 |  | 0.4 | 809.6 | 1873.2538 | Arial |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | swapping with city walk | Swap Cases | SWAPPED |  |  | City Walk | 4637080.9375 | 254 | I240682 | Timeline not applicable
I250210 | 2024-09-14 | Sargodha | Sargodha | Al Freed Garden Phase 1 | 480 | 192 |  |  | Not Active |  | Not Live | NOT LIVE - RETAIN BUDGET | 70% | 192 | 7111635.2 | 2880212.256 | 4231422.944 | -1 |  | 0.4 | 1465.1 | 6090 | Hybrid | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 61 | 62 | 14 | In Progress | 2 Months | May-2026 | This Colony linked with the DPLC backup connectivity; once completed, the area will go live. | Swap Cases | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250210 | 2026-05-01
I250210 | 2024-09-14 | Sargodha | Sargodha | Al Freed Garden Phase 2 | 670 | 268 |  |  | Not Active |  | Not Live | NOT LIVE - RETAIN BUDGET | 70% | 268 | 8501572.75 | 3443136.9638 | 5058435.7862 | -0.765 |  | 0.4 | 1472 | 8346.25 | Hybrid | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 61 | 62 | 14 | In Progress | 2 Months | May-2026 | This Colony linked with the DPLC backup connectivity; once completed, the area will go live. | Swap Cases | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250210 | 2026-05-01
I260361 | No Initiation Date | Lahore | Lhr MW City & Al Hafeez Ph-1 | Al Hafeez Garden Ph-1 | 1406 | 562.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 23973146.368 | 23973146.368 |  |  |  |  | 10945.7 | 10112.5 | Buried | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 4 moths | Jul-2026 | Hold by Society end. | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
I260105 | No Initiation Date | Lahore | Al Hafeez Garden & Tariq Garden | Al Hafeez Garden Ph-5 | 1450 | 580 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 26639854.6273 | 26639854.6273 |  |  |  |  | 14837.408 | 13184.9864 | Buried | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 months | Jun-2026 | Duct Plan Shared / Hold by Society end. | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I260105 | No Initiation Date | Lahore | Al Hafeez Garden & Tariq Garden | Al Hafeez Gdn Ph-2 | 1404 | 561.6 | [5 empty] | LIVE - 100% Completed | 100% |  | 29240431.6706 | 4386064.7506 |  |  |  |  | 14059.4256 | 11125.5495 | Buried | 15% | Live | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
I240440 | 2024-01-19 | Lahore | Al Jalil & Al khalil LHE | Al Hamra | 424 | 169.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 40% | 169.6 | 6253881.2668 | 4127561.6361 | 2126319.6307 | -1 |  | 0.4 | 1585.85 | 5599.5 | Hybrid | 40% | NOT LIVE |  | 40% | 0.4 | 2026-03-01 | 31 | 32 | -16 | In Progress | 46113 | Apr-2026 | Civil Work in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 | 1 |  |  |  | I240440 | 2026-04-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Garden Town | 488 | 219.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 219.6 | 12126847.3489 | 12126847.3489 |  |  |  | 0.45 | 6265.9846 | 4904.8718 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Gul zameen Colony | 196 | 88.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 88.2 | 3336731.8637 | 3336731.8637 |  |  |  | 0.45 | 804.36 | 2478.3943 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Gulberg housing Society | 1166 | 524.7 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 524.7 | 31413471.477 | 31413471.477 |  |  |  | 0.45 | 15330.5387 | 14229.6488 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Indus Smart City | 148 | 66.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 66.6 | 2754114.6152 | 2754114.6152 |  |  |  | 0.45 | 578.3662 | 2335.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240440 | 2024-01-19 | Lahore | Al Jalil & Al khalil LHE | Al Jalil Housing P2 | 2232 | 892.8 | [5 empty] | LIVE - 100% Completed | 100% | 892.8 | 49814022.8742 | 7472103.4311 | 42341919.4431 | -0.85 |  | 0.4 | 27165.9468 | 25218.6673 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 1 |  |  |  | I240440 | Timeline not applicable
I240440 | 2024-01-19 | Lahore | Al Jalil & Al khalil LHE | Al Jalil Housing P3 | 2210 | 884 | [5 empty] | LIVE - 100% Completed | 100% | 884 | 38711034.9319 | 5806655.2398 | 32904379.6921 | -1 |  | 0.4 | 20894.584 | 19995.7218 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 1 |  |  |  | I240440 | Timeline not applicable
I240440 | 2024-01-19 | Lahore | Al Jalil & Al khalil LHE | Al Jalil Housing P4 | 2106 | 842.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 842.4 | 39895632.5908 | 39895632.5908 | 0 | -0.85 |  | 0.4 | 22634.9773 | 21018.6755 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 | 1 |  |  |  | I240440 | Feedback Awaited
I240440 | 2024-01-19 | Lahore | Al Jalil & Al khalil LHE | Al Kabeer Ph-2-Pk1 | 2268 | 907.2 | [5 empty] | LIVE - 100% Completed | 100% | 907.2 | 39719478.4952 | 5957921.7743 | 33761556.7209 | -1 |  | 0.4 | 20815.7223 | 21072.583 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240440 | Timeline not applicable
I240440 | 2024-01-19 | Lahore | Al Jalil & Al khalil LHE | Al Kabeer Ph-2-Pk2 | 3086 | 1234.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 25% | 1234.4 | 65205216.987 | 51349108.3773 | 13856108.6097 | -0.85 |  | 0.4 | 33751.263 | 28797.2282 | Buried | 25% | NOT LIVE |  | 25% | 0.25 | 2026-03-01 | 31 | 32 | -16 | In Progress | 46113 | Apr-2026 | Duct Plan Shared | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240440 | 2026-04-01
I240440 | 2024-01-19 | Lahore | Al Jalil & Al khalil LHE | Al Kabeer Ph-2-Pk3 | 776 | 310.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 310.4 | 18028082.9882 | 18028082.9882 | 0 | -1 |  | 0.4 | 9468.5702 | 7634.6282 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240440 | Feedback Awaited
I240440 | 2024-01-19 | Lahore | Al Jalil & Al khalil LHE | Al Kabeer Town Ph-1 | 512 | 204.8 | [5 empty] | LIVE - 100% Completed | 100% | 204.8 | 10728206.488 | 1609230.9732 | 9118975.5148 | -0.85 |  | 0.4 | 4849.5 | 3910.5 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240440 | Timeline not applicable
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | K Gaardens | 360 | 162 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 162 | 11056413.3623 | 11056413.3623 |  |  |  | 0.45 | 5275.5827 | 4704 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Khayaban e Sarwar | 1110 | 499.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 499.5 | 17604297.4664 | 17604297.4664 |  |  |  | 0.45 | 3995.2781 | 15367.227 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Al Khalil Housing Scheme | 140 | 70 |  |  |  |  | On hold | LIVE - 100% Completed | 100% | 70 | 2080552.75 | 312082.9125 | 1768469.8375 | 0 |  | 0.5 | 408.25 | 2460.65 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240537 | 2024-02-29 | Abbottabad | Abbottabad Ph2 | Al Mansoor Town Ext. | 440 | 176 | 15 | 0 |  |  |  | LIVE - 100% Completed | 100% | 176 | 3932662.0499 | 589899.3075 | 3342762.7424 | -0.85 |  | 0.4 | 0 | 6073.9018 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240537 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Al mansoorah colony | 492 | 196.8 | [5 empty] | LIVE - 100% Completed | 100% | 196.8 | 6719191.7721 | 1007878.7658 | 5711313.0063 | -0.5 |  | 0.4 | 2142.8 | 3517.2525 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Al Nawab Rehman Villas AlKareem | 1470 | 588 | 41 | 2 | 8 | 31 |  | LIVE - 100% Completed | 100% | 588 | 13947728.6988 | 2092159.3048 | 11855569.394 | -1 |  | 0.4 | 2288.5 | 12414.8938 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I260105 | No Initiation Date | Lahore | Al Hafeez Garden & Tariq Garden | Al Raheem Gdn Ph-2 Extn. | 1150 | 460 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 22652075.7062 | 22652075.7062 |  |  |  |  | 11108.95 | 9658.75 | Buried | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | To be started soon | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Al Rahim City Ph-1 | 488 | 195.2 | [5 empty] | LIVE - 100% Completed | 100% | 195.2 | 7250852.7932 | 1087627.919 | 6163224.8742 | -0.765 |  | 0.4 | 1076.1328 | 3028.925 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Al Rahim City Ph-2 | 480 | 192 | [5 empty] | LIVE - 100% Completed | 100% | 192 | 8776314.0793 | 1316447.1119 | 7459866.9674 | -1 |  | 0.4 | 1365.2114 | 3028.925 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Khayaban i Abid | 242 | 108.9 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 108.9 | 6512643.4617 | 6512643.4617 |  |  |  | 0.45 | 3217.0834 | 3051 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260160 | No Initiation Date | Lahore | Khyban-e-Amin, High court & Al Rehman PH4 | Al Rehman Garden 4 | 978 | 391.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% |  | 21170251.6177 | 4975009.1302 |  |  |  |  | 10028 | 7602.6683 | Buried | 90% | Not Live |  | 90% | 0.9 | 2026-03-01 | 61 | 62 | 14 | In Progress | 2 months | May-2026 | Civil Work in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-05-01
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Al Rehmat Villa | 228 | 91.2 |  | 6 | 14 | 41 | Occupancy: 100 | LIVE - 100% Completed | 100% | 91.2 | 3471646.7 | 520747.005 | 2950899.695 | 0 |  | 0.4 | 671.6 | 2087.45 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Alamgir&Jannat ul Barkat | 1020 | 408 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 7583418.9193 | 7583418.9193 |  |  |  |  | 1115.291 | 9719.1381 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Alfalah Society | 1330 | 532 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 9706625.8913 | 9706625.8913 |  |  |  |  | 1495.12 | 7634.7687 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00437 | 2022-12-29 | Lahore | Lahore Misc Areas | Al-Hamd Society | 264 | 132 | [5 empty] | LIVE - 100% Completed | 100% | 132 | 2532898.0576 | 379934.7086 | 2152963.3489 | 0 |  | 0.5 | 487.8524 | 1459.4008 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00437 | Timeline not applicable
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Main Area P1 | 3176 | 1429.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1429.2 | 34606678.234 | 34606678.234 |  |  |  | 0.45 | 7104 | 31407.0098 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240680 | 2024-05-16 | Rahim Yar Khan | RahimYar Khan Ph2 | ALi + Fort + Madina | 312 | 124.8 | 23 | 6 |  |  |  | LIVE - 100% Completed | 100% | 124.8 | 6278514.496 | 941777.1744 | 5336737.3216 | -1 |  | 0.4 | 1569.75 | 3452.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240680 | Timeline not applicable
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Main Area P2 | 3656 | 1645.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1645.2 | 23123139.1405 | 23123139.1405 |  |  |  | 0.45 | 2232 | 34874.2189 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250681 | 2025-03-26 | Lahore | CTC Lahore | Ali Park & Nadirabad P1 | 1424 | 569.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 569.6 | 9547055.0217 | 2243557.9301 | 7303497.0916 | -1 |  |  | 2700.41 | 11590.9702 | Hybrid | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46054 | Mar-2026 | Cable and ADT Plan Shared | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250681 | 2026-03-01
I250681 | 2025-03-26 | Lahore | CTC Lahore | Ali Park & Nadirabad P2 | 1512 | 604.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 70% | 604.8 | 9890121.2877 | 4005499.1215 | 5884622.1662 | -0.85 |  |  | 3207 | 11713.0818 | Hybrid | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46082 | Mar-2026 | Civil Work Completion | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 | 1 |  |  |  | I250681 | 2026-03-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Main Area P3 | 1776 | 799.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 799.2 | 21710706.2245 | 21710706.2245 |  |  |  | 0.45 | 4438 | 21449.5247 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Model Town | 1012 | 455.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 455.4 | 13749012.1858 | 13749012.1858 |  |  |  | 0.45 | 3082.2647 | 12538.1305 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240704 | 2024-05-15 | Multan | Multan Ph3 | Ali Town | 1486 | 594.4 | 144 | 15 | 25 | 104 |  | LIVE - 100% Completed | 100% | 594.4 | 15226492.861 | 2283973.9291 | 12942518.9319 | -1 |  | 0.4 | 1975.05 | 10888.05 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Alibad_Colony | 278 | 111.2 |  |  |  | 20 |  | LIVE - 100% Completed | 100% | 111.2 | 2159567.6403 | 323935.146 |  |  |  |  | 286.35 | 2148.6131 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | New Defence | 930 | 418.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 418.5 | 27241910.0803 | 27241910.0803 |  |  |  | 0.45 | 14073.2059 | 11862.51 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | New Model Town | 398 | 179.1 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 179.1 | 4776860.6915 | 4776860.6915 |  |  |  | 0.45 | 894.355 | 5500.1274 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | NMC Colony 1 | 296 | 133.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 133.2 | 4506777.1603 | 4506777.1603 |  |  |  | 0.45 | 1160.4 | 4682.6666 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Allabad, AliTown & IslamPura | 1024 | 512 | 55 | 3 | 3 | 49 |  | LIVE - 100% Completed | 100% | 512 | 10704521.738 | 1605678.2607 | 9098843.4773 | -1 |  | 0.5 | 2779.55 | 8165.33 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Part of New Defence | 262 | 117.9 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 117.9 | 7649956.5744 | 7649956.5744 |  |  |  | 0.45 | 3704.7405 | 3480.9257 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Railway Civil Lines P1 | 596 | 268.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 268.2 | 12742348.2107 | 12742348.2107 |  |  |  | 0.45 | 3247.6 | 10985.0171 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | AlNoor Exct-Haram-Garden Ph-4 | 298 | 119.2 |  |  |  | 37 |  | LIVE - 100% Completed | 100% | 119.2 | 10573838.2354 | 1586075.7353 |  |  |  |  | 5217.4146 | 4654.9212 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | AlQuresh Phase 1 | 1366 | 683 | 200 | 23 | 33 | 144 |  | LIVE - 100% Completed | 100% | 683 | 36186976.9457 | 5428046.5419 | 30758930.4038 | -0.85 |  | 0.5 | 19648.4427 | 17427.9718 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | AlQuresh Phase 2 | 1420 | 710 | 0 | 0 | 0 | 0 | On hold | NOT LIVE - RETAIN BUDGET | 100% | 710 | 30642179.0184 | 4596326.8528 | 26045852.1657 | -1 |  | 0.5 | 15771.5705 | 13938.3349 | Hybrid | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 0 | 1 | -47 | Completed | 46082 | Mar-2026 | Permission Issue With Cable Operator/C.W completed | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | INT-23-00439 | 2026-03-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Railway Civil Lines P2 | 570 | 256.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 256.5 | 10735975.7207 | 10735975.7207 |  |  |  | 0.45 | 2379.35 | 13118.5547 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Royal city | 166 | 74.7 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 74.7 | 4378505.6711 | 4378505.6711 |  |  |  | 0.45 | 2043.4812 | 1900.95 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00437 | 2022-12-29 | Lahore | Lahore Misc Areas | Al-Raheems Homes | 120 | 60 | [5 empty] | LIVE - 100% Completed | 100% | 60 | 1163619.7957 | 174542.9694 | 989076.8263 | -1 |  | 0.5 | 169.7537 | 790.6628 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00437 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Al-Rahim Garden & Crystal Homes | 484 | 193.6 | Not Live Yet |  |  |  |  | LIVE - 100% Completed | 100% | 193.6 | 9615395.3961 | 1442309.3094 |  |  |  |  | 1552.6323 | 6093.614 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Crystal Home live but Al- Rahim Garden NoC Pending by society | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Royal Pearl Enclave | 1768 | 795.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 795.6 | 55303643.6133 | 55303643.6133 |  |  |  | 0.45 | 28101.0153 | 23997.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Sana Valley | 424 | 190.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 190.8 | 4178279.6924 | 4178279.6924 |  |  |  | 0.45 | 831.6 | 4651.9726 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260599 | No Initiation Date | Feeders/Transportations | DG Khan | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 9800000 | 9800000 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I240539 | 2024-02-28 | Swat | Swat Ph2 | Aman kot | 2538 | 1015.2 |  |  |  |  | Civil Work in progress | NOT LIVE - RETAIN BUDGET | 80% | 812.16 | 24196911.6054 | 7743011.7137 | 16453899.8917 | -0.85 |  | 0.4 | 1710.9265 | 28333.3898 | Hybrid | 80% | NOT LIVE |  | 80% | 0.8 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 | Civil Work Completion | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240539 | 2026-07-01
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Aman Society | 96 | 38.4 | [5 empty] | LIVE - 100% Completed | 100% | 38.4 | 4862657.4787 | 729398.6218 | 4133258.8569 | -1 |  | 0.4 | 0 | 988.9213 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Usmania Village | 230 | 103.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 103.5 | 6047770.3361 | 6047770.3361 |  |  |  | 0.45 | 2892.5515 | 2350.8906 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Amir Street Cap Rd & Model Town | 210 | 84 |  | 0 | 0 | 0 | Not Lived Yet | NOT LIVE - RETAIN BUDGET | 0% | 84 | 1419695.8245 | 1419695.8245 | 0 | -0.85 |  | 0.4 | 0 | 1540.9022 | Arial | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240678 | Feedback Awaited
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Amynabad | 290 | 116 | [5 empty] | LIVE - 100% Completed | 100% | 116 | 5312050.9033 | 796807.6355 | 4515243.2678 | -0.765 |  | 0.4 | 1201.1767 | 2458.9867 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Live - Completed | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I260599 | No Initiation Date | Dera Ghazi Khan | DG Khan | Zam Zam City | 262 | 117.9 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 117.9 | 6037590.2704 | 6037590.2704 |  |  |  | 0.45 | 1251.9677 | 3555.4 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Anwarabad Colony | 332 | 132.8 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 85% | 132.8 | 5059405.5968 | 1403985.0531 |  |  |  |  | 1168.579 | 5137.5 | Arial | 85% | Not Live |  | 85% | 0.85 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Due to Fahad colony cable pulling pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Anwar-e-Ibrahim | 558 | 223.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 5089046.74 | 5089046.74 |  |  |  |  | 865.7 | 4069.829 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Akhtar Town & Tarrar Road | 1390 | 625.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 625.5 | 11011025.1555 | 11011025.1555 |  |  |  | 0.45 | 1722.6 | 12543.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Al Kareem City | 1606 | 722.7 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 722.7 | 13235679.776 | 13235679.776 |  |  |  | 0.45 | 2091.85 | 11495 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250375 | 2024-11-25 | Bahawalpur | Bahawalpur (P3) | Asif & Hassan Town | 1740 | 696 |  | 28 | 29 | 100 |  | LIVE - 100% Completed | 100% | 696 | 17285837.436 | 2592875.6154 | 14692961.8206 | -1 |  | 0.4 | 2976.2 | 11942.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250375 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Askari | 108 | 43.2 |  | 2 | 7 | 61 |  | LIVE - 100% Completed | 100% | 43.2 | 5063460.1389 | 759519.0208 |  |  |  |  | 2318.4 | 2176.25 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
INT-23-00447 | 2022-12-29 | Peshawar | Peshawar Misc Areas | Askari 01 | 214 | 107 | 54 | 36 | 7 | 11 |  | LIVE - 100% Completed | 100% | 107 | 3654552.44 | 548182.866 | 3106369.574 | -1 |  | 0.5 | 1628.35 | 1463.34 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00447 | Timeline not applicable
INT-23-00447 | 2022-12-29 | Peshawar | Peshawar Misc Areas | Askari 02 | 364 | 182 | 148 | 111 | 13 | 24 |  | LIVE - 100% Completed | 100% | 182 | 6767940.43 | 1015191.0645 | 5752749.3655 | -1 |  | 0.5 | 2726.02 | 2062.75 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00447 | Timeline not applicable
INT-23-00447 | 2022-12-29 | Peshawar | Peshawar Misc Areas | Askari 03 | 52 | 26 | 40 | 27 | 3 | 10 |  | LIVE - 100% Completed | 100% | 26 | 2298298.029 | 344744.7044 | 1953553.3247 | -1 |  | 0.5 | 1051.215 | 830.625 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00447 | Timeline not applicable
INT-23-00447 | 2022-12-29 | Peshawar | Peshawar Misc Areas | Askari 04 | 84 | 42 | 71 | 45 | 14 | 12 |  | LIVE - 100% Completed | 100% | 42 | 3444816.139 | 516722.4208 | 2928093.7181 | -1 |  | 0.5 | 1643.39 | 1311.5 | Buried | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00447 | Timeline not applicable
INT-23-00447 | 2022-12-29 | Peshawar | Peshawar Misc Areas | Askari 05 | 142 | 71 | 121 | 96 | 6 | 19 |  | NOT LIVE - RETAIN BUDGET | 95% | 71 | 5237497.18 | 1008218.2072 | 4229278.9728 | -1 |  | 0.5 | 2524.95 | 2071.125 | Buried | 95% | NOT LIVE |  | 95% | 0.95 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 | Hold By Askari Management | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | INT-23-00447 | 2026-07-01
I240437 | 2024-01-18 | Lahore | Askari Lahore | Askari-1 | 720 | 288 | [5 empty] | LIVE - 100% Completed | 100% | 288 | 7568487.9035 | 1135273.1855 | 6433214.718 | -1 |  | 0.4 | 1852.5 | 6008 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Running over Askari's Buried Network | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240437 | Timeline not applicable
I250326 | 2024-11-05 | Multan | Askari Multan | Askari-1 | 182 | 72.8 | 19 | 0 | 1 | 18 |  | LIVE - 100% Completed | 100% | 72.8 | 2509791.8501 | 376468.7775 | 2133323.0726 | -1 |  | 0.4 | 471.5 | 2036.0007 | Hybrid | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250326 | Timeline not applicable
I240684 | 2024-05-16 | Rawalpindi | Askari RWP (4-7-10) | Askari-10 | 372 | 148.8 | 128 | 5 | 8 | 115 |  | LIVE - 100% Completed | 100% | 148.8 | 12016518.425 | 1802477.7638 | 10214040.6613 | -1 |  | 0.4 | 4950.7875 | 3830.75 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 1 |  |  |  | I240684 | Timeline not applicable
I240437 | 2024-01-18 | Lahore | Askari Lahore | Askari-10 P1 | 3018 | 1207.2 | [5 empty] | LIVE - 50% Completed | 50% | 1207.2 | 50000662.3657 | 28750380.8603 | 42500563.0108 | -1 |  | 0.4 | 15177.0388 | 37535.1829 | Hybrid |  | LIVE | Hybrid | 50% | 0.5 | 2026-03-01 | 31 | 32 | -16 | In Progress | Feb-Mar-26 | Apr-2026 | Attachment and Hybrid Model/50% Live | Live - As per Plan | LIVE - 50% Completed | [5 empty] | I240437 | 2026-04-01
I240437 | 2024-01-18 | Lahore | Askari Lahore | Askari-10 P2 | 1734 | 693.6 | [5 empty] | LIVE - 50% Completed | 50% | 693.6 | 42127753.6052 | 24223458.323 | 35808590.5644 | -0.34 |  | 0.4 | 21772.7255 | 10226.0543 | Hybrid |  | LIVE | Hybrid | 50% | 0.5 | 2026-03-01 | 31 | 32 | -16 | In Progress | Feb-Mar-26 | Apr-2026 | Attachment and Hybrid Model/50% Live | Live - As per Plan | LIVE - 50% Completed | [5 empty] | I240437 | 2026-04-01
I240437 | 2024-01-18 | Lahore | Askari Lahore | Askari-10 Sec-S | 216 | 86.4 | [5 empty] | LIVE - 50% Completed | 50% | 43.2 | 2902263.4492 | 1668801.4833 | 1233461.9659 | -1 |  | 0.4 | 413.9019 | 344.9183 | Buried |  | LIVE | Buried | 50% | 0.5 | 2026-03-01 | 31 | 32 | -16 | In Progress | Feb-Mar-26 | Apr-2026 | 6 Buildings Live-6 Remaining | Live - As per Plan | LIVE - 50% Completed | 1 |  |  |  |  | I240437 | 2026-04-01
I240437 | 2024-01-18 | Lahore | Askari Lahore | Askari-11 P1 | 972 | 388.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 388.8 | 39086034.6659 | 39086034.6659 | 0 | -0.85 |  | 0.4 | 18501.8337 | 17167.4136 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240437 | Feedback Awaited
I240437 | 2024-01-18 | Lahore | Askari Lahore | Askari-11 P2 | 1628 | 651.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 651.2 | 25162162.4574 | 25162162.4574 | 0 | -1 |  | 0.4 | 9673.8396 | 9881.3529 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 | 1 |  |  |  | I240437 | Feedback Awaited
I240437 | 2024-01-18 | Lahore | Askari Lahore | Askari-11 P3 | 960 | 384 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 384 | 34570243.5293 | 34570243.5293 | 0 | -0.85 |  | 0.4 | 15736.3245 | 17396.8342 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240437 | Feedback Awaited
I240437 | 2024-01-18 | Lahore | Askari Lahore | Askari-2 | 228 | 91.2 | [5 empty] | LIVE - 100% Completed | 100% | 91.2 | 2749976.342 | 412496.4513 | 2337479.8907 | -1 |  | 0.4 | 636 | 2468.8 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Running over Askari's Buried Network | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240437 | Timeline not applicable
I250326 | 2024-11-05 | Multan | Askari Multan | Askari-2 | 292 | 116.8 | 42 | 3 | 3 | 36 |  | LIVE - 100% Completed | 100% | 116.8 | 4009278.4591 | 601391.7689 | 3407886.6903 | -0.85 |  | 0.4 | 820.9906 | 3597.7453 | Hybrid | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250326 | Timeline not applicable
I250326 | 2024-11-05 | Multan | Askari Multan | Askari-3 | 506 | 202.4 | 64 | 6 | 10 | 48 |  | LIVE - 100% Completed | 100% | 202.4 | 16555149.996 | 2483272.4994 | 14071877.4966 | -1 |  | 0.4 | 6503.97 | 5500.35 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250326 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Ilyas Colony | 616 | 246.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 100% | 246.4 | 6653569.246 | 998035.3869 | 5655533.8591 | 0 |  | 0.4 | 1343.2 | 5092.5 | Hybrid | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 0 | 1 | -47 | Completed | 46054 | Mar-2026 | Some road crossing spurs pending on old Route | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240703 | 2026-03-01
I240684 | 2024-05-16 | Rawalpindi | Askari RWP (4-7-10) | Askari-4 | 864 | 345.6 | 25 | 1 | 1 | 23 |  | LIVE - 100% Completed | 100% | 345.6 | 10931590.177 | 1639738.5265 | 9291851.6505 | -1 |  | 0.4 | 2962.3995 | 1678.698 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240684 | Timeline not applicable
I240437 | 2024-01-18 | Lahore | Askari Lahore | Askari-5 | 1104 | 441.6 | [5 empty] | LIVE - 100% Completed | 100% | 441.6 | 15047904.3885 | 2257185.6583 | 12790718.7302 | 0 |  | 0.4 | 4204.8 | 11907.2 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Running over Askari's Buried Network | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240437 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Jail Road Bird Wood & Waris Co | 454 | 181.6 | [5 empty] | LIVE - 50% Completed | 50% | 90.8 | 9167838.242 | 5271506.9892 | 3896331.2528 | -1 |  | 0.4 | 2933.65 | 6827.8 | Hybrid |  | LIVE | Hybrid | 50% | 0.5 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 | Only Birdwood road live . & Waris Road - Permission Issue (partial live) | Live - Permission Awaited | LIVE - 50% Completed | 1 |  |  |  |  | I240703 | 2026-07-01
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Jinnah Colony Aerial | 216 | 86.4 | [5 empty] | LIVE - 100% Completed | 100% | 86.4 | 1623340 | 243501 | 1379839 | 0 |  | 0.4 | 0 | 1828.5 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Lawarance Road & China Road | 372 | 148.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 148.8 | 11970860 | 11970860 | 0 | -1 |  | 0.4 | 4255 | 7060.2 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46113 | Apr-2026 | permission issue | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240703 | 2026-04-01
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | LC_P1 | 1818 | 727.2 | [5 empty] | LIVE - 100% Completed | 100% | 727.2 | 14027862.1192 | 2104179.3179 | 11923682.8013 | #DIV/0! |  | 0.4 | 2763.5622 | 17394.8122 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | LC_P2 | 742 | 296.8 | [5 empty] | LIVE - 100% Completed | 100% | 296.8 | 8682513.744 | 1302377.0616 | 7380136.6824 | #DIV/0! |  | 0.4 | 1619.3706 | 14828.5166 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | LC_P3 | 790 | 316 | [5 empty] | LIVE - 100% Completed | 100% | 316 | 8152193.0138 | 1222828.9521 | 6929364.0617 | #DIV/0! |  | 0.4 | 2283.503 | 10459.3625 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | LC_P4 | 828 | 331.2 | [5 empty] | LIVE - 100% Completed | 100% | 331.2 | 8439464.4158 | 1265919.6624 | 7173544.7535 | #DIV/0! |  | 0.4 | 2911.377 | 9970.4097 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Alipur Chatta Road Pocket 1 | 666 | 299.7 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 299.7 | 6120322.588 | 6120322.588 |  |  |  | 0.45 | 1062.6 | 6433.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Alipur Chatta Road Pocket 2 | 1622 | 729.9 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 729.9 | 9219199.576 | 9219199.576 |  |  |  | 0.45 | 1041.9 | 10708.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Anarkali Bazar | 362 | 162.9 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 162.9 | 2857555.4 | 2857555.4 |  |  |  | 0.45 | 420.9 | 2287.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | LDA_Ph-1 | 1956 | 782.4 | [5 empty] | LIVE - 100% Completed | 100% | 782.4 | 36425243 | 5463786.45 | 30961456.55 | #DIV/0! |  | 0.4 | 8787.15 | 37420.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | LDA_Ph-2 | 1970 | 788 | [5 empty] | LIVE - 100% Completed | 100% | 788 | 37082122.7013 | 5562318.4052 | 31519804.2961 | #DIV/0! |  | 0.4 | 8845.8 | 38742 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | LDA_Ph-3 | 2082 | 832.8 | [5 empty] | LIVE - 100% Completed | 100% | 832.8 | 33797398.8293 | 5069609.8244 | 28727789.0049 | #DIV/0! |  | 0.4 | 7590 | 38374.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Mall Road | 820 | 328 | [5 empty] | LIVE - 100% Completed | 100% | 328 | 9290951.828 | 1393642.7742 | 7897309.0538 | #DIV/0! |  | 0.4 | 2201.1 | 2440 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | N LHR City P1 | 1940 | 776 | [5 empty] | LIVE - 100% Completed | 100% | 776 | 59050962.7125 | 8857644.4069 | 50193318.3056 | #DIV/0! |  | 0.4 | 28904.1 | 22196.25 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | N LHR City P2 | 1560 | 624 | [5 empty] | LIVE - 100% Completed | 100% | 624 | 45136121.4329 | 6770418.2149 | 38365703.2179 | #DIV/0! |  | 0.4 | 21901.75 | 17875 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240684 | 2024-05-16 | Rawalpindi | Askari RWP (4-7-10) | Askari-7 P1 | 472 | 188.8 | 0 |  |  |  |  | SWAPPED | 0% | 188.8 | 6238771.269 | 0 | 6238771.269 | -1 |  | 0.4 | 1938.3435 | 1150.534 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Askari-12 | Swap Cases | SWAPPED |  |  | Askari 12 | 6355978.3 | 160 | I240684 | Timeline not applicable
I240684 | 2024-05-16 | Rawalpindi | Askari RWP (4-7-10) | Askari-7 P2 | 964 | 385.6 | 0 |  |  |  |  | SWAPPED | 0% | 385.6 | 14207822.697 | 0 | 14207822.697 | -0.5 |  | 0.4 | 4421.6685 | 3298.834 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Askari-12 | Swap Cases | SWAPPED |  |  | Askari 12 | 6355978.3 | 160 | I240684 | Timeline not applicable
I240437 | 2024-01-18 | Lahore | Askari Lahore | Askari-9 | 828 | 331.2 | [5 empty] | LIVE - 100% Completed | 100% | 331.2 | 16227439.496 | 2434115.9244 | 13793323.5716 | -1 |  | 0.4 | 3013 | 14874 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240437 | Timeline not applicable
I240459 | 2024-01-24 | Sialkot | Askari Sialkot | Askari-I | 272 | 163.2 |  | 2 | 6 | 27 |  | LIVE - 100% Completed | 100% | 163.2 | 4206494.4701 | 630974.1705 | 3575520.2996 | 0 |  | 0.6 | 1001.781 | 2587.0521 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240459 | Timeline not applicable
I240459 | 2024-01-24 | Sialkot | Askari Sialkot | Askari-II | 500 | 300 |  | 11 | 3 | 86 |  | LIVE - 100% Completed | 100% | 300 | 7292510.539 | 1093876.5809 | 6198633.9582 | -1 |  | 0.6 | 1736.3694 | 4869.6679 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240459 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Aslam, Mujtuba & Canal Colony | 1036 | 518 | 176 | 24 | 26 | 126 |  | LIVE - 100% Completed | 100% | 518 | 11005899.1832 | 1650884.8775 | 9355014.3057 | -1 |  | 0.5 | 4101.8 | 8720.3523 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240680 | 2024-05-16 | Rahim Yar Khan | RahimYar Khan Ph2 | Atta Housing + Canal + Paradise | 786 | 314.4 | 28 | 2 |  |  |  | LIVE - 60% Completed | 60% | 188.64 | 3844489.114 | 1883799.6659 | 1960689.4481 | -1 |  | 0.4 | 0 | 5116.25 | Hybrid |  | LIVE | Hybrid | 60% | 0.6 | 2026-03-01 | 92 | 93 | 45 | In Progress | 46174 | Jun-2026 | Paradise society NOC issue | Live - Permission Awaited | LIVE - 60% Completed | 1 |  |  |  |  | I240680 | 2026-06-01
INT-23-00440 | 2022-12-29 | Sargodha | Sargodha | Atta Muhammad Coloy HH To 47 Ch | 214 | 107 | 203 | 13 | 20 | 170 | Live | LIVE - 100% Completed | 100% | 107 | 2068997.315 | 310349.5972 | 1758647.7177 | -1 |  | 0.5 | 453.1 | 2566.2 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | This Area will be converted to Hybrid Model | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00440 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Aurangzaib Town | 594 | 237.6 | [5 empty] | LIVE - 100% Completed | 100% | 237.6 | 6125077.7097 | 918761.6565 | 5206316.0533 | -0.85 |  | 0.4 | 1936.1727 | 5066.0685 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
INT-23-00440 | 2022-12-29 | Sargodha | Sargodha | Awan Chowk To Gulberg City | 640 | 320 | 112 | 18 |  | 94 | Live | LIVE - 100% Completed | 100% | 320 | 5106533.0775 | 765979.9616 | 4340553.1159 | -0.5 |  | 0.5 | 711.85 | 8313.2 | Arial | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Converted to Hybrid Model | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00440 | Timeline not applicable
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Azam Garden | 446 | 200.7 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 200.7 | 4086687.8 | 4086687.8 |  |  |  | 0.45 | 611.8 | 3868.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Ayan Garden | 56 | 22.4 |  | 1 | 2 | 14 |  | LIVE - 100% Completed | 100% | 22.4 | 2136679.75 | 320501.9625 | 1816177.7875 | -0.85 |  | 0.4 | 596.8 | 1600.8 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
INT-23-00445 | 2022-12-29 | Rawalpindi | Rawalpindi Misc Areas | Ayub Park | 16 | 8 | 1 |  | 1 |  |  | LIVE - 100% Completed | 100% | 8 | 10620027.25 | 1593004.0875 | 9027023.1625 | #DIV/0! |  | 0.5 | 5145 | 917.238 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00445 | Timeline not applicable
I240683 | 2024-05-15 | Okara | Okara | Ayub Park | 1368 | 547.2 | 863 | 228 |  | 635 |  | LIVE - 100% Completed | 100% | 547.2 | 20188867.029 | 3028330.0543 | 17160536.9746 | -1 |  | 0.4 | 3457.2593 | 22803.5574 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240683 | Timeline not applicable
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Canal & Officer & Faisal | 1310 | 589.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 589.5 | 12101210.618 | 12101210.618 |  |  |  | 0.45 | 1672.1 | 15158.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Defence Colony | 996 | 448.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 448.2 | 9005479.986 | 9005479.986 |  |  |  | 0.45 | 1695.1 | 9502.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250210 | 2024-09-14 | Sargodha | Sargodha | Aziz,Imran,Nawab,Gondl,Fjr,Srwr | 1432 | 572.8 | 46 |  |  | 46 | Live | LIVE - 100% Completed | 100% | 572.8 | 9902784.1803 | 1485417.627 | 8417366.5533 | -1 |  | 0.4 | 1778.9489 | 8959.2066 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250210 | Timeline not applicable
UI2560600 | No Initiation Date | Feeders/Transportations | Hafizabad | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 62013688 | 62013688 |  |  |  |  | 20312.4 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | B-17 Blk-D extn | 588 | 235.2 | 378 | 54 | 44 | 280 |  | LIVE - 100% Completed | 100% | 235.2 | 13737914.575 | 2060687.1862 | 11677227.3887 | -1 |  | 0.4 | 6949.2775 | 5603.71 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250376 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | B-17 BlockD | 1124 | 449.6 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 449.6 | 23877998.0164 | 3581699.7025 | 19281483.3982 | -0.85 |  | 0.4 | 12386.0512 | 8828.5659 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | 1 | Add 9 count |  |  |  | I250376 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | B-17 BlockF-P1 | 1978 | 791.2 | 832 | 92 | 108 | 632 |  | LIVE - 100% Completed | 100% | 791.2 | 50643660.5822 | 7596549.0873 | 40894755.9201 | -1 |  | 0.4 | 23860.8856 | 27114.6427 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | 1 | Add 9 count |  |  |  | I250376 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | B-17 BlockF-P2 | 2512 | 1004.8 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 1004.8 | 45858969.2637 | 6878845.3896 | 37031117.6804 | -0.85 |  | 0.4 | 21030.9924 | 23898.855 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | 1 | Add 9 count |  |  |  | I250376 | Timeline not applicable
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Bagga | 228 | 91.2 |  |  | Yes |  |  | LIVE - 100% Completed | 100% |  | 3869211.6667 | 580381.75 |  |  |  | 0.4 | 1184.5 | 3472.75 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Done-Replaced by Chak Jamal-Shamspur and their Feeder Connectivity-I250205 | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
I250205 | 2024-09-12 | Jhelum | Jhelum Ph2 | Bagh Mohalla & Naya Mohallla | 1252 | 500.8 | 410 | 33 |  |  |  | LIVE - 100% Completed | 100% | 500.8 | 8919579.102 | 1337936.8653 | 7581642.2367 | -1 |  | 0.4 | 1509.95 | 7205.05 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250205 | Timeline not applicable
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Bagh-e-Malir | 792 | 316.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 7735109.7626 | 7735109.7626 |  |  |  |  | 1471.8 | 5638.5317 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250114 | 2024-08-08 | Karachi | Bahadurabad (KTTC) | Bahadurabad & Sharfabad | 2446 | 978.4 | [5 empty] | LIVE - 100% Completed | 100% | 978.4 | 36812251.6233 | 5521837.7435 | 31290413.8798 | -1 |  | 0.4 | 16479 | 8869.7135 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Partial Live | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250114 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Bahadurpur | 1306 | 653 | 848 | 152 | 136 | 560 |  | LIVE - 100% Completed | 100% | 653 | 24999125.9513 | 3749868.8927 | 21249257.0586 | -1 |  | 0.5 | 6784.4893 | 32574.7519 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I250737 | 2025-04-16 | Islamabad | ISB-BT-Ph-8 | Bahria P10 | 2892 | 1156.8 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 1156.8 | 63349646.9943 | 63349646.9943 | 0 | -0.85 |  | 0.4 | 27476.588 | 22003.98 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250737 | 2026-10-01
I250737 | 2025-04-16 | Islamabad | ISB-BT-Ph-8 | Bahria P25 | 1092 | 436.8 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 436.8 | 29163266.9811 | 29163266.9811 | 0 | -1 |  | 0.4 | 13283.1215 | 10448.505 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250737 | 2026-10-01
I250737 | 2025-04-16 | Islamabad | ISB-BT-Ph-8 | Bahria P26 | 2298 | 919.2 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 919.2 | 39121877.9919 | 39121877.9919 | 0 | -0.85 |  | 0.4 | 16916.0232 | 13954.47 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250737 | 2026-10-01
I250737 | 2025-04-16 | Islamabad | ISB-BT-Ph-8 | Bahria P3 | 994 | 397.6 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 80% | 397.6 | 36877033.0426 | 11800650.5736 | 25076382.469 | -1 |  | 0.4 | 18057.9835 | 14755.425 | Buried | 80% | NOT LIVE |  | 80% | 0.8 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 | Civil Work Completion | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250737 | 2026-07-01
I250737 | 2025-04-16 | Islamabad | ISB-BT-Ph-8 | Bahria P6 | 1910 | 764 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 764 | 66366860.458 | 66366860.458 | 0 | -0.5 |  | 0.4 | 27978.974 | 22868.22 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250737 | 2026-10-01
I250737 | 2025-04-16 | Islamabad | ISB-BT-Ph-8 | Bahria P8 | 2144 | 857.6 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 857.6 | 67629564.43 | 67629564.43 | 0 | -1 |  | 0.4 | 30998.5225 | 24492.375 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250737 | 2026-10-01
I250737 | 2025-04-16 | Islamabad | ISB-BT-Ph-8 | Bahria P9 | 2312 | 924.8 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 924.8 | 54789680.353 | 54789680.353 | 0 | -0.85 |  | 0.4 | 25904.8572 | 23125.68 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250737 | 2026-10-01
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Gulberg | 210 | 94.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 94.5 | 2050093.375 | 2050093.375 |  |  |  | 0.45 | 243 | 1904.85 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250210 | 2024-09-14 | Sargodha | Sargodha | Bajwa Colony | 340 | 136 |  |  |  |  | Not Live | NOT LIVE - RETAIN BUDGET | 70% | 136 | 2704965.4045 | 1095510.9888 | 1609454.4157 | -0.85 |  | 0.4 | 416.3356 | 2092.3992 | Buried | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Only Cable Pulling Pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250210 | 2026-04-01
I250211 | 2024-09-14 | Okara | Okara | Bajwa Colony, Samad Pura Road,S | 2438 | 975.2 | 185 | 18 |  | 167 |  | LIVE - 100% Completed | 100% | 975.2 | 21950451.45 | 3292567.7175 | 18657883.7325 | -0.68 |  | 0.4 | 3810.4 | 23587.15 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250211 | Timeline not applicable
I240442 | 2024-01-19 | Chitral | Chitral Ph1 | Bakarabad & Jughoor | 714 | 285.6 | 233 | 225 | 2 | 7 |  | NOT LIVE - RETAIN BUDGET | 0% | 285.6 | 19216845.1332 | 19216845.1332 | 0 | -1 |  | 0.4 | 4785.5637 | 24559.2583 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 3 Months | Jul-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240442 | 2026-07-01
I250205 | 2024-09-12 | Jhelum | Jhelum Ph2 | Bala Gujjran | 246 | 98.4 | 36 | 1 |  |  |  | LIVE - 100% Completed | 100% | 98.4 | 2525046 | 378756.9 | 2146289.1 | -0.85 |  | 0.4 | 0 | 7784.95 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250205 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Band Road Extension & Makhdumpu | 2086 | 834.4 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 834.4 | 9218380.3807 | 9218380.3807 |  |  |  |  | 960.2005 | 12009.6467 | Hybrid | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 months | Jun-2026 | TMA stop the civip work | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Hassan Town | 2056 | 925.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 925.2 | 13007997.672 | 13007997.672 |  |  |  | 0.45 | 2387.4 | 13010 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Bari Chum | 1134 | 453.6 | 1134 | 130 | 109 | 14 | 7 |  | 100% | 453.6 | 8863381.6013 | 1329507.2402 | 7533874.3611 | -0.5 |  | 0.4 | 749.3333 | 12524.3923 | Arial | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Barkat Town | 592 | 236.8 |  |  |  |  | NOT ENERGISED AS YET | LIVE - 100% Completed | 100% | 236.8 | 7571571.9902 | 1135735.7985 | 6435836.1917 | -1 |  | 0.4 | 1448.1518 | 6968.4368 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250206 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Barrage Colony | 608 | 243.2 | 475 | 440 | 17 | 1 | 0 | LIVE - 100% Completed | 100% | 243.2 | 2945464.0374 | 441819.6056 | 2503644.4318 | -1 |  | 0.4 | 0 | 4444.3008 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Due to Permission issue area live in aerial | Live - Permission Awaited | LIVE - 100% Completed | [5 empty] | I240702 | Timeline not applicable
I260296 | No Initiation Date | Sukkur | Sukkur | Barrage Colony | 964 | 385.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 80% |  | 10509049.2072 | 3362895.7463 |  |  |  |  | 1430 | 16113.8564 | Hybrid | 80% | NOT LIVE |  | 80% | 0.8 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Work in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Barrage Officer Colony | 114 | 45.6 | 113 | 105 | 5 | 1 | 0 | LIVE - 100% Completed | 100% | 45.6 | 1016258.9922 | 152438.8488 | 863820.1434 | -1 |  | 0.4 | 0 | 1412.8622 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Due to Permission issue area live in aerial | Live - Permission Awaited | LIVE - 100% Completed | [5 empty] | I240702 | Timeline not applicable
I250210 | 2024-09-14 | Sargodha | Sargodha | Bashir,Chuna Bhati,Jamil | 1038 | 415.2 | 53 |  |  | 53 | Live | LIVE - 100% Completed | 100% | 415.2 | 7733889.0635 | 1160083.3595 | 6573805.704 | -1 |  | 0.4 | 977.0391 | 7095.4977 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250210 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Bast Shor Kot | 508 | 254 | 88 | 11 | 10 | 67 |  | LIVE - 100% Completed | 100% | 254 | 5197129.05 | 779569.3575 | 4417559.6925 | -1 |  | 0.5 | 1248.9 | 3729.4 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Bhatti Colony | 536 | 214.4 |  |  |  |  | NOT ENERGISED AS YET | SWAPPED | 0% | 214.4 | 5635736.0276 | 0 | 5635736.0276 | -0.5 |  | 0.4 | 992.4627 | 4986.8027 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Meraj Housing | Swap Cases | SWAPPED |  |  | Meraj Housing | 22604832.2609 | 542 | I250206 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Bhutta Colony | 94 | 37.6 | 67 | 10 | 11 | 46 |  | LIVE - 100% Completed | 100% | 37.6 | 2844066.7289 | 426610.0093 | 2417456.7196 | -1 |  | 0.4 | 484.15 | 1372.364 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
INT-23-00442 | 2022-12-29 | Sahiwal | Sahiwal Misc Areas | Bhutto Colony | 1860 | 930 | 245 | 77 | 50 |  |  | LIVE - 100% Completed | 100% | 930 | 12286385.28 | 1842957.792 | 10443427.488 | -0.85 |  | 0.5 | 1582.4 | 14056.3 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00442 | Timeline not applicable
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Bicket Gunj | 654 | 261.6 | 654 | 91 | 76 | 11 | 4 |  | 100% | 261.6 | 7057021.5905 | 1058553.2386 | 5998468.352 | -1 |  | 0.4 | 591.3333 | 6996.1797 | Arial | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Bilal City | 170 | 68 |  | 2 | 2 | 10 | Occupancy :100 | LIVE - 100% Completed | 100% | 68 | 2142858.4549 | 321428.7682 | 1821429.6867 | -1 |  | 0.4 | 406.1685 | 1359.1952 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Bilal Colony & Mukhtyar Town | 1444 | 722 | 343 | 33 | 26 | 284 |  | LIVE - 100% Completed | 100% | 722 | 15526564.503 | 2328984.6755 | 13197579.8276 | -1 |  | 0.5 | 6066.45 | 12421.7938 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Bilal Town | 2212 | 884.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 19560927.9296 | 19560927.9296 |  |  |  |  | 3424.19 | 14348.0718 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Bismillah City & Ext | 1042 | 416.8 | 2000 | 1000 | 60 | 2 | 9 | LIVE - 100% Completed | 100% | 416.8 | 11146535.1834 | 1671980.2775 | 9474554.9059 | 0 |  | 0.4 | 1601.49 | 8984.2228 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240702 | Timeline not applicable
I250213 | 2024-09-14 | Mardan | Mardan | Bismillah Town | 512 | 204.8 | 512 | 45 | 44 | 1 | 0 |  | 100% | 204.8 | 11678766.9776 | 1751815.0466 | 9926951.931 | -1 |  | 0.4 | 3118.8401 | 7097.385 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250213 | Timeline not applicable
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | HVTR & MB & POR & JBR | 2656 | 1195.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1195.2 | 19840408.232 | 19840408.232 |  |  |  | 0.45 | 3666.2 | 18775 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Iqbal Garden | 372 | 167.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 167.4 | 3189798.92 | 3189798.92 |  |  |  | 0.45 | 491.05 | 3507.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00446 | 2022-12-29 | Wahh | Wah Cant Misc Ares | Block N & O New City Ph2 | 1008 | 504 | 0 |  |  |  |  | REMOVE BUDGET (T) | 0% | 504 | 28794080.4397 | 0 | 28794080.4397 | #DIV/0! |  | 0.5 | 16996.4657 | 13891.6885 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | remove (after June) | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | INT-23-00446 | Timeline not applicable
INT-23-00446 | 2022-12-29 | Wahh | Wah Cant Misc Ares | Block P New City Ph2 | 614 | 307 | 0 |  |  |  |  | REMOVE BUDGET (T) | 0% | 307 | 16449167.1098 | 0 | 16449167.1098 | #DIV/0! |  | 0.5 | 9620.6839 | 7285.516 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | remove (after June) | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | INT-23-00446 | Timeline not applicable
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Kassoki Road P1 | 1050 | 472.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 472.5 | 8117194.944 | 8117194.944 |  |  |  | 0.45 | 1438.65 | 8011.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00446 | 2022-12-29 | Wahh | Wah Cant Misc Ares | Block Q New City Ph2 | 304 | 152 | 0 |  |  |  |  | REMOVE BUDGET (T) | 0% | 152 | 12498736.1986 | 0 | 12498736.1986 | #DIV/0! |  | 0.5 | 7461.3414 | 7969.345 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | remove (after June) | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | INT-23-00446 | Timeline not applicable
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Kassoki Road P2 | 1096 | 493.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 493.2 | 8044576.308 | 8044576.308 |  |  |  | 0.45 | 1438.65 | 7940 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00446 | 2022-12-29 | Wahh | Wah Cant Misc Ares | Block R & S New City Ph2 | 1548 | 774 | 0 |  |  |  |  | REMOVE BUDGET (T) | 0% | 774 | 37192045.7419 | 0 | 37192045.7419 | #DIV/0! |  | 0.5 | 23169.9461 | 20692.3719 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | remove (after June) | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | INT-23-00446 | Timeline not applicable
INT-23-00446 | 2022-12-29 | Wahh | Wah Cant Misc Ares | Block U & V New City Ph2 | 554 | 277 | 0 |  |  |  |  | REMOVE BUDGET (T) | 0% | 277 | 16449728.5186 | 0 | 16449728.5186 | #DIV/0! |  | 0.5 | 9532.7881 | 7969.345 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | remove (after June) | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | INT-23-00446 | Timeline not applicable
INT-23-00446 | 2022-12-29 | Wahh | Wah Cant Misc Ares | Block W & Y New City Ph2 | 570 | 285 | 0 |  |  |  |  | REMOVE BUDGET (T) | 0% | 285 | 16159860.2171 | 0 | 16159860.2171 | #DIV/0! |  | 0.5 | 9345.4869 | 7285.516 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | remove (after June) | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | INT-23-00446 | Timeline not applicable
INT-23-00446 | 2022-12-29 | Wahh | Wah Cant Misc Ares | Block Y & Z New City Ph2 | 554 | 277 | 0 |  |  |  |  | REMOVE BUDGET (T) | 0% | 277 | 16387309.4963 | 0 | 16387309.4963 | #DIV/0! |  | 0.5 | 9495.9829 | 7969.345 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | remove (after June) | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | INT-23-00446 | Timeline not applicable
I240435 | 2024-01-18 | Islamabad | Top City Islamabad | Block-A | 2270 | 1135 | 294 | 21 | 27 | 246 |  | LIVE - 100% Completed | 100% | 1135 | 60990062.0906 | 9148509.3136 | 51841552.777 | -1 |  | 0.5 | 32492.7632 | 30129.5029 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240435 | Timeline not applicable
I240435 | 2024-01-18 | Islamabad | Top City Islamabad | Block-B | 1576 | 788 | 297 | 16 | 94 | 187 |  | LIVE - 100% Completed | 100% | 788 | 54012524.1069 | 8101878.616 | 45910645.4909 | -0.5 |  | 0.5 | 29684.691 | 26861.8 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240435 | Timeline not applicable
I240435 | 2024-01-18 | Islamabad | Top City Islamabad | Block-C | 2308 | 1154 | 248 | 18 | 44 | 186 |  | LIVE - 100% Completed | 100% | 1154 | 59900388.9159 | 8985058.3374 | 50915330.5785 | -1 |  | 0.5 | 31688.0061 | 28568.9 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240435 | Timeline not applicable
I240435 | 2024-01-18 | Islamabad | Top City Islamabad | Block-D | 1548 | 774 | 339 | 27 | 40 | 272 |  | LIVE - 100% Completed | 100% | 774 | 41952267.9316 | 6292840.1897 | 35659427.7418 | -1 |  | 0.5 | 22414.5467 | 20692.3719 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240435 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Bodla Town | 1514 | 757 | 791 | 125 | 119 | 547 |  | LIVE - 100% Completed | 100% | 757 | 13860044.68 | 2079006.702 | 11781037.978 | -0.5 |  | 0.5 | 2602.6 | 13328.4 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240678 | 2024-05-16 | Sialkot | Sialkot | Bograh Ext | 528 | 211.2 |  | 0 | 0 | 0 | Not Lived Yet | NOT LIVE - RETAIN BUDGET | 0% | 211.2 | 2826961.8911 | 2826961.8911 | 0 | -0.5 |  | 0.4 | 0 | 3652.5099 | Arial | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240678 | Feedback Awaited
I240678 | 2024-05-16 | Sialkot | Sialkot | Bonkan | 550 | 220 |  | 90 | 23 | 306 |  | LIVE - 100% Completed | 100% | 220 | 6807438.958 | 1021115.8437 | 5786323.1143 | -1 |  | 0.4 | 1017.5 | 4003.75 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
INT-23-00437 | 2022-12-29 | Lahore | Lahore Misc Areas | BOR | 788 | 394 | [5 empty] | LIVE - 100% Completed | 100% | 394 | 10556905.2608 | 1583535.7891 | 8973369.4717 | 0 |  | 0.5 | 2616.2794 | 8000.1038 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00437 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Buch Villas Extn. | 464 | 185.6 |  |  |  |  | included in BUCH Villas | LIVE - 100% Completed | 100% | 185.6 | 13726018.7013 | 2058902.8052 | 11667115.8961 | -0.85 |  | 0.4 | 5905.207 | 6127.3306 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Bukhari Villas | 476 | 238 | 134 | 16 | 31 | 87 |  | LIVE - 100% Completed | 100% | 238 | 6889778.3736 | 1033466.756 | 5856311.6176 | -1 |  | 0.5 | 1283.4 | 4783.5428 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240518 | 2024-02-27 | Islamabad | Naval Anchorage and other Areas (ISB) | C-18 | 832 | 416 | 115 | 5 | 16 | 94 |  | LIVE - 100% Completed | 100% | 416 | 8691545.13 | 1303731.7695 | 7387813.3605 | 0 |  | 0.5 | 2074 | 12585.174 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240518 | Timeline not applicable
I240701 | 2024-05-16 | Feeders/Transportations | Swat | Cable Stringing | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 2610550 | 1305275 | 1305275 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240701 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Callachi Society | 1626 | 650.4 | [5 empty] | LIVE - 50% Completed | 50% | 325.2 | 24132567.1137 | 13876226.0904 | 10256341.0233 | -1 |  | 0.4 | 9223.8191 | 5888.3008 | Hybrid |  | LIVE | Hybrid | 50% | 0.5 | 2026-03-01 | 214 | 215 | 167 | In Progress | 6 months | Oct-2026 | Only MDUs live. (partial live) | Live - As per Plan | LIVE - 50% Completed | 1 |  |  |  |  | I240705 | 2026-10-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Camp Gujran | 556 | 222.4 |  | 0 | 0 | 0 | Not Lived Yet | NOT LIVE - RETAIN BUDGET | 0% | 222.4 | 3779405.0163 | 3779405.0163 | 0 | -1 |  | 0.4 | 0 | 5370.0082 | Arial | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240678 | Feedback Awaited
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Kot Hashmat 1 & Kot Hashmat 2 | 920 | 414 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 414 | 10423168.046 | 10423168.046 |  |  |  | 0.45 | 2091.85 | 8088.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Canal Burg | 206 | 82.4 |  | 1 | 0 | 3 | Occupancy : 150 | LIVE - 100% Completed | 100% | 82.4 | 3532696.25 | 529904.4375 | 3002791.8125 | 0 |  | 0.4 | 770.5 | 2781.25 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Canal Cantt Views | 1048 | 524 | 259 | 31 | 35 | 193 |  | LIVE - 100% Completed | 100% | 524 | 14637051.7975 | 2195557.7696 | 12441494.0279 | -0.5 |  | 0.5 | 2572.8 | 9713.0699 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Canal Garden_Canal Rd | 342 | 136.8 |  | 0 | 0 | 0 | Yet not active | LIVE - 100% Completed | 100% | 136.8 | 3817833.337 | 572675.0005 | 3245158.3364 | -1 | Zia Town | 0.4 | 621 | 3438.5351 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Canal Park | 140 | 56 |  | 9 | 12 | 59 | Occupancy : 150 | LIVE - 100% Completed | 100% | 56 | 1611020 | 241653 | 1369367 | 0 |  | 0.4 | 0 | 3991.5 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Madina Town | 238 | 107.1 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 107.1 | 3375209.592 | 3375209.592 |  |  |  | 0.45 | 734.85 | 1926.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240519 | 2024-02-27 | Gujranwala | Royal Palm & Canal View | Canal View | 1950 | 780 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 780 | 63778454.5611 | 63778454.5611 | 0 | -1 |  | 0.4 | 31968.5498 | 26764.0327 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | NOC awaited/Need to retain | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240519 | Feedback Awaited
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Makkah Town & Ali Town | 2248 | 1011.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1011.6 | 17987941.88 | 17987941.88 |  |  |  | 0.45 | 3050.95 | 17191.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240704 | 2024-05-15 | Multan | Multan Ph3 | Canal View Multan | 564 | 225.6 | - | - | - | - |  | LIVE - 100% Completed | 100% | 225.6 | 6117188.75 | 917578.3125 | 5199610.4375 | -1 |  | 0.4 | 971.75 | 5784 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Cantt | 314 | 125.6 | 314 | 263 | 210 | 37 | 16 |  | 100% | 125.6 | 15812329.1932 | 2371849.379 | 13440479.8142 | -0.85 |  | 0.4 | 3882.4 | 11532.4381 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
I240190 | 2023-09-27 | Sialkot | Sialkot Cantt | Cantt Commercial | 1382 | 691 |  | 169 | 52 | 1059 |  | LIVE - 100% Completed | 100% | 691 | 13840028.9636 | 2076004.3445 | 11764024.619 | -1 |  | 0.5 | 4784.8148 | 0 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240190 | Timeline not applicable
I240190 | 2023-09-27 | Sialkot | Sialkot Cantt | Cantt.P_1 | 748 | 374 |  | 72 | 28 | 576 |  | LIVE - 100% Completed | 100% | 374 | 36030554.2106 | 5404583.1316 | 30625971.079 | -0.85 |  | 0.5 | 16522.56 | 0 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240190 | Timeline not applicable
I240190 | 2023-09-27 | Sialkot | Sialkot Cantt | Cantt.P_2 | 884 | 442 |  | 102 | 34 | 672 |  | LIVE - 100% Completed | 100% | 442 | 26416626.7324 | 3962494.0099 | 22454132.7225 | -1 |  | 0.5 | 11008.4969 | 0 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240190 | Timeline not applicable
I240190 | 2023-09-27 | Sialkot | Sialkot Cantt | Cantt.P_3 | 562 | 281 |  | 86 | 23 | 445 |  | LIVE - 100% Completed | 100% | 281 | 39763165.7338 | 5964474.8601 | 33798690.8737 | -0.85 |  | 0.5 | 18195.255 | 0 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240190 | Timeline not applicable
I240189 | 2023-09-27 | Quetta | Quetta Cantt | Cantt_P1 | 1108 | 554 | 570 | 24 | 26 | 520 |  | LIVE - 100% Completed | 100% | 554 | 31883343.1412 | 4782501.4712 | 27100841.67 | -1 |  | 0.5 | 10028 | 6538.351 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240189 | Timeline not applicable
I240189 | 2023-09-27 | Quetta | Quetta Cantt | Cantt_P2 | 4717 | 2358.5 | 805 | 25 | 18 | 764 |  | LIVE - 100% Completed | 100% | 2358.5 | 90886442.0248 | 13632966.3037 | 77253475.721 | -0.5 |  | 0.5 | 24615.7281 | 32429.0363 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240189 | Timeline not applicable
I240678 | 2024-05-16 | Sialkot | Sialkot | Capital Rd & Model Town Ext | 358 | 143.2 |  | 27 | 19 | 166 | Updated 385 HP, but Rizwan colony in Not lived yet | LIVE - 100% Completed | 100% | 143.2 | 2125684.9966 | 318852.7495 | 1806832.2471 | -1 |  | 0.4 | 0 | 3724.1618 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
INT-23-00437 | 2022-12-29 | Lahore | Lahore Misc Areas | Cavalry Ext Aerial | 1792 | 896 | [5 empty] | LIVE - 100% Completed | 100% | 896 | 8882245.8522 | 1332336.8778 | 7549908.9744 | -1 |  | 0.5 | 0 | 16083.3595 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00437 | Timeline not applicable
INT-23-00437 | 2022-12-29 | Lahore | Lahore Misc Areas | Cavalry Ext Hybrid | 1792 | 896 | [5 empty] | LIVE - 100% Completed | 100% | 896 | 19687880.1022 | 2953182.0153 | 16734698.0869 | 0 |  | 0.5 | 3539.25 | 16083.3595 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00437 | Timeline not applicable
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Center Colony | 288 | 115.2 | 288 | 61 | 56 | 4 | 1 |  | 100% | 115.2 | 5039998.7945 | 755999.8192 | 4283998.9753 | -1 |  | 0.4 | 786.6667 | 6113.7633 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
I240440 | 2024-01-19 | Lahore | Al Jalil & Al khalil LHE | Central Park Housing-P1 | 1526 | 610.4 | [5 empty] | REMOVE BUDGET (P) | 0% | 610.4 | 23697315.4167 | 0 | 23697315.4167 | -1 |  | 0.4 | 7337.4 | 20817 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I240440 | Timeline not applicable
I240440 | 2024-01-19 | Lahore | Al Jalil & Al khalil LHE | Central Park Housing-P2 | 1200 | 480 | [5 empty] | REMOVE BUDGET (P) | 0% | 480 | 16799037.5347 | 0 | 16799037.5347 | -0.85 |  | 0.4 | 5178.6 | 15960 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I240440 | Timeline not applicable
I240440 | 2024-01-19 | Lahore | Al Jalil & Al khalil LHE | Central Park Housing-P3 | 1206 | 482.4 | [5 empty] | REMOVE BUDGET (P) | 0% | 482.4 | 20897023.9583 | 0 | 20897023.9583 | -1 |  | 0.4 | 7545.3 | 19717.5 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  | 1 |  | 0 |  | I240440 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Chah Hadi Wala | 384 | 192 | 66 | 5 | 10 | 51 |  | LIVE - 100% Completed | 100% | 192 | 7121761.05 | 1068264.1575 | 6053496.8925 | -1 |  | 0.5 | 2319 | 4128.15 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I250210 | 2024-09-14 | Sargodha | Sargodha | Chak 43 NB,Ali & Yousuf Park | 832 | 332.8 | 13 |  | 1 | 12 | Live | LIVE - 100% Completed | 100% | 332.8 | 5852374.0686 | 877856.1103 | 4974517.9583 | -0.85 |  | 0.4 | 925.75 | 5300.7058 | Buried | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250210 | Timeline not applicable
INT-23-00442 | 2022-12-29 | Sahiwal | Sahiwal Misc Areas | Chak 89 | 916 | 458 | 173 | 50 | 22 |  |  | LIVE - 100% Completed | 100% | 458 | 7372192.3082 | 1105828.8462 | 6266363.462 | -1 |  | 0.5 | 1821.9225 | 8714.5521 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00442 | Timeline not applicable
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Chak Akka | 1976 | 790.4 |  |  | Yes |  |  | REMOVE BUDGET (P) | 0% |  | 8306728.6407 | 0 |  |  |  |  | 0 | 21461.7775 | Arial | 100% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | 2km backhauling req. beside NHA /14km away from PoP/Need to Remove | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | #N/A | Timeline not applicable
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Chak Doulat | 154 | 61.6 |  |  | Yes |  |  | REMOVE BUDGET (P) | 0% |  | 1603424.197 | 0 |  |  |  | 0.4 | 328.9 | 2199.4608 | Hybrid | 100% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | 14.5km backhauling req.and distance from would be 22km/Need to Remove | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | #N/A | Timeline not applicable
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Chak Hafizan | 168 | 67.2 |  |  | Yes |  |  | REMOVE BUDGET (P) | 0% |  | 1785086.5201 | 0 |  |  |  | 0.4 | 418.6 | 1833.4721 | Hybrid | 100% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | 14.5km backhauling req.and distance from would be 22km/Need to Remove | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | #N/A | Timeline not applicable
I250205 | 2024-09-12 | Jhelum | Jhelum Ph2 | Chal Jamal | 312 | 124.8 |  |  | Yes |  |  | SWAPPED | 0% | 124.8 | 5688152.996 | 0 | 5688152.996 | -1 |  | 0.4 | 1657.15 | 5093.85 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped by Gharmala, Gharmala Monan & Chittan | Swap Cases | SWAPPED |  |  | Gharmala, Gharmala Monan & Chittan | 5811629.0927 | 628 | I250205 | Timeline not applicable
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Qazipura_Qadirabad Srndg Area | 806 | 362.7 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 362.7 | 7316177.114 | 7316177.114 |  |  |  | 0.45 | 1368.5 | 6516.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Chandni Chowk | 1390 | 556 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 556 | 9944758.6132 | 9944758.6132 | 0 | -1 |  | 0.4 | 600 | 3107.7876 | Arial | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46113 | Apr-2026 | Permission Issue | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240705 | 2026-04-01
INT-23-00447 | 2022-12-29 | Peshawar | Peshawar Misc Areas | Charkhana P01 | 4508 | 2254 | 189 | 146 | 15 | 28 | Akbar Colony,Usmania colony,Amin Colony,Shah Faisal Colony Street 1,Street 2,Ghari Arbab,Ghulam Haider colony, | LIVE - 100% Completed | 100% | 2254 | 35531410.3937 | 5329711.559 | 30201698.8346 | -1 |  | 0.5 | 4035.35 | 47919.6382 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00447 | Timeline not applicable
INT-23-00447 | 2022-12-29 | Peshawar | Peshawar Misc Areas | Charkhana P02 | 2780 | 1390 | 472 | 397 | 21 | 54 | Manakro,Malik Street,Zaid Street,Khalid street,Mouhalla Mushtaq abad,Umeed Abad no1,2,TV Colony | LIVE - 100% Completed | 100% | 1390 | 28190592.2818 | 4228588.8423 | 23962003.4395 | -1 |  | 0.5 | 3888.15 | 32991.7755 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00447 | Timeline not applicable
INT-23-00447 | 2022-12-29 | Peshawar | Peshawar Misc Areas | Charkhana P03 | 2992 | 1496 | 124 | 88 | 17 | 19 | Riaz Shaheed Colony,Sher Ali Street,Haider lane,Rehman Street | LIVE - 100% Completed | 100% | 1496 | 29088930.8481 | 4363339.6272 | 24725591.2209 | -1 |  | 0.5 | 3703 | 33364.5416 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00447 | Timeline not applicable
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Sattellite Town | 512 | 230.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 230.4 | 5795516.4 | 5795516.4 |  |  |  | 0.45 | 1143.1 | 4711.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250375 | 2024-11-25 | Bahawalpur | Bahawalpur (P3) | Cheema Town Ph-2 | 700 | 280 |  | 17 | 28 | 166 |  | LIVE - 100% Completed | 100% | 280 | 9068984.096 | 1360347.6144 | 7708636.4816 | -0.765 |  | 0.4 | 1833.1 | 6447.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250375 | Timeline not applicable
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Shalimar_Al Hamra Town | 540 | 243 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 243 | 4715244.6 | 4715244.6 |  |  |  | 0.45 | 900.45 | 4371.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Sukheke Hafizabad Road | 2214 | 996.3 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 996.3 | 12064838.7 | 12064838.7 |  |  |  | 0.45 | 1178.75 | 15636.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240438 | 2024-01-09 | Lahore | Chinar Bagh Lahore | Chinar_Bagh_P01 | 694 | 277.6 | [5 empty] | LIVE - 100% Completed | 100% | 277.6 | 14738549.5 | 2210782.425 | 12527767.075 | -1 |  | 0.4 | 4373.45 | 11558.4 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240438 | Timeline not applicable
I240438 | 2024-01-09 | Lahore | Chinar Bagh Lahore | Chinar_Bagh_P02 | 962 | 384.8 | [5 empty] | LIVE - 100% Completed | 100% | 384.8 | 14712946.1454 | 2206941.9218 | 12506004.2236 | -1 |  | 0.4 | 3792.5673 | 12190.7545 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 1 |  |  |  | I240438 | Timeline not applicable
I240438 | 2024-01-09 | Lahore | Chinar Bagh Lahore | Chinar_Bagh_P03 | 898 | 359.2 | [5 empty] | LIVE - 100% Completed | 100% | 359.2 | 12654960.868 | 1898244.1302 | 10756716.7378 | -1 |  | 0.4 | 3339.7 | 10666.25 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 1 |  |  |  | I240438 | Timeline not applicable
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Chitan | 294 | 117.6 | 29 | 1 |  | Yes |  | LIVE - 100% Completed | 100% |  | 4559364.7847 | 683904.7177 |  |  |  | 0.4 | 1496.15 | 3536.55 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
I240442 | 2024-01-19 | Chitral | Chitral Ph1 | Chitral City | 3118 | 1247.2 | 236 | 219 | 21 | 16 |  | LIVE - 50% Completed | 50% | 623.6 | 88240636.8765 | 50738366.204 | 37502270.6725 | 0 |  | 0.4 | 23264.677 | 93467.1588 | Hybrid |  | LIVE | Hybrid | 50% | 0.5 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 |  | Live - As per Plan | LIVE - 50% Completed | 1 |  |  |  |  | I240442 | 2026-07-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Christian Town & Muslim Town | 868 | 347.2 |  | 79 | 124 | 405 |  | LIVE - 100% Completed | 100% | 347.2 | 10976792.667 | 1646518.9 | 9330273.7669 | -1 |  | 0.4 | 2499.5129 | 8034.3104 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Sultan Residencia Park | 464 | 208.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 208.8 | 6438506.696 | 6438506.696 |  |  |  | 0.45 | 1337.45 | 5843.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Circular Road | 628 | 251.2 |  | 12 | 19 | 143 |  | LIVE - 100% Completed | 100% | 251.2 | 8168013.75 | 1225202.0625 | 6942811.6875 | -1 |  | 0.4 | 1600.8 | 6771.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
I250205 | 2024-09-12 | Jhelum | Jhelum Ph2 | Citi Housing Block D_E_F Extn. | 1426 | 570.4 |  |  | Yes |  |  | NOT LIVE - RETAIN BUDGET | 0% | 570.4 | 58088988.301 | 58088988.301 | 0 | -0.85 |  | 0.4 | 36757.3022 | 24213.9766 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250205 | Feedback Awaited
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | CITI Housing D Block | 524 | 209.6 |  | 32 | 21 | 154 | Occupancy : 350 | LIVE - 100% Completed | 100% | 209.6 | 15950173.12 | 2392525.968 | 13557647.152 | -1 |  | 0.4 | 6077.86 | 10171.056 | Buried | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
I240678 | 2024-05-16 | Sialkot | Sialkot | CITI Housing E_F_G | 1894 | 757.6 |  | 158 | 324 | 1324 |  | LIVE - 100% Completed | 100% | 757.6 | 46492805.0893 | 6973920.7634 | 39518884.3259 | -1 |  | 0.4 | 20381.5511 | 28725.9766 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Citi Housing Jinnah Block-P1 | 2128 | 851.2 | - | - | - | - |  | LIVE - 100% Completed | 100% | 851.2 | 43696979.714 | 6554546.9571 | 37142432.7569 | -1 |  | 0.4 | 19665 | 17975.65 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Citi Housing Jinnah Block-P2 | 2024 | 809.6 | - | - | - | - |  | LIVE - 100% Completed | 100% | 809.6 | 44461740.044 | 6669261.0066 | 37792479.0374 | -1 |  | 0.4 | 19959.65 | 17885.75 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
INT-23-00441 | 2022-12-29 | Faisalabad | Faisalabad Misc Areas | CITI Housing PH-2_Main | 2620 | 1310 |  | 48 | 75 | 419 | Occupancy : 1000 | LIVE - 100% Completed | 100% | 1310 | 60760833.7639 | 9114125.0646 | 51646708.6993 | -1 |  | 0.5 | 37093.8523 | 29768.5506 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00441 | Timeline not applicable
I240678 | 2024-05-16 | Sialkot | Sialkot | Citi Housing Sec-A_Sectn-1 | 1426 | 570.4 |  | 113 | 264 | 993 |  | LIVE - 100% Completed | 100% | 570.4 | 36040392.6333 | 5406058.895 | 30634333.7383 | -1 |  | 0.4 | 15161.2511 | 24213.9766 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Citi Housing Sector A | 526 | 263 | - | - | - | - |  | LIVE - 100% Completed | 100% | 263 | 13287927.285 | 1993189.0927 | 11294738.1923 | -0.425 |  | 0.5 | 7532.65 | 6395.95 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Citi Housing Sector B | 1082 | 541 | - | - | - | - |  | LIVE - 100% Completed | 100% | 541 | 24670022.42 | 3700503.363 | 20969519.057 | -1 |  | 0.5 | 13177.8 | 10996.8 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Citi Housing Sector C | 1274 | 637 | - | - | - | - |  | LIVE - 100% Completed | 100% | 637 | 24448471.3 | 3667270.695 | 20781200.605 | -0.85 |  | 0.5 | 13471.15 | 11414.4 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Citi Housing Sector D | 1256 | 502.4 | - | - | - | - |  | LIVE - 100% Completed | 100% | 502.4 | 29894273.638 | 4484141.0457 | 25410132.5923 | -1 |  | 0.4 | 13732.8 | 12352.55 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I250377 | 2024-11-25 | Peshawar | Peshawar (P2) | City Side P01 | 1048 | 419.2 | 145 | 131 | 10 | 4 | Yakatoot ,Yakatoot Gate,Darakhshan Colony,Ganj Gate, | NOT LIVE - RETAIN BUDGET | 0% | 419.2 | 15290998.9 | 15290998.9 | 0 | -0.85 |  | 0.4 | 2301.15 | 11482.83 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 4 Months | Jul-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250377 | 2026-07-01
I250377 | 2024-11-25 | Peshawar | Peshawar (P2) | City Side P02 | 976 | 390.4 | 159 | 124 | 16 | 19 | Shaheen Muslim Town, | LIVE - 100% Completed | 100% | 390.4 | 16459433.1524 | 2468914.9729 | 13990518.1795 | -1 |  | 0.4 | 2727.8 | 11588.6728 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Partial Active | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250377 | Timeline not applicable
I250377 | 2024-11-25 | Peshawar | Peshawar (P2) | City Side P03 | 1060 | 424 | 219 | 178 | 19 | 22 | Shaikh Abad street,1,2,3,4,5,6,7,8,Chairman Office ,Phandu Road,Al Sudais street, | LIVE - 100% Completed | 100% | 424 | 10937734.6527 | 1640660.1979 | 9297074.4548 | -0.85 |  | 0.4 | 1185.65 | 9617.9111 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250377 | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Civil Line Area BOQ | 1728 | 691.2 | [5 empty] | LIVE - 100% Completed | 100% | 691.2 | 17833985.5 | 2675097.825 | 15158887.675 | -1 |  | 0.4 | 2220 | 15442.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Civil lines | 598 | 239.2 |  |  |  |  | NOT ENERGISED AS YET | NOT LIVE - RETAIN BUDGET | 0% | 239.2 | 4866797.75 | 4866797.75 | 0 | -1 |  | 0.4 | 422.05 | 6339.4 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46113 | Apr-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-04-01
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Civil Lines | 1248 | 499.2 | [5 empty] | LIVE - 100% Completed | 100% | 499.2 | 17792789.955 | 2668918.4932 | 15123871.4617 | -1 |  | 0.4 | 9119.5 | 16572.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Sunny Garden | 580 | 261 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 261 | 15393935.114 | 15393935.114 |  |  |  | 0.45 | 7372.5 | 5931.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560600 | No Initiation Date | Feeders/Transportations | Hafizabad | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 6360000 | 6360000 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Civil lines Lower End | 280 | 112 | [5 empty] | LIVE - 100% Completed | 100% | 112 | 2962483.996 | 444372.5994 | 2518111.3966 | 0 |  | 0.4 | 538.2 | 2087.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Tulip City | 908 | 408.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 408.6 | 23406249.736 | 23406249.736 |  |  |  | 0.45 | 11143.75 | 8465 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Unknown Society 2 & Iqbal Town | 296 | 133.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 133.2 | 3838115.2 | 3838115.2 |  |  |  | 0.45 | 814.2 | 3252.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | CTD_ANF_Police Lines_H11 | 522 | 261 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 50% | 261 | 14206617.625 | 8168805.1344 | 6037812.4906 | -1 |  | 0.5 | 5132.75 | 14407.456 | Hybrid | 50% | NOT LIVE |  | 50% | 0.5 | 2026-03-01 | 92 | 93 | 45 | In Progress | 46174 | Jun-2026 | Inside CTD & Police Line work is pending | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | INT-23-00444 | 2026-06-01
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Custom Preventive CHS | 258 | 103.2 | [5 empty] | LIVE - 100% Completed | 100% | 103.2 | 6521567.0436 | 978235.0565 | 5543331.9871 | -1 |  | 0.4 | 1628.4398 | 3322.1313 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | 61 | 62 | 14 | Completed | 2 Months | May-2026 | Map given for ROW permission | Live - Permission Awaited | LIVE - 100% Completed | [5 empty] | I240705 | 2026-05-01
I260294 | No Initiation Date | Karachi | Darussalam_LucknowSociety_DadabhoyTown | Dadabhoy Town | 662 | 264.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 3637949.2255 | 3637949.2255 |  |  |  |  | 496 | 1221.0608 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Daman & Kilo Town | 612 | 244.8 | 612 | 28 | 24 | 2 | 2 |  | 100% | 244.8 | 9579973.295 | 1436995.9942 | 8142977.3007 | -0.5 |  | 0.4 | 0 | 18667.155 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Darakhshan Society PK1 | 222 | 88.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 3979448.6124 | 3979448.6124 |  |  |  |  | 895.0324 | 1870.6511 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Darakhshan Society PK2 | 2078 | 831.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 15803943.4835 | 15803943.4835 |  |  |  |  | 2554.8738 | 13834.5879 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Unknown Society 5 | 500 | 225 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 225 | 5671521.546 | 5671521.546 |  |  |  | 0.45 | 1159.2 | 5103.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260294 | No Initiation Date | Karachi | Darussalam_LucknowSociety_DadabhoyTown | Darussalam Society | 1074 | 429.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 75% |  | 18047048.0325 | 6542054.9118 |  |  |  |  | 3990 | 12986.9814 | Hybrid | 75% | NOT LIVE |  | 75% | 0.75 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Handpoles pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I240538 | 2024-02-29 | Haripur | Haripur Ph2 | Darvesh P1 | 300 | 120 | 53 | 44 | 5 | 4 |  | LIVE - 100% Completed | 100% | 120 | 12851468.907 | 1927720.336 | 10923748.571 | -1 |  | 0.4 | 1542.15 | 3796.651 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240538 | Timeline not applicable
I240538 | 2024-02-29 | Haripur | Haripur Ph2 | Darvesh P2 | 684 | 273.6 | 72 | 56 | 7 | 9 |  | LIVE - 100% Completed | 100% | 273.6 | 15400465.45 | 2310069.8175 | 13090395.6325 | -0.85 |  | 0.4 | 1968 | 11075.245 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240538 | Timeline not applicable
I240680 | 2024-05-16 | Rahim Yar Khan | RahimYar Khan Ph2 | Dastgeer Colony | 378 | 151.2 | Not Live | 0 |  |  | Not Live | REMOVE BUDGET (T) | 0% | 151.2 | 2421984 | 0 | 2421984 | -1 |  | 0.4 | 0 | 3477.5 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 4 Months | Jun-2026 | 2026-07-01 | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | I240680 | 2026-06-01
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | DC Colony ext.PK_1 | 1230 | 492 | [5 empty] | LIVE - 100% Completed | 100% | 492 | 27298514.5741 | 4094777.1861 | 23203737.388 | -0.5 |  | 0.4 | 17317.7143 | 12271.3967 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | DC Colony ext.PK_2 | 722 | 288.8 | [5 empty] | LIVE - 100% Completed | 100% | 288.8 | 20330444.4573 | 3049566.6686 | 17280877.7887 | -1 |  | 0.4 | 12045.6678 | 7724.5148 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Zahoor Orchard | 426 | 191.7 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 191.7 | 8843280.05 | 8843280.05 |  |  |  | 0.45 | 2313.8 | 6322.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560600 | No Initiation Date | Hafizabad | Hafizabad | Zahoor Orchard Town | 736 | 331.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 331.2 | 5419869.964 | 5419869.964 |  |  |  | 0.45 | 1014.3 | 5937.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Defence Housing | 50 | 20 | 50 | 14 | 13 | 0 | 1 |  | 100% | 20 | 1722211.5095 | 258331.7264 | 1463879.7831 | -1 |  | 0.4 | 299 | 1232.2532 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Defence Housing Society | 518 | 259 | 0 | 0 | 0 | 0 | Budget Shifted | SWAPPED | 0% | 259 | 12724227.8253 | 0 | 12724227.8253 | -1 |  | 0.5 | 6884.6077 | 6437.5466 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Pace City and White House Scoiety Swapped | Swap Cases | SWAPPED |  |  | Pace City and White House Scoiety | 11729454.64 | 844 | INT-23-00439 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Defence villas | 272 | 136 | 24 | 3 | 3 | 18 |  | LIVE - 100% Completed | 100% | 136 | 5164579.3524 | 774686.9029 | 4389892.4495 | -0.5 |  | 0.5 | 921.15 | 3601.9437 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240701 | 2024-05-16 | Swat | Swat | Derai P1 | 1032 | 412.8 | 395 | 367 | 19 | 9 |  | LIVE - 100% Completed | 100% | 412.8 | 3668695 | 550304.25 | 3118390.75 | -1 |  | 0.4 | 0 | 435 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240701 | Timeline not applicable
I240701 | 2024-05-16 | Swat | Swat | Derai P2 | 848 | 339.2 | 319 | 289 | 15 | 15 |  | LIVE - 100% Completed | 100% | 339.2 | 2920040 | 438006 | 2482034 | -1 |  | 0.4 | 0 | 5757 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240701 | Timeline not applicable
I240701 | 2024-05-16 | Swat | Swat | Derai P3 | 512 | 204.8 | 177 | 155 | 9 | 13 |  | LIVE - 100% Completed | 100% | 204.8 | 1904430 | 285664.5 | 1618765.5 | -1 |  | 0.4 | 0 | 4758 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240701 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Dewan ka Bagh | 1598 | 639.2 | 350 | 60 | 54 | 236 |  | LIVE - 100% Completed | 100% | 639.2 | 14886613.1486 | 2232991.9723 | 12653621.1763 | -1 |  | 0.4 | 2490.21 | 10626.2056 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I260068 | 2025-07-17 | Lahore | DHA PH 1-5 | DHA PH-4 KK | 1106 | 553 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 553 | 34927094.4201 | 34927094.4201 | 0 | -1 |  | 0.5 | 11556.087 | 19395.3205 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Duct Plan not shared | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I260068 | 2026-06-01
I250201 | 2024-09-13 | Islamabad | ISB DHA Ph4 | DHA Ph-4 P1 | 2138 | 855.2 | 1 |  | 1 |  |  | LIVE - 100% Completed | 100% | 855.2 | 18891835.5 | 2833775.325 | 16058060.175 | -1 |  | 0.4 | 6091.75 | 5208.75 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250201 | Timeline not applicable
I250201 | 2024-09-13 | Islamabad | ISB DHA Ph4 | DHA Ph-4 P2 | 1982 | 792.8 | 0 |  |  |  |  | REMOVE BUDGET (P) | 0% | 792.8 | 23806775.7205 | 0 | 23806775.7205 | -0.5 |  | 0.4 | 6368.7 | 6717 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  | 2 |  | 0 |  | I250201 | Timeline not applicable
I260068 | 2025-07-17 | Lahore | DHA PH 1-5 | DHA PH-5 M | 926 | 463 | [5 empty] | LIVE - 100% Completed | 100% | 463 | 41815514.4979 | 6272327.1747 | 35543187.3232 | -1 |  | 0.5 | 15722.3266 | 24652.0899 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I260068 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | LC_P5 | 862 | 344.8 | [5 empty] | LIVE - 100% Completed | 100% | 344.8 | 6747145.4348 | 1012071.8152 | 5735073.6196 | #DIV/0! |  | 0.4 | 2927.0649 | 0 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I260060 | No Initiation Date | Gujranwala | DHA Gujranwala | DHA Sector A ( Villas ) | 528 | 264 | [5 empty] | NOT LIVE - RETAIN BUDGET | 100% |  | 12342069.5 | 1851310.425 |  |  |  |  | 6621.7 | 5565 | Buried | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 31 | 32 | -16 | Completed | 1 month | Apr-2026 | Feeder Cable Pulling in progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | LC_P6 | 1176 | 470.4 | [5 empty] | LIVE - 100% Completed | 100% | 470.4 | 6902776.0357 | 1035416.4054 | 5867359.6303 | #DIV/0! |  | 0.4 | 2407.4658 | 0 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240188 | 2023-09-27 | Islamabad | Islamabad DHA Ph1 | DHA_Ph-1_P1 | 930 | 372 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 372 | 25806283.6573 | 3870942.5486 | 21935341.1087 | -0.5 |  | 0.4 | 18001.5371 | 17776.9287 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240188 | Timeline not applicable
I240188 | 2023-09-27 | Islamabad | Islamabad DHA Ph1 | DHA_Ph-1_P2 | 1258 | 503.2 | 0 |  |  |  |  | REMOVE BUDGET (T) | 0% | 503.2 | 35995839.4142 | 0 | 35995839.4142 | -1 |  | 0.4 | 28620.3155 | 15845.3755 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | More than 6 months | Oct-2026 | More than 6 months (Oct26) | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | I240188 | 2026-10-01
I240188 | 2023-09-27 | Islamabad | Islamabad DHA Ph1 | DHA_Ph-1_P3 | 1112 | 444.8 | 0 |  |  |  |  | REMOVE BUDGET (T) | 0% | 444.8 | 31101622.7144 | 0 | 31101622.7144 | -0.85 |  | 0.4 | 21001.3114 | 18015.2937 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | More than 6 months | Oct-2026 | More than 6 months (Oct26) | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | I240188 | 2026-10-01
UI2560601 | No Initiation Date | Jhang | Jhang | Al Karam City Phase 1 | 602 | 270.9 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 270.9 | 6837358.6125 | 6837358.6125 |  |  |  | 0.45 | 1551.35 | 5729.2255 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560601 | No Initiation Date | Jhang | Jhang | Ali Town | 1610 | 724.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 724.5 | 16141722.8125 | 16141722.8125 |  |  |  | 0.45 | 3342.5 | 16881.625 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Diamond Citi P2 | 2282 | 912.8 |  | 8 | 6 | 106 | Correct HPs : 195 | LIVE - 100% Completed | 100% | 912.8 | 57635414.868 | 8645312.2302 | 48990102.6378 | -1 |  | 0.4 | 28971.1138 | 28725.9766 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Diamond City_Wasi Country Park | 1154 | 461.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 461.6 | 14732011.5002 | 14732011.5002 | 0 | -1 |  | 0.4 | 2430.1484 | 9208.5283 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 46204 | Jul-2026 | Permission Issue | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240705 | 2026-07-01
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Disposal Road | 814 | 325.6 | [5 empty] | LIVE - 100% Completed | 100% | 325.6 | 8785958.347 | 1317893.7521 | 7468064.595 | -1 |  | 0.4 | 1644.5 | 5669.9309 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
UI2560601 | No Initiation Date | Jhang | Jhang | Chaudary Colony | 1020 | 459 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 459 | 8741254.6125 | 8741254.6125 |  |  |  | 0.45 | 1463.95 | 10058.853 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | LC_P7 | 908 | 363.2 | [5 empty] | LIVE - 100% Completed | 100% | 363.2 | 6426551.5576 | 963982.7336 | 5462568.824 | #DIV/0! |  | 0.4 | 2184.2165 | 0 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
UI2560601 | No Initiation Date | Jhang | Jhang | Civil Lines | 950 | 427.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 427.5 | 15965696.4263 | 15965696.4263 |  |  |  | 0.45 | 3818 | 20151.1393 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00437 | 2022-12-29 | Lahore | Lahore Misc Areas | Dream Avenue | 506 | 253 | [5 empty] | LIVE - 100% Completed | 100% | 253 | 5158055.2855 | 773708.2928 | 4384346.9927 | -1 |  | 0.5 | 1069.6266 | 4352.8641 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00437 | Timeline not applicable
UI2560601 | No Initiation Date | Feeders/Transportations | Jhang | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 67800529.25 | 67800529.25 |  |  |  |  | 22058.4 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Dream Valley | 118 | 47.2 | 7 | 1 | 2 | 4 |  | LIVE - 100% Completed | 100% | 47.2 | 6120818.599 | 918122.7898 | 5202695.8091 | -1 |  | 0.4 | 2486.0466 | 1896.4353 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240437 | 2024-01-18 | Feeders/Transportations | Askari Lahore | Drop Cable Installation till Premises Wall | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 6796800 | 3398400 | 3398400 | -0.85 |  |  | 0 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240437 | Timeline not applicable
I250211 | 2024-09-14 | Okara | Okara | Dubai Town | 738 | 295.2 | 87 | 3 |  | 84 |  | LIVE - 100% Completed | 100% | 295.2 | 6884087.45 | 1032613.1175 | 5851474.3325 | -1 |  | 0.4 | 1241.9 | 6757 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250211 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | E-16 | 726 | 363 | 543 | 29 | 44 | 470 |  | LIVE - 100% Completed | 100% | 363 | 21505105.4334 | 3225765.815 | 18279339.6184 | -1 |  | 0.5 | 13058.8218 | 9671.3176 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00444 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | E-17 | 876 | 350.4 | 178 | 11 | 19 | 148 |  | LIVE - 100% Completed | 100% | 350.4 | 35124206.05 | 5268630.9075 | 29855575.1425 | -1 |  | 0.4 | 17929.95 | 13823.75 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250376 | Timeline not applicable
I240438 | 2024-01-09 | Lahore | Chinar Bagh Lahore | Eden Lane Villas 2 | 814 | 325.6 | [5 empty] | REMOVE BUDGET (P) | 0% | 325.6 | 9337513.4213 | 0 | 9337513.4213 | -1 |  | 0.4 | 1846.2058 | 6940.2234 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I240438 | Timeline not applicable
INT-23-00441 | 2022-12-29 | Faisalabad | Faisalabad Misc Areas | Eden Orchards | 1778 | 889 |  | 123 | 80 | 515 | Occupancy : 1000 | LIVE - 100% Completed | 100% | 889 | 41802673.1826 | 6270400.9774 | 35532272.2052 | -1 |  | 0.5 | 24331.067 | 16346.3021 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00441 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Eden Villas | 1088 | 435.2 |  | 0 | 0 | 0 | Yet not active | LIVE - 100% Completed | 100% | 435.2 | 13035848.5625 | 1955377.2844 | 11080471.2781 | 0 | Defence Paradise | 0.4 | 2117.15 | 11887.0622 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Eid Gah | 206 | 82.4 |  |  | Yes |  |  | LIVE - 100% Completed | 100% |  | 3357905.5377 | 503685.8307 |  |  |  | 0.4 | 1068.35 | 2720.2 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Done-Replaced by Chak Jamal-Shamspur and their Feeder Connectivity-I250205 | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
UI2560601 | No Initiation Date | Jhang | Jhang | Ghaziabad | 2296 | 1033.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1033.2 | 20528937.5019 | 20528937.5019 |  |  |  | 0.45 | 3435.05 | 28769.5556 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560601 | No Initiation Date | Jhang | Jhang | Gulshan Colony | 1372 | 617.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 617.4 | 12066151.3625 | 12066151.3625 |  |  |  | 0.45 | 2287.35 | 11740.128 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | Emaar P1 | 324 | 129.6 | 0 |  |  |  |  | REMOVE BUDGET (P) | 0% | 129.6 | 20091272.16 | 0 | 20091272.16 | -0.5 |  | 0.4 | 10294.4515 | 5165.846 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I250376 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | Emaar P2 | 356 | 142.4 | 0 |  |  |  |  | REMOVE BUDGET (P) | 0% | 142.4 | 11170003.53 | 0 | 11170003.53 | -1 |  | 0.4 | 5354.832 | 3759.448 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I250376 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | Emaar P3 | 462 | 184.8 | 0 |  |  |  |  | REMOVE BUDGET (T) | 0% | 184.8 | 13434006.59 | 0 | 13434006.59 | -0.5 |  | 0.4 | 8546.684 | 4467.064 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | remove (after June) | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | I250376 | Timeline not applicable
I250379 | 2024-11-25 | Wahh | Wahh Estate | Estate Area P2 | 618 | 247.2 | 4 | 1 |  | 3 |  | LIVE - 100% Completed | 100% | 247.2 | 11052351.3333 | 1657852.7 | 9394498.6333 | #DIV/0! |  | 0.4 | 2626.7 | 7694.54 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250379 | Timeline not applicable
I250379 | 2024-11-25 | Wahh | Wahh Estate | Estate Area P3 | 1538 | 615.2 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 615.2 | 14959544.71 | 14959544.71 | 0 | #DIV/0! |  | 0.4 | 2492 | 14621.936 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 3 Months | Jul-2026 | Aerial network expansion in area 20 & 21 / Need to reconfirm | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250379 | 2026-07-01
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | PAEC T.Buried | 1364 | 545.6 | [5 empty] | LIVE - 100% Completed | 100% | 545.6 | 44228331.6892 | 6634249.7534 | 37594081.9359 | #DIV/0! |  | 0.4 | 21167.5338 | 3655 | Hybrid | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | F.B Area Block-21 | 2160 | 864 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 864 | 26510079.703 | 26510079.703 | 0 | -1 |  | 0.4 | 5679.3 | 15165.9179 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46113 | Apr-2026 | Permission Issue | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240705 | 2026-04-01
I250210 | 2024-09-14 | Sargodha | Sargodha | Factory_Area | 350 | 140 |  |  |  |  | Not Live | NOT LIVE - RETAIN BUDGET | 70% | 140 | 6143183.75 | 2487989.4188 | 3655194.3312 | -1 |  | 0.4 | 911.95 | 6957 | Buried | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Only Cable Pulling Pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250210 | 2026-04-01
I240680 | 2024-05-16 | Rahim Yar Khan | RahimYar Khan Ph2 | Fahad Town | 328 | 131.2 | 3 | 0 |  |  |  | LIVE - 100% Completed | 100% | 131.2 | 5505721.25 | 825858.1875 | 4679863.0625 | -0.85 |  | 0.4 | 1190.25 | 3296.25 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | 2026-07-01 | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240680 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | Faisal Town P2 | 1516 | 606.4 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 606.4 | 26027930.18 | 3904189.527 | 22123740.653 | -1 |  | 0.4 | 12852.574 | 10423.336 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250376 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | Faisal Town P3 | 2208 | 883.2 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 883.2 | 40657979.338 | 6098696.9007 | 34559282.4373 | -0.6375 |  | 0.4 | 18184.2045 | 15061.214 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250376 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | Faisal Town P4 | 1434 | 573.6 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 573.6 | 28656438.61 | 4298465.7915 | 24357972.8185 | -1 |  | 0.4 | 14091.059 | 12446.476 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250376 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Faisal_Town | 320 | 128 |  |  |  |  | NOT ENERGISED AS YET | SWAPPED | 0% | 128 | 5536549 | 0 | 5536549 | -0.85 |  | 0.4 | 1147.7 | 4422.5 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Meraj Housing | Swap Cases | SWAPPED |  |  | Meraj Housing | 22604832.2609 | 542 | I250206 | Timeline not applicable
UI2560601 | No Initiation Date | Jhang | Jhang | Khokar Colony | 244 | 109.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 109.8 | 3813896.7625 | 3813896.7625 |  |  |  | 0.45 | 865.95 | 2943.2245 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00435 | 2022-12-29 | Karachi | Karachi Misc Areas | Falaknaz Pebbles | 108 | 54 | [5 empty] | LIVE - 100% Completed | 100% | 54 | 4362489 | 654373.35 | 3708115.65 | 0 |  | 0.5 | 1627.25 | 1023.7 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00435 | Timeline not applicable
I240683 | 2024-05-15 | Okara | Okara | Farid Town | 2470 | 988 | 432 | 62 |  | 370 |  | LIVE - 100% Completed | 100% | 988 | 20610112.4335 | 3091516.865 | 17518595.5685 | -1 |  | 0.4 | 3026.8 | 18496.25 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240683 | Timeline not applicable
I240678 | 2024-05-16 | Sialkot | Sialkot | Fatehgarh | 232 | 92.8 |  | 45 | 83 | 80 |  | LIVE - 100% Completed | 100% | 92.8 | 1833623.474 | 275043.5211 | 1558579.9529 | -1 |  | 0.4 | 0 | 2127.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
I240678 | 2024-05-16 | Sialkot | Sialkot | Fatehger Ext | 2120 | 848 |  | 105 | 195 | 351 |  | NOT LIVE - RETAIN BUDGET | 0% | 848 | 22340090.4386 | 22340090.4386 | 0 | -1 |  | 0.4 | 4763.3983 | 18592.973 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240678 | Feedback Awaited
I240704 | 2024-05-15 | Multan | Multan Ph3 | Fatima Jinnah Town A | 940 | 376 | - | - | - | - |  | LIVE - 100% Completed | 100% | 376 | 15503851.5 | 2325577.725 | 13178273.775 | -1 |  | 0.4 | 3547.75 | 14407.2 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Fatima Jinnah Town B | 1158 | 463.2 | - | - | - | - |  | LIVE - 100% Completed | 100% | 463.2 | 16359053.613 | 2453858.0419 | 13905195.571 | 0 |  | 0.4 | 3675.4 | 16677.9 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Fatima Jinnah Town C | 502 | 200.8 | - | - | - | - |  | LIVE - 100% Completed | 100% | 200.8 | 7638496.5 | 1145774.475 | 6492722.025 | -1 |  | 0.4 | 1716.95 | 9068.3 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Fatima Jinnah Town D | 1472 | 588.8 | - | - | - | - |  | LIVE - 100% Completed | 100% | 588.8 | 16956120.235 | 2543418.0352 | 14412702.1997 | -0.85 |  | 0.4 | 3646.35 | 15203.25 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Fatima Jinnah Town E | 716 | 286.4 | - | - | - | - |  | LIVE - 100% Completed | 100% | 286.4 | 11996653 | 1799497.95 | 10197155.05 | -1 |  | 0.4 | 3343.05 | 8205.55 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Fatima Jinnah Town F | 928 | 371.2 | - | - | - | - |  | LIVE - 100% Completed | 100% | 371.2 | 15717416.25 | 2357612.4375 | 13359803.8125 | -0.7 |  | 0.4 | 3963.6 | 13193.55 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Fatima Jinnah Town G | 650 | 260 | - | - | - | - |  | LIVE - 100% Completed | 100% | 260 | 10973603.996 | 1646040.5994 | 9327563.3966 | -1 |  | 0.4 | 2540.35 | 9001.6 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Fatima Jinnah Town H | 1004 | 401.6 | - | - | - | - |  | LIVE - 100% Completed | 100% | 401.6 | 15747558.243 | 2362133.7365 | 13385424.5066 | 0 |  | 0.4 | 3646.35 | 16647.45 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Fatima Jinnah Town J | 572 | 228.8 | - | - | - | - |  | LIVE - 100% Completed | 100% | 228.8 | 9626270.75 | 1443940.6125 | 8182330.1375 | -1 |  | 0.4 | 2548.8 | 9222 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Fauji Basti | 1206 | 482.4 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 85% | 482.4 | 6184910.4312 | 1716312.6447 |  |  |  |  | 603.334 | 8418.4558 | Hybrid | 85% | Not Live |  | 85% | 0.85 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 month | Apr-2026 | Cable pulling pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
INT-23-00437 | 2022-12-29 | Lahore | Lahore Misc Areas | Fazaiya Society P1 | 1470 | 735 | [5 empty] | LIVE - 100% Completed | 100% | 735 | 38825399.9368 | 5823809.9905 | 33001589.9463 | -0.85 |  | 0.5 | 21865.0704 | 22383.9986 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00437 | Timeline not applicable
INT-23-00437 | 2022-12-29 | Lahore | Lahore Misc Areas | Fazaiya Society P2 | 1492 | 746 | [5 empty] | LIVE - 100% Completed | 100% | 746 | 41698131.8369 | 6254719.7755 | 35443412.0614 | -1 |  | 0.5 | 23518.6437 | 25182.0012 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00437 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Fazal Sun City | 3446 | 1378.4 | 2638 | 352 |  |  |  | NOT LIVE - RETAIN BUDGET | 20% | 1378.4 | 29043845.2729 | 24106391.5765 | 4937453.6964 | -1 |  | 0.4 | 3234.605 | 23041.173 | Hybrid | 20% | NOT LIVE |  | 20% | 0.2 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46082 | Mar-2026 | Fazal & Sun only Back Haul Work Done/inside society work pending due to local cable operator permission dispute. | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240702 | 2026-03-01
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Fazal Town | 544 | 217.6 | [5 empty] | LIVE - 100% Completed | 100% | 217.6 | 5006676.5 | 751001.475 | 4255675.025 | -1 |  | 0.4 | 649.35 | 3901.25 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
INT-23-00440 | 2022-12-29 | Sargodha | Sargodha | Fazil Town FDT To Khizar Masjio | 784 | 392 | 117 | 16 |  | 101 | Live | LIVE - 100% Completed | 100% | 392 | 6536804.4375 | 980520.6656 | 5556283.7719 | -1 |  | 0.5 | 1181.05 | 10010 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | This Area will be converted to Hybrid Model | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00440 | Timeline not applicable
INT-23-00435 | 2022-12-29 | Karachi | Karachi Misc Areas | FB Area Block-22 | 326 | 163 | [5 empty] | LIVE - 100% Completed | 100% | 163 | 8178330.6332 | 1226749.595 | 6951581.0382 | -1 |  | 0.5 | 2164.3 | 7686.293 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00435 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | FDA City_P1 | 3278 | 1311.2 |  | 1 | 10 | 231 | Occupancy : 400 | LIVE - 100% Completed | 100% | 1311.2 | 71741582.6573 | 10761237.3986 | 60980345.2587 | -1 |  | 0.4 | 14106.0713 | 42466.291 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | FDA City_P2 | 3476 | 1390.4 |  | 0 | 0 | 0 | No occupancy yet | LIVE - 100% Completed | 100% | 1390.4 | 65415581.5843 | 9812337.2376 | 55603244.3467 | 0 |  | 0.4 | 11876.611 | 47661.0175 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | FDA City_P3 | 5098 | 2039.2 |  | 0 | 0 | 0 | No occupancy yet | LIVE - 100% Completed | 100% | 2039.2 | 89271460.9699 | 13390719.1455 | 75880741.8244 | -1 |  | 0.4 | 16595.4277 | 65826.987 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
UI2560601 | No Initiation Date | Jhang | Jhang | Lalazar Colony | 532 | 239.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 239.4 | 6851061.5937 | 6851061.5937 |  |  |  | 0.45 | 1723.4077 | 6562.4425 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560601 | No Initiation Date | Jhang | Jhang | Madina Colony | 814 | 366.3 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 366.3 | 9576095.0924 | 9576095.0924 |  |  |  | 0.45 | 1959.6 | 11892.1859 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560601 | No Initiation Date | Jhang | Jhang | Officers Colony | 330 | 148.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 148.5 | 3495495.8375 | 3495495.8375 |  |  |  | 0.45 | 615.25 | 4449.8615 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560601 | No Initiation Date | Jhang | Jhang | Paradise City | 602 | 270.9 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 270.9 | 8668608.7879 | 8668608.7879 |  |  |  | 0.45 | 2228.8492 | 7932.6761 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560601 | No Initiation Date | Jhang | Jhang | Samanabad | 1302 | 585.9 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 585.9 | 11360811.6 | 11360811.6 |  |  |  | 0.45 | 1930.85 | 14580.098 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560601 | No Initiation Date | Jhang | Jhang | Satellite Town_PK1 | 1770 | 796.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 796.5 | 21217272.9222 | 21217272.9222 |  |  |  | 0.45 | 4919.5219 | 21107.175 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560601 | No Initiation Date | Jhang | Jhang | Satellite Town_PK2 | 920 | 414 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 414 | 7121857.3327 | 7121857.3327 |  |  |  | 0.45 | 1250.9433 | 9583.8226 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560601 | No Initiation Date | Jhang | Jhang | Satellite Town_PK3 | 746 | 335.7 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 335.7 | 7762765.0994 | 7762765.0994 |  |  |  | 0.45 | 1688.4823 | 8481.7493 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560601 | No Initiation Date | Jhang | Jhang | Shadab Colony | 490 | 220.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 220.5 | 7991526.9999 | 7991526.9999 |  |  |  | 0.45 | 1877.95 | 8889.915 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560601 | No Initiation Date | Jhang | Jhang | Shah Block | 270 | 121.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 121.5 | 3723681.7625 | 3723681.7625 |  |  |  | 0.45 | 930.35 | 2511.2695 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560601 | No Initiation Date | Jhang | Jhang | Sultan Colony | 630 | 283.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 283.5 | 6758877.15 | 6758877.15 |  |  |  | 0.45 | 1320.2 | 6800.819 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560601 | No Initiation Date | Feeders/Transportations | Jhang | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 6165000 | 6165000 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I240188 | 2023-09-27 | Feeders/Transportations | Islamabad DHA Ph1 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 14355885 | 7177942.5 | 7177942.5 | -1 |  |  | 5335 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240188 | Timeline not applicable
I240189 | 2023-09-27 | Feeders/Transportations | Quetta Cantt | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 2801000 | 1400500 | 1400500 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240189 | Timeline not applicable
I240190 | 2023-09-27 | Feeders/Transportations | Sialkot Cantt | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 11777000 | 5888500 | 5888500 | -1 |  |  | 1500 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240190 | Timeline not applicable
I240435 | 2024-01-18 | Feeders/Transportations | Top City Islamabad | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 27369620 | 13684810 | 13684810 | -1 |  |  | 3832.8 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240435 | Timeline not applicable
I240437 | 2024-01-18 | Feeders/Transportations | Askari Lahore | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 38321700 | 19160850 | 19160850 | -1 |  |  | 8400 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240437 | Timeline not applicable
I240438 | 2024-01-09 | Feeders/Transportations | Chinar Bagh Lahore | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 28370300 | 14185150 | 14185150 | -1 |  |  | 5700 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240438 | Timeline not applicable
I240440 | 2024-01-19 | Feeders/Transportations | Al Jalil & Al khalil LHE | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 47108350 | 23554175 | 23554175 | 0 |  |  | 13560 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240440 | Timeline not applicable
I240442 | 2024-01-19 | Feeders/Transportations | Chitral Ph1 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 8582170 | 4291085 | 4291085 | -1 |  |  | 1470 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240442 | Timeline not applicable
I240459 | 2024-01-24 | Feeders/Transportations | Askari Sialkot | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 639000 | 319500 | 319500 | 0 |  |  | 0 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240459 | Timeline not applicable
I240518 | 2024-02-27 | Feeders/Transportations | Naval Anchorage and other Areas (ISB) | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 14537350 | 7268675 | 7268675 | -1 |  |  | 4950 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240518 | Timeline not applicable
I240519 | 2024-02-27 | Feeders/Transportations | Royal Palm & Canal View | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 14522680 | 7261340 | 7261340 | -0.5 |  |  | 500 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240519 | Timeline not applicable
I240537 | 2024-02-29 | Feeders/Transportations | Abbottabad Ph2 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3407850 | 1703925 | 1703925 | -1 |  |  | 1000 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240537 | Timeline not applicable
I240538 | 2024-02-29 | Feeders/Transportations | Haripur Ph2 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 55243020 | 27621510 | 27621510 | -1 |  |  | 16182 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240538 | Timeline not applicable
I240539 | 2024-02-28 | Feeders/Transportations | Swat Ph2 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 27545740 | 13772870 | 13772870 | -1 |  |  | 10765.2 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240539 | Timeline not applicable
I240540 | 2024-02-28 | Feeders/Transportations | Mardan Ph2 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 34252320 | 17126160 | 17126160 | -0.85 |  |  | 8000 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240540 | Timeline not applicable
I240557 | 2024-03-08 | Feeders/Transportations | Jhelum- Kala Gojran | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 758000 | 379000 | 379000 | -1 |  |  | 0 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240557 | Timeline not applicable
I240678 | 2024-05-16 | Feeders/Transportations | Sialkot | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 51328444 | 25664222 | 25664222 | -1 |  |  | 13524 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240678 | Timeline not applicable
I240681 | No Initiation Date | Feeders/Transportations | Quetta | Feeder | [7 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240681 | Timeline not applicable
I240679 | No Initiation Date | Feeders/Transportations | Sargodha | Feeder | [7 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240679 | Timeline not applicable
I240680 | 2024-05-16 | Feeders/Transportations | RahimYar Khan Ph2 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 20697000 | 10348500 | 10348500 | -1 |  |  | 6000 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240680 | Timeline not applicable
I240682 | 2024-05-16 | Feeders/Transportations | Faisalabad Ph4 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 75747800 | 37873900 | 37873900 | 0 |  |  | 18480 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240682 | Timeline not applicable
I240683 | 2024-05-15 | Feeders/Transportations | Okara | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 21047446 | 10523723 | 10523723 | -0.85 |  |  | 6798 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240683 | Timeline not applicable
I240684 | 2024-05-16 | Feeders/Transportations | Askari RWP (4-7-10) | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 11206780 | 5603390 | 5603390 | -1 |  |  | 1980 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240684 | Timeline not applicable
I240700 | 2024-05-15 | Feeders/Transportations | Gujranwala Ph3 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 110301300 | 55150650 | 55150650 | -1 |  |  | 33690 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240700 | Timeline not applicable
I240702 | 2024-05-15 | Feeders/Transportations | Hyderabad | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 27521326.8 | 13760663.4 | 13760663.4 | 0 |  |  | 8481.55 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240702 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Park View_Hybrid_P1 | 1266 | 506.4 | [5 empty] | REMOVE BUDGET (P) | 0% | 506.4 | 17307482.1627 | 0 | 17307482.1627 | #DIV/0! |  | 0.4 | 5376 | 13165.5 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I240703 | Timeline not applicable
I240704 | 2024-05-15 | Feeders/Transportations | Multan Ph3 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 126328830 | 63164415 | 63164415 | 0 |  |  | 44580 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240704 | Timeline not applicable
I240705 | 2024-05-15 | Feeders/Transportations | Karachi Ph5 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 73079460 | 36539730 | 36539730 | -0.765 |  |  | 15410 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240705 | Timeline not applicable
I240782 | No Initiation Date | Feeders/Transportations | Torkhan Border | Feeder | [7 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 | [7 empty] | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240782 | Timeline not applicable
I250114 | 2024-08-08 | Feeders/Transportations | Bahadurabad (KTTC) | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 27000 | 13500 | 13500 | -1 |  |  | 0 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250114 | Timeline not applicable
I250201 | 2024-09-13 | Feeders/Transportations | ISB DHA Ph4 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 4369350 | 2184675 | 2184675 | -1 |  |  | 1100 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET |  | 2 |  |  |  | I250201 | Timeline not applicable
I250202 | 2024-09-13 | Feeders/Transportations | Haripur Hazara | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 2765450 | 1382725 | 1382725 | -1 |  |  | 960 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250202 | Timeline not applicable
I250203 | 2024-09-13 | Feeders/Transportations | Gujranwala | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3976000 | 1988000 | 1988000 | -0.85 |  |  | 1440 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250203 | Timeline not applicable
I250205 | 2024-09-12 | Feeders/Transportations | Jhelum Ph2 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 14855300 | 7427650 | 7427650 | -1 |  |  | 1800 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250205 | Timeline not applicable
I250206 | 2024-09-12 | Feeders/Transportations | Daska | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 103687298.4 | 51843649.2 | 51843649.2 | -1 |  |  | 29696.4 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250206 | Timeline not applicable
I250207 | 2024-09-12 | Feeders/Transportations | Abbottabad | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3740300 | 1870150 | 1870150 | -1 |  |  | 1200 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250207 | Timeline not applicable
I250208 | 2024-09-14 | Feeders/Transportations | Wah Cantt | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 10936748 | 5468374 | 5468374 | -1 |  |  | 3458 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250208 | Timeline not applicable
I250209 | 2024-09-14 | Feeders/Transportations | Rawalpindi | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 44351050 | 22175525 | 22175525 | -1 |  |  | 15360 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250209 | Timeline not applicable
I250210 | 2024-09-14 | Feeders/Transportations | Sargodha | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 39500434 | 19750217 | 19750217 | -0.85 |  |  | 9114 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250210 | Timeline not applicable
I250211 | 2024-09-14 | Feeders/Transportations | Okara | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3194750 | 1597375 | 1597375 | 0 |  |  | 1000 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250211 | Timeline not applicable
I250212 | 2024-09-14 | Feeders/Transportations | Mingora | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 58670322 | 29335161 | 29335161 | -0.85 |  |  | 18567.6 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250212 | Timeline not applicable
I250213 | 2024-09-14 | Feeders/Transportations | Mardan | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 10234010 | 5117005 | 5117005 | -0.85 |  |  | 2875 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250213 | Timeline not applicable
I250298 | 2024-10-17 | Feeders/Transportations | ISB DHA Ph-5 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 10372500 | 5186250 | 5186250 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET |  | 2 |  |  |  | I250298 | Timeline not applicable
I250307 | No Initiation Date | Feeders/Transportations | DHA KHI - Common Corridor Project | Feeder | [7 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250307 | Timeline not applicable
I250326 | 2024-11-05 | Feeders/Transportations | Askari Multan | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 2794250 | 1397125 | 1397125 | -0.85 |  |  | 1000 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250326 | Timeline not applicable
I250327 | 2024-11-05 | Feeders/Transportations | Islamabad | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 77285018 | 38642509 | 38642509 | -0.85 |  |  | 26378 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250327 | Timeline not applicable
I250374 | No Initiation Date | Feeders/Transportations | Faisalabad | Feeder | [7 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 |  |  |  |  | 0 | 10850 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250374 | Timeline not applicable
I250375 | 2024-11-25 | Feeders/Transportations | Bahawalpur (P3) | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 11698450 | 5849225 | 5849225 | -1 |  |  | 5700 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250375 | Timeline not applicable
I250376 | 2024-11-25 | Feeders/Transportations | Islamabad Ph3 (P2) | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 124964950 | 62482475 | 62482475 | -0.765 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250376 | Timeline not applicable
I250377 | 2024-11-25 | Feeders/Transportations | Peshawar (P2) | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 66248400 | 33124200 | 33124200 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250377 | Timeline not applicable
I250378 | 2024-11-25 | Feeders/Transportations | Sahiwal (P2) | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 43905040 | 21952520 | 21952520 | #DIV/0! |  |  | 13560 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250378 | Timeline not applicable
I250379 | 2024-11-25 | Feeders/Transportations | Wahh Estate | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 20617144.8 | 10308572.4 | 10308572.4 | #DIV/0! |  |  | 15327.6 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250379 | Timeline not applicable
I250380 | 2024-11-27 | Feeders/Transportations | Gulshan-e-Maymar | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 19431191 | 9715595.5 | 9715595.5 | #DIV/0! |  |  | 37769 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250380 | Timeline not applicable
I250681 | 2025-03-26 | Feeders/Transportations | CTC Lahore | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 68989386.8355 | 34494693.4177 | 34494693.4177 | -1 |  |  | 22800 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET |  | 2 |  |  |  | I250681 | Timeline not applicable
I250734 | No Initiation Date | Feeders/Transportations | Bahwalpur (P2)-B | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 33598134.4 | 33598134.4 |  | -0.85 |  |  | 10780.8 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I250737 | 2025-04-16 | Feeders/Transportations | ISB-BT-Ph-8 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 17485740 | 8742870 | 8742870 | -1 |  |  | 3720 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250737 | Timeline not applicable
I260060 | No Initiation Date | Feeders/Transportations | DHA Gujranwala | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 12572800 | 12572800 |  | -1 |  |  | 3850 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260061 | No Initiation Date | Feeders/Transportations | Jhelum (P4) | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 49748549.6 | 49748549.6 |  | -1 |  |  | 18975 |  |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260068 | 2025-07-17 | Feeders/Transportations | DHA PH 7-8 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 53433666 | 26716833 | 37403566.2 | -1 |  |  | 7123.6 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET |  | 1 |  |  |  | I260068 | Timeline not applicable
I260068 | 2025-07-17 | Feeders/Transportations | DHA PH 1-5 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 11487956 | 5743978 | 8041569.2 | -1 |  |  | 2592 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I260068 | Timeline not applicable
I260105 | No Initiation Date | Feeders/Transportations | Al Hafeez Garden & Tariq Garden | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1756000 | 1756000 |  | -1 |  |  | 600 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260105 | No Initiation Date | Feeders/Transportations | Al Hafeez Garden & Tariq Garden | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 365500 | 365500 |  | -1 |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260159 | No Initiation Date | Feeders/Transportations | Faisalabad Citi Hosuing Extension | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1065000 | 1065000 |  | -1 |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET |  | 1 |  |  |  | #N/A | Timeline not applicable
I260160 | No Initiation Date | Feeders/Transportations | Khyban-e-Amin, High court & Al Rehman PH4 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 29916860 | 29916860 |  | -1 |  |  | 7637 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260179 | No Initiation Date | Feeders/Transportations | Palm City Lahore | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 4101650 | 4101650 |  | -1 |  |  | 715 |  |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260180 | No Initiation Date | Feeders/Transportations | Gujranwala Makki Road | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 45402400 | 45402400 |  | -0.85 |  |  | 12562 |  |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260208 | No Initiation Date | Feeders/Transportations | LHE - DHA Phase 6, EME, Rahbar | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 4132000 | 4132000 |  | -0.68 |  |  | 500 |  |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260294 | No Initiation Date | Feeders/Transportations | Darussalam_LucknowSociety_DadabhoyTown | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3219200 | 3219200 |  | -0.85 |  |  | 105 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260295 | No Initiation Date | Feeders/Transportations | Model Town_Sh Faisal_Faisal Cant | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 144288500 | 144288500 |  | -0.68 |  |  | 42940 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260296 | No Initiation Date | Feeders/Transportations | Sukkur | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 82409884 | 82409884 |  | -0.85 |  |  | 24103.3 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260298 | No Initiation Date | Feeders/Transportations | Petaro Garrison, Hyderabad | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3319155 | 3319155 |  | -0.85 |  |  | 2600 |  |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260361 | No Initiation Date | Feeders/Transportations | Lhr MW City & Al Hafeez Ph-1 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 6136100 | 6136100 |  | -0.85 |  |  | 600 |  |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
INT-21-00315 | 2020-12-30 | Feeders/Transportations | Gujranwala Ph2 | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 39206675 | 19603337.5 | 19603337.5 | 0 |  |  | 43312.5 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-21-00315 | Timeline not applicable
INT-23-00435 | 2022-12-29 | Feeders/Transportations | Karachi Misc Areas | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 19217000 | 9608500 | 9608500 | 0 |  |  | 16200 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00435 | Timeline not applicable
INT-23-00436 | 2022-12-29 | Feeders/Transportations | Hyderabad Misc Areas | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 12437052 | 6218526 | 6218526 | -1 |  |  | 22518 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00436 | Timeline not applicable
INT-23-00437 | 2022-12-29 | Feeders/Transportations | Lahore Misc Areas | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 30608068 | 15304034 | 15304034 | 0 |  |  | 20320.8 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00437 | Timeline not applicable
INT-23-00438 | 2022-12-29 | Feeders/Transportations | Bahawalpur | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 688600 | 344300 | 344300 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00438 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Feeders/Transportations | Multan Misc. Areas | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 56286420 | 28143210 | 28143210 | -1 |  |  | 46200 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00439 | Timeline not applicable
INT-23-00440 | 2022-12-29 | Feeders/Transportations | Sargodha | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 18298070 | 9149035 | 9149035 | -0.85 |  |  | 11640 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00440 | Timeline not applicable
INT-23-00441 | 2022-12-29 | Feeders/Transportations | Faisalabad Misc Areas | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 12486620 | 6243310 | 6243310 | -1 |  |  | 8316 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00441 | Timeline not applicable
INT-23-00442 | 2022-12-29 | Feeders/Transportations | Sahiwal Misc Areas | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 21831160 | 10915580 | 10915580 | -0.85 |  |  | 13200 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00442 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Feeders/Transportations | Islamabad Misc Areas | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 30248305 | 15124152.5 | 15124152.5 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00444 | Timeline not applicable
INT-23-00445 | 2022-12-29 | Feeders/Transportations | Rawalpindi Misc Areas | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 15912980 | 7956490 | 7956490 | #DIV/0! |  |  | 38400 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00445 | Timeline not applicable
INT-23-00446 | 2022-12-29 | Feeders/Transportations | Wah Cant Misc Ares | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 21054892.8 | 10527446.4 | 10527446.4 | #DIV/0! |  |  | 19040 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00446 | Timeline not applicable
INT-23-00447 | 2022-12-29 | Feeders/Transportations | Peshawar Misc Areas | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 44315022.08 | 22157511.04 | 22157511.04 | -1 |  |  | 30700.4 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00447 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Park View_T.B_P2 | 2378 | 951.2 | [5 empty] | REMOVE BUDGET (P) | 0% | 951.2 | 61531383.75 | 0 | 61531383.75 | #DIV/0! |  | 0.4 | 33802.5 | 34890 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I240703 | Timeline not applicable
I240701 | 2024-05-16 | Feeders/Transportations | Swat | Feeder From PoP | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 142000 | 71000 | 71000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240701 | Timeline not applicable
UI2560601 | No Initiation Date | Jhang | Jhang | Unknown Society 3 | 266 | 119.7 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 119.7 | 4177044.5875 | 4177044.5875 |  |  |  | 0.45 | 0 | 3295.0815 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560601 | No Initiation Date | Jhang | Jhang | Unknown-1 | 270 | 121.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 121.5 | 3370953.3108 | 3370953.3108 |  |  |  | 0.45 | 752.8246 | 3119.6334 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Park View_T.B_P3 | 1510 | 604 | [5 empty] | REMOVE BUDGET (P) | 0% | 604 | 40966537.118 | 0 | 40966537.118 | #DIV/0! |  | 0.4 | 21847.5 | 21898.5 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I240703 | Timeline not applicable
I250374 | 2024-11-11 | Faisalabad | Faisalabad | Fesco Abdullahpur | 50 | 20 |  | 0 | 3 | 29 | Occupancy : 50 | LIVE - 100% Completed | 100% | 20 | 467960 | 70194 | 397766 | -1 |  | 0.4 | 0 | 2550 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250374 | Timeline not applicable
I250374 | 2024-11-11 | Faisalabad | Faisalabad | Fesco Colony 132 KV | 24 | 9.6 |  | 1 | 6 | 24 | Occupancy : 50 | LIVE - 100% Completed | 100% | 9.6 | 359370 | 53905.5 | 305464.5 | -0.85 |  | 0.4 | 0 | 2050 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250374 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | FMC_Partial | 3146 | 1258.4 | 493 | 18 | 59 | 416 |  | LIVE - 100% Completed | 100% | 1258.4 | 41368501.8917 | 6205275.2838 | 35163226.6079 | -0.85 |  | 0.4 | 17799.711 | 16829.955 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250376 | Timeline not applicable
INT-23-00436 | 2022-12-29 | Hyderabad | Hyderabad Misc Areas | Fortune Arcade | 46 | 18.4 | 50 | 30 |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 18.4 | 970858.33 | 970858.33 | 0 | -1 |  | 0.4 | 305 | 217.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | INT-23-00436 | Feedback Awaited
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | G magnolia Remaining Part | 1520 | 608 | [5 empty] | LIVE - 100% Completed | 100% | 608 | 38506087.7501 | 5775913.1625 | 32730174.5876 | -0.85 |  | 0.4 | 22396.7193 | 6517.1055 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
I250327 | 2024-11-05 | Islamabad | Islamabad | G-11 P1 | 1444 | 577.6 | 122 |  | 60 | 62 |  | NOT LIVE - RETAIN BUDGET | 0% | 577.6 | 41525780.6429 | 41525780.6429 | 0 | -0.85 |  | 0.4 | 21734.4736 | 15005.7626 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46113 | Apr-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250327 | 2026-04-01
I250327 | 2024-11-05 | Islamabad | Islamabad | G-11 P2 | 1944 | 777.6 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 777.6 | 36706878.9535 | 36706878.9535 | 0 | -1 |  | 0.4 | 16828.4535 | 11691.9014 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46113 | Apr-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250327 | 2026-04-01
I250327 | 2024-11-05 | Islamabad | Islamabad | G-11 P3 | 2684 | 1073.6 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 1073.6 | 38089386.1276 | 38089386.1276 | 0 | -0.85 |  | 0.4 | 15445.9907 | 9906.1066 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46113 | Apr-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250327 | 2026-04-01
I250327 | 2024-11-05 | Islamabad | Islamabad | G-11 P4 | 3684 | 1473.6 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 1473.6 | 43334319.812 | 43334319.812 | 0 | -1 |  | 0.4 | 16848.1215 | 10217.9 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46113 | Apr-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250327 | 2026-04-01
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Gaju_Khaksar_Shams Gunj | 1262 | 504.8 | 1262 | 204 | 163 | 31 | 10 | Shamsi Road | 100% | 504.8 | 10306434.7834 | 1545965.2175 | 8760469.5659 | -0.85 |  | 0.4 | 0 | 21762.6674 | Arial | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Garden Town | 1288 | 515.2 |  |  |  |  | NOT ENERGISED AS YET | NOT LIVE - RETAIN BUDGET | 0% | 515.2 | 9860830.8219 | 9860830.8219 | 0 | -1 |  | 0.4 | 992.4627 | 13593.3196 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 61 | 62 | 14 | Yet to Start | 46143 | May-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-05-01
UI2560601 | No Initiation Date | Jhang | Jhang | Unknown-2 | 324 | 145.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 145.8 | 4743642.2415 | 4743642.2415 |  |  |  | 0.45 | 1141.4388 | 3847.0116 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
104 | No Initiation Date | Feeders/Transportations | Buffer Zone Khi | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 12278350 | 12278350 |  | -1 |  |  | 1210 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Garden Town_P1 | 2208 | 883.2 | [5 empty] | LIVE - 100% Completed | 100% | 883.2 | 36987052.6072 | 5548057.8911 | 31438994.7162 | -1 |  | 0.4 | 16036.1792 | 10360.1224 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Garden Town_P2 | 892 | 356.8 | [5 empty] | LIVE - 100% Completed | 100% | 356.8 | 21570089.468 | 3235513.4202 | 18334576.0478 | 0 |  | 0.4 | 10025.43 | 6882.5843 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Garden Town_P3 | 1132 | 452.8 | [5 empty] | LIVE - 100% Completed | 100% | 452.8 | 31611971.2201 | 4741795.683 | 26870175.5371 | -1 |  | 0.4 | 15727.2061 | 10982.4251 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Garjakh Road | 3480 | 1392 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 1392 | 21941670.885 | 5156292.658 | 16785378.227 | -1 |  | 0.4 | 5651.1 | 28995 | Hybrid | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46111 | Mar-2026 | Cable hanging is in process | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | INT-21-00315 | 2026-03-01
I250206 | 2024-09-12 | Daska | Daska | Ghalotian Mor | 456 | 182.4 |  |  |  |  | NOT ENERGISED AS YET | NOT LIVE - RETAIN BUDGET | 0% | 182.4 | 5655827.356 | 5655827.356 | 0 | -0.85 |  | 0.4 | 1060.1268 | 5527.3972 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 | 2 |  |  |  | I250206 | 2026-06-01
104 | No Initiation Date | Karachi | Buffer Zone Khi | P1 | 2246 | 673.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 10899966.376 | 10899966.376 |  |  |  |  | 1235.9079 | 8800.7242 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | To be started soon | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00440 | 2022-12-29 | Sargodha | Sargodha | Ghani Park FDT To Steel Welding | 386 | 193 | 82 | 13 |  | 69 | Live | LIVE - 100% Completed | 100% | 193 | 2992116.875 | 448817.5312 | 2543299.3438 | -0.8075 |  | 0.5 | 494.5 | 4865 | Arial | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Converted to Hybrid Model | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00440 | Timeline not applicable
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Gharmala | 202 | 80.8 | 32 | 3 |  | Yes |  | LIVE - 100% Completed | 100% |  | 2178203.0417 | 326730.4563 |  |  |  | 0.4 | 541.65 | 2208.35 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Gharmala Monan | 132 | 52.8 | 26 | 2 |  | Yes |  | REMOVE BUDGET (P) | 0% |  | 1417650.1014 | 0 |  |  |  | 0.4 | 320.7808 | 1572.1315 | Hybrid | 100% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | 14.5km backhauling req.and distance from would be 22km/Need to Remove | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | #N/A | Timeline not applicable
104 | No Initiation Date | Karachi | Buffer Zone Khi | P1 | 2246 | 673.8 | [5 empty] | LIVE - 100% Completed | 100% | 673.8 | 10899966.376 | 1634994.9564 |  | -1 |  | 0.3 | 1235.9079 | 8800.7242 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Ghordor Road P1 | 3824 | 1529.6 | [5 empty] | LIVE - 100% Completed | 100% | 1529.6 | 21039940.385 | 3155991.0578 | 17883949.3272 | -0.5 |  | 0.4 | 5609.7 | 23622.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | ADT Plan Received, Cable Hanging in process | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Ghordor Road P2 | 4278 | 1711.2 | [5 empty] | LIVE - 100% Completed | 100% | 1711.2 | 17075825.69 | 2561373.8535 | 14514451.8365 | -1 |  | 0.4 | 3459.2 | 22673.75 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Ghordor Road P3 | 3376 | 1350.4 | [5 empty] | LIVE - 100% Completed | 100% | 1350.4 | 18246117.395 | 2736917.6092 | 15509199.7857 | -0.85 |  | 0.4 | 5655.7 | 21146.25 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Ghordor Road P4 | 2012 | 804.8 | [5 empty] | LIVE - 100% Completed | 100% | 804.8 | 14651256.53 | 2197688.4795 | 12453568.0505 | -1 |  | 0.4 | 5681 | 17158.75 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Area Merged with P-3 | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Ghorrdo Road | 1276 | 510.4 | [5 empty] | LIVE - 100% Completed | 100% | 510.4 | 13083996.25 | 1962599.4375 | 11121396.8125 | 0 |  | 0.4 | 2114.85 | 11476.25 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Megred into Ghorrdo Road P1 | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
104 | No Initiation Date | Karachi | Buffer Zone Khi | P2 | 1880 | 564 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 15577085.5529 | 15577085.5529 |  |  |  |  | 2210.48 | 16031.3312 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | To be started soon | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Gohaddpur to Ghaniabad | 470 | 188 |  | 0 | 0 | 0 | Not Lived Yet | NOT LIVE - RETAIN BUDGET | 0% | 188 | 7229931.944 | 7229931.944 | 0 | -1 |  | 0.4 | 1265 | 4061.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240678 | Feedback Awaited | 0
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Gohar Green | 1906 | 762.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 29290908.987 | 29290908.987 |  |  |  |  | 10847.4088 | 8455.1798 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250378 | 2024-11-25 | Sahiwal | Sahiwal (P2) | Golf City | 286 | 114.4 | N/A | N/A | N/A |  | Not Live | NOT LIVE - RETAIN BUDGET | 0% | 114.4 | 3945742 | 3945742 | 0 | #DIV/0! |  | 0.4 | 870.55 | 3032.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250378 | Feedback Awaited
I260296 | No Initiation Date | Sukkur | Sukkur | Golimar Area | 292 | 116.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 95% |  | 3389734.3987 | 652523.8718 |  |  |  |  | 0 | 8930.8923 | Arial | 95% | NOT LIVE |  | 95% | 0.95 | 2026-03-01 | 92 | 93 | 45 | In Progress | 3 months | Jun-2026 | Work in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
INT-23-00440 | 2022-12-29 | Sargodha | Sargodha | Govt Central Model School To Th | 688 | 344 | 140 | 22 |  | 118 | Live | LIVE - 100% Completed | 100% | 344 | 5113957.095 | 767093.5642 | 4346863.5307 | -1 |  | 0.5 | 756.7 | 7336 | Arial | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Converted to Hybrid Model | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00440 | Timeline not applicable
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Green Acres P1 | 966 | 386.4 | 966 | 296 | 243 | 28 | 25 |  | 100% | 386.4 | 15982780.272 | 2397417.0408 | 13585363.2312 | -1 |  | 0.4 | 2647.3 | 12821.97 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Green Acres P2 | 500 | 200 | 500 | 21 | 19 | 2 | 0 |  | 100% | 200 | 8013488.6 | 1202023.29 | 6811465.31 | -0.85 |  | 0.4 | 1352.4 | 6213.525 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Green and Al-hafeez Town | 1886 | 754.4 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 85% | 754.4 | 11863479.4195 | 3292115.5389 |  |  |  |  | 1691.4733 | 14248.2564 | Hybrid | 85% | Not Live |  | 85% | 0.85 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Civil work and hand hole complete cable pulling is pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
104 | No Initiation Date | Karachi | Buffer Zone Khi | P2 | 1880 | 564 | [5 empty] | LIVE - 100% Completed | 100% | 564 | 15577085.5529 | 2336562.8329 |  | -1 |  | 0.3 | 2210.48 | 16031.3312 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Green Fort Housing Society | 1094 | 437.6 | 70 | 2 | 15 | 53 |  | LIVE - 100% Completed | 100% | 437.6 | 13221453.9073 | 1983218.0861 | 11238235.8212 | 0 |  | 0.4 | 2717.7589 | 13065.5398 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I250210 | 2024-09-14 | Sargodha | Sargodha | Green valley | 288 | 115.2 |  |  |  |  | Not Live | NOT LIVE - RETAIN BUDGET | 70% | 115.2 | 4126192.4 | 1671107.922 | 2455084.478 | -0.85 |  | 0.4 | 784.3 | 3316.25 | Hybrid | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 61 | 62 | 14 | In Progress | 2 Months | May-2026 | This Colony linked with the DPLC backup connectivity; once completed, the area will go live. | Swap Cases | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250210 | 2026-05-01
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Green Valley Ph-6 | 442 | 176.8 | [5 empty] | LIVE - 100% Completed | 100% | 176.8 | 4874990.6821 | 731248.6023 | 4143742.0798 | -0.85 |  | 0.4 | 1270.5 | 3517.2525 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Green Village | 60 | 24 |  | 0 | 0 | 0 | Yet not active | LIVE - 100% Completed | 100% | 24 | 1244540.225 | 186681.0338 | 1057859.1913 | -0.5 | New Garden Block | 0.4 | 146.05 | 1343.475 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | GT Rd Pocket 06 | 636 | 254.4 | [5 empty] | LIVE - 100% Completed | 100% | 254.4 | 6584948.726 | 987742.3089 | 5597206.4171 | -1 |  | 0.4 | 440.5 | 4555 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | GT Rd Pocket 07 | 1006 | 402.4 | [5 empty] | LIVE - 100% Completed | 100% | 402.4 | 8889140.73 | 1333371.1095 | 7555769.6205 | -1 |  | 0.4 | 828.5 | 9080 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | GT Rd Pocket 08 | 980 | 392 | [5 empty] | LIVE - 100% Completed | 100% | 392 | 9003697.116 | 1350554.5674 | 7653142.5486 | -1 |  | 0.4 | 815.3333 | 10653.75 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | GT Rd Pocket 09 | 1388 | 555.2 | [5 empty] | LIVE - 100% Completed | 100% | 555.2 | 13166615.618 | 1974992.3427 | 11191623.2753 | 0 |  | 0.4 | 1064.6667 | 16088.75 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | GT Rd Pocket 10 | 1400 | 560 | [5 empty] | LIVE - 100% Completed | 100% | 560 | 14571886.73 | 2185783.0095 | 12386103.7205 | -1 |  | 0.4 | 1272 | 15263.75 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | GT Rd Pocket 11 | 1466 | 586.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 586.4 | 16698561.168 | 16698561.168 | 0 | 0 |  | 0.4 | 1250.4 | 17010 | Arial | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 61 | 62 | 14 | Yet to Start | 46143 | May-2026 | Hold due to Metro Project | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240700 | 2026-05-01
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | GT Rd Pocket 12 | 1084 | 433.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 433.6 | 9483172.864 | 9483172.864 | 0 | -1 |  | 0.4 | 811 | 8876.25 | Arial | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 61 | 62 | 14 | Yet to Start | 46143 | May-2026 | Hold due to Metro Project | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240700 | 2026-05-01
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Gujjar pur | 126 | 50.4 |  |  | Yes |  |  | NOT LIVE - RETAIN BUDGET | 60% |  | 2275726.5417 | 1115106.0054 |  |  |  | 0.4 | 672.1 | 1513.75 | Hybrid | 60% | NOT LIVE |  | 60% | 0.6 | 2026-03-01 | 92 | 93 | 45 | In Progress | 3 Months | Jun-2026 | Railway crossing required even on Aerial network | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I240539 | 2024-02-28 | Swat | Swat Ph2 | Gul Kada | 816 | 326.4 | 40 | 30 | 6 | 4 | Civil Work in progress | LIVE - 80% Completed | 80% | 261.12 | 12199624.6265 | 3903879.8805 | 8295744.746 | -1 |  | 0.4 | 1936.6 | 11379.3336 | Hybrid |  | LIVE | Arial | 80% | 0.8 | 2026-03-01 | 61 | 62 | 14 | In Progress | 2 Months | May-2026 | Civil work is on going | Live - As per Plan | LIVE - 80% Completed | 1 | Add 9 count |  |  |  | I240539 | 2026-05-01
104 | No Initiation Date | Karachi | Buffer Zone Khi | P3 | 1774 | 532.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 10266067.8215 | 10266067.8215 |  |  |  |  | 1257.7561 | 7587.1158 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | To be started soon | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
104 | No Initiation Date | Karachi | Buffer Zone Khi | P3 | 1774 | 532.2 | [5 empty] | LIVE - 100% Completed | 100% | 532.2 | 10266067.8215 | 1539910.1732 |  | -0.5 |  | 0.3 | 1257.7561 | 7587.1158 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 2 |  |  |  | #N/A | Timeline not applicable
104 | No Initiation Date | Karachi | Buffer Zone Khi | P4 | 3244 | 973.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 12636229.7224 | 12636229.7224 |  |  |  |  | 1436.9125 | 9796.7409 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | To be started soon | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Gulberg & New Gulberg | 1084 | 542 | 365 | 40 | 66 | 259 |  | LIVE - 100% Completed | 100% | 542 | 10141888.97 | 1521283.3455 | 8620605.6245 | -1 |  | 0.5 | 1925 | 11586.95 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I250210 | 2024-09-14 | Sargodha | Sargodha | Gulberg City | 792 | 316.8 |  |  |  |  | Not Live | REMOVE BUDGET (P) | 0% | 316.8 | 6516815.064 | 0 | 6516815.064 | -1 |  | 0.4 | 809.6 | 7282.5 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I250210 | Timeline not applicable
104 | No Initiation Date | Karachi | Buffer Zone Khi | P4 | 3244 | 973.2 | [5 empty] | LIVE - 100% Completed | 100% | 973.2 | 12636229.7224 | 1895434.4584 |  | -1 |  | 0.3 | 1436.9125 | 9796.7409 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 2 |  |  |  | #N/A | Timeline not applicable
104 | No Initiation Date | Karachi | Buffer Zone Khi | P5 | 6000 | 1800 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 27949767.8371 | 27949767.8371 |  |  |  |  | 3919.79 | 20659.7138 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | To be started soon | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250213 | 2024-09-14 | Mardan | Mardan | Gulberg Town | 552 | 220.8 | 552 | 161 | 132 | 12 | 17 |  | 100% | 220.8 | 7090995.45 | 1063649.3175 | 6027346.1325 | -0.85 |  | 0.4 | 1392.65 | 5311.8 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250213 | Timeline not applicable
I240680 | 2024-05-16 | Rahim Yar Khan | RahimYar Khan Ph2 | Gulberg+Ahmed+Air view | 576 | 230.4 | 54 | 4 |  |  | Air view not lived & 60 | LIVE - 100% Completed | 100% | 230.4 | 8023985 | 1203597.75 | 6820387.25 | -1 |  | 0.4 | 1761.8 | 5392.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240680 | Timeline not applicable
I250207 | 2024-09-12 | Abbottabad | Abbottabad | Gulfam Town_Mera Muzzafar | 450 | 180 | 205 | 10 | 4 | 195 |  | LIVE - 100% Completed | 100% | 180 | 4099485.6016 | 614922.8402 | 3484562.7613 | -1 |  | 0.4 | 0 | 11096.8257 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250207 | Timeline not applicable
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Guli Bagh | 1122 | 448.8 | 1122 | 117 | 94 | 18 | 5 |  | 100% | 448.8 | 11284382.9875 | 1692657.4481 | 9591725.5394 | -1 |  | 0.4 | 898 | 14794.3062 | Arial | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
I250208 | 2024-09-14 | Wahh | Wah Cantt | Gulistan Colony | 1750 | 700 | 0 |  |  |  |  | REMOVE BUDGET (P) | 0% | 700 | 15880849.536 | 0 | 15880849.536 | -1 |  | 0.4 | 2536.9 | 13315.1905 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I250208 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Gulistan_town | 1100 | 440 | 17 | 0 | 0 | 17 |  | NOT LIVE - RETAIN BUDGET | 0% | 440 | 11004993.246 | 11004993.246 | 0 | -1 |  | 0.4 | 1607.7 | 12706.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 0 | 1 | -47 | Yet to Start | 46054 | Mar-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-03-01
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Gulistan-i-Ashar | 1012 | 506 | 7 | 2 | 3 | 2 |  | NOT LIVE - RETAIN BUDGET | 0% | 506 | 10236969.55 | 10236969.55 | 0 | -0.85 |  | 0.5 | 4208.65 | 9230.7 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | INT-23-00439 | Feedback Awaited
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Gulraiz Town | 720 | 360 | 216 | 37 | 56 | 123 |  | LIVE - 100% Completed | 100% | 360 | 6083947.67 | 912592.1505 | 5171355.5195 | -1 |  | 0.5 | 1275.35 | 5060.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Gulshan Aziz Colony | 388 | 155.2 | [5 empty] | LIVE - 100% Completed | 100% | 155.2 | 4794235.3527 | 719135.3029 | 4075100.0498 | -1 |  | 0.4 | 1515.36 | 1557.682 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
INT-23-00435 | 2022-12-29 | Karachi | Karachi Misc Areas | Gulshan Block-19 | 768 | 384 | [5 empty] | LIVE - 100% Completed | 100% | 384 | 6882564.7835 | 1032384.7175 | 5850180.066 | 0 |  | 0.5 | 1465.5151 | 4859.8001 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00435 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Gulshan Block-4A | 580 | 232 | [5 empty] | LIVE - 100% Completed | 100% | 232 | 5345360.4463 | 801804.067 | 4543556.3794 | -0.765 |  | 0.4 | 0 | 3995.2021 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Live - on Aerial Partial | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Gulshan Colony | 752 | 300.8 | 4 | 0 | 0 | 4 |  | NOT LIVE - RETAIN BUDGET | 0% | 300.8 | 7973142.75 | 7973142.75 | 0 | -0.85 |  | 0.4 | 1354.7 | 7435.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 0 | 1 | -47 | Yet to Start | 46082 | Mar-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-03-01
104 | No Initiation Date | Karachi | Buffer Zone Khi | P5 | 6000 | 1800 | [5 empty] | LIVE - 100% Completed | 100% | 1800 | 27949767.8371 | 4192465.1756 |  | -0.85 |  | 0.3 | 3919.79 | 20659.7138 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
I250681 | 2025-03-26 | Lahore | CTC Lahore | Gulshan e Ali | 934 | 373.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 373.6 | 6627791.724 | 1557531.0551 | 5070260.6689 | -1 |  |  | 2078.26 | 8087.9764 | Hybrid | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46054 | Mar-2026 | As-built Done , Cable Plan will be shared after the FDT Placement Conformation | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 | 1 |  |  |  | I250681 | 2026-03-01
I250208 | 2024-09-14 | Wahh | Wah Cantt | Gulshan e Anwar T.Buried | 730 | 292 | 44 |  | 1 | 43 |  | LIVE - 100% Completed | 100% | 292 | 19016409.8545 | 2852461.4782 | 16163948.3764 | -1 |  | 0.4 | 9446.7365 | 6730.925 | Buried | 15% | LIVE |  | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250208 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Gulshan e Bakhtawar Ext | 502 | 200.8 | 260 | 200 |  |  |  | LIVE - 25% Completed | 25% | 50.2 | 6132597.0046 | 4829420.1411 | 1303176.8635 | 0 |  | 0.4 | 1063.865 | 4781.6152 | Hybrid |  | LIVE | Arial | 25% | 0.25 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | In Progress | No more work req | Feedback Awaited | Due to permission constraints, some sections are live on buried, and the remaining pockets are live on aerial | Live - Permission Awaited | LIVE - 25% Completed | 1 | Add 9 count |  |  |  | I240702 | Feedback Awaited
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Gulshan e Faiz | 1328 | 664 | 251 | 23 | 27 | 201 |  | LIVE - 100% Completed | 100% | 664 | 12247902.501 | 1837185.3752 | 10410717.1259 | -0.85 |  | 0.5 | 2325.8813 | 14265.4747 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Gulshan e Haram-II | 346 | 138.4 |  | 4 | 3 | 13 | Occupancy : 50 | LIVE - 100% Completed | 100% | 138.4 | 4172942.5047 | 625941.3757 | 3547001.129 | -1 |  | 0.4 | 796.605 | 2951.8267 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Gulshan e Iqbal | 216 | 108 | 280 | 38 | 29 | 213 |  | LIVE - 100% Completed | 100% | 108 | 7563981.5313 | 1134597.2297 | 6429384.3016 | -1 |  | 0.5 | 4187.7608 | 3734.3571 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Gulshan e Makkah | 460 | 184 |  | 11 | 26 | 41 | Occupancy : 150 | LIVE - 100% Completed | 100% | 184 | 5118255.5 | 767738.325 | 4350517.175 | 0 |  | 0.4 | 716.45 | 6475.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
I250213 | 2024-09-14 | Mardan | Mardan | Gulshan Town Ph1 | 376 | 150.4 | 376 | 52 | 45 | 4 | 3 |  | 100% | 150.4 | 3607102.1 | 541065.315 | 3066036.785 | -1 |  | 0.4 | 591.1 | 3872.805 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250213 | Timeline not applicable
I250209 | 2024-09-14 | Rawalpindi | Rawalpindi | Gulshanabad P01 | 1758 | 703.2 | 0 |  |  |  |  | SWAPPED | 0% | 703.2 | 17094645.258 | 0 | 17094645.258 | -1 |  | 0.4 | 2826.7 | 19588.601 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with G-16 developed part only | Swap Cases | SWAPPED |  |  | G-16 developed part only | 54483572 | 1606 | I250209 | Timeline not applicable
I250209 | 2024-09-14 | Rawalpindi | Rawalpindi | Gulshanabad P02 | 1470 | 588 | 0 |  |  |  |  | SWAPPED | 0% | 588 | 16562638.7071 | 0 | 16562638.7071 | -0.85 |  | 0.4 | 3055.55 | 20330.0372 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with G-16 developed part only | Swap Cases | SWAPPED |  |  | G-16 developed part only | 54483572 | 1606 | I250209 | Timeline not applicable
I250209 | 2024-09-14 | Rawalpindi | Rawalpindi | Gulshanabad P03 | 916 | 366.4 | 0 |  |  |  |  | SWAPPED | 0% | 366.4 | 11424746.21 | 0 | 11424746.21 | -1 |  | 0.4 | 2458.7 | 10956.3015 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with G-16 developed part only | Swap Cases | SWAPPED |  |  | G-16 developed part only | 54483572 | 1606 | I250209 | Timeline not applicable
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Gulshan-e-Rafi | 712 | 284.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 7181085.395 | 7181085.395 |  |  |  |  | 1326.6 | 5448.2876 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Gulshan-e-Tayyaba | 488 | 195.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 5401796.4313 | 5401796.4313 |  |  |  |  | 1072.5 | 3180.5276 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240704 | 2024-05-15 | Multan | Multan Ph3 | Gulshan-i-Ghafoor | 108 | 43.2 | 35 | 2 | 2 | 31 |  | LIVE - 100% Completed | 100% | 43.2 | 4516010.7689 | 677401.6153 | 3838609.1536 | -1 |  | 0.4 | 2184.124 | 2009.8553 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Gulshen e Yousaf & Stadium | 1684 | 673.6 | 23 | 2 | 6 | 15 |  | LIVE - 100% Completed | 100% | 673.6 | 23471595.9206 | 3520739.3881 | 19950856.5325 | 0 |  | 0.4 | 4313.6395 | 21284.5297 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
104 | No Initiation Date | Karachi | Buffer Zone Khi | P6 | 3298 | 989.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 17265584.4862 | 17265584.4862 |  |  |  |  | 2892.6805 | 15505.0119 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | To be started soon | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
104 | No Initiation Date | Karachi | Buffer Zone Khi | P6 | 3298 | 989.4 | [5 empty] | LIVE - 100% Completed | 100% | 989.4 | 17265584.4862 | 2589837.6729 |  | -1 |  | 0.3 | 2892.6805 | 15505.0119 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 1 |  |  |  | #N/A | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Gulshen-i-Sardar | 228 | 114 | 137 | 16 | 31 | 90 |  | LIVE - 100% Completed | 100% | 114 | 2658424.64 | 398763.696 | 2259660.944 | -0.85 |  | 0.5 | 626.75 | 2209.8 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240538 | 2024-02-29 | Haripur | Haripur Ph2 | Gulzar Colony & Main Rd | 424 | 169.6 | 256 | 209 | 23 | 24 |  | LIVE - 100% Completed | 100% | 169.6 | 12900110.767 | 1935016.6151 | 10965094.1519 | -1 |  | 0.4 | 1397.25 | 5771.522 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240538 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Abdul Khaliq Colony | 82 | 32.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 100% | 32.8 | 1063732.4 | 159559.86 |  | #DIV/0! |  |  | 136.85 | 851.25 | Hybrid | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 214 | 215 | 167 | Completed |  | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560602 | No Initiation Date | Kasur | Kasur | Ali Ahmed Shah Colony | 712 | 284.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 284.8 | 5884214.1563 | 5884214.1563 |  | #DIV/0! |  |  | 1132.6731 | 6545.9252 | Hybrid | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start |  | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250327 | 2024-11-05 | Islamabad | Islamabad | H13_Mainly Hostels | 908 | 363.2 | 39 | 2 | 6 | 31 |  | LIVE - 100% Completed | 100% | 363.2 | 11805696.199 | 1770854.4298 | 10034841.7692 | -0.85 |  | 0.4 | 4754.73 | 2527.275 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250327 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Habib Colony | 518 | 207.2 |  |  |  | 7 |  | LIVE - 100% Completed | 100% | 207.2 | 4735859.3238 | 710378.8986 |  |  |  |  | 913.5722 | 5242.8052 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Al-Kareem Garden | 440 | 176 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 176 | 4726646.4231 | 4726646.4231 |  | #DIV/0! |  |  | 906.7987 | 5767.1684 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250206 | 2024-09-12 | Daska | Daska | Habibpura | 778 | 311.2 | 12 | 0 | 0 | 12 |  | NOT LIVE - RETAIN BUDGET | 0% | 311.2 | 7991093.25 | 7991093.25 | 0 | -1 |  | 0.4 | 1269.6 | 8031 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 0 | 1 | -47 | Yet to Start | 46054 | Mar-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-03-01
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Hafizabad Road | 234 | 93.6 | [5 empty] | LIVE - 100% Completed | 100% | 93.6 | 2203171.9215 | 330475.7882 | 1872696.1333 | -0.5 |  | 0.4 | 304.75 | 1426.4357 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Hafizabad Road | 4144 | 1657.6 | [5 empty] | LIVE - 100% Completed | 100% | 1657.6 | 23641914.205 | 3546287.1307 | 20095627.0742 | -0.5 |  | 0.4 | 5651.1 | 34422.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Al-Majeed Housing Scheme | 460 | 184 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 184 | 4561609.9315 | 4561609.9315 |  | #DIV/0! |  |  | 936.0879 | 3647.2655 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560602 | No Initiation Date | Kasur | Kasur | Azhar Colony Khara Road and Bas | 1660 | 664 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 664 | 9210426.618 | 9210426.618 |  | #DIV/0! |  |  | 941.85 | 14640 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560602 | No Initiation Date | Kasur | Kasur | Defence Colony | 632 | 252.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 252.8 | 5728470.6785 | 5728470.6785 |  | #DIV/0! |  |  | 1111.7593 | 5680 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560602 | No Initiation Date | Kasur | Kasur | Dhorr Kot Road & Kot Fateh Din | 2180 | 872 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 872 | 15044734.3908 | 15044734.3908 |  | #DIV/0! |  |  | 2910.1968 | 15626.1919 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560602 | No Initiation Date | Feeders/Transportations | Kasur | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 181830916 | 181830916 |  | #DIV/0! |  |  | 47944.2563 | 331810.9803 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Gulberg | 1394 | 557.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 557.6 | 9973112.426 | 9973112.426 |  | #DIV/0! |  |  | 1894.05 | 10575 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560602 | No Initiation Date | Kasur | Kasur | Haji Park Bypass | 328 | 131.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 131.2 | 3933270.8111 | 3933270.8111 |  | #DIV/0! |  |  | 891.2978 | 3384.3068 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Haneef Garden | 78 | 31.2 |  | 0 | 0 | 0 | Yet not active | LIVE - 100% Completed | 100% | 31.2 | 1039842 | 155976.3 | 883865.7 | -1 |  | 0.4 | 0 | 1280 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Hansabad | 528 | 211.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 5393428.6324 | 5393428.6324 |  |  |  |  | 994.4 | 4037.8923 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560602 | No Initiation Date | Kasur | Kasur | Haji Park Commercial | 114 | 45.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 45.6 | 1407193.5638 | 1407193.5638 |  | #DIV/0! |  |  | 242.281 | 993.8861 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Haseeb Town,Fahad Colony & Dila | 3180 | 1272 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 85% | 1272 | 17710511.0732 | 4914666.8228 |  |  |  |  | 2339.4784 | 18928.45 | Hybrid | 85% | Not Live |  | 85% | 0.85 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Civil work and hand hole complete cable pulling is pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
UI2560602 | No Initiation Date | Kasur | Kasur | Haji Park Phase 1 | 390 | 156 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 156 | 4050841.2497 | 4050841.2497 |  | #DIV/0! |  |  | 700.3807 | 3844.6732 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560602 | No Initiation Date | Kasur | Kasur | Hamza Town | 204 | 81.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 81.6 | 2459324.3916 | 2459324.3916 |  | #DIV/0! |  |  | 467.5546 | 1614.4163 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560602 | No Initiation Date | Kasur | Kasur | Ideal Garden Housing | 388 | 155.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 155.2 | 5003191.4 | 5003191.4 |  | #DIV/0! |  |  | 1129.3 | 5383.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Redline | 310 | 124 | [5 empty] | NOT LIVE - RETAIN BUDGET | 40% | 124 | 49423135 | 32619269.1 | 16803865.9 | -1 |  | 0.4 | 13800 | 0 | Hybrid | 40% | NOT LIVE |  | 40% | 0.4 | 2026-03-01 | 92 | 93 | 45 | In Progress | 46174 | Jun-2026 | Work in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240705 | 2026-06-01
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | Hostel City | 394 | 197 | 952 | 311 | 340 | 301 |  | LIVE - 100% Completed | 100% | 197 | 3073935 | 461090.25 | 2612844.75 | -1 |  | 0.5 | 0 | 4661.51 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00444 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | Hostel City_Extn | 278 | 111.2 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 111.2 | 2460240.8 | 369036.12 | 2091204.68 | -1 |  | 0.4 | 0 | 3663.78 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250376 | Timeline not applicable
I240678 | 2024-05-16 | Sialkot | Sialkot | Hunterpura Ext | 534 | 213.6 |  | 0 | 0 | 0 | Not Lived Yet | NOT LIVE - RETAIN BUDGET | 0% | 213.6 | 6361725.1975 | 6361725.1975 | 0 | -1 |  | 0.4 | 1129.7 | 3361.6056 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240678 | Feedback Awaited
UI2560602 | No Initiation Date | Kasur | Kasur | Kasur Raiwand Road | 902 | 360.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 360.8 | 8520569.396 | 8520569.396 |  | #DIV/0! |  |  | 1796.3 | 9450 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560602 | No Initiation Date | Kasur | Kasur | Khara Road | 1968 | 787.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 787.2 | 14061195.508 | 14061195.508 |  | #DIV/0! |  |  | 2371.3 | 17831.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Hyd Cantt P01 | 190 | 76 | - | - |  |  |  | LIVE - 100% Completed | 100% | 76 | 7394796.3365 | 1109219.4505 | 6285576.8861 | -1 |  | 0.4 | 1680.8886 | 8184.8857 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | This area lived in aerial before plan /further permission issue on burried | Live - Permission Awaited | LIVE - 100% Completed | [5 empty] | I240702 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Hyd Cantt P02 | 368 | 147.2 | 300 | 150 | 292 | 63 | 8 | LIVE - 100% Completed | 100% | 147.2 | 17174177.9258 | 2576126.6889 | 14598051.2369 | -1 |  | 0.4 | 4538.8436 | 15078.6097 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | This area lived in aerial before plan /further permission issue on burried | Live - Permission Awaited | LIVE - 100% Completed | [5 empty] | I240702 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Hyd Cantt P03 | 56 | 22.4 | - | - |  |  |  | LIVE - 100% Completed | 100% | 22.4 | 1760631.1978 | 264094.6797 | 1496536.5181 | -1 |  | 0.4 | 0 | 2925.282 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | This area lived in aerial before plan /further permission issue on burried | Live - Permission Awaited | LIVE - 100% Completed | [5 empty] | I240702 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | I-10 P1 | 1220 | 610 | 1137 | 211 | 150 | 776 |  | LIVE - 100% Completed | 100% | 610 | 6464348.8 | 969652.32 | 5494696.48 | -0.85 |  | 0.5 | 0 | 10231.718 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00444 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | I-10 P2 | 812 | 406 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 406 | 3703399.595 | 555509.9393 | 3147889.6557 | -1 |  | 0.5 | 0 | 6727.238 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00444 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | I-10 P3 | 1192 | 596 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 596 | 4744210.99 | 711631.6485 | 4032579.3415 | -0.85 |  | 0.5 | 0 | 8492.694 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00444 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | I-10 P4 | 1810 | 905 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 905 | 7318747.545 | 1097812.1317 | 6220935.4133 | -1 |  | 0.5 | 0 | 12106.878 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00444 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | I-10 P5 | 2218 | 1109 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 1109 | 10046106.76 | 1506916.014 | 8539190.746 | -0.85 |  | 0.5 | 0 | 16647.568 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00444 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | I-11 Aerial | 418 | 209 | 804 | 208 | 142 | 454 |  | LIVE - 100% Completed | 100% | 209 | 2699070.25 | 404860.5375 | 2294209.7125 | -1 |  | 0.5 | 0 | 4536.21 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00444 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | I-11P1 | 570 | 285 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 285 | 18662773 | 2799415.95 | 15863357.05 | -0.85 |  | 0.5 | 8532.319 | 7285.516 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00444 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | I-11P2 | 1504 | 752 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 752 | 31097808 | 4664671.2 | 26433136.8 | -1 |  | 0.5 | 12513.66 | 12770.954 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00444 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | I-14-P1 | 1978 | 791.2 | 946 | 208 | 101 | 637 |  | LIVE - 100% Completed | 100% | 791.2 | 23373779.3635 | 3506066.9045 | 19867712.459 | -0.85 |  | 0.4 | 5058.045 | 27114.6427 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250376 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | I-14-P2 | 1606 | 642.4 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 642.4 | 16443581.9725 | 2466537.2959 | 13977044.6766 | -1 |  | 0.4 | 3088.9 | 23898.855 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250376 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | I-14-P3 | 1710 | 684 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 684 | 19457426.6675 | 2918614.0001 | 16538812.6674 | -0.85 |  | 0.4 | 4778.71 | 24305.855 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250376 | Timeline not applicable
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | I-14-P4 | 1848 | 739.2 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 739.2 | 16630801.3391 | 2494620.2009 | 14136181.1382 | -1 |  | 0.4 | 3591.45 | 19512.3029 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250376 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | I-9 P1 | 1222 | 611 | 291 | 46 | 33 | 212 |  | LIVE - 100% Completed | 100% | 611 | 6106061.05 | 915909.1575 | 5190151.8925 | -0.5 |  | 0.5 | 0 | 7569.436 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00444 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | I-9 P2 | 794 | 397 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 397 | 3534044.74 | 530106.711 | 3003938.029 | -1 |  | 0.5 | 0 | 2526.398 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00444 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | I-9 P3 | 752 | 376 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 376 | 4231495.95 | 634724.3925 | 3596771.5575 | #DIV/0! |  | 0.5 | 0 | 2332.4 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00444 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Islamabad | Islamabad Misc Areas | I-9 P4 | 836 | 418 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 418 | 4061320.88 | 609198.132 | 3452122.748 | #DIV/0! |  | 0.5 | 0 | 6607.692 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00444 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Ibrahim Garden | 174 | 69.6 | 0 | 0 | 0 | 0 |  | REMOVE BUDGET (P) | 0% | 69.6 | 7399143.2532 | 0 | 7399143.2532 | -1 |  | 0.4 | 3641.4455 | 3057.6693 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I240704 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Khara Road and Nafees Colony | 2524 | 1009.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1009.6 | 19264679.5 | 19264679.5 |  |  |  |  | 3462.65 | 23170 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Park View_T.B_P4 | 3186 | 1274.4 | [5 empty] | REMOVE BUDGET (P) | 0% | 1274.4 | 75992968.75 | 0 | 75992968.75 | #DIV/0! |  | 0.4 | 42690 | 45483 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I240703 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Inam City | 148 | 74 | 0 | 0 | 0 | 0 | On Hold | REMOVE BUDGET (P) | 0% | 74 | 2302362.335 | 0 | 2302362.335 | -1 |  | 0.5 | 948.9 | 1349.95 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | INT-23-00439 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Madina Town | 136 | 54.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 54.4 | 2357347.4672 | 2357347.4672 |  | #DIV/0! |  |  | 528.4838 | 1704.2674 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00436 | 2022-12-29 | Hyderabad | Hyderabad Misc Areas | Indus Society | 212 | 84.8 | 177 | 10 |  |  |  | LIVE - 100% Completed | 100% | 84.8 | 3210107.9956 | 481516.1993 | 2728591.7963 | -0.5 |  | 0.4 | 770.8728 | 1768.9374 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00436 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Main Kasur P-1 | 2010 | 804 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 804 | 7046454.8012 | 7046454.8012 |  | #DIV/0! |  |  | 795.6397 | 10525.71 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250212 | 2024-09-14 | Swat | Mingora | Ingaroderai-Takhtaband P01 | 2350 | 940 | 189 | 189 |  |  |  | LIVE - 100% Completed | 100% | 940 | 27911300.6344 | 4186695.0952 | 23724605.5393 | -0.765 |  | 0.4 | 4889.5 | 40881.6831 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Ingaroderai-Takhtaband P02 | 1080 | 432 | 113 | 113 |  |  |  | LIVE - 100% Completed | 100% | 432 | 18368658.0084 | 2755298.7013 | 15613359.3072 | -1 |  | 0.4 | 3657.5 | 24896.1733 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Ingaroderai-Takhtaband P03 | 946 | 378.4 | 51 | 51 |  |  |  | LIVE - 100% Completed | 100% | 378.4 | 15385762.2494 | 2307864.3374 | 13077897.912 | -0.765 |  | 0.4 | 3363.8 | 17400.6607 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Ink City 02 P01 | 174 | 69.6 | 280 | 85 | 130 | 26 | 1 | LIVE - 100% Completed | 100% | 69.6 | 2574427.8476 | 386164.1771 | 2188263.6704 | 0 |  | 0.4 | 441.485 | 2083.8562 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240702 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Ink City 02 P02 | 90 | 36 | 150 | 21 | 15 | 2 | 0 | REMOVE BUDGET (P) | 0% | 36 | 2132321.0793 | 0 | 2132321.0793 | -1 |  | 0.4 | 645.15 | 742.6764 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  | 1 |  | 0 |  | I240702 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Ink City 02 P03 | 216 | 86.4 | 500 | 0 |  |  |  | LIVE - 100% Completed | 100% | 86.4 | 3319800.2236 | 497970.0335 | 2821830.19 | 0 |  | 0.4 | 704.605 | 2259.4491 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240702 | Timeline not applicable
I240437 | 2024-01-18 | Feeders/Transportations | Askari Lahore | Installation / Termination of Cables & Testing of Man ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 50000 | 25000 | 25000 | -1 |  |  | 0 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240437 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Main Kasur P-2 | 3350 | 1340 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1340 | 20048350.4218 | 20048350.4218 |  | #DIV/0! |  |  | 4174.7149 | 20857.8909 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Iqbal Stadium Comm.Area | 106 | 42.4 |  | 2 | 6 | 16 | Occupancy : 50 | LIVE - 100% Completed | 100% | 42.4 | 1481417.3939 | 222212.6091 | 1259204.7848 | -0.425 |  | 0.4 | 0 | 2180.3269 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Islamia Colony PK1 | 1158 | 463.2 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 85% | 463.2 | 5130125.54 | 1423609.8373 |  |  |  |  | 277.5372 | 6425.9245 | Hybrid | 85% | Not Live |  | 85% | 0.85 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Civil work and hand hole complete cable pulling is pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Islamia Colony PK2 | 2030 | 812 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 85% | 812 | 11811776.4031 | 3277767.9519 |  |  |  |  | 1568.4337 | 12506.8313 | Hybrid | 85% | Not Live |  | 85% | 0.85 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Civil work and hand hole complete cable pulling is pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Islamia Colony PK3 | 1498 | 599.2 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 85% | 599.2 | 7103852.773 | 1971319.1445 |  |  |  |  | 965.5428 | 8040.9881 | Hybrid | 85% | Not Live |  | 85% | 0.85 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Civil work in progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I250206 | 2024-09-12 | Daska | Daska | Islampura | 1132 | 452.8 |  |  |  |  | NOT ENERGISED AS YET | SWAPPED | 0% | 452.8 | 8329511.368 | 0 | 8329511.368 | -0.85 |  | 0.4 | 961.4 | 9642.5 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Meraj Housing | Swap Cases | SWAPPED |  |  | Meraj Housing | 22604832.2609 | 542 | I250206 | Timeline not applicable
I240679 | 2024-05-16 | Sargodha | Sargodha | Islampura | 2800 | 1120 | 135 | 23 | 10 | 102 | Live | LIVE - 100% Completed | 100% | 1120 | 2809208 | 421381.2 | 2387826.8 | -1 |  | 0.4 | 0 | 5655 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240679 | Timeline not applicable
I240679 | 2024-05-16 | Sargodha | Sargodha | Istiqlalabad | 1800 | 720 | 46 | 5 | 11 | 41 | Live | LIVE - 100% Completed | 100% | 720 | 2524524 | 378678.6 | 2145845.4 | -1 |  | 0.4 | 0 | 5845 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240679 | Timeline not applicable
I240680 | 2024-05-16 | Rahim Yar Khan | RahimYar Khan Ph2 | Ittehad Garden P1 | 712 | 284.8 | 76 | 5 |  |  |  | LIVE - 100% Completed | 100% | 284.8 | 21998362.996 | 3299754.4494 | 18698608.5466 | -0.85 |  | 0.4 | 10175.55 | 11145 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240680 | Timeline not applicable
I240680 | 2024-05-16 | Rahim Yar Khan | RahimYar Khan Ph2 | Ittehad Garden P2 | 1000 | 400 | 5 | 1 |  |  | not fully lived due to Etihad duckting pending | LIVE - 100% Completed | 100% | 400 | 24597880.232 | 3689682.0348 | 20908198.1972 | -1 |  | 0.4 | 11997.05 | 11145 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240680 | Timeline not applicable
I240680 | 2024-05-16 | Rahim Yar Khan | RahimYar Khan Ph2 | Ittehad Town & Other | 268 | 107.2 | 64 | 1 |  |  | Mereged with Ali + Fort + Madina | REMOVE BUDGET (T) | 0% | 107.2 | 4749140.5 | 0 | 4749140.5 | -1 |  | 0.4 | 1124.7 | 2582.5 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 4 Months | Jun-2026 | 2026-07-01 | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | I240680 | 2026-06-01
UI2560602 | No Initiation Date | Kasur | Kasur | Main Kasur P-3 | 424 | 169.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 169.6 | 5609377.1 | 5609377.1 |  | #DIV/0! |  |  | 1330.55 | 6394.95 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Jahangir | 214 | 85.6 |  |  | Yes |  |  | REMOVE BUDGET (P) | 0% |  | 2604761.892 | 0 |  |  |  | 0.4 | 674.822 | 3075.2329 | Hybrid | 100% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | 14.5km backhauling req.and distance from would be 22km/Need to Remove | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | #N/A | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Rehan Gardens Ph 1&2 | 538 | 215.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 215.2 | 6348748.3333 | 6348748.3333 | 0 | #DIV/0! |  | 0.4 | 1738.8 | 5110.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240703 | Feedback Awaited
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Jalil Town | 1492 | 596.8 | [5 empty] | LIVE - 100% Completed | 100% | 596.8 | 11012079.33 | 1651811.8995 | 9360267.4305 | -1 |  | 0.4 | 2541.5 | 14683.75 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
I240678 | 2024-05-16 | Sialkot | Sialkot | Jallianwala | 620 | 248 |  | 1 | 3 | 52 |  | LIVE - 100% Completed | 100% | 248 | 10086239.8749 | 1512935.9812 | 8573303.8936 | -1 |  | 0.4 | 2800.3649 | 6507.3193 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Jalvi Market | 524 | 209.6 |  | 1 | 9 | 17 | Occupancy : 100 | LIVE - 100% Completed | 100% | 209.6 | 4751834.612 | 712775.1918 | 4039059.4202 | -1 |  | 0.4 | 0 | 1968 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Main Kasur P-4 | 1954 | 781.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 781.6 | 13505012.086 | 13505012.086 |  | #DIV/0! |  |  | 2275.85 | 16688.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250375 | 2024-11-25 | Bahawalpur | Bahawalpur (P3) | Japan Town | 486 | 194.4 |  | N/A | N/A | N/A |  | LIVE - 100% Completed | 100% | 194.4 | 13764761.648 | 2064714.2472 | 11700047.4008 | -0.765 |  | 0.4 | 6708.6247 | 5120.6827 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250375 | Timeline not applicable
INT-23-00438 | 2022-12-29 | Bahawalpur | Bahawalpur | Japan Town | 486 | 243 |  | 20 | 14 | 47 |  | LIVE - 100% Completed | 100% | 243 | 12265711.807 | 1839856.771 | 10425855.0359 | -1 |  | 0.5 | 6708.6247 | 5120.6827 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00438 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Main Kasur P-5 | 1158 | 463.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 463.2 | 8585286.7 | 8585286.7 |  | #DIV/0! |  |  | 1469.7 | 9453.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Jhakkarr | 448 | 179.2 |  |  | Yes |  |  | REMOVE BUDGET (P) | 0% |  | 2988945.0352 | 0 |  |  |  | 0.4 | 521.9526 | 5593.3807 | Hybrid | 100% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | 14.5km backhauling req.and distance from would be 22km/Need to Remove | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | #N/A | Timeline not applicable
I240537 | 2024-02-29 | Abbottabad | Abbottabad Ph2 | Jhangi Qazian | 420 | 168 | 180 | 15 | 3 | 165 |  | LIVE - 100% Completed | 100% | 168 | 5907572.5406 | 886135.8811 | 5021436.6595 | -1 |  | 0.4 | 893.5881 | 7638.847 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240537 | Timeline not applicable
I240537 | 2024-02-29 | Abbottabad | Abbottabad Ph2 | Jhangi Saeedan Extension | 482 | 192.8 | 40 | 10 | 6 | 30 |  | LIVE - 100% Completed | 100% | 192.8 | 4832000.6495 | 724800.0974 | 4107200.5521 | 0 |  | 0.4 | 0 | 8027.2315 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240537 | Timeline not applicable
I250209 | 2024-09-14 | Rawalpindi | Rawalpindi | Jhelum Road Buildings | 1082 | 432.8 | 6 |  |  | 6 |  | LIVE - 100% Completed | 100% | 432.8 | 5650821.262 | 847623.1893 | 4803198.0727 | -0.85 |  | 0.4 | 1150 | 1767.3905 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250209 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Maqbool Town | 126 | 50.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 50.4 | 1624577.2 | 1624577.2 |  | #DIV/0! |  |  | 328.9 | 1703.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Sherwani_Shadab Hsng Scty | 1362 | 544.8 | [5 empty] | LIVE - 100% Completed | 100% | 544.8 | 21309165 | 3196374.75 | 18112790.25 | #DIV/0! |  | 0.4 | 3861.25 | 23299.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Jinnah Road | 6232 | 2492.8 | [5 empty] | LIVE - 100% Completed | 100% | 2492.8 | 30701632.275 | 4605244.8412 | 26096387.4337 | -0.85 |  | 0.4 | 6313.5 | 44773.75 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Saima Villas | 1342 | 536.8 | [5 empty] | LIVE - 100% Completed | 100% | 536.8 | 4694006.4864 | 704100.973 | 3989905.5134 | #DIV/0! |  | 0.4 | 0 |  | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Munir Shaheed Colony | 682 | 272.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 272.8 | 4631297.3 | 4631297.3 |  | #DIV/0! |  |  | 430.1 | 7417.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00437 | 2022-12-29 | Lahore | Lahore Misc Areas | Judicial Colony Ph 2 | 466 | 233 | [5 empty] | LIVE - 100% Completed | 100% | 233 | 6815105.2276 | 1022265.7841 | 5792839.4435 | 0 |  | 0.5 | 1821.2833 | 4245.4667 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00437 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Mustafa Park | 186 | 74.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 74.4 | 1983904.1059 | 1983904.1059 |  | #DIV/0! |  |  | 302.9937 | 1870.4455 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250212 | 2024-09-14 | Swat | Mingora | Kabal P01 | 104 | 41.6 | 30 | 29 | 1 | 0 |  | LIVE - 100% Completed | 100% | 41.6 | 4717806.0151 | 707670.9023 | 4010135.1128 | -1 |  | 0.4 | 1391.5 | 2242.2751 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Kabal P02 | 132 | 52.8 | 44 | 39 | 5 | 0 |  | LIVE - 100% Completed | 100% | 52.8 | 2564178.3447 | 384626.7517 | 2179551.593 | -0.85 |  | 0.4 | 551.1 | 1346.706 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Kabal P03 | 422 | 168.8 | 123 | 113 | 7 | 3 |  | LIVE - 100% Completed | 100% | 168.8 | 8467114.0566 | 1270067.1085 | 7197046.9481 | -1 |  | 0.4 | 2233 | 6684.3683 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Kabal P04 | 150 | 60 | 40 | 39 | 1 | 0 |  | LIVE - 100% Completed | 100% | 60 | 3628236.8741 | 544235.5311 | 3084001.343 | -0.85 |  | 0.4 | 904.2 | 2215.4134 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Kabal P05 | 508 | 203.2 | 149 | 142 | 5 | 2 |  | LIVE - 100% Completed | 100% | 203.2 | 12177400.397 | 1826610.0596 | 10350790.3375 | -1 |  | 0.4 | 2999.7 | 13487.7778 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Kabal P06 | 162 | 64.8 | 43 | 41 | 1 | 1 |  | LIVE - 100% Completed | 100% | 64.8 | 3601741.1456 | 540261.1718 | 3061479.9737 | -0.85 |  | 0.4 | 855.8 | 2576.9385 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Kabal P07 | 180 | 72 | 38 | 36 | 1 | 1 |  | LIVE - 100% Completed | 100% | 72 | 5452457.0074 | 817868.5511 | 4634588.4563 | -1 |  | 0.4 | 1507 | 4103.4518 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Kabal P08 | 462 | 184.8 | 134 | 127 | 5 | 2 |  | LIVE - 100% Completed | 100% | 184.8 | 7995614.8006 | 1199342.2201 | 6796272.5805 | -0.85 |  | 0.4 | 1855.7 | 8206.5414 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Kabal P09 | 1228 | 491.2 | 333 | 325 | 5 | 3 |  | LIVE - 100% Completed | 100% | 491.2 | 17540699.525 | 2631104.9288 | 14909594.5963 | -1 |  | 0.4 | 3096.5 | 28504.2823 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
INT-23-00440 | 2022-12-29 | Sargodha | Sargodha | Kachari Road To Awan Colony Dep | 220 | 110 | 110 | 15 |  | 95 | Live | LIVE - 100% Completed | 100% | 110 | 2484388.7675 | 372658.3151 | 2111730.4524 | -0.8075 |  | 0.5 | 573.85 | 3172.4 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | This Area will be converted to Hybrid Model | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00440 | Timeline not applicable
INT-23-00440 | 2022-12-29 | Sargodha | Sargodha | Kacheela House To Gujjar House | 336 | 168 | 105 | 15 |  | 90 | Live | LIVE - 100% Completed | 100% | 168 | 2660058.875 | 399008.8312 | 2261050.0438 | -1 |  | 0.5 | 660.1 | 452.2 | Arial | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Converted to Hybrid Model | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00440 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Nadeem Park | 354 | 141.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 141.6 | 4720679.3 | 4720679.3 |  | #DIV/0! |  |  | 1160.35 | 4045 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240537 | 2024-02-29 | Abbottabad | Abbottabad Ph2 | Kaghan Colony Extension | 302 | 120.8 | 60 | 16 | 8 | 44 |  | LIVE - 100% Completed | 100% | 120.8 | 3140415.331 | 471062.2997 | 2669353.0314 | -1 |  | 0.4 | 0 | 5323.9063 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240537 | Timeline not applicable
I240557 | 2024-03-08 | Jhelum | Jhelum- Kala Gojran | Kala Gujran_P1 | 680 | 272 | 310 | 15 |  |  |  | LIVE - 100% Completed | 100% | 272 | 9739356.116 | 1460903.4174 | 8278452.6986 | -1 |  | 0.4 | 1464 | 7292.5 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240557 | Timeline not applicable
I240557 | 2024-03-08 | Jhelum | Jhelum- Kala Gojran | Kala Gujran_P2 | 422 | 168.8 | 185 | 20 |  |  |  | LIVE - 100% Completed | 100% | 168.8 | 8945102.75 | 1341765.4125 | 7603337.3375 | -0.85 |  | 0.4 | 1773 | 7176.25 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240557 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | New City | 940 | 376 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 376 | 7226067.8 | 7226067.8 |  |  |  |  | 1135.05 | 10580 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00441 | 2022-12-29 | Faisalabad | Faisalabad Misc Areas | Kaleem Shaheed Colony-2 | 842 | 421 |  | 26 | 19 | 87 | Occupancy : 400 | LIVE - 100% Completed | 100% | 421 | 7640328.3692 | 1146049.2554 | 6494279.1138 | -1 |  | 0.5 | 2113.5581 | 4943.6884 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00441 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Officer Colony | 204 | 81.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 81.6 | 2833942.6 | 2833942.6 |  | #DIV/0! |  |  | 466.9 | 3801.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240538 | 2024-02-29 | Haripur | Haripur Ph2 | Kangra Colony P1 | 978 | 391.2 | 100 | 97 | 2 | 1 |  | LIVE - 100% Completed | 100% | 391.2 | 12535901.446 | 1880385.2169 | 10655516.2291 | -0.85 |  | 0.4 | 1964.6 | 10278.125 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240538 | Timeline not applicable
I240538 | 2024-02-29 | Haripur | Haripur Ph2 | Kangra Colony P2 | 1168 | 467.2 | 145 | 140 | 3 | 2 |  | LIVE - 100% Completed | 100% | 467.2 | 13923254.55 | 2088488.1825 | 11834766.3675 | -1 |  | 0.4 | 2165.9 | 10292.7375 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240538 | Timeline not applicable
I240539 | 2024-02-28 | Swat | Swat Ph2 | Kanju Road P01 | 758 | 303.2 | 363 | 303 | 27 | 33 |  | LIVE - 100% Completed | 100% | 303.2 | 14014522.149 | 2102178.3223 | 11912343.8266 | -0.85 |  | 0.4 | 0 | 28086.5328 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240539 | Timeline not applicable
I240539 | 2024-02-28 | Swat | Swat Ph2 | Kanju Road P02 | 1222 | 488.8 | 559 | 489 | 33 | 37 |  | LIVE - 100% Completed | 100% | 488.8 | 16687554.831 | 2503133.2247 | 14184421.6064 | -1 |  | 0.4 | 0 | 31970.7826 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240539 | Timeline not applicable
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Kantrila | 238 | 95.2 |  |  | Yes |  |  | REMOVE BUDGET (P) | 0% |  | 3129442.0417 | 0 |  |  |  | 0.4 | 917.7 | 3014.55 | Hybrid | 100% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | 3 Months | Timeline not applicable | 2.5km backhauling req./Need to Remove (June 26) | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | #N/A | Timeline not applicable
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Kantrili | 208 | 83.2 |  |  | Yes |  |  | REMOVE BUDGET (P) | 0% |  | 2162403.1667 | 0 |  |  |  | 0.4 | 541.65 | 2082.2 | Hybrid | 100% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | 2.5km backhauling req./Need to Remove | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | #N/A | Timeline not applicable
I240537 | 2024-02-29 | Abbottabad | Abbottabad Ph2 | Kareenpura Extension | 182 | 72.8 | 30 | 9 | 2 | 21 |  | LIVE - 100% Completed | 100% | 72.8 | 1595937.8415 | 239390.6762 | 1356547.1652 | 0 |  | 0.4 | 0 | 2324.7166 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 2 |  |  |  | I240537 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Peeru wala Road | 1370 | 548 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 548 | 8539504.064 | 8539504.064 |  | #DIV/0! |  |  | 928.05 | 14117.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240683 | 2024-05-15 | Okara | Okara | Karmawala | 30 | 12 | 5 | 1 |  | 4 |  | LIVE - 100% Completed | 100% | 12 | 1883183.75 | 282477.5625 | 1600706.1875 | -1 |  | 0.4 | 591.1 | 369 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240683 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Kashmir Colony 1 & 2 | 2096 | 838.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 838.4 | 17191720.405 | 17191720.405 | 0 | -1 |  | 0.4 | 6787.3 | 18760 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Hold Due to Metro Project | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | INT-21-00315 | 2026-06-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Kashmir Rd Jani Shop st | 386 | 154.4 |  | 0 | 0 |  | Not Lived Yet | NOT LIVE - RETAIN BUDGET | 0% | 154.4 | 3718468.3579 | 3718468.3579 | 0 | -1 |  | 0.4 | 462 | 2180.3269 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240678 | Feedback Awaited
UI2560602 | No Initiation Date | Kasur | Kasur | Qadirabad , NoorShah Wali and K | 4836 | 1934.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1934.4 | 32642123.324 | 32642123.324 |  | #DIV/0! |  |  | 5329.1 | 42746.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560602 | No Initiation Date | Kasur | Kasur | Road Kot | 1406 | 562.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 562.4 | 7040133.3604 | 7040133.3604 |  | #DIV/0! |  |  | 1047.5 | 8097.4103 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560602 | No Initiation Date | Kasur | Kasur | Saeedabad | 2064 | 825.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 825.6 | 10500538.268 | 10500538.268 |  | #DIV/0! |  |  | 872.85 | 15951.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Katcheri Road | 444 | 177.6 | 444 | 26 | 24 | 0 | 2 |  | 100% | 177.6 | 7855486.2691 | 1178322.9404 | 6677163.3288 | -0.5 |  | 0.4 | 1480 | 7411.2423 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Saif City | 376 | 150.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 150.4 | 4614691.8786 | 4614691.8786 |  | #DIV/0! |  |  | 1009.873 | 5027.7228 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Kazimabad | 1154 | 461.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 10519705.22 | 10519705.22 |  |  |  |  | 1940.4 | 8481.6555 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Kent Housing Ext. | 184 | 73.6 |  | 12 | 5 | 95 |  | LIVE - 100% Completed | 100% | 73.6 | 14855923.92 | 2228388.588 | 12627535.332 | -1 |  | 0.4 | 5571.92 | 8354.796 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
I240678 | 2024-05-16 | Sialkot | Sialkot | Khadim Ali Rd | 240 | 96 |  | 0 | 0 | 0 | Not Lived Yet | LIVE - 100% Completed | 100% | 96 | 1460913.1758 | 219136.9764 | 1241776.1995 | -1 |  | 0.4 | 0 | 2411.3133 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Khakwani Colony | 708 | 283.2 |  |  | 1 | 7 |  | LIVE - 100% Completed | 100% | 283.2 | 5967951.0897 | 895192.6635 |  |  |  |  | 1382.0597 | 4505.2706 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Khan Village II | 454 | 227 | 12 | 1 | 1 | 10 |  | LIVE - 100% Completed | 100% | 227 | 5602190.6346 | 840328.5952 | 4761862.0394 | -0.85 |  | 0.5 | 2339.3721 | 5214.6516 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
UI2560602 | No Initiation Date | Kasur | Kasur | Saleem Town Ph-1 | 1420 | 568 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 568 | 10362321.2226 | 10362321.2226 |  | #DIV/0! |  |  | 2041.7713 | 11047.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560602 | No Initiation Date | Kasur | Kasur | Tariq Colony | 1330 | 532 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 532 | 8417546.636 | 8417546.636 |  | #DIV/0! |  |  | 1284.55 | 10775 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250205 | 2024-09-12 | Jhelum | Jhelum Ph2 | Kharala | 640 | 256 | 102 | 7 |  |  |  | LIVE - 100% Completed | 100% | 256 | 14067650.8782 | 2110147.6317 | 11957503.2465 | -1 |  | 0.4 | 3660.8137 | 11248.1633 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250205 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Khayaban e Kubra | 170 | 85 | 1 | 0 | 0 | 1 |  | LIVE - 100% Completed | 100% | 85 | 5614652.9278 | 842197.9392 | 4772454.9886 | -1 |  | 0.5 | 3057.4649 | 2737.9082 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Aerial plan in progress | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
UI2560602 | No Initiation Date | Feeders/Transportations | Kasur | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 10200000 | 10200000 |  | #DIV/0! |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Ajnianwala | 1998 | 799.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 799.2 | 11132334.1304 | 11132334.1304 |  | -0.5 |  |  | 2546.0939 | 29280.0795 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Bahrrian Wala | 698 | 279.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 279.2 | 1943361.1832 | 1943361.1832 |  | -1 |  |  | 327.957 | 3771.5056 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Khayaban-e-Patni CHS | 212 | 84.8 | [5 empty] | SWAPPED | 0% | 84.8 | 4887798.4991 | 0 | 4887798.4991 | -1 |  | 0.4 | 1079.9494 | 2731.3402 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Hansa | Swap Cases | SWAPPED |  |  | Hansa | 9247425.9799 | 0 | I240705 | Timeline not applicable
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Chalk no.12 | 1355 | 542 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 542 | 4600102.8753 | 4600102.8753 |  | -0.85 |  |  | 918.9485 | 10567.9083 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Khokhar k_BOQ | 1920 | 768 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 768 | 18335788.746 | 4308910.3553 | 14026878.3907 | -1 |  | 0.4 | 1263.5 | 20308.75 | Hybrid | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46082 | Mar-2026 | Aerial Hanging in process | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240700 | 2026-03-01
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Khursheed Town | 300 | 120 | 600 | 400 |  |  |  | REMOVE BUDGET (P) | 0% | 120 | 3913624.9611 | 0 | 3913624.9611 | -1 |  | 0.4 | 531.3 | 2268.1377 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I240702 | Timeline not applicable
I240539 | 2024-02-28 | Swat | Swat Ph2 | Khwaja abad | 860 | 344 |  |  |  |  | NOC and Civil work pending | LIVE - 80% Completed | 80% | 275.2 | 11648788.2039 | 3727612.2252 | 0 | -0.5 |  | 0.4 | 1682.45 | 13027.3442 | Hybrid |  | LIVE | Arial | 80% | 0.8 | 2026-03-01 | 92 | 93 | 45 | In Progress | 46174 | Jun-2026 |  | Live - As per Plan | LIVE - 80% Completed | 2 | Add 9 count |  |  |  | I240539 | 2026-06-01
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Khy-e-Manzoor | 432 | 172.8 |  | 0 | 0 | 0 | Yet not active | SWAPPED | 0% | 172.8 | 5761950.425 | 0 | 5761950.425 | -0.5 |  | 0.4 | 1139.65 | 4442.475 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Timeline not applicable | swap with Pine Garden - Uncertain | Swap Cases | SWAPPED | budget will be given by Pine |  | Pine Garden | 0 | ?! | I240682 | Timeline not applicable
I240681 | 2024-05-16 | Quetta | Quetta | Killi Payen | 400 | 160 | 55 | 10 | 15 | 40 |  | LIVE - 100% Completed | 100% | 160 | 7733000 | 1159950 | 6573050 | -1 |  | 0.4 | 4000 | 4600 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Partial Active | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240681 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Kings_ASF_ Tower_P01 | 2016 | 806.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 806.4 | 5803344.508 | 5803344.508 | 0 | -0.765 |  | 0.4 | 0 | 696 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 0 | 1 | -47 | Yet to Start | 46174 | Mar-2026 | Internal Permission issue (Only 6-7 Office Links Live) /Building Construction work almost ended | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240705 | 2026-03-01
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Kings_ASF_ Tower_P02 | 2016 | 806.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 806.4 | 5803344.508 | 5803344.508 | 0 | -1 |  | 0.4 | 0 | 696 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Internal Permission issue /Building Construction work almost ended | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240705 | 2026-06-01
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Kokan CHS | 346 | 138.4 | [5 empty] | SWAPPED | 0% | 138.4 | 11269033.0773 | 0 | 11269033.0773 | -0.765 |  | 0.4 | 2155.1646 | 5318.6079 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Hansa | Swap Cases | SWAPPED |  |  | Hansa | 9247425.9799 | 0 | I240705 | Timeline not applicable
UI2560605 | No Initiation Date | Feeders/Transportations | Muridky, Kalasha Kako, Shadra | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 |  | -1 |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Feroz Wattowan-i | 1428 | 571.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 571.2 | 14716494.9292 | 14716494.9292 |  | -0.85 |  |  | 3596.4676 | 41359.3773 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Ferozewala | 36000 | 14400 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 14400 | 71464607.368 | 71464607.368 |  | -1 |  |  | 12875.7424 | 148071.0374 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Kotli Allahyar | 266 | 106.4 |  |  | Yes |  |  | LIVE - 100% Completed | 100% |  | 2708058.2917 | 406208.7438 |  |  |  | 0.4 | 677.35 | 2775.3 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Ghang | 1457 | 582.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 582.8 | 6900631.9435 | 6900631.9435 |  | -0.68 |  |  | 1511.816 | 17385.8838 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Labour Colony | 458 | 183.2 | 458 | 0 | 0 | 0 | 0 | On Hold due to Low Potential | 0% | 183.2 | 3640923.6491 | 0 | 3640923.6491 | -1 |  | 0.4 | 0 | 6608.7884 | Arial |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I240540 | Timeline not applicable
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Jandiala Sher Khan | 1478 | 591.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 591.2 | 9252455.1853 | 9252455.1853 |  | -1 |  |  | 2130.4594 | 24500.2827 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Jatri Kohna | 1428 | 571.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 571.2 | 5486969.5895 | 5486969.5895 |  | -0.85 |  |  | 1142.2718 | 13136.1258 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240539 | 2024-02-28 | Swat | Swat Ph2 | Landikas_Rang Mohalla | 3236 | 1294.4 | 299 | 223 | 31 | 45 |  | LIVE - 100% Completed | 100% | 1294.4 | 29993500.7323 | 4499025.1099 | 25494475.6225 | -1 |  | 0.4 | 2335.2244 | 33607.9236 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240539 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Lasani Colony | 816 | 408 | 100 | 13 | 15 | 72 |  | LIVE - 100% Completed | 100% | 408 | 7581424.3777 | 1137213.6567 | 6444210.7211 | -0.85 |  | 0.5 | 1603.1 | 6630.9737 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Latifabad No 04 | 888 | 355.2 | 1041 | 800 |  |  |  | NOT LIVE - RETAIN BUDGET | 90% | 355.2 | 12674410.1971 | 2978486.3963 | 9695923.8008 | 0 |  | 0.4 | 2527.47 | 8436.3636 | Hybrid | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 31 | 32 | -16 | In Progress | Next Month | Apr-2026 | Civil Work in progress // As-built expected next month (before Ramadan). | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240702 | 2026-04-01
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Latifabad No 09 | 1316 | 526.4 | 2172 | 1800 |  |  |  | SWAPPED | 0% | 526.4 | 15091680.8626 | 0 | 15091680.8626 | -1 |  | 0.4 | 2605.9 | 11969.4064 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Sales team/ BuH don’t want to start this area now / buget utilized in Latifabad # 2 after Management approval (swapped) | Swap Cases | SWAPPED |  |  | Latifabad #2 | 7901516.3743 | 858 | I240702 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Latifabad No 10 | 1912 | 764.8 | 850 | 700 |  |  |  | LIVE - 100% Completed | 100% | 764.8 | 22250724.5064 | 3337608.676 | 18913115.8305 | 0 |  | 0.4 | 4169.44 | 17307.0563 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Due to Permission issue area live in aerial after BuH consensus | Live - Permission Awaited | LIVE - 100% Completed | [5 empty] | I240702 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Township_A2_P01 | 1338 | 535.2 | [5 empty] | LIVE - 100% Completed | 100% | 535.2 | 14974851.242 | 2246227.6863 | 12728623.5557 | #DIV/0! |  | 0.4 | 2766.9 | 12077.8 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Layllpur Garden | 482 | 192.8 |  | 0 | 2 | 12 | Occupancy : 150 | LIVE - 100% Completed | 100% | 192.8 | 4761079.475 | 714161.9212 | 4046917.5537 | -1 |  | 0.4 | 813.05 | 3666.875 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Township_A2_P02 | 2004 | 801.6 | [5 empty] | LIVE - 100% Completed | 100% | 801.6 | 19709183.0862 | 2956377.4629 | 16752805.6232 | #DIV/0! |  | 0.4 | 3479.2639 | 14998.8157 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Township_B1_P01 | 766 | 306.4 | [5 empty] | LIVE - 100% Completed | 100% | 306.4 | 11366702 | 1705005.3 | 9661696.7 | #DIV/0! |  | 0.4 | 2339.1 | 7774.2 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Township_B1_P02 | 928 | 371.2 | [5 empty] | LIVE - 100% Completed | 100% | 371.2 | 12734060.118 | 1910109.0177 | 10823951.1003 | #DIV/0! |  | 0.4 | 2610.5 | 9744 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Township_B1_P03 | 1378 | 551.2 | [5 empty] | LIVE - 100% Completed | 100% | 551.2 | 14102580.726 | 2115387.1089 | 11987193.6171 | #DIV/0! |  | 0.4 | 2654.2 | 10869.6 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Township_B1_P04 | 1354 | 541.6 | [5 empty] | LIVE - 100% Completed | 100% | 541.6 | 15753493 | 2363023.95 | 13390469.05 | #DIV/0! |  | 0.4 | 3069.35 | 9179.8 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Township_B2_P01 | 434 | 173.6 | [5 empty] | LIVE - 100% Completed | 100% | 173.6 | 6438723 | 965808.45 | 5472914.55 | #DIV/0! |  | 0.4 | 1308.7 | 5192.6 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Township_B2_P02 | 620 | 248 | [5 empty] | LIVE - 100% Completed | 100% | 248 | 9041721.746 | 1356258.2619 | 7685463.4841 | #DIV/0! |  | 0.4 | 1879.1 | 7247.8 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Township_C1_BL03 | 558 | 223.2 | [5 empty] | LIVE - 100% Completed | 100% | 223.2 | 7416454.496 | 1112468.1744 | 6303986.3216 | #DIV/0! |  | 0.4 | 1576.65 | 5082 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Lahore | Lahore Ph5 | Township_C2_BL03 | 558 | 223.2 | [5 empty] | LIVE - 100% Completed | 100% | 223.2 | 7416454.496 | 1112468.1744 | 6303986.3216 | #DIV/0! |  | 0.4 | 1576.65 | 5082 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240703 | Timeline not applicable
I240703 | 2024-05-15 | Feeders/Transportations | Lahore Ph5 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 10060000 | 5030000 | 5030000 | #DIV/0! |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240703 | Timeline not applicable
I240679 | 2024-05-16 | Sargodha | Sargodha | Liaquat Colony | 450 | 180 | 56 | 10 |  |  | Live | LIVE - 100% Completed | 100% | 180 | 1308019 | 196202.85 | 1111816.15 | -1 |  | 0.4 | 0 | 2052 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240679 | Timeline not applicable
I260294 | No Initiation Date | Karachi | Darussalam_LucknowSociety_DadabhoyTown | Lucknow Society | 1322 | 528.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 16195392.3801 | 16195392.3801 |  |  |  |  | 3096 | 11216.0314 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | M.Ali Shaheed Society_Maaz Town | 596 | 238.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 6445888.8368 | 6445888.8368 |  |  |  |  | 1278 | 4317.8084 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | M3-Ind.Estate_P1 | 322 | 128.8 |  | 0 | 0 | 0 | Yet not active | REMOVE BUDGET (P) | 0% | 128.8 | 44731041.7 | 0 | 44731041.7 | -0.5 |  | 0.4 | 17498.4 | 40076.25 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I240682 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | M3-Ind.Estate_P2 | 298 | 119.2 |  | 0 | 0 | 0 | Yet not active | REMOVE BUDGET (P) | 0% | 119.2 | 51690420.75 | 0 | 51690420.75 | -1 |  | 0.4 | 19987 | 43837.5 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  | 2 |  | 0 |  | I240682 | Timeline not applicable
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Kala Shah Kaku | 11500 | 4600 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 4600 | 60442056.6902 | 60442056.6902 |  | -1 |  |  | 14046.0876 | 161530.0069 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Madina Town | 2346 | 938.4 |  | 1268 | 1333 | 3087 | Occupancy : 7000 | LIVE - 100% Completed | 100% | 938.4 | 22215389.541 | 3332308.4312 | 18883081.1099 | -0.5 |  | 0.4 | 2419.945 | 14901.9309 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 2 |  |  |  | I240682 | Timeline not applicable
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Kaloke | 2317 | 926.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 926.8 | 5674768.9695 | 5674768.9695 |  | -0.5 |  |  | 1043.7192 | 12002.7708 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | KOT Abdul Malik | 14800 | 5920 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 5920 | 83086096.9739 | 83086096.9739 |  | -1 |  |  | 14874.2002 | 171053.3018 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Madras CHS | 734 | 293.6 | [5 empty] | LIVE - 100% Completed | 100% | 293.6 | 22361414.9857 | 3354212.2479 | 19007202.7378 | -1 |  | 0.4 | 10803.1713 | 9525.0736 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Live - Completed | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Kot Sondha | 2463 | 985.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 985.2 | 6081189.8417 | 6081189.8417 |  | -0.085 |  |  | 1127.951 | 12971.4365 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Kurkle Androon | 573 | 229.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 229.2 | 4243517.9948 | 4243517.9948 |  | -1 |  |  | 960.1851 | 11042.129 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Lahore Jaranwala Road | 16400 | 6560 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 6560 | 36464951.2744 | 36464951.2744 |  | -0.85 |  |  | 6866.1381 | 78960.5879 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240539 | 2024-02-28 | Swat | Swat Ph2 | Main Bazar Mingora | 3102 | 1240.8 | 865 | 713 | 67 | 85 |  | LIVE - 100% Completed | 100% | 1240.8 | 42224419.9662 | 6333662.9949 | 35890756.9712 | -0.5 |  | 0.4 | 3197.0966 | 30029.4814 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240539 | Timeline not applicable
I260296 | No Initiation Date | Sukkur | Sukkur | Main City P1 | 2372 | 948.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 17722825.1654 | 17722825.1654 |  |  |  |  | 2280.45 | 19662.7974 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 months | Jun-2026 | Not started yet | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I260296 | No Initiation Date | Sukkur | Sukkur | Main City P2 | 2494 | 997.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 20560985.5305 | 20560985.5305 |  |  |  |  | 2596.7 | 19417.6357 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 months | Jun-2026 | Not started yet | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I240435 | 2024-01-18 | Feeders/Transportations | Top City Islamabad | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 535000 | 267500 | 267500 | -1 |  |  | 0 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240435 | Timeline not applicable
I240437 | 2024-01-18 | Feeders/Transportations | Askari Lahore | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1100000 | 550000 | 550000 | 0 |  |  | 0 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET |  | 2 |  |  |  | I240437 | Timeline not applicable
I240440 | 2024-01-19 | Feeders/Transportations | Al Jalil & Al khalil LHE | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 550000 | 275000 | 275000 | -0.85 |  |  | 0 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240440 | Timeline not applicable
I240442 | 2024-01-19 | Feeders/Transportations | Chitral Ph1 | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 535000 | 267500 | 267500 | -1 |  |  | 0 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET |  | 1 |  |  |  | I240442 | Timeline not applicable
I240538 | 2024-02-29 | Feeders/Transportations | Haripur Ph2 | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 550000 | 275000 | 275000 | -0.5 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240538 | Timeline not applicable
I240539 | 2024-02-28 | Feeders/Transportations | Swat Ph2 | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 550000 | 275000 | 275000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240539 | Timeline not applicable
I240540 | 2024-02-28 | Feeders/Transportations | Mardan Ph2 | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 535000 | 267500 | 267500 | -0.85 |  |  | 0 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240540 | Timeline not applicable
I240678 | 2024-05-16 | Feeders/Transportations | Sialkot | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 650000 | 325000 | 325000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240678 | Timeline not applicable
I250114 | 2024-08-08 | Feeders/Transportations | Bahadurabad (KTTC) | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 650000 | 325000 | 325000 | -0.85 |  |  | 0 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250114 | Timeline not applicable
I250205 | 2024-09-12 | Feeders/Transportations | Jhelum Ph2 | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 550000 | 275000 | 275000 | -0.85 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250205 | Timeline not applicable
I250209 | 2024-09-14 | Feeders/Transportations | Rawalpindi | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 650000 | 325000 | 325000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250209 | Timeline not applicable
I250210 | 2024-09-14 | Feeders/Transportations | Sargodha | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 650000 | 325000 | 325000 | -0.85 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250210 | Timeline not applicable
I250212 | 2024-09-14 | Feeders/Transportations | Mingora | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 650000 | 325000 | 325000 | -0.85 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250212 | Timeline not applicable
I250378 | 2024-11-25 | Feeders/Transportations | Sahiwal (P2) | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 650000 | 325000 | 325000 | #DIV/0! |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250378 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Feeders/Transportations | Gujranwala Ph2 | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1070000 | 535000 | 535000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-21-00315 | Timeline not applicable
INT-23-00435 | 2022-12-29 | Feeders/Transportations | Karachi Misc Areas | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 550000 | 275000 | 275000 | -1 |  |  |  | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00435 | Timeline not applicable
INT-23-00436 | 2022-12-29 | Feeders/Transportations | Hyderabad Misc Areas | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 535000 | 267500 | 267500 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00436 | Timeline not applicable
INT-23-00437 | 2022-12-29 | Feeders/Transportations | Lahore Misc Areas | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1100000 | 550000 | 550000 | -1 |  |  | 0 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00437 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Feeders/Transportations | Multan Misc. Areas | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 2200000 | 1100000 | 1100000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00439 | Timeline not applicable
INT-23-00441 | 2022-12-29 | Feeders/Transportations | Faisalabad Misc Areas | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 550000 | 275000 | 275000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00441 | Timeline not applicable
INT-23-00442 | 2022-12-29 | Feeders/Transportations | Sahiwal Misc Areas | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 550000 | 275000 | 275000 | -0.5 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00442 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Feeders/Transportations | Islamabad Misc Areas | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 2200000 | 1100000 | 1100000 | #DIV/0! |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00444 | Timeline not applicable
INT-23-00445 | 2022-12-29 | Feeders/Transportations | Rawalpindi Misc Areas | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 535000 | 267500 | 267500 | #DIV/0! |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00445 | Timeline not applicable
INT-23-00446 | 2022-12-29 | Feeders/Transportations | Wah Cant Misc Ares | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 550000 | 275000 | 275000 | #DIV/0! |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00446 | Timeline not applicable
INT-23-00447 | 2022-12-29 | Feeders/Transportations | Peshawar Misc Areas | Main CO ODF Rack | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 550000 | 275000 | 275000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00447 | Timeline not applicable
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Mirza Virkan | 1264 | 505.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 505.6 | 7245702.433 | 7245702.433 |  | -1 |  |  | 1635.5075 | 18808.3359 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Muradey Kalan | 460 | 184 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 184 | 2908640.0667 | 2908640.0667 |  | -0.425 |  |  | 623.9122 | 7174.9907 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Muridke | 32100 | 12840 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 12840 | 76529365.9052 | 76529365.9052 |  | -1 |  |  | 19503.388 | 224288.9626 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Nazri Lubana | 497 | 198.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 198.8 | 1868516.6762 | 1868516.6762 |  | -0.85 |  |  | 340.6926 | 3917.9649 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Nokhar | 1122 | 448.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 448.8 | 4145070.9414 | 4145070.9414 |  | -1 |  |  | 837.817 | 9634.8951 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240538 | 2024-02-29 | Haripur | Haripur Ph2 | Main KKH & Lari Adda | 782 | 312.8 | 226 | 169 | 37 | 20 |  | LIVE - 100% Completed | 100% | 312.8 | 17930917.315 | 2689637.5973 | 15241279.7177 | -1 |  | 0.4 | 2347.15 | 8520.577 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240538 | Timeline not applicable
I240539 | 2024-02-28 | Swat | Swat Ph2 | Makan Bagh | 522 | 208.8 | 156 | 128 | 11 | 17 |  | LIVE - 100% Completed | 100% | 208.8 | 6734786.6544 | 1010217.9982 | 5724568.6562 | -0.85 |  | 0.4 | 527.85 | 3691.9684 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240539 | Timeline not applicable
I250202 | 2024-09-13 | Haripur | Haripur Hazara | Makhan_Malikyar_Kalas | 350 | 140 | 88 | 79 | 6 | 3 |  | LIVE - 100% Completed | 100% | 140 | 4538550.8632 | 680782.6295 | 3857768.2337 | -1 |  | 0.4 | 0 | 10671.7919 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250202 | Timeline not applicable
I250205 | 2024-09-12 | Jhelum | Jhelum Ph2 | Makhdoomabad | 726 | 290.4 | 135 | 12 |  |  |  | LIVE - 100% Completed | 100% | 290.4 | 6711032.738 | 1006654.9107 | 5704377.8273 | -1 |  | 0.4 | 1399.55 | 6207.45 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250205 | Timeline not applicable
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Rakh Hiran Minara | 4466 | 1786.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1786.4 | 6313771.3333 | 6313771.3333 |  | 0 |  |  | 863.7635 | 9933.28 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250207 | 2024-09-12 | Abbottabad | Abbottabad | Malikpura | 714 | 285.6 | 100 | 12 | 1 | 88 |  | LIVE - 100% Completed | 100% | 285.6 | 9380343.8632 | 1407051.5795 | 7973292.2837 | -0.765 |  | 0.4 | 2059.4 | 10671.7919 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250207 | Timeline not applicable
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Akari-1 | 320 | 160 | [5 empty] | LIVE - 100% Completed | 100% | 160 | 3896358.2746 | 584453.7412 | 3311904.5334 | -1 |  | 0.5 | 0 | 1243.434 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Attachment Model | Live - As per Plan | LIVE - 100% Completed |  | 2 |  |  |  | INT-23-00764 | Timeline not applicable
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Safdarabad | 13000 | 5200 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 5200 | 20085212.4944 | 20085212.4944 |  | -1 |  |  | 3083.6302 | 35461.7468 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00437 | 2022-12-29 | Lahore | Lahore Misc Areas | Mansoora | 140 | 70 | [5 empty] | LIVE - 100% Completed | 100% | 70 | 2544395.145 | 381659.2718 | 2162735.8733 | -0.85 |  | 0.5 | 534.4837 | 2547.6594 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00437 | Timeline not applicable
UI2560605 | No Initiation Date | Lahore | Muridky, Kalasha Kako, Shadra | Shahdara Town | 64000 | 25600 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 25600 | 88337113.7868 | 88337113.7868 |  | -0.85 |  |  | 12674.4218 | 145755.851 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 0% | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Maqam Mandi | 120 | 48 | 120 | 113 | 100 | 10 | 3 |  | 100% | 48 | 2781121.6606 | 417168.2491 | 2363953.4115 | -1 |  | 0.4 | 478.4 | 2330.2066 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
UI2560605 | No Initiation Date | Feeders/Transportations | Muridky, Kalasha Kako, Shadra | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 9000000 | 9000000 |  | -1 |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I240678 | 2024-05-16 | Sialkot | Sialkot | Marala Road & Muradpur | 604 | 241.6 |  | 13 | 21 | 235 |  | LIVE - 100% Completed | 100% | 241.6 | 14022844.71 | 2103426.7065 | 11919418.0035 | -1 |  | 0.4 | 4522 | 13266.05 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Marhaba Canal View | 1078 | 431.2 |  |  |  |  | On hold | REMOVE BUDGET (P) | 0% | 431.2 | 9166557.646 | 0 | 9166557.646 | 0 |  | 0.4 | 1524.9 | 8395.5 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I240704 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Marvi Town & Marvi Garden | 592 | 236.8 | 610 | 570 | 60 | 9 | 1 | LIVE - 100% Completed | 100% | 236.8 | 8638863.8526 | 1295829.5779 | 7343034.2748 | -1 |  | 0.4 | 1749.9491 | 5754.9874 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240702 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Master Citi Pk-1 | 1678 | 671.2 | [5 empty] | LIVE - 100% Completed | 100% | 671.2 | 46188722.4147 | 6928308.3622 | 39260414.0525 | -0.5 |  | 0.4 | 29953.3096 | 26902.5231 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Master Citi Pk-2 | 3232 | 1292.8 | [5 empty] | LIVE - 100% Completed | 100% | 1292.8 | 58508740.9684 | 8776311.1453 | 49732429.8231 | -1 |  | 0.4 | 40494.0494 | 39172.0897 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Master Citi Pk-3 | 2608 | 1043.2 | [5 empty] | LIVE - 100% Completed | 100% | 1043.2 | 35372528.0849 | 5305879.2127 | 30066648.8721 | -0.5 |  | 0.4 | 22128.2514 | 20407.3 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | MB Shora Colony | 902 | 360.8 | 1000 | 548 | 7 | 0 | 0 | LIVE - 80% Completed | 80% | 288.64 | 10416857.7484 | 3333394.4795 | 7083463.2689 | -1 |  | 0.4 | 1525.59 | 10504.7738 | Hybrid |  | LIVE | Hybrid | 80% | 0.8 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | In Progress | No more work req | Feedback Awaited | Due to permission issue some part Live on Aerial | Live - Permission Awaited | LIVE - 80% Completed | 1 | Add 9 count |  |  |  | I240702 | Feedback Awaited
INT-23-00435 | 2022-12-29 | Karachi | Karachi Misc Areas | MBCHS | 720 | 360 | [5 empty] | LIVE - 100% Completed | 100% | 360 | 14316329.2575 | 2147449.3886 | 12168879.8689 | -0.68 |  | 0.5 | 4966.9038 | 9007.5136 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00435 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Meadows_I | 144 | 57.6 |  | 0 | 0 | 8 | Occupancy : 50 | LIVE - 100% Completed | 100% | 57.6 | 4930686.9796 | 739603.0469 | 4191083.9327 | -1 |  | 0.4 | 2205.0426 | 1594.1506 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 2 |  |  |  | I240682 | Timeline not applicable
I250375 | 2024-11-25 | Bahawalpur | Bahawalpur (P3) | Medical Colony | 432 | 172.8 |  | 52 | 31 | 144 |  | LIVE - 100% Completed | 100% | 172.8 | 4969725.2362 | 745458.7854 | 4224266.4508 | -1 |  | 0.4 | 0 | 4973.4024 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250375 | Timeline not applicable
UI2560603 | No Initiation Date | Lalamusa | Lalamusa | Darbari, Qureshi Muhallah,Shad | 1678 | 755.1 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 755.1 | 13877663.1647 | 13877663.1647 |  |  |  | 0.45 | 2555.592 | 16533 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560603 | No Initiation Date | Lalamusa | Lalamusa | Dhamah,Lalazar & Railway Colony | 532 | 239.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 239.4 | 8557429.0511 | 8557429.0511 |  |  |  | 0.45 | 2160.2819 | 8658 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250209 | 2024-09-14 | Rawalpindi | Rawalpindi | Metro Homes | 528 | 211.2 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 211.2 | 6570635.56 | 6570635.56 | 0 | -0.85 |  | 0.4 | 1237.4 | 5636.179 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retian | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250209 | Feedback Awaited
I250210 | 2024-09-14 | Sargodha | Sargodha | Milatabad | 766 | 306.4 | 34 | 10 | 4 | 20 | Live | NOT LIVE - RETAIN BUDGET | 70% | 306.4 | 5476771.334 | 2218092.3903 | 3258678.9437 | -1 |  | 0.4 | 777.4 | 4453.75 | Hybrid | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 61 | 62 | 14 | In Progress | 2 Months | May-2026 | This Colony linked with the DPLC backup connectivity; once completed, the area will go live. | Swap Cases | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250210 | 2026-05-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Millat Garden | 610 | 244 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 5136341.9697 | 5136341.9697 |  |  |  |  | 816.2 | 4197.525 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560603 | No Initiation Date | Lalamusa | Lalamusa | Eid Gah, Rehmat Abbas,Kaira Muh | 2802 | 1260.9 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1260.9 | 28090440.4339 | 28090440.4339 |  |  |  | 0.45 | 5621.3823 | 38308.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00437 | 2022-12-29 | Lahore | Lahore Misc Areas | Misc. Areas | 400 | 200 | [5 empty] | LIVE - 100% Completed | 100% | 200 | 8971993.39 | 1345799.0085 | 7626194.3815 | -1 |  | 0.5 | 0 | 50000 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00437 | Timeline not applicable
I250377 | 2024-11-25 | Peshawar | Peshawar (P2) | Misc.Areas Warsak | 1584 | 633.6 | 6903 | 4403 | 1281 | 1219 | All warsak Road | LIVE - 100% Completed | 100% | 633.6 | 20084790.2544 | 3012718.5382 | 17072071.7162 | -1 |  | 0.4 | 4532.2 | 4532.2 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250377 | Timeline not applicable
UI2560603 | No Initiation Date | Feeders/Transportations | Lalamusa | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 50911802.4 | 50911802.4 |  |  |  |  | 16597.2 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
UI2560603 | No Initiation Date | Lalamusa | Lalamusa | Gunjra Road,Bagh e Syedan & Bud | 1600 | 720 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 720 | 17132082.0519 | 17132082.0519 |  |  |  | 0.45 | 3906.2173 | 19098 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Model Colony | 1302 | 520.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 12104452.8181 | 12104452.8181 |  |  |  |  | 2178 | 9493.5968 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00435 | 2022-12-29 | Karachi | Karachi Misc Areas | Model Colony | 1302 | 651 | [5 empty] | LIVE - 100% Completed | 100% | 651 | 12456480.7295 | 1868472.1094 | 10588008.6201 | -1 |  | 0.5 | 2277 | 11012.5723 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | partial live | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00435 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Model Town | 556 | 222.4 |  |  |  |  | NOT ENERGISED AS YET | NOT LIVE - RETAIN BUDGET | 0% | 222.4 | 6178829 | 6178829 | 0 | -1 |  | 0.4 | 1090.2 | 6474.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46113 | Apr-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-04-01
UI2560603 | No Initiation Date | Lalamusa | Lalamusa | Karimpura, Hajipura, SabriMuhal | 1876 | 844.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 844.2 | 23853361.6106 | 23853361.6106 |  |  |  | 0.45 | 6175.0772 | 24726 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240538 | 2024-02-29 | Haripur | Haripur Ph2 | Model Town | 398 | 159.2 | 75 | 74 | 0 | 1 |  | LIVE - 100% Completed | 100% | 159.2 | 5188072.176 | 778210.8264 | 4409861.3496 | -0.5 |  | 0.4 | 1021.2 | 5137.698 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240538 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Model Town C Extension | 750 | 300 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 85% | 300 | 7408754.7269 | 2055929.4367 |  |  |  |  | 1569.0232 | 5999.7503 | Hybrid | 85% | Not Live |  | 85% | 0.85 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 month | Apr-2026 | Cable pulling pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
UI2560603 | No Initiation Date | Lalamusa | Lalamusa | Mehar Muhallah,Weraowala,Sadiqa | 1454 | 654.3 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 654.3 | 18338633.8708 | 18338633.8708 |  |  |  | 0.45 | 5014.6683 | 14805 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560603 | No Initiation Date | Lalamusa | Lalamusa | Syda Gol,Faisalpur,Jogi&Qasbah& | 3950 | 1777.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1777.5 | 25689959.4923 | 25689959.4923 |  |  |  | 0.45 | 4093.9035 | 38043 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560603 | No Initiation Date | Lalamusa | Lalamusa | Thirkian,Asghar Town,Ahmad Town | 1096 | 493.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 493.2 | 16249969.6436 | 16249969.6436 |  |  |  | 0.45 | 4037.113 | 17886 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250213 | 2024-09-14 | Mardan | Mardan | Mohabatabad P1 | 340 | 136 | 340 | 73 | 52 | 14 | 7 | Run from orchard FDT.. | 0% | 136 | 4566394 | 0 | 4566394 | -0.6375 |  | 0.4 | 845.25 | 3726.45 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | has been swapped with new muhabbatabad | Swap Cases | SWAPPED | budget will be provided by ODN for new area |  | new muhabbatabad | 0 | ? | I250213 | Timeline not applicable
I250213 | 2024-09-14 | Mardan | Mardan | Mohabatabad P2 | 456 | 182.4 | 456 | [5 empty] | 0% | 182.4 | 5853007.9 | 0 | 5853007.9 | -1 |  | 0.4 | 1220.15 | 4251.57 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | has been swapped with new muhabbatabad | Swap Cases | SWAPPED | budget will be provided by ODN for new area |  | new muhabbatabad | 0 | ? | I250213 | Timeline not applicable
UI2560603 | No Initiation Date | Feeders/Transportations | Lalamusa | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 4740000 | 4740000 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Mohallah Aam Khass and Noor Sha | 830 | 332 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 85% | 332 | 5788452.0143 | 1606295.434 |  |  |  |  | 976.3034 | 5769.6332 | Hybrid | 85% | Not Live |  | 85% | 0.85 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 month | Apr-2026 | Cable pulling pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Mohsin Town & Rasheed Avenue | 428 | 214 | 9 | 0 | 4 | 5 |  | LIVE - 100% Completed | 100% | 214 | 6301716.4687 | 945257.4703 | 5356458.9984 | -0.85 |  | 0.5 | 2570.7 | 4016.7272 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I250378 | 2024-11-25 | Sahiwal | Sahiwal (P2) | Montgomery Society | 188 | 75.2 | 41 | 10 | 4 |  |  | LIVE - 100% Completed | 100% | 75.2 | 1699838.75 | 254975.8125 | 1444862.9375 | #DIV/0! |  | 0.4 | 788.9 | 1961.25 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250378 | Timeline not applicable
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Muftian | 130 | 52 |  |  | Yes |  |  | REMOVE BUDGET (P) | 0% |  | 1700283.8209 | 0 |  |  |  | 0.4 | 418.6 | 1633.5227 | Hybrid | 100% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | 14.5km backhauling req.and distance from would be 22km/Need to Remove | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | #N/A | Timeline not applicable
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Al-Rehman, Eiffel, Sultan Town | 1566 | 704.7 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 704.7 | 18133210.564 | 18133210.564 |  |  |  |  | 5270.54 | 12145 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250378 | 2024-11-25 | Sahiwal | Sahiwal (P2) | Muhall Noor & Park Salamat Park | 916 | 366.4 | 67 | 0 | 0 |  | 46055 | NOT LIVE - RETAIN BUDGET | 70% | 366.4 | 8506579.8369 | 3445164.8339 | 5061415.003 | #DIV/0! |  | 0.4 | 1221.9225 | 8714.5521 | Hybrid | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46054 | Mar-2026 | cable pulling remains | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250378 | 2026-03-01
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Arshad Town and Model Town | 2134 | 960.3 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 960.3 | 12010555.312 | 12010555.312 |  | -0.85 |  |  | 1765.25 | 13607.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Mujahid Town_Ali Town | 334 | 133.6 |  | 1 | 0 | 1 | Occupancy : 100 | LIVE - 100% Completed | 100% | 133.6 | 5274317.9532 | 791147.693 | 4483170.2602 | -0.765 |  | 0.4 | 858.13 | 3489.4565 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Multan Golf City | 370 | 148 | 0 | 0 | 0 | 0 | will be live on 1st April | NOT LIVE - RETAIN BUDGET | 100% | 148 | 15447935.7261 | 2317190.3589 | 13130745.3672 | -1 |  | 0.4 | 7308.134 | 6228.776 | Buried | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 0 | 1 | -47 | Completed | 46065 | Mar-2026 | Tawakkal Town also included in its budget later/ As built of MGC completed | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240704 | 2026-03-01
I250327 | 2024-11-05 | Islamabad | Islamabad | Mumtaz City P1 | 2016 | 806.4 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 806.4 | 31071003.3855 | 31071003.3855 | 0 | -1 |  | 0.4 | 12376.074 | 8519.05 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retian | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250327 | Feedback Awaited
I240782 | 2024-06-04 | Torkhan Border | PSW to Torkham Border | PSW to Torkham Border | 0 | 0 | [5 empty] | LIVE - 100% Completed | 100% | 0 | 125214350 | 18782152.5 | 106432197.5 | -1 |  |  | 43000 | 0 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Longhaul Connectivity | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240782 | Timeline not applicable
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Bangali Town | 750 | 337.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 337.5 | 6990826.496 | 6990826.496 |  | -1 |  |  | 1293.75 | 7950 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | District Complex, Complex City | 250 | 112.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 112.5 | 10682400.3 | 10682400.3 |  | -0.85 |  |  | 3191.25 | 10417.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560604 | No Initiation Date | Feeders/Transportations | Mandi Bahauddin | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 88591580 | 88591580 |  | -1 |  |  | 30504 | #REF! |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Gillani Town,Tariqabad,Sufipura | 3164 | 1423.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1423.8 | 21544834.31 | 21544834.31 |  | -0.85 |  |  | 3293.6 | 23825 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Gulberg Town | 326 | 146.7 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 146.7 | 3631270.096 | 3631270.096 |  | -1 |  |  | 796.95 | 2977.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00435 | 2022-12-29 | Karachi | Karachi Misc Areas | Muslim Khatri CHS | 352 | 176 | [5 empty] | LIVE - 100% Completed | 100% | 176 | 7713828.9002 | 1157074.335 | 6556754.5652 | 0 |  | 0.5 | 2213.1107 | 3632.9798 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00435 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Muslim Town | 502 | 251 | 218 | 31 | 27 | 160 |  | LIVE - 100% Completed | 100% | 251 | 4589413.72 | 688412.058 | 3901001.662 | -1 |  | 0.5 | 885.5 | 6016.05 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Muslimabad | 2262 | 904.8 | 2262 | 290 | 244 | 33 | 13 | Shamsi Road | 100% | 904.8 | 18305168.7878 | 2745775.3182 | 15559393.4696 | -0.5 |  | 0.4 | 0 | 35500.9737 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Gurrah Muhallah | 3690 | 1660.5 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1660.5 | 17541561.6754 | 17541561.6754 |  | -0.85 |  |  | 2024.7142 | 23325 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Hajipura | 788 | 354.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 354.6 | 6185625.744 | 6185625.744 |  | -1 |  |  | 1229.35 | 5405 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Akari-2 | 240 | 120 | [5 empty] | LIVE - 100% Completed | 100% | 120 | 3054248.5159 | 458137.2774 | 2596111.2385 | -0.5 |  | 0.5 | 0 | 1044.7851 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 2 |  |  |  | INT-23-00764 | Timeline not applicable
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Akari-3 | 970 | 485 | [5 empty] | LIVE - 100% Completed | 100% | 485 | 10967769.6005 | 1645165.4401 | 9322604.1604 | -1 |  | 0.5 | 0 | 2269.5919 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 2 |  |  |  | INT-23-00764 | Timeline not applicable
I250327 | 2024-11-05 | Islamabad | Islamabad | N.Blue Ar. & Other Buildings | 2404 | 961.6 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 961.6 | 17629621.859 | 2644443.2788 | 14985178.5802 | -1 |  | 0.4 | 5902.73 | 2527.275 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250327 | Timeline not applicable
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Hamza Ali town | 548 | 246.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 246.6 | 5668798.368 | 5668798.368 |  | -0.85 |  |  | 1282.25 | 4103.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Naimat Colony | 1434 | 573.6 |  | 127 | 150 | 381 | Occupancy : 1000 | LIVE - 100% Completed | 100% | 573.6 | 13904295.2886 | 2085644.2933 | 11818650.9953 | -1 |  | 0.4 | 1576.88 | 10798.2807 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Jinnah City | 224 | 100.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 100.8 | 4226035.7143 | 4226035.7143 |  | -1 |  |  | 517.5 | 10417.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240518 | 2024-02-27 | Islamabad | Naval Anchorage and other Areas (ISB) | Naval ANchorage | 1726 | 863 | 256 | 5 | 9 | 242 |  | LIVE - 100% Completed | 100% | 863 | 50275476.872 | 7541321.5308 | 42734155.3412 | -1 |  | 0.5 | 25538.228 | 24529.792 | Buried | 15% | Not Live |  | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240518 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Nawab Bhatta Colony | 1050 | 420 | 63 | 8 | 8 | 47 |  | LIVE - 100% Completed | 100% | 420 | 10598204.5074 | 1589730.6761 | 9008473.8313 | 0 |  | 0.4 | 1673.825 | 8501.0863 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Nawab City | 350 | 140 |  | 10 | 19 | 69 | Occupancy : 200 | LIVE - 100% Completed | 100% | 140 | 9457438.106 | 1418615.7159 | 8038822.3901 | -0.595 |  | 0.4 | 4550.6101 | 5056.2335 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 1 |  |  |  | I240682 | Timeline not applicable
I250374 | 2024-11-11 | Faisalabad | Faisalabad | NAYAB Colony Directors Residencies | 4 | 1.6 |  | 6 | 4 | 38 | Occupancy : 50 | LIVE - 100% Completed | 100% | 1.6 | 132580 | 19887 | 112693 | -1 |  | 0.4 | 0 | 50 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250374 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Nayab Grace City | 554 | 221.6 | 24 | 1 | 3 | 20 |  | LIVE - 100% Completed | 100% | 221.6 | 8619121.3126 | 1292868.1969 | 7326253.1157 | -1 |  | 0.4 | 1771.74 | 5567.0776 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Nayyab City & Extension | 1196 | 478.4 | 53 | 5 | 7 | 43 |  | LIVE - 100% Completed | 100% | 478.4 | 19505251.6999 | 2925787.755 | 16579463.9449 | 0 |  | 0.4 | 3358.8 | 11254.8078 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240684 | 2024-05-16 | Rawalpindi | Askari RWP (4-7-10) | Nazeer Apt. | 54 | 21.6 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 21.6 | 1719073.622 | 257861.0433 | 1461212.5787 | -1 |  | 0.4 | 1086.615 | 735 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240684 | Timeline not applicable
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Kachehri Area | 2708 | 1218.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1218.6 | 16522746.578 | 16522746.578 |  | -0.85 |  |  | 2689.85 | 19555 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | New Bagh Colony | 524 | 209.6 | 524 | 18 | 16 | 1 | 1 |  | 100% | 209.6 | 6637157.9 | 995573.685 | 5641584.215 | -1 |  | 0.4 | 914 | 7600.74 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Manzoorabad | 412 | 185.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 185.4 | 2882264.068 | 2882264.068 |  | -1 |  |  | 354.2 | 3563.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Paradise Complex | 134 | 60.3 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 60.3 | 2619910.4286 | 2619910.4286 |  | -0.85 |  |  | 241.5 | 7132.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Qila Gujjran, Rehmanpura | 1708 | 768.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 768.6 | 10451512.856 | 10451512.856 |  | -1 |  |  | 1644.5 | 10733.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | New Naqshband Colony | 990 | 495 | 355 | 48 | 65 | 242 |  | LIVE - 100% Completed | 100% | 495 | 11255102.04 | 1688265.306 | 9566836.734 | -0.85 |  | 0.5 | 3243.2 | 10761.9 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I250210 | 2024-09-14 | Sargodha | Sargodha | New Raza Garden | 1128 | 451.2 |  |  |  |  | Not Live | NOT LIVE - RETAIN BUDGET | 70% | 451.2 | 26117780.8485 | 10577701.2436 | 15540079.6049 | -0.85 |  | 0.4 | 12333.832 | 8614.3923 | Hybrid | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 61 | 62 | 14 | In Progress | 2 Months | May-2026 | Only Cable Pulling Pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250210 | 2026-05-01
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | New Surkh Dheri | 480 | 192 | 480 | 81 | 75 | 6 | 0 |  | 100% | 192 | 6713549.9197 | 1007032.488 | 5706517.4317 | -0.5 |  | 0.4 | 1003.4783 | 10160.4445 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | New Wahdat Colony | 706 | 282.4 | 600 | 500 |  |  |  | NOT LIVE - RETAIN BUDGET | 100% | 282.4 | 9434686.59 | 1415202.9885 | 8019483.6015 | -1 |  | 0.4 | 1884.8431 | 7502.182 | Hybrid | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 0 | 1 | -47 | Completed | 46054 | Mar-2026 | As-built Done/ Cable pulling plan awaiting | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240702 | 2026-03-01
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | New_Muslim town | 892 | 356.8 |  |  |  | 7 |  | LIVE - 100% Completed | 100% | 356.8 | 7066012.3616 | 1059901.8542 |  |  |  |  | 1077.1182 | 6783.8885 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
I260296 | No Initiation Date | Sukkur | Sukkur | NewSukkurCityTownship | 762 | 304.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 7542578.1916 | 7542578.1916 |  |  |  |  | 1284.665 | 7697.2927 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 months | Jun-2026 | Not started yet | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I240680 | 2024-05-16 | Rahim Yar Khan | RahimYar Khan Ph2 | Niazi Colony | 2506 | 1002.4 | 52 | 5 |  |  |  | LIVE - 100% Completed | 100% | 1002.4 | 20801141.496 | 3120171.2244 | 17680970.2716 | -1 |  | 0.4 | 2474 | 20575 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240680 | Timeline not applicable
I240678 | 2024-05-16 | Sialkot | Sialkot | Nihalchand & Greenwood St | 980 | 392 |  | 10 | 11 | 64 | Nihal Chand Not Lived Yet, its only Greenwood sale | LIVE - 100% Completed | 100% | 392 | 4560919.5322 | 684137.9298 | 3876781.6024 | -1 |  | 0.4 | 0 | 5779.5227 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | NIPA Society | 284 | 113.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 113.6 | 5162500.0898 | 5162500.0898 | 0 | -0.765 |  | 0.4 | 886.7271 | 2277.3909 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 0 | 1 | -47 | Yet to Start | 46113 | Mar-2026 | Map given for ROW permission | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240705 | 2026-03-01
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Ranger Colony | 382 | 171.9 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 171.9 | 9355307 | 9355307 |  | -0.5 |  |  | 2775 | 8206.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Royal Palm City | 312 | 140.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 140.4 | 3837274.85 | 3837274.85 |  | -1 |  |  | 796.95 | 2883.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Sattelite Town | 736 | 331.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 331.2 | 6079006.896 | 6079006.896 |  | -0.85 |  |  | 1166.1 | 5642.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240538 | 2024-02-29 | Haripur | Haripur Ph2 | Noor Colony | 846 | 338.4 | 47 | 39 | 2 | 6 |  | LIVE - 100% Completed | 100% | 338.4 | 9723833.699 | 1458575.0548 | 8265258.6442 | -1 |  | 0.4 | 1259.25 | 10993.581 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240538 | Timeline not applicable
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Shalimar City | 562 | 252.9 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 252.9 | 5448762.808 | 5448762.808 |  | -1 |  |  | 1216.7 | 3601.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Nowshehra Road | 3950 | 1580 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1580 | 21599069.71 | 21599069.71 | 16523288.3282 | -1 |  | 0.4 | 5073.8 | 29521.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 61 | 62 | 14 | Yet to Start | 46143 | May-2026 | civil work completed, Pole Marking complete, ADT plan received | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | INT-21-00315 | 2026-05-01
I250307 | 2024-10-28 | Karachi | DHA KHI - Common Corridor Project | DKTCC (Remaining Areas) | 19009 | 7603.6 | [5 empty] | LIVE - 100% Completed | 100% | 7603.6 | 517994073.7885 | 77699111.0683 | 440294962.7202 | -0.85 |  | 0.4 | 198037 | 0 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250307 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Oasis Park Residencia | 346 | 138.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 138.4 | 6003613.7219 | 6003613.7219 | 0 | -1 |  | 0.4 | 0 | 3661.2782 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240705 | Feedback Awaited
I250212 | 2024-09-14 | Swat | Mingora | Odigram P01 | 536 | 214.4 | 31 | 30 | 1 |  |  | LIVE - 100% Completed | 100% | 214.4 | 6715426.7303 | 1007314.0095 | 5708112.7207 | -1 |  | 0.4 | 1296.9 | 7535.5624 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Odigram P02 | 1110 | 444 | 57 | 55 | 2 |  |  | LIVE - 100% Completed | 100% | 444 | 13881109.0389 | 2082166.3558 | 11798942.6831 | -0.85 |  | 0.4 | 2449.7 | 20006.8128 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Odigram P03 | 1086 | 434.4 | 46 | 45 | 1 |  |  | LIVE - 100% Completed | 100% | 434.4 | 14166409.2815 | 2124961.3922 | 12041447.8893 | -1 |  | 0.4 | 2498.1 | 20601.0342 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Odigram P04 | 426 | 170.4 | 34 | 33 | 1 |  |  | LIVE - 100% Completed | 100% | 170.4 | 5971524.1928 | 895728.6289 | 5075795.5639 | -0.85 |  | 0.4 | 986.7 | 8476.421 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Odigram P05 | 114 | 45.6 | 28 | 27 | 1 |  |  | LIVE - 100% Completed | 100% | 45.6 | 3548077.562 | 532211.6343 | 3015865.9277 | -1 |  | 0.4 | 807.4 | 4034.4612 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Odigram P06 | 764 | 305.6 | 66 | 63 | 3 |  |  | LIVE - 100% Completed | 100% | 305.6 | 9024427.4219 | 1353664.1133 | 7670763.3086 | -0.85 |  | 0.4 | 1425.6 | 13917.4852 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
INT-23-00447 | 2022-12-29 | Peshawar | Peshawar Misc Areas | Officer & Professor Colony_PU | 336 | 168 | 163 | 122 | 13 | 28 | Profficer Colony Street,1,2,3,4,5,6,7, | LIVE - 100% Completed | 100% | 168 | 4296838.1661 | 644525.7249 | 3652312.4412 | -1 |  | 0.5 | 1097.8 | 3946.8381 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00447 | Timeline not applicable
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Sufi City Housing Scheme PK-1 | 1542 | 693.9 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 693.9 | 35888476.974 | 35888476.974 |  | -0.5 |  |  | 17253 | 14013 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Sufi City Housing Scheme PK-2 | 2672 | 1202.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1202.4 | 48109241.458 | 48109241.458 |  | -1 |  |  | 23564.25 | 20688.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250374 | 2024-11-11 | Faisalabad | Faisalabad | Officers Colony Canal Road | 90 | 36 |  | 222 | 224 | 632 | Occupancy : 1200 | LIVE - 100% Completed | 100% | 36 | 764480 | 114672 | 649808 | -0.765 |  | 0.4 | 0 | 50 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250374 | Timeline not applicable
I250377 | 2024-11-25 | Peshawar | Peshawar (P2) | OPF Colony | 788 | 315.2 | 247 | 206 | 17 | 24 | Doranpur, Taskeen Gerden,officer colony ,New Ofiicer colony, Malik Saad colony, | LIVE - 100% Completed | 100% | 315.2 | 13599054.5589 | 2039858.1838 | 11559196.3751 | #DIV/0! |  | 0.4 | 2784.15 | 9529.2355 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250377 | Timeline not applicable
INT-23-00447 | 2022-12-29 | Peshawar | Peshawar Misc Areas | OPF Colony | 788 | 394 | 61 | 53 | 3 | 5 | OPF Colony Block A,B,C, All Street | LIVE - 100% Completed | 100% | 394 | 11470409.9916 | 1720561.4987 | 9749848.4928 | -1 |  | 0.5 | 2784.15 | 9529.2355 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00447 | Timeline not applicable
I250213 | 2024-09-14 | Mardan | Mardan | Orchird Villas | 286 | 114.4 | 286 | 72 | 62 | 5 | 5 |  | 100% | 114.4 | 4823762.97 | 723564.4455 | 4100198.5245 | -0.85 |  | 0.4 | 1013.84 | 3716.565 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250213 | Timeline not applicable
I240519 | 2024-02-27 | Gujranwala | Royal Palm & Canal View | P1 | 1030 | 412 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 412 | 37154045.68 | 37154045.68 | 0 | -0.5 |  | 0.4 | 18737.25 | 14527.55 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | NOC awaited/Need to retain | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240519 | Feedback Awaited
I250298 | 2024-10-17 | Islamabad | ISB DHA Ph-5 | P1 | 598 | 239.2 | 14 | 3 | 2 | 9 |  | LIVE - 100% Completed | 100% | 239.2 | 10738401.2869 | 1610760.193 | 9127641.0939 | -1 |  | 0.4 | 6082.0329 | 9938.2153 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 2 |  |  |  | I250298 | Timeline not applicable
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Tajpura, Shalimar & Amin Twn | 2636 | 1186.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1186.2 | 13388109.496 | 13388109.496 |  | -0.85 |  |  | 1538.7 | 16331.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560604 | No Initiation Date | Feeders/Transportations | Mandi Bahauddin | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 8020000 | 8020000 |  | -1 |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | P1 muslim town | 636 | 254.4 | [5 empty] | LIVE - 100% Completed | 100% | 254.4 | 6806252.4841 | 1020937.8726 | 5785314.6115 | -1 |  | 0.4 | 3037.69 | 1518.8453 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
I260159 | No Initiation Date | Faisalabad | Faisalabad Citi Hosuing Extension | P1, Extended Part | 386 | 231.6 |  | 0 | 0 | 0 | Yet not active | NOT LIVE - RETAIN BUDGET | 100% |  | 8628786.096 | 1294317.9144 |  |  |  |  | 3922.8 | 3584.4 | Buried | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 31 | 32 | -16 | Completed | 1 Month | Apr-2026 | Cable plan will be shared this week. | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I240519 | 2024-02-27 | Gujranwala | Royal Palm & Canal View | P2 | 1566 | 626.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 626.4 | 54534546.08 | 54534546.08 | 0 | -1 |  | 0.4 | 29058.9 | 25981.1 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | NOC awaited/Need to retain | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240519 | Feedback Awaited
I250298 | 2024-10-17 | Islamabad | ISB DHA Ph-5 | P2 | 816 | 326.4 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 326.4 | 13081769.1152 | 1962265.3673 | 11119503.7479 | -0.85 |  | 0.4 | 6361.5104 | 13694.9479 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250298 | Timeline not applicable
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Unkown Area 2 | 1338 | 602.1 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 602.1 | 10528495.476 | 10528495.476 |  | -0.85 |  |  | 1890.6 | 10458.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Unkown Area 3 | 1152 | 518.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 518.4 | 7362935.326 | 7362935.326 |  | -1 |  |  | 1121.25 | 9166.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | P2 muslim town | 440 | 176 | [5 empty] | LIVE - 100% Completed | 100% | 176 | 4164351.2157 | 624652.6824 | 3539698.5334 | -0.85 |  | 0.4 | 1672.43 | 836.2163 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
I240519 | 2024-02-27 | Gujranwala | Royal Palm & Canal View | P3 | 2314 | 925.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 925.6 | 70152015.906 | 70152015.906 | 0 | -0.85 |  | 0.4 | 17654.1 | 15019.1 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | NOC awaited/Need to retain | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240519 | Feedback Awaited
I250298 | 2024-10-17 | Islamabad | ISB DHA Ph-5 | P3 | 1148 | 459.2 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 459.2 | 16436728.2988 | 2465509.2448 | 13971219.054 | -1 |  | 0.4 | 6089.0294 | 16503.5588 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250298 | Timeline not applicable
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Unkown Area 4 | 940 | 423 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 423 | 9360953 | 9360953 |  | -0.85 |  |  | 1999.85 | 9458.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560604 | No Initiation Date | Mandi Bahauddin | Mandi Bahauddin | Unkown Area 6 | 2806 | 1262.7 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1262.7 | 14595629.996 | 14595629.996 |  | -1 |  |  | 1887.15 | 20217.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250298 | 2024-10-17 | Islamabad | ISB DHA Ph-5 | P4 | 850 | 340 | 0 |  |  |  |  | LIVE - 100% Completed | 100% | 340 | 19039261.4559 | 2855889.2184 | 16183372.2375 | -0.5 |  | 0.4 | 13313.493 | 15260.5256 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250298 | Timeline not applicable
109 | No Initiation Date | Multan | DHA Multan | Additional Cost | 0 | 0 | 0 | 0 | 0 | 0 |  | NOT LIVE - RETAIN BUDGET | 10% | 0 | 9998966.7491 | 9149054.5754 |  | -1 |  |  | 1200 | 0 | Buried | 10% | NOT LIVE |  | 10% | 0.1 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
109 | No Initiation Date | Multan | DHA Multan | Block M | 2576 | 1545.6 | 107 | 0 | 7 | 100 |  | NOT LIVE - RETAIN BUDGET | 10% | 1545.6 | 63000000 | 57645000 |  | -0.425 |  | 0.6 | 0 | 0 | Buried | 10% | NOT LIVE |  | 10% | 0.1 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
I260159 | No Initiation Date | Faisalabad | Faisalabad Citi Hosuing Extension | P4-Citi Housing | 2926 | 1755.6 |  | 0 | 0 | 0 | Yet not active | NOT LIVE - RETAIN BUDGET | 100% |  | 57161538.184 | 8574230.7276 |  |  |  |  | 24765.6 | 25015.4 | Buried | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 31 | 32 | -16 | Completed | 1 Month | Apr-2026 | Cable pulling in progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I250298 | 2024-10-17 | Islamabad | ISB DHA Ph-5 | P5 | 1116 | 446.4 | 0 |  |  |  |  | LIVE - 80% Completed | 80% | 357.12 | 17326510.6309 | 5544483.4019 | 11782027.229 | -1 |  | 0.4 | 8779.8053 | 18004.9719 | Buried |  | LIVE | Buried | 80% | 0.8 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 | Partial Live/Some C.W work and Cable Pulling going on | Live - As per Plan | LIVE - 80% Completed | 1 | Add 9 count |  |  |  | I250298 | 2026-07-01
109 | No Initiation Date | Multan | DHA Multan | Block Q | 2914 | 1748.4 | 44 | 0 | 3 | 41 |  | NOT LIVE - RETAIN BUDGET | 10% | 1748.4 | 63000000 | 57645000 |  | -1 |  | 0.6 | 0 | 0 | Buried | 10% | NOT LIVE |  | 10% | 0.1 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
109 | No Initiation Date | Multan | DHA Multan | Block R | 2466 | 1479.6 | 22 | 0 | 3 | 19 |  | NOT LIVE - RETAIN BUDGET | 10% | 1479.6 | 63000000 | 57645000 |  | 0 |  | 0.6 | 0 | 0 | Buried | 10% | NOT LIVE |  | 10% | 0.1 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
109 | No Initiation Date | Multan | DHA Multan | DHA Rumanza-P1 | 724 | 434.4 | 2 | 0 | 0 | 2 |  | NOT LIVE - RETAIN BUDGET | 10% | 434.4 | 63000000 | 57645000 |  | -1 |  | 0.6 | 0 | 0 | Buried | 10% | NOT LIVE |  | 10% | 0.1 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
109 | No Initiation Date | Multan | DHA Multan | DHA Villas | 618 | 370.8 | 381 | 0 | 5 | 376 |  | NOT LIVE - RETAIN BUDGET | 10% | 370.8 | 63000000 | 57645000 |  | -0.85 |  | 0.6 | 0 | 0 | Buried | 10% | NOT LIVE |  | 10% | 0.1 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
I240519 | 2024-02-27 | Gujranwala | Royal Palm & Canal View | P9 | 1908 | 763.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 763.2 | 53764767.08 | 53764767.08 | 0 | -1 |  | 0.4 | 25388.1 | 23034.7 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | NOC awaited/Need to retain | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240519 | Feedback Awaited
I250327 | 2024-11-05 | Islamabad | Islamabad | Mumtaz City P2 | 1100 | 440 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 440 | 33046606.071 | 33046606.071 | 0 | 0 |  | 0.4 | 15584.3295 | 0 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retian | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250327 | Feedback Awaited
I260160 | No Initiation Date | Lahore | Khyban-e-Amin, High court & Al Rehman PH4 | High Court Society | 776 | 310.4 | [5 empty] | LIVE - 100% Completed | 100% |  | 9966467.3674 | 1494970.1051 |  |  |  |  | 1668.41 | 0 | Hybrid | 15% | Live | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
I250327 | 2024-11-05 | Islamabad | Islamabad | PAF Tarnol-P1 | 1550 | 620 | 169 | 3 | 6 | 160 |  | LIVE - 60% Completed | 60% | 372 | 54936288.8413 | 26918781.5322 | 28017507.309 | 0 |  | 0.4 | 22788.034 | 22120.0873 | Buried |  | LIVE | Buried | 60% | 0.6 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 |  | Live - As per Plan | LIVE - 60% Completed | 1 |  |  |  |  | I250327 | 2026-07-01
I250327 | 2024-11-05 | Islamabad | Islamabad | PAF Tarnol-P2 | 1444 | 577.6 | 0 |  |  |  |  | LIVE - 60% Completed | 60% | 346.56 | 47513138.0216 | 23281437.6306 | 24231700.391 | -1 |  | 0.4 | 19881.7605 | 19648.1392 | Buried |  | LIVE | Buried | 60% | 0.6 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 |  | Live - As per Plan | LIVE - 60% Completed | 1 |  |  |  |  | I250327 | 2026-07-01
I240538 | 2024-02-29 | Haripur | Haripur Ph2 | Pak China Phosphate Colony | 200 | 80 | Planned | 0 | 0 | 0 |  | NOT LIVE - RETAIN BUDGET | 0% | 80 | 6032088.98 | 6032088.98 | 0 | -0.5 |  | 0.4 | 1666.8 | 3713.2905 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240538 | 2026-06-01
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Pak Ideal CHS P1 | 452 | 180.8 | [5 empty] | LIVE - 100% Completed | 100% | 180.8 | 11035268.3486 | 1655290.2523 | 9379978.0963 | -0.85 |  | 0.4 | 2056.1577 | 3995.2021 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Pak Ideal CHS P2 | 448 | 179.2 | [5 empty] | LIVE - 100% Completed | 100% | 179.2 | 12937608.7805 | 1940641.3171 | 10996967.4635 | -1 |  | 0.4 | 2486.0641 | 3995.2021 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Pak Kausar Town | 1034 | 413.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 6765403.0162 | 6765403.0162 |  |  |  |  | 1049.4 | 5835.5778 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260179 | No Initiation Date | Lahore | Palm City Lahore | Palm City | 732 | 293 | [5 empty] | NOT LIVE - RETAIN BUDGET | 100% |  | 13587284.5 | 2038092.675 |  |  |  |  | 1541.25 | 13250 | Buried | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 61 | 62 | 14 | Completed | 2 Months | May-2026 | Asbuilt Pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-05-01
INT-23-00436 | 2022-12-29 | Hyderabad | Hyderabad Misc Areas | Palm Village | 1248 | 499.2 | 1185 | 130 | 148 | 0 | 11 | LIVE - 100% Completed | 100% | 499.2 | 31229436.6848 | 4684415.5027 | 26545021.1821 | -0.5 |  | 0.4 | 14259.9826 | 14019.2351 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00436 | Timeline not applicable
109 | No Initiation Date | Feeders/Transportations | DHA Multan | Feeder | [7 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
109 | No Initiation Date | Feeders/Transportations | DHA Multan | Transportation | [7 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Abdullah City | 396 | 158.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 158.4 | 3256516.4889 | 3256516.4889 |  | -0.85 |  |  | 455.4 | 4262.6009 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Paragon Ideal Homes | 824 | 329.6 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 329.6 | 6115314.2955 | 6115314.2955 |  |  |  |  | 1067.6346 | 6260.6419 | Hybrid | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 months | Jun-2026 | NOC pending by society | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Parao Road | 2006 | 802.4 | [5 empty] | LIVE - 100% Completed | 100% | 802.4 | 12431253.73 | 1864688.0595 | 10566565.6705 | -1 |  | 0.4 | 1362.75 | 10319.7165 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Jinnah Road 2 | 3502 | 1400.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 80% | 1400.8 | 19626958.875 | 6280626.84 | 13346332.035 | -1 |  | 0.4 | 5411.9 | 0 | Hybrid | 80% | NOT LIVE |  | 80% | 0.8 | 2026-03-01 | 92 | 93 | 45 | In Progress | 46174 | Jun-2026 | civil work completed (Pole marking done waiting FOR ADT Plan) | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | INT-21-00315 | 2026-06-01
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Nowshehra Sansi Road | 2714 | 1085.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1085.6 | 19895078.32 | 19895078.32 | 15219734.9148 | -0.5 |  | 0.4 | 5138.2 | 0 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 61 | 62 | 14 | Yet to Start | 46143 | May-2026 | civil work completed, Pole Marking complete, ADT plan received | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | INT-21-00315 | 2026-05-01
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Sialkot By Pass | 1586 | 634.4 | [5 empty] | LIVE - 100% Completed | 100% | 634.4 | 12397330.98 | 1859599.647 | 10537731.333 | -1 |  | 0.4 | 4241.2 | 0 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Sialkot Road | 3022 | 1208.8 | [5 empty] | LIVE - 100% Completed | 100% | 1208.8 | 17816932.93 | 2672539.9395 | 15144392.9905 | -0.85 |  | 0.4 | 4112.4 | 0 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Al-Hamra City | 230 | 92 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 92 | 2551353.303 | 2551353.303 |  | -1 |  |  | 497.95 | 1972.046 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560606 | No Initiation Date | Narowal | Narowal | Al-Rafeh Garden | 248 | 99.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 99.2 | 2323310.4 | 2323310.4 |  | -0.85 |  |  | 386.4 | 2212.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Pasrur Rd & Skt Bypass | 3576 | 1430.4 | [5 empty] | LIVE - 100% Completed | 100% | 1430.4 | 27918709.246 | 4187806.3869 | 23730902.8591 | -1 |  | 0.4 | 3601.8 | 29016.25 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Megred into Ghorrdo Road P1 | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Al-Raheem Residencia | 370 | 148 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 148 | 3967175.8548 | 3967175.8548 |  | -1 |  |  | 847.9076 | 3376.3396 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Peerwali | 978 | 391.2 |  | 5 | 10 | 25 |  | LIVE - 100% Completed | 100% | 391.2 | 12226729.571 | 1834009.4357 | 10392720.1354 | -1 |  | 0.4 | 1964.6 | 10278.125 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
I250378 | 2024-11-25 | Sahiwal | Sahiwal (P2) | Peoples & Bitholdi Colony | 2948 | 1179.2 | 19 | 0 | 0 |  | 17-2-2026 | LIVE - 100% Completed | 100% | 1179.2 | 21649146.7713 | 3247372.0157 | 14721419.8045 | #DIV/0! |  | 0.4 | 2962.2148 | 23791.0094 | Hybrid | 15% | LIVE |  | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | 1 |  |  |  |  | I250378 | Timeline not applicable
I260298 | No Initiation Date | Hyderabad | Petaro Garrison, Hyderabad | Petaro | 740 | 296 | 600 | 350 | 149 | 0 | 2 | LIVE - 100% Completed | 100% |  | 7276483.8012 | 1091472.5702 |  |  |  |  | 2118 | 5854.0918 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
I260068 | 2025-07-17 | Lahore | DHA PH 1-5 | Ph-1 G & H Block | 930 | 465 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 465 | 18394558.7993 | 18394558.7993 | 0 | -1 |  | 0.5 | 4746.85 | 5776.8 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Duct Plan Shared | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I260068 | 2026-06-01
I260068 | 2025-07-17 | Lahore | DHA PH 1-5 | Ph-1 K Block | 252 | 126 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 126 | 6965667.836 | 6965667.836 | 0 | -0.5 |  | 0.5 | 2080.2 | 2202.55 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Duct Plan not shared | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I260068 | 2026-06-01
I260068 | 2025-07-17 | Lahore | DHA PH 1-5 | Ph-2 Q Block | 286 | 143 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 143 | 7160506.532 | 7160506.532 | 0 | -1 |  | 0.5 | 2046.2 | 2199.65 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Duct Plan not shared | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I260068 | 2026-06-01
I260068 | 2025-07-17 | Lahore | DHA PH 1-5 | Ph-2 T Block | 234 | 117 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 117 | 5304058.866 | 5304058.866 | 0 | -0.85 |  | 0.5 | 1178 | 1708.1 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Duct Plan not shared | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I260068 | 2026-06-01
I260068 | 2025-07-17 | Lahore | DHA PH 1-5 | Ph-3 XX Block | 162 | 81 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 81 | 3707602.484 | 3707602.484 | 0 | -1 |  | 0.5 | 812 | 1096.2 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Duct Plan not shared | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I260068 | 2026-06-01
I260068 | 2025-07-17 | Lahore | DHA PH 1-5 | Ph-3 Y & Z Block | 700 | 350 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 350 | 14846732.9073 | 14846732.9073 | 0 | -0.85 |  | 0.5 | 3114 | 5505.65 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Duct Plan not shared | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I260068 | 2026-06-01
I260068 | 2025-07-17 | Lahore | DHA PH 1-5 | Ph-4 K Commercial | 580 | 290 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 290 | 14228806.6293 | 14228806.6293 | 0 | -1 |  | 0.5 | 4419.2 | 4490.65 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Duct Plan not shared | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I260068 | 2026-06-01
I260068 | 2025-07-17 | Lahore | DHA PH 1-5 | Ph-5 K Commercial | 282 | 141 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 141 | 6546073.4027 | 6546073.4027 | 0 | -0.85 |  | 0.5 | 1370 | 2678.15 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Duct Plan not shared | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I260068 | 2026-06-01
I260068 | 2025-07-17 | Lahore | DHA PH 7-8 | PH-7-P1 | 4170 | 2085 | [5 empty] | NOT LIVE - RETAIN BUDGET | 98% | 2085 | 172517652.1536 | 28810447.9096 | 143707204.2439 | -1 |  | 0.5 | 85280.2743 | 75606.3987 | Buried | 98% | NOT LIVE |  | 98% | 0.98 | 2026-03-01 | 31 | 32 | -16 | In Progress | 46113 | Apr-2026 | Civil Work Completion | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I260068 | 2026-04-01
I260068 | 2025-07-17 | Lahore | DHA PH 7-8 | PH-7-P2 | 3496 | 1748 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 1748 | 137720852.0029 | 32364400.2207 | 105356451.7822 | -0.5 |  | 0.5 | 68827.2965 | 60275.9565 | Buried | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 31 | 32 | -16 | In Progress | 46113 | Apr-2026 | Civil Work Complete , HH in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I260068 | 2026-04-01
I260068 | 2025-07-17 | Lahore | DHA PH 7-8 | PH-7-P3 | 6980 | 3490 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 3490 | 305942020.5743 | 71896374.835 | 234045645.7393 | -1 |  | 0.5 | 151781.0062 | 131204.5461 | Buried | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 31 | 32 | -16 | In Progress | 46113 | Apr-2026 | Civil Work Complete , HH in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 | 1 |  |  |  | I260068 | 2026-04-01
I260068 | 2025-07-17 | Lahore | DHA PH 7-8 | PH-7-P5 | 5536 | 2768 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 2768 | 154265075.962 | 36252292.8511 | 118012783.1109 | -0.2125 |  | 0.5 | 72968.5498 | 62852.8275 | Buried | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 31 | 32 | -16 | In Progress | 46113 | Apr-2026 | Civil Work Complete , HH in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I260068 | 2026-04-01
I260068 | 2025-07-17 | Lahore | DHA PH 7-8 | Ph-8-IVY-P1 | 2918 | 1459 | [5 empty] | REMOVE BUDGET (T) | 0% | 1459 | 80298361.2279 | 0 | 80298361.2279 | -1 |  | 0.5 | 33513.8122 | 51145.5753 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 4 Months | Jun-2026 | Duct Plan Not share due to Low Occupancy - jul26 | Temporary Budget Removal | REMOVE BUDGET (T) |  | 1 |  | 0 |  | I260068 | 2026-06-01
I260068 | 2025-07-17 | Lahore | DHA PH 7-8 | Ph-8-IVY-P2 | 3820 | 1910 | [5 empty] | REMOVE BUDGET (T) | 0% | 1910 | 101171592.5956 | 0 | 101171592.5956 | -0.85 |  | 0.5 | 43249.1631 | 67661.4539 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 4 Months | Jun-2026 | Duct Plan Not share due to Low Occupancy - jul26 | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | I260068 | 2026-06-01
I260068 | 2025-07-17 | Lahore | DHA PH 7-8 | PH-8-P1 | 1992 | 996 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 996 | 71198771.5866 | 16731711.3228 | 54467060.2637 | -1 |  | 0.5 | 34549.0127 | 28083.3414 | Buried | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46054 | Mar-2026 | Cable and ADT Plan Shared | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 | 1 |  |  |  | I260068 | 2026-03-01
I260068 | 2025-07-17 | Lahore | DHA PH 7-8 | PH-8-P2 | 2412 | 1206 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 1206 | 109329032.8408 | 25692322.7176 | 83636710.1232 | -0.85 |  | 0.5 | 52759.6751 | 39777.4211 | Buried | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46054 | Mar-2026 | Cable Pulling in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I260068 | 2026-03-01
I260068 | 2025-07-17 | Lahore | DHA PH 7-8 | PH-8-P3 | 1386 | 693 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 693 | 55535848.1534 | 13050924.3161 | 42484923.8374 | -1 |  | 0.5 | 26700.6113 | 20789.9105 | Buried | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46082 | Mar-2026 | Asbuilt Complete | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I260068 | 2026-03-01
I260068 | 2025-07-17 | Lahore | DHA PH 7-8 | PH-8-P4 | 1420 | 710 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 710 | 68581191.7365 | 16116580.0581 | 52464611.6784 | -0.85 |  | 0.5 | 33134.852 | 24139.0279 | Buried | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46082 | Mar-2026 | Asbuilt Complete | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I260068 | 2026-03-01
I260068 | 2025-07-17 | Lahore | DHA PH 7-8 | PH-8-P5 | 930 | 465 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 465 | 45370777.822 | 10662132.7882 | 34708645.0338 | -1 |  | 0.5 | 21860.3537 | 15942.4222 | Buried | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46082 | Mar-2026 | Asbuilt Complete | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I260068 | 2026-03-01
I260068 | 2025-07-17 | Lahore | DHA PH 7-8 | PH-8-P6 | 842 | 421 | [5 empty] | NOT LIVE - RETAIN BUDGET | 100% | 421 | 42169604.5351 | 6325440.6803 | 35844163.8548 | -0.85 |  | 0.5 | 20225.8771 | 14825.7372 | Buried | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 31 | 32 | -16 | Completed | 46113 | Apr-2026 | Civil Work Completion | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I260068 | 2026-04-01
I260068 | 2025-07-17 | Lahore | DHA PH 7-8 | PH-8-P7 | 980 | 490 | [5 empty] | REMOVE BUDGET (T) | 0% | 490 | 43995521.5609 | 0 | 43995521.5609 | -1 |  | 0.5 | 21468.3076 | 17297.0551 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 4 Months | Jun-2026 | Duct Plan Not share due to Low Occupancy - jul26 | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | I260068 | 2026-06-01
I260068 | 2025-07-17 | Lahore | DHA PH 7-8 | PH-8-P8 | 802 | 401 | [5 empty] | REMOVE BUDGET (T) | 0% | 401 | 26653396.6693 | 0 | 26653396.6694 | -1 |  | 0.5 | 12254.3024 | 9073.9279 | Buried |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 4 Months | Jun-2026 | Duct Plan Not share due to Low Occupancy - jul26 | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | I260068 | 2026-06-01
I250327 | 2024-11-05 | Islamabad | Islamabad | PHA G-11 & I12 | 4674 | 1869.6 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 1869.6 | 26554382.379 | 26554382.379 | 0 | -0.85 |  | 0.4 | 5261.4 | 10370.2125 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retian | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250327 | Feedback Awaited
INT-23-00435 | 2022-12-29 | Karachi | Karachi Misc Areas | PIB Colony | 2248 | 1124 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1124 | 21107233.8367 | 21107233.8367 | 0 | -1 |  | 0.5 | 3421.6331 | 15496.9432 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | INT-23-00435 | Feedback Awaited
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | PiliBheet Society | 728 | 291.2 | [5 empty] | LIVE - 100% Completed | 100% | 291.2 | 10959915.1033 | 1643987.2655 | 9315927.8378 | -1 |  | 0.4 | 1959.76 | 5314.6931 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Live - Completed | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Pioneer Fountain_KHI UNI | 262 | 104.8 | [5 empty] | LIVE - 100% Completed | 100% | 104.8 | 2397603.2297 | 359640.4845 | 2037962.7452 | -1 |  | 0.4 | 0 | 3544.022 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Live - On Aerial | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I260160 | No Initiation Date | Lahore | Khyban-e-Amin, High court & Al Rehman PH4 | PK01 | 4706 | 1882.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 60% |  | 86408046.75 | 42339942.9075 |  |  |  |  | 47548.65 | 43293.75 | Buried | 60% | Not Live |  | 60% | 0.6 | 2026-03-01 | 92 | 93 | 45 | In Progress | 3 months | Jun-2026 | Civil Work in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I260180 | No Initiation Date | Gujranwala | Gujranwala Makki Road | PK-01 | 5402 | 2160.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% |  | 36230431.9062 | 8514151.498 |  |  |  |  | 4771.35 | 51586.65 | Hybrid | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 month | Apr-2026 | Cable Pulling pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I260160 | No Initiation Date | Lahore | Khyban-e-Amin, High court & Al Rehman PH4 | PK02 | 938 | 375.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 15310091.5 | 15310091.5 |  |  |  |  | 8152.95 | 8006.25 | Buried | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 4 moths | Jul-2026 | Hold due to Low occupancy | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
I260180 | No Initiation Date | Gujranwala | Gujranwala Makki Road | PK-02 | 7946 | 3178.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% |  | 37856034.625 | 8896168.1369 |  |  |  |  | 2417.3 | 66483.95 | Hybrid | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 month | Apr-2026 | Cable Pulling pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I260160 | No Initiation Date | Lahore | Khyban-e-Amin, High court & Al Rehman PH4 | PK03 | 2990 | 1196 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 60220180.5 | 60220180.5 |  |  |  |  | 34483.9 | 32412.5 | Buried | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 4 moths | Jul-2026 | Duct Plan will be shared as per development team demand | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
I260160 | No Initiation Date | Lahore | Khyban-e-Amin, High court & Al Rehman PH4 | PK04 | 2590 | 1036 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 52810322 | 52810322 |  |  |  |  | 30341.65 | 28508.75 | Buried | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 4 moths | Jul-2026 | Duct Plan will be shared as per development team demand | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
I260160 | No Initiation Date | Lahore | Khyban-e-Amin, High court & Al Rehman PH4 | PK05 | 1756 | 702.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 44141308.5 | 44141308.5 |  |  |  |  | 25962.85 | 24158.75 | Hybrid | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 4 moths | Jul-2026 | Hold due to Low occupancy | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
I260361 | No Initiation Date | Lahore | Lhr MW City & Al Hafeez Ph-1 | Pocket-1 | 1948 | 779.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 70% |  | 30287495.44 | 12266435.6532 |  |  |  |  | 16031.455 | 12183.75 | Buried | 70% | Not Live |  | 70% | 0.7 | 2026-03-01 | 61 | 62 | 14 | In Progress | 2 months | May-2026 | Civil Work in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-05-01
I260361 | No Initiation Date | Lahore | Lhr MW City & Al Hafeez Ph-1 | Pocket-2 | 828 | 331.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 15% |  | 27941058.86 | 24378573.8553 |  |  |  |  | 16931.805 | 13596.25 | Buried | 15% | Not Live |  | 15% | 0.15 | 2026-03-01 | 122 | 123 | 75 | In Progress | 4 moths | Jul-2026 | Civil Work in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
I260361 | No Initiation Date | Lahore | Lhr MW City & Al Hafeez Ph-1 | Pocket-3 | 2042 | 816.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 45803599.988 | 45803599.988 |  |  |  |  | 28458.1 | 22395 | Buried | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 4 moths | Jul-2026 | Duct Plan will be shared as per development team demand | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
I260361 | No Initiation Date | Lahore | Lhr MW City & Al Hafeez Ph-1 | Pocket-4 | 2728 | 1091.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 49809689.072 | 49809689.072 |  |  |  |  | 26927.89 | 21280 | Buried | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 4 moths | Jul-2026 | Duct Plan will be shared as per development team demand | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
I260361 | No Initiation Date | Lahore | Lhr MW City & Al Hafeez Ph-1 | Pocket-5 | 2654 | 1061.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 51751094.568 | 51751094.568 |  |  |  |  | 28172.705 | 21598.75 | Buried | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 4 moths | Jul-2026 | Hold due to Low occupancy | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
I260361 | No Initiation Date | Lahore | Lhr MW City & Al Hafeez Ph-1 | Pocket-6 | 986 | 394.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 22463919.244 | 22463919.244 |  |  |  |  | 12747.9 | 9620 | Buried | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 4 moths | Jul-2026 | Duct Plan will be shared as per development team demand | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
I260361 | No Initiation Date | Lahore | Lhr MW City & Al Hafeez Ph-1 | Pocket-7 | 1778 | 711.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 45344853.868 | 45344853.868 |  |  |  |  | 27073.695 | 21018.75 | Buried | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 4 moths | Jul-2026 | Duct Plan will be shared as per development team demand | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-07-01
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Pohan Colony | 460 | 184 | 460 | 277 | 258 | 13 | 6 |  | 100% | 184 | 6317205.3688 | 947580.8053 | 5369624.5635 | -1 |  | 0.4 | 795.3333 | 7803.2252 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Posh AVenue | 68 | 27.2 | 8 | 0 | 0 | 8 |  | LIVE - 100% Completed | 100% | 27.2 | 3421784.875 | 513267.7312 | 2908517.1437 | -1 |  | 0.4 | 1284.7 | 1022.25 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-4 | 1612 | 806 | [5 empty] | LIVE - 100% Completed | 100% | 806 | 44582414.6557 | 6687362.1984 | 37895052.4573 | -0.85 |  | 0.5 | 12392.6368 | 0 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00764 | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Al-Reheem Garden | 1060 | 424 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 424 | 11177102.2039 | 11177102.2039 |  | -0.85 |  |  | 2278.0223 | 12431.0382 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560606 | No Initiation Date | Narowal | Narowal | Al-Rehmanpura and Zafarwal Road | 962 | 384.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 384.8 | 7043480.036 | 7043480.036 |  | -1 |  |  | 1221.3 | 8228.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250206 | 2024-09-12 | Daska | Daska | Punjab Small Ind. Estate | 196 | 78.4 |  |  |  |  | NOT ENERGISED AS YET | NOT LIVE - RETAIN BUDGET | 0% | 78.4 | 3402608.5822 | 3402608.5822 | 0 | -0.85 |  | 0.4 | 516.35 | 5522.8644 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-06-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Punjabi Sodagran Society | 450 | 180 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 6586551.8239 | 6586551.8239 |  |  |  |  | 1291.7697 | 5285.6106 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560606 | No Initiation Date | Narowal | Narowal | Bismilllah Society | 616 | 246.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 246.4 | 6303993.845 | 6303993.845 |  | -0.85 |  |  | 1335.15 | 5053.927 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Qaiserabad | 944 | 472 | 352 | 33 | 57 | 262 |  | LIVE - 100% Completed | 100% | 472 | 9904201.38 | 1485630.207 | 8418571.173 | -1 |  | 0.5 | 2319 | 9052.35 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Qasim Pur Colony | 996 | 498 | 97 | 10 | 12 | 75 |  | LIVE - 100% Completed | 100% | 498 | 8225369.2713 | 1233805.3907 | 6991563.8806 | -0.85 |  | 0.5 | 1465.56 | 7273.6274 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Qasim Town | 1774 | 709.6 | [5 empty] | LIVE - 100% Completed | 100% | 709.6 | 12865111.9959 | 1929766.7994 | 10935345.1965 | -1 |  | 0.4 | 4811.97 | 13676.8887 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Qasim Villas & Shams Colony | 452 | 226 | 62 | 5 | 7 | 50 |  | LIVE - 100% Completed | 100% | 226 | 6980813.5783 | 1047122.0367 | 5933691.5416 | -1 |  | 0.5 | 2735.7641 | 5762.1367 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Qazi Town | 460 | 184 |  |  |  |  | NOT ENERGISED AS YET | NOT LIVE - RETAIN BUDGET | 0% | 184 | 5594650.75 | 5594650.75 | 0 | -1 |  | 0.4 | 930.35 | 5520 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 0 | 1 | -47 | Yet to Start | 46082 | Mar-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-03-01
UI2560606 | No Initiation Date | Narowal | Narowal | Circular Road | 2074 | 829.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 829.6 | 17653857.046 | 17653857.046 |  | -1 |  |  | 3239.55 | 19453.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560606 | No Initiation Date | Narowal | Narowal | Civil Lines | 2220 | 888 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 888 | 20147379.5617 | 20147379.5617 |  | -0.85 |  |  | 3085.7145 | 29967.1516 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Rafah-e-Aam Society | 834 | 333.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 8920240.4115 | 8920240.4115 |  |  |  |  | 1590.6 | 8007.8138 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Rafi Gardens_Gulshan e Muneer | 890 | 356 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 7641320.7956 | 7641320.7956 |  |  |  |  | 1239.7 | 6050.7621 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260208 | No Initiation Date | Lahore | LHE - DHA Phase 6, EME, Rahbar | Rahbr-Sec-1-P1 | 1190 | 476 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 36151846.5 | 36151846.5 |  |  |  |  | 21861.6 | 17600 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 Months | Jun-2026 | Civil work will start after eid. | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I260208 | No Initiation Date | Lahore | LHE - DHA Phase 6, EME, Rahbar | Rahbr-Sec-1-P2 | 952 | 380.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 24294953.8888 | 24294953.8888 |  |  |  |  | 14717.181 | 12977.9109 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 Months | Jun-2026 | Civil work will start after eid. | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I260208 | No Initiation Date | Lahore | LHE - DHA Phase 6, EME, Rahbar | Rahbr-Sec-2-P1 | 2848 | 1139.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 61787735.75 | 61787735.75 |  |  |  |  | 34024.8 | 30542.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 Months | Jun-2026 | Civil work will start after eid. | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I260208 | No Initiation Date | Lahore | LHE - DHA Phase 6, EME, Rahbar | Rahbr-Sec-2-P2 | 2836 | 1134.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 58301250.8659 | 58301250.8659 |  |  |  |  | 35524.2681 | 31060.6959 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 Months | Jun-2026 | Civil work will start after eid. | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I240539 | 2024-02-28 | Swat | Swat Ph2 | Rahimabad_Qambar | 1758 | 703.2 | 450 | 360 | 36 | 54 |  | LIVE - 100% Completed | 100% | 703.2 | 27428030.2084 | 4114204.5313 | 23313825.6771 | -1 |  | 0.4 | 3237.3033 | 28873.266 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240539 | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Doctor's Colony | 1434 | 573.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 573.6 | 12893106.621 | 12893106.621 |  | -1 |  |  | 2457.55 | 13098.4332 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560606 | No Initiation Date | Feeders/Transportations | Narowal | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 21067416 | 21067416 |  | -0.85 |  |  | 3535.5 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Garden Town | 582 | 232.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 232.8 | 5859077.0304 | 5859077.0304 |  | -1 |  |  | 1232.9739 | 5655.8822 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560606 | No Initiation Date | Narowal | Narowal | Green City Park | 448 | 179.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 179.2 | 3932409.496 | 3932409.496 |  | -0.85 |  |  | 787.75 | 3296.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560606 | No Initiation Date | Narowal | Narowal | Habib Garden | 248 | 99.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 99.2 | 6014260.1729 | 6014260.1729 |  | -1 |  |  | 1869.2557 | 2590 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Rangpura Road | 632 | 252.8 |  | 65 | 84 | 248 |  | LIVE - 100% Completed | 100% | 252.8 | 7867048.75 | 1180057.3125 | 6686991.4375 | -1 |  | 0.4 | 1265 | 4310 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Ranjha Mahira | 532 | 212.8 |  |  | Yes |  |  | REMOVE BUDGET (P) | 0% |  | 5161699.6917 | 0 |  |  |  | 0.4 | 1303.0549 | 7626.9859 | Hybrid | 100% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | 14.5km backhauling req.and distance from would be 22km/Need to Remove | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | #N/A | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Hayat Town | 638 | 255.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 255.2 | 6763400.6 | 6763400.6 |  |  |  |  | 1591.6 | 5636.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250210 | 2024-09-14 | Sargodha | Sargodha | Raza Gardan Phase 1 & 2 | 1116 | 446.4 |  |  |  |  | Not Live | NOT LIVE - RETAIN BUDGET | 70% | 446.4 | 13011483.6086 | 5269650.8615 | 7741832.7471 | -1 |  | 0.4 | 2303.1272 | 7689.0744 | Hybrid | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Only Cable Pulling Pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250210 | 2026-04-01
I250378 | 2024-11-25 | Sahiwal | Sahiwal (P2) | Razaq Royal Ph-3_P1 | 774 | 309.6 | N/A | N/A | N/A |  | Not Live | NOT LIVE - RETAIN BUDGET | 0% | 309.6 | 19772977.6585 | 19772977.6585 | 0 | #DIV/0! |  | 0.4 | 9080.3125 | 7560.253 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250378 | Feedback Awaited
I250378 | 2024-11-25 | Sahiwal | Sahiwal (P2) | Razaq Royal Ph-3_P2 | 286 | 114.4 | N/A | N/A | N/A |  | Not Live | NOT LIVE - RETAIN BUDGET | 0% | 114.4 | 8584221.25 | 8584221.25 | 0 | #DIV/0! |  | 0.4 | 4774.5 | 3032.5 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250378 | Feedback Awaited
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-5 P1 | 728 | 364 | [5 empty] | LIVE - 100% Completed | 100% | 364 | 21817638.7565 | 3272645.8135 | 18544992.943 | -1 |  | 0.5 | 8758.84 | 0 | Buried | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00764 | Timeline not applicable
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-5 P2 | 3460 | 1730 | [5 empty] | LIVE - 100% Completed | 100% | 1730 | 54684502.1091 | 8202675.3164 | 46481826.7928 | -0.85 |  | 0.5 | 9719.3 | 0 | Buried | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00764 | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Katchery Road and Allama Iqbal | 888 | 355.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 355.2 | 6713072.6671 | 6713072.6671 |  | -1 |  |  | 1125.85 | 6649.402 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Rehman Colony | 334 | 167 |  |  |  |  | Unspecified area | LIVE - 100% Completed | 100% | 167 | 4300340.605 | 645051.0908 | 3655289.5143 | -0.85 |  | 0.5 | 1625.65 | 3925.15 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240438 | 2024-01-09 | Lahore | Chinar Bagh Lahore | Rehman Garden-2 Pk-1 | 2366 | 946.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 100% | 946.4 | 22536237.5793 | 3380435.6369 | 19155801.9424 | -1 |  | 0.4 | 3988.2 | 20634 | Hybrid | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 0 | 1 | -47 | Completed | 46054 | Mar-2026 | Civil work completed | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240438 | 2026-03-01
I240438 | 2024-01-09 | Lahore | Chinar Bagh Lahore | Rehman Garden-2 Pk-2 | 1540 | 616 | [5 empty] | NOT LIVE - RETAIN BUDGET | 100% | 616 | 15232268.9247 | 2284840.3387 | 12947428.586 | -0.5 |  | 0.4 | 3027.95 | 13503 | Hybrid | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 0 | 1 | -47 | Completed | 46054 | Mar-2026 | Civil work completed | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240438 | 2026-03-01
I240438 | 2024-01-09 | Lahore | Chinar Bagh Lahore | Rehman Garden-2 Pk-3 | 1118 | 447.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 447.2 | 8092254.3293 | 8092254.3293 | 0 | -1 |  | 0.4 | 1210.95 | 7401 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46113 | Apr-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240438 | 2026-04-01
I240438 | 2024-01-09 | Lahore | Chinar Bagh Lahore | Rehman Garden-2 Pk-4 | 824 | 329.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 329.6 | 12061812.3127 | 12061812.3127 | 0 | -0.5 |  | 0.4 | 2740.45 | 10671 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 61 | 62 | 14 | Yet to Start | 46143 | May-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 | 1 |  |  |  | I240438 | 2026-05-01
I240438 | 2024-01-09 | Lahore | Chinar Bagh Lahore | Rehman Garden-2 Pk-5 | 1320 | 528 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 528 | 19981192.246 | 19981192.246 | 0 | -1 |  | 0.4 | 4956.5 | 17536.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 61 | 62 | 14 | Yet to Start | 46143 | May-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240438 | 2026-05-01
I240438 | 2024-01-09 | Lahore | Chinar Bagh Lahore | Rehman Garden-2 Pk-6 | 984 | 393.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 393.6 | 11355424.3333 | 11355424.3333 | 0 | -0.5 |  | 0.4 | 2208 | 10990.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 | 1 |  |  |  | I240438 | 2026-06-01
I240438 | 2024-01-09 | Lahore | Chinar Bagh Lahore | Rehman Garden-2 Pk-7 | 846 | 338.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 338.4 | 16077278.3667 | 16077278.3667 | 0 | -1 |  | 0.4 | 3448.85 | 14593.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240438 | 2026-06-01
I240438 | 2024-01-09 | Lahore | Chinar Bagh Lahore | Rehman Garden-2 Pk-8 | 944 | 377.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 377.6 | 9419404.5167 | 9419404.5167 | 0 | -0.85 |  | 0.4 | 1698.55 | 8317.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 46204 | Jul-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240438 | 2026-07-01
I250206 | 2024-09-12 | Daska | Daska | Rehmanpura | 652 | 260.8 |  |  |  |  | NOT ENERGISED AS YET | SWAPPED | 0% | 260.8 | 6639116.496 | 0 | 6639116.496 | -1 |  | 0.4 | 1094.8 | 6366 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Meraj Housing | Swap Cases | SWAPPED |  |  | Meraj Housing | 22604832.2609 | 542 | I250206 | Timeline not applicable
I240679 | 2024-05-16 | Sargodha | Sargodha | Rehmanpura | 1800 | 720 |  |  |  |  | Live | LIVE - 100% Completed | 100% | 720 | 2327996.5 | 349199.475 | 1978797.025 | -1 |  | 0.4 | 0 | 5818 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240679 | Timeline not applicable
I240680 | 2024-05-16 | Rahim Yar Khan | RahimYar Khan Ph2 | Rehmat Colony | 1620 | 648 | Not Live | 0 |  |  | Not Live | REMOVE BUDGET (T) | 0% | 648 | 12850226.618 | 0 | 12850226.618 | -0.5 |  | 0.4 | 1338.6667 | 11266.25 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 4 Months | Jun-2026 | 2026-07-01 | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | I240680 | 2026-06-01
I250210 | 2024-09-14 | Sargodha | Sargodha | Remount Depot | 206 | 82.4 |  |  |  |  | Not Live | SWAPPED | 0% | 82.4 | 13163801.0798 | 0 | 13163801.0798 | -0.85 |  | 0.4 | 3986.2481 | 6688.1052 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Grand A-1 City | Swap Cases | SWAPPED |  |  | Grand A-1 City | 9854031.3448 | 252 | I250210 | Timeline not applicable
INT-23-00447 | 2022-12-29 | Peshawar | Peshawar Misc Areas | Ring Road P01 | 2236 | 1118 | 2072 | 1050 | 390 | 632 |  | LIVE - 100% Completed | 100% | 1118 | 15617686.1744 | 2342652.9262 | 13275033.2482 | -1 |  | 0.5 | 3525.9 | 8270.1549 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00447 | Timeline not applicable
I240539 | 2024-02-28 | Swat | Swat Ph2 | River Area_Hayatabad | 1394 | 557.6 | 373 | 301 | 29 | 43 |  | LIVE - 100% Completed | 100% | 557.6 | 18563418.5396 | 2784512.7809 | 15778905.7586 | -0.85 |  | 0.4 | 1500.1389 | 16850.1386 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240539 | Timeline not applicable
I240678 | 2024-05-16 | Sialkot | Sialkot | Rizwan Colony Deen Pura | 170 | 68 |  | 0 | 0 | 0 | Not Lived Yet | LIVE - 100% Completed | 100% | 68 | 1076980.3621 | 161547.0543 | 915433.3078 | -1 |  | 0.4 | 72.6 | 661.7908 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Khayaban-e-Nawab | 562 | 224.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 224.8 | 7222952.4898 | 7222952.4898 |  | -0.85 |  |  | 1675.2289 | 7307.9889 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Roras Road | 1092 | 436.8 |  | 0 | 2 | 72 | Recently Lived | LIVE - 100% Completed | 100% | 436.8 | 15748870.67 | 2362330.6005 | 13386540.0695 | -1 |  | 0.4 | 2293.5 | 10022.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
I240518 | 2024-02-27 | Islamabad | Naval Anchorage and other Areas (ISB) | Roshan Pakistan | 1180 | 590 | 254 | 11 | 28 | 215 |  | LIVE - 100% Completed | 100% | 590 | 27408756.8855 | 4111313.5328 | 23297443.3527 | 0 |  | 0.5 | 12853.3625 | 10262.826 | Buried | 15% | Not Live |  | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240518 | Timeline not applicable
I250202 | 2024-09-13 | Haripur | Haripur Hazara | Roshan_Noor ext._Madina_Uni | 680 | 272 | 130 | 88 | 24 | 18 |  | LIVE - 100% Completed | 100% | 272 | 4720088.1016 | 708013.2152 | 4012074.8863 | -1 |  | 0.4 | 0 | 11096.8257 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250202 | Timeline not applicable
I240538 | 2024-02-29 | Haripur | Haripur Ph2 | Roshanabad | 208 | 83.2 | 64 | 55 | 6 | 3 |  | LIVE - 100% Completed | 100% | 83.2 | 5488594.86 | 823289.229 | 4665305.631 | -1 |  | 0.4 | 1695.1 | 3171.4835 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240538 | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Manik Road Mohala Hussainabad | 524 | 209.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 209.6 | 5424268.1106 | 5424268.1106 |  | -1 |  |  | 1016.6 | 5418.1626 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560606 | No Initiation Date | Narowal | Narowal | MOh Bijli Ghar | 970 | 388 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 388 | 11387051.8 | 11387051.8 |  | -0.85 |  |  | 2463.3 | 12220 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560606 | No Initiation Date | Narowal | Narowal | Moh Meera Shah Hussain | 4458 | 1783.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1783.2 | 24962668.204 | 24962668.204 |  | -1 |  |  | 3259.1 | 28918.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240704 | 2024-05-15 | Multan | Multan Ph3 | Royal Residencia | 614 | 245.6 | 54 | 3 | 9 | 42 |  | LIVE - 100% Completed | 100% | 245.6 | 9757149.1851 | 1463572.3778 | 8293576.8073 | 0 |  | 0.4 | 2955.73 | 5219.6475 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Royal Villas EXT. | 298 | 119.2 |  | 13 | 27 | 132 | Occupancy : 300 | LIVE - 100% Completed | 100% | 119.2 | 9251729.783 | 1387759.4674 | 7863970.3155 | -1 |  | 0.4 | 3829.3511 | 2704.4455 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 2 |  |  |  | I240682 | Timeline not applicable
INT-23-00440 | 2022-12-29 | Sargodha | Sargodha | RPO Office TO Session Court Roa | 252 | 126 | 124 | 18 |  | 103 |  | LIVE - 100% Completed | 100% | 126 | 2038258.5775 | 305738.7866 | 1732519.7909 | -0.8075 |  | 0.5 | 371.45 | 2693.6 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | This Area will be converted to Hybrid Model | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00440 | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Mohala Hajver Nagar Open Area | 762 | 304.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 304.8 | 8949238.1 | 8949238.1 |  | -0.85 |  |  | 2068.85 | 9433.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250210 | 2024-09-14 | Sargodha | Sargodha | Sabar Wall Colony | 1662 | 664.8 |  |  |  |  | Not Live | NOT LIVE - RETAIN BUDGET | 70% | 664.8 | 15887336.15 | 6434371.1408 | 9452965.0093 | -1 |  | 0.4 | 2400.05 | 13385 | Hybrid | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Only Cable Pulling Pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250210 | 2026-04-01
I240681 | 2024-05-16 | Quetta | Quetta | Sabzal Road | 800 | 320 | 0 | 0 | 0 | 0 |  | NOT LIVE - RETAIN BUDGET | 50% | 320 | 4836175 | 2780800.625 | 2055374.375 | -0.85 |  | 0.4 | 2500 | 2875 | Hybrid | 50% | NOT LIVE |  | 50% | 0.5 | 2026-03-01 | 92 | 93 | 45 | In Progress | May-June | Jun-2026 | Permission issues | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240681 | 2026-06-01
I260296 | No Initiation Date | Sukkur | Sukkur | Sachal Township_Kings Crystal | 1864 | 745.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 50% |  | 12254249.1767 | 7046193.2766 |  |  |  |  | 1459.35 | 15764.4846 | Hybrid | 50% | NOT LIVE |  | 50% | 0.5 | 2026-03-01 | 92 | 93 | 45 | In Progress | 3 months | Jun-2026 | Work in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Sadabad Society | 348 | 139.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 139.2 | 6777562.4437 | 6777562.4437 | 0 | -1 |  | 0.4 | 1192.757 | 3965.2706 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46113 | Apr-2026 | Map given for ROW permission | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240705 | 2026-04-01
UI2560606 | No Initiation Date | Narowal | Narowal | Mushtaq Town | 1750 | 700 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 700 | 9830358.5965 | 9830358.5965 |  | -1 |  |  | 1367.787 | 9602.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240704 | 2024-05-15 | Multan | Multan Ph3 | Sadiqabad latifabad Wahidabad | 2080 | 832 | 152 | 9 | 16 | 127 |  | LIVE - 100% Completed | 100% | 832 | 19519436.9594 | 2927915.5439 | 16591521.4155 | -1 |  | 0.4 | 2682.95 | 16434.1369 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Sadiqabad latifabad Wahidabad | 2080 | 1040 |  |  |  |  | Duplicate Entry | LIVE - 100% Completed | 100% | 1040 | 16056315.0481 | 2408447.2572 | 13647867.7909 | -1 |  | 0.5 | 2682.95 | 16434.1369 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Narowal Bypass to Nawab Town (C | 1356 | 542.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 542.4 | 9456907.646 | 9456907.646 |  | -0.85 |  |  | 1697.4 | 8718.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Saeela | 694 | 277.6 |  |  | Yes |  |  | LIVE - 100% Completed | 100% |  | 4676213.2837 | 701431.9926 |  |  |  | 0.4 | 917.7 | 7554.5 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Done-Replaced by Chak Jamal-Shamspur and their Feeder Connectivity-I250205 | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Safari Garden Phase 1 | 204 | 81.6 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 81.6 | 1896605.9377 | 1896605.9377 |  |  |  |  | 362.25 | 1814.521 | Hybrid | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 months | Jun-2026 | NOC pending by society | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Safari Garden Phase 2 | 308 | 123.2 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 123.2 | 2679026.7 | 2679026.7 |  |  |  |  | 524.4 | 2258.75 | Hybrid | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 months | Jun-2026 | NOC pending by society | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
UI2560606 | No Initiation Date | Narowal | Narowal | Nisari Muhallah & Muslim Town S | 1008 | 403.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 403.2 | 7403364.446 | 7403364.446 |  | -1 |  |  | 1354.7 | 5986.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240701 | 2024-05-16 | Swat | Swat | Saidu Ext | 864 | 345.6 |  |  |  |  | Civil Work in progress | LIVE - 100% Completed | 100% | 345.6 | 3172740 | 475911 | 2696829 | -1 |  | 0.4 | 0 | 8951 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240701 | Timeline not applicable
I240539 | 2024-02-28 | Swat | Swat Ph2 | Saidu Sharif P1 | 568 | 227.2 | 409 | 341 | 31 | 37 |  | LIVE - 100% Completed | 100% | 227.2 | 13559138.7208 | 2033870.8081 | 11525267.9127 | -1 |  | 0.4 | 3152.15 | 10784.9725 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240539 | Timeline not applicable
I240539 | 2024-02-28 | Swat | Swat Ph2 | Saidu Sharif P2 | 818 | 327.2 | 505 | 435 | 39 | 31 |  | LIVE - 100% Completed | 100% | 327.2 | 16505535.0586 | 2475830.2588 | 14029704.7998 | -1 |  | 0.4 | 3414.35 | 12030.4309 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240539 | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Pan peer Road Societies | 1868 | 747.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 747.2 | 11690229.008 | 11690229.008 |  | -0.85 |  |  | 1743.4 | 12648.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Saima Down Town | 436 | 174.4 | 407 | 40 | 162 | 6 | 0 | LIVE - 80% Completed | 80% | 139.52 | 4515036.7912 | 1444811.7732 | 3070225.018 | -1 |  | 0.4 | 0 | 7033.5639 | Buried |  | LIVE | Buried | 80% | 0.8 | 2026-03-01 | 214 | 215 | 167 | In Progress | 6 months | Oct-2026 | Block A and Block B are completely live. Block C is partially live. | Live - As per Plan | LIVE - 80% Completed | 1 | Add 9 count |  |  |  | I240702 | 2026-10-01
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-5G | 282 | 141 | [5 empty] | LIVE - 100% Completed | 100% | 141 | 17875349.8752 | 2681302.4813 | 15194047.3939 | -1 |  | 0.5 | 6597.4504 | 0 | Buried | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00764 | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Pasrur Bypass , City Commercial | 1348 | 539.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 539.2 | 11691326.75 | 11691326.75 |  | -1 |  |  | 2225.25 | 13182.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250207 | 2024-09-12 | Abbottabad | Abbottabad | Salhad | 700 | 280 | not live | not live | not live | not live |  | SWAPPED | 0% | 280 | 13746943.2437 | 0 | 13746943.2437 | -1 |  | 0.4 | 2963.1422 | 19896.0444 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped With Banda Jaat & Iqbal Road | Swap Cases | SWAPPED | budget will be given by ODN |  | Banda Jaat & Iqbal Road | 0 | ? | I250207 | Timeline not applicable
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Salman Gardens | 382 | 152.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 3373988.4876 | 3373988.4876 |  |  |  |  | 541.5 | 2600.354 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250210 | 2024-09-14 | Sargodha | Sargodha | Salman Pura - Saleem Park | 622 | 248.8 |  |  |  |  | Not Live | NOT LIVE - RETAIN BUDGET | 70% | 248.8 | 7805702.1861 | 3161309.3854 | 4644392.8007 | -0.85 |  | 0.4 | 1345.8838 | 5490.2794 | Hybrid | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Only Cable Pulling Pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250210 | 2026-04-01
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Samanabad | 2792 | 1116.8 |  | 280 | 367 | 688 | Occupancy : 2000 | LIVE - 100% Completed | 100% | 1116.8 | 30231048.6212 | 4534657.2932 | 25696391.328 | -0.5 |  | 0.4 | 4263.405 | 19069.1162 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Punjab Housing & NPS | 908 | 363.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 363.2 | 10369565.25 | 10369565.25 |  | -1 |  |  | 2380.5 | 9873.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560606 | No Initiation Date | Narowal | Narowal | Rana Shami Town & Satellite Tow | 420 | 168 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 168 | 5852915.8 | 5852915.8 |  | -1 |  |  | 1531.8 | 4530 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250209 | 2024-09-14 | Rawalpindi | Rawalpindi | Samarzar Housing Society | 1824 | 729.6 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 729.6 | 14597310.504 | 14597310.504 | 0 | -1 |  | 0.4 | 2572.55 | 15725.076 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retian | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250209 | Feedback Awaited
I250206 | 2024-09-12 | Daska | Daska | Sambrial_Road | 256 | 102.4 |  |  |  |  | NOT ENERGISED AS YET | NOT LIVE - RETAIN BUDGET | 0% | 102.4 | 3634440.492 | 3634440.492 | 0 | -1 |  | 0.4 | 1069.5 | 1302.1 | Arial | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | Feedback Awaited
UI2560606 | No Initiation Date | Narowal | Narowal | Sadeeqpura | 296 | 118.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 118.4 | 2696340.0679 | 2696340.0679 |  | -1 |  |  | 451.4911 | 3265.5209 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250209 | 2024-09-14 | Rawalpindi | Rawalpindi | Sanobar City | 1454 | 581.6 | 0 |  |  |  |  | SWAPPED | 0% | 581.6 | 11170103.204 | 0 | 11170103.204 | -0.5 |  | 0.4 | 1561.7 | 12560.364 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with G-16 developed part only | Swap Cases | SWAPPED |  |  | G-16 developed part only | 54483572 | 1606 | I250209 | Timeline not applicable
I250202 | 2024-09-13 | Haripur | Haripur Hazara | Sarai Saleh | 714 | 285.6 | Dev In progress | 0 | 0 | 0 |  | NOT LIVE - RETAIN BUDGET | 25% | 285.6 | 14200357.9861 | 11182781.914 | 3017576.072 | -1 |  | 0.4 | 3499.2722 | 13869.6742 | Hybrid | 25% | NOT LIVE |  | 25% | 0.25 | 2026-03-01 | 61 | 62 | 14 | In Progress | 2 Months | May-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250202 | 2026-05-01
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Sarfaraz Colony | 242 | 96.8 | 150 | 135 |  |  |  | LIVE - 100% Completed | 100% | 96.8 | 1291096.7832 | 193664.5175 | 1097432.2657 | 0 |  | 0.4 | 0 | 1547.9114 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | This area lived in aerial before plan and sales team no need to extend further area. | Live - Permission Awaited | LIVE - 100% Completed | [5 empty] | I240702 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Satellite Town | 1610 | 644 |  | 90 | 81 | 203 | Occupancy : 1000 | LIVE - 100% Completed | 100% | 644 | 17696339.4056 | 2654450.9108 | 15041888.4947 | -1 |  | 0.4 | 2277 | 12828.6641 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Samanabad-College Area | 3420 | 1368 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 1368 | 26622703.168 | 26622703.168 |  | -1 |  |  | 4107.8 | 34718.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560606 | No Initiation Date | Feeders/Transportations | Narowal | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3350000 | 3350000 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
UI2560606 | No Initiation Date | Narowal | Narowal | Usman Trade City | 368 | 147.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 147.2 | 4585306.2 | 4585306.2 |  | -1 |  |  | 1055.7 | 3543.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
111 | No Initiation Date | Rawalpindi | PAF Base Chaklala | PAF Base Chaklala | 2830 | 1132 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 1132 | 16500000 | 16500000 |  | -1 |  | 0.4 | 0 | 0 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
111 | No Initiation Date | Feeders/Transportations | Rawalpindi | Feeder | [7 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
111 | No Initiation Date | Feeders/Transportations | Rawalpindi | Transportation | [7 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Sayyam City | 376 | 150.4 | 8 | 0 | 0 | 8 |  | LIVE - 100% Completed | 100% | 150.4 | 5908729 | 886309.35 | 5022419.65 | -0.7 |  | 0.4 | 1111.05 | 4000.5 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Aerial plan demanded by MTN Team | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Scheme33_MalirCantt_MDU_P01 | 2356 | 942.4 | [5 empty] | LIVE - 100% Completed | 100% | 942.4 | 9461121.5093 | 1419168.2264 | 8041953.2829 | #DIV/0! |  | 0.4 | 0 | 2952.9081 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Scheme33_MalirCantt_MDU_P02 | 1320 | 528 | [5 empty] | LIVE - 100% Completed | 100% | 528 | 4123164.1164 | 618474.6175 | 3504689.4989 | -0.85 |  | 0.4 | 0 | 684.199 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Scheme33_MalirCantt_MDU_P03 | 1238 | 495.2 | [5 empty] | LIVE - 100% Completed | 100% | 495.2 | 4096156.0384 | 614423.4058 | 3481732.6326 | -1 |  | 0.4 | 0 | 979.8702 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Scheme33_MalirCantt_MDU_P04 | 1104 | 441.6 | [5 empty] | LIVE - 100% Completed | 100% | 441.6 | 3744371.1637 | 561655.6746 | 3182715.4891 | -0.85 |  | 0.4 | 0 | 1071.6941 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I250380 | 2024-11-27 | Karachi | Gulshan-e-Maymar | Sector P, U, V & SPECHS | 1262 | 504.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 75% | 504.8 | 31592476.3012 | 11452272.6592 | 20140203.642 | #DIV/0! |  | 0.4 | 20271.6239 | 14201.9828 | Hybrid | 75% | NOT LIVE |  | 75% | 0.75 | 2026-03-01 | 31 | 32 | -16 | In Progress | April | Apr-2026 | Civil Work Completion | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250380 | 2026-04-01
I250380 | 2024-11-27 | Karachi | Gulshan-e-Maymar | Sector Q | 204 | 81.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 81.6 | 18083814.5305 | 4249696.4147 | 13834118.1158 | #DIV/0! |  | 0.4 | 12444.9719 | 9031.1945 | Hybrid | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 31 | 32 | -16 | In Progress | Mar | Apr-2026 | Civil Work Completion | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250380 | 2026-04-01
I250380 | 2024-11-27 | Karachi | Gulshan-e-Maymar | Sector R | 1036 | 414.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 100% | 414.4 | 27786838.8441 | 4168025.8266 | 23618813.0175 | -0.5 |  | 0.4 | 16985.7069 | 12051.1698 | Hybrid | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 31 | 32 | -16 | Completed | Feb-Mar | Apr-2026 | Live to be confirmed by BuH | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250380 | 2026-04-01
I250380 | 2024-11-27 | Karachi | Gulshan-e-Maymar | Sector S | 172 | 68.8 | [5 empty] | LIVE - 100% Completed | 100% | 68.8 | 17725416.4429 | 2658812.4664 | 15066603.9765 | -1 |  | 0.4 | 12528.1334 | 9615.5656 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250380 | Timeline not applicable
I250380 | 2024-11-27 | Karachi | Gulshan-e-Maymar | Sector T | 382 | 152.8 | [5 empty] | LIVE - 100% Completed | 100% | 152.8 | 19435334.9674 | 2915300.2451 | 16520034.7223 | -0.85 |  | 0.4 | 13157.8485 | 9605.4158 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250380 | Timeline not applicable
I250380 | 2024-11-27 | Karachi | Gulshan-e-Maymar | Sector W, ZA & Colonies | 1912 | 764.8 | [5 empty] | LIVE - 100% Completed | 100% | 764.8 | 43136395.1716 | 6470459.2757 | 36665935.8959 | -1 |  | 0.4 | 27575.9111 | 19475.0562 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250380 | Timeline not applicable
I250380 | 2024-11-27 | Karachi | Gulshan-e-Maymar | Sector X | 2072 | 828.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 100% | 828.8 | 46800166.8864 | 7020025.033 | 39780141.8534 | -0.85 |  | 0.4 | 29373.9454 | 21235.1936 | Hybrid | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 31 | 32 | -16 | Completed | Feb-Mar | Apr-2026 | Live to be confirmed by BuH | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250380 | 2026-04-01
I250380 | 2024-11-27 | Karachi | Gulshan-e-Maymar | Sector Y | 598 | 239.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 100% | 239.2 | 21692841.6113 | 3253926.2417 | 18438915.3696 | -1 |  | 0.4 | 13358.7734 | 9143.1922 | Hybrid | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 31 | 32 | -16 | Completed | Mar | Apr-2026 | Live to be confirmed by BuH | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250380 | 2026-04-01
I250380 | 2024-11-27 | Karachi | Gulshan-e-Maymar | Sector Z | 1644 | 657.6 | [5 empty] | LIVE - 100% Completed | 100% | 657.6 | 38022819.242 | 5703422.8863 | 32319396.3557 | -0.2125 |  | 0.4 | 23044.7459 | 16281.0263 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250380 | Timeline not applicable
INT-23-00440 | 2022-12-29 | Sargodha | Sargodha | SGD Bhalwal Road TO Fatima Jinn | 586 | 293 | 75 | 11 |  | 64 | Live | LIVE - 100% Completed | 100% | 293 | 5496689.8125 | 824503.4719 | 4672186.3406 | -1 |  | 0.5 | 888.95 | 8898.4 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | This Area will be converted to Hybrid Model | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00440 | Timeline not applicable
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Abid Colony | 474 | 189.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 189.6 | 4072745.3242 | 4072745.3242 |  | -1 |  |  | 688.1132 | 4686.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250212 | 2024-09-14 | Swat | Mingora | Shagai & Akhon Baba P01 | 818 | 327.2 |  |  |  |  | Civil Work in progress | NOT LIVE - RETAIN BUDGET | 0% | 327.2 | 11134439.1751 | 11134439.1751 | 0 | -1 |  | 0.4 | 1772.1 | 19794.3191 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250212 | 2026-06-01
I250212 | 2024-09-14 | Swat | Mingora | Shagai & Akhon Baba P02 | 704 | 281.6 |  |  |  |  | Civil Work in progress | NOT LIVE - RETAIN BUDGET | 80% | 281.6 | 9540068.5919 | 3052821.9494 | 6487246.6425 | -0.5 |  | 0.4 | 1897.5 | 11617.1774 | Hybrid | 80% | NOT LIVE |  | 80% | 0.8 | 2026-03-01 | 122 | 123 | 75 | In Progress | 3 Months | Jul-2026 | Civil Work Completion | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250212 | 2026-07-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Ajmal Town,Faisal Town | 1160 | 464 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 464 | 8751089.8015 | 8751089.8015 |  | 0 |  |  | 1174.1012 | 14981.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00436 | 2022-12-29 | Hyderabad | Hyderabad Misc Areas | Shah Nawaz Grand City | 186 | 74.4 | 323 | 127 | 78 | 13 | 0 | LIVE - 100% Completed | 100% | 74.4 | 2714981.4828 | 407247.2224 | 2307734.2604 | -1 |  | 0.4 | 908.16 | 1489.6697 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00436 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Shahabpura | 946 | 378.4 |  |  |  |  | NOT ENERGISED AS YET | NOT LIVE - RETAIN BUDGET | 0% | 378.4 | 9237891.614 | 9237891.614 | 0 | -0.85 |  | 0.4 | 1624.95 | 8110.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 61 | 62 | 14 | Yet to Start | 46143 | May-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-05-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Shahabpura Main Rd | 440 | 176 |  | 0 | 0 | 0 | Not Lived Yet | LIVE - 100% Completed | 100% | 176 | 3513900.9229 | 527085.1384 | 2986815.7845 | -1 |  | 0.4 | 216.7 | 3863.1726 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Shahdara & Habib Colony | 1746 | 698.4 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 698.4 | 9089171.8668 | 9089171.8668 |  |  |  |  | 1331.5378 | 8869.3955 | Hybrid | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 months | Jun-2026 | BDA NOC pending | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Akbar Town & Laghari Colony | 902 | 360.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 360.8 | 6847319.0922 | 6847319.0922 |  | -1 |  |  | 1104.2564 | 8306.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Al Haram City, Hamza City Overs | 378 | 151.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 151.2 | 5272626.4923 | 5272626.4923 |  | -0.85 |  |  | 1122.1262 | 5936.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Shalimar Town | 598 | 239.2 | [5 empty] | LIVE - 100% Completed | 100% | 239.2 | 10984948.1584 | 1647742.2238 | 9337205.9346 | -0.85 |  | 0.4 | 6222.1047 | 6763.1573 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Al Hassan, Jamal City, Al Noor | 460 | 184 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 184 | 7794242.0845 | 7794242.0845 |  | -1 |  |  | 2212.5585 | 5807.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250205 | 2024-09-12 | Jhelum | Jhelum Ph2 | Shamas Pur | 198 | 79.2 |  |  | Yes |  |  | SWAPPED | 0% | 79.2 | 2131177.996 | 0 | 2131177.996 | -0.85 |  | 0.4 | 409.4 | 1628.35 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped by Gharmala, Gharmala Monan & Chittan | Swap Cases | SWAPPED |  |  | Gharmala, Gharmala Monan & Chittan | 5811629.0927 | 628 | I250205 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Shamsi Colony | 252 | 126 | 12 | 1 | 1 | 10 |  | LIVE - 100% Completed | 100% | 126 | 9323406.4486 | 1398510.9673 | 7924895.4813 | -0.85 |  | 0.5 | 5204.0979 | 4689.3237 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Shamsi Rd | 462 | 184.8 | 462 | 885 | 707 | 108 | 40 | Shamsi Road | 100% | 184.8 | 3624598.8368 | 543689.8255 | 3080909.0113 | -0.5 |  | 0.4 | 0 | 5402.5186 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240540 | Timeline not applicable
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Shamsi Society | 1744 | 697.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 17108465.7763 | 17108465.7763 |  |  |  |  | 3376.23 | 10962.2851 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | Sharifabad | 300 | 120 | 300 |  |  |  |  | On Hold due to Low Potential | 0% | 120 | 2549522 | 0 | 2549522 | -1 |  | 0.4 | 0 | 4016.95 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I240540 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Shehzad Colony | 414 | 165.6 |  | 8 | 8 | 44 | Occupancy : 200 | LIVE - 100% Completed | 100% | 165.6 | 5814364.5793 | 872154.6869 | 4942209.8924 | -0.765 |  | 0.4 | 1162.88 | 4741.9408 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
I250211 | 2024-09-14 | Okara | Okara | Sher Rabbani Town & Ghaziabad | 1710 | 684 | 52 | 2 |  | 50 |  | LIVE - 100% Completed | 100% | 684 | 16231430 | 2434714.5 | 13796715.5 | -0.5 |  | 0.4 | 3085.5 | 16032.65 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250211 | Timeline not applicable
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-6 Sec 01 | 566 | 283 | [5 empty] | LIVE - 100% Completed | 100% | 283 | 13191286.1125 | 1978692.9169 | 11212593.1956 | -0.85 |  | 0.5 | 9319.27 | 10196.2 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed |  | 1 |  |  |  | INT-23-00764 | Timeline not applicable
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | SHFT Pocket-1 | 658 | 263.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 6004577.2636 | 6004577.2636 |  |  |  |  | 915.7447 | 5269.5908 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | SHFT Pocket-2 | 1814 | 725.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 15570489.25 | 15570489.25 |  |  |  |  | 2498.1 | 11275 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | SHFT Pocket-3 | 1438 | 575.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 13171602.75 | 13171602.75 |  |  |  |  | 1886.5 | 9125 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | SHFT Pocket-4 | 810 | 324 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 11834428.25 | 11834428.25 |  |  |  |  | 2531.1 | 7196.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | SHFT Pocket-5 | 1628 | 651.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 12786389.5 | 12786389.5 |  |  |  |  | 1995.4 | 10693.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250212 | 2024-09-14 | Swat | Mingora | Shia Bagh & BUH Qambar P01 | 714 | 285.6 | 149 | 139 | 5 | 5 |  | LIVE - 100% Completed | 100% | 285.6 | 5083884.6132 | 762582.692 | 4321301.9212 | -1 |  | 0.4 | 0 | 10671.7919 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I250212 | 2024-09-14 | Swat | Mingora | Shia Bagh & BUH Qambar P02 | 450 | 180 | 81 | 73 | 5 | 3 |  | LIVE - 100% Completed | 100% | 180 | 4128985.6016 | 619347.8402 | 3509637.7613 | -0.85 |  | 0.4 | 0 | 11096.8257 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250212 | Timeline not applicable
I260296 | No Initiation Date | Sukkur | Sukkur | Shikarpur Rd | 1058 | 423.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 80% |  | 16261340.1708 | 5203628.8547 |  |  |  |  | 3277.2 | 19826.2697 | Hybrid | 80% | NOT LIVE |  | 80% | 0.8 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Work in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-5H | 216 | 108 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 108 | 9022078.4424 | 9022078.4424 | 0 | -0.5 |  | 0.5 | 3329.0216 | 0 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | INT-23-00764 | Feedback Awaited
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-5J | 1300 | 650 | [5 empty] | LIVE - 100% Completed | 100% | 650 | 46489873.9889 | 6973481.0983 | 39516392.8906 | -1 |  | 0.5 | 6002.9872 | 0 | Buried | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | live on arial | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00764 | Timeline not applicable
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Ali Tiown & New Ali Town | 348 | 139.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 139.2 | 4464019.1192 | 4464019.1192 |  | -0.85 |  |  | 1013.0709 | 4308.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250378 | 2024-11-25 | Sahiwal | Sahiwal (P2) | Sitara City | 156 | 62.4 | N/A | N/A | N/A |  | Not Live | REMOVE BUDGET (P) | 0% | 62.4 | 1964253.2752 | 0 | 1964253.2752 | #DIV/0! |  | 0.4 | 373.1642 | 1417.7225 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I250378 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Site Area & Shanghai Tower | 270 | 108 | 130 | 50 | 16 | 3 | 0 | LIVE - 100% Completed | 100% | 108 | 4056491.3956 | 608473.7093 | 3448017.6863 | -1 |  | 0.4 | 1087.4865 | 2167.8751 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240702 | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | SKT Rd Pocket 01 | 1660 | 664 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 664 | 14593136.598 | 3429387.1005 | 11163749.4975 | 0 |  | 0.4 | 2226.4 | 15960 | Hybrid | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 61 | 62 | 14 | In Progress | 46082 | May-2026 | Civil Work Completion | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240700 | 2026-05-01
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | SKT Rd Pocket 02 | 3386 | 1354.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 1354.4 | 32721681.118 | 7689595.0627 | 25032086.0553 | -1 |  | 0.4 | 5982.3 | 29562.5 | Hybrid | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46082 | Mar-2026 | Civil Work Completion | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240700 | 2026-03-01
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | SKT Rd Pocket 03 | 986 | 394.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 394.4 | 12359571.496 | 2904499.3016 | 9455072.1944 | 0 |  | 0.4 | 2363.25 | 10466.25 | Hybrid | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 61 | 62 | 14 | In Progress | 46082 | May-2026 | Civil Work Completion | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240700 | 2026-05-01
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | SKT Rd Pocket 04 | 750 | 300 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 300 | 10382748.246 | 2439945.8378 | 7942802.4082 | -1 |  | 0.4 | 2145.9 | 7012.5 | Hybrid | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46082 | Mar-2026 | Civil Work Completion | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240700 | 2026-03-01
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | SKT Rd Pocket 05 | 424 | 169.6 | [5 empty] | LIVE - 100% Completed | 100% | 169.6 | 5782795.25 | 867419.2875 | 4915375.9625 | 0 |  | 0.4 | 1124.7 | 5171.25 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Small Industrial Estate | 700 | 280 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 280 | 4615233.6846 | 4615233.6846 |  |  |  |  | 545.5825 | 7146.969 | Hybrid | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 months | Jun-2026 | NOC pending by society | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
INT-23-00435 | 2022-12-29 | Karachi | Karachi Misc Areas | Soomra Society | 548 | 274 | [5 empty] | LIVE - 100% Completed | 100% | 274 | 11653658.764 | 1748048.8146 | 9905609.9494 | 0 |  | 0.5 | 3359.4734 | 7242.8053 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00435 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | SSGC Housing | 370 | 148 | 498 | 40 | 10 | 1 | 0 | LIVE - 100% Completed | 100% | 148 | 5068113.0159 | 760216.9524 | 4307896.0635 | -1 |  | 0.4 | 978.351 | 3380.3917 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | done as per plan | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240702 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | State and Middle Town | 934 | 373.6 |  |  |  | 31 |  | LIVE - 100% Completed | 100% | 373.6 | 7919523.892 | 1187928.5838 |  |  |  |  | 1441.6 | 7272.9806 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | #N/A | Timeline not applicable
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Allama Iqbal Town, Aslam Town, | 1924 | 769.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 769.6 | 11165262.9539 | 11165262.9539 |  | -1 |  |  | 1205.2201 | 20005 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Amir Canal View, Canal Residenc | 262 | 104.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 104.8 | 3341392.845 | 3341392.845 |  | -0.85 |  |  | 714.7483 | 3283.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Sui Gas Road | 5620 | 2248 | [5 empty] | LIVE - 100% Completed | 100% | 2248 | 44198001.75 | 6629700.2625 | 37568301.4875 | -1 |  | 0.4 | 5346.35 | 41305 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Sui Gas Road Pk1 | 3292 | 1316.8 | [5 empty] | LIVE - 100% Completed | 100% | 1316.8 | 19311505.0673 | 2896725.7601 | 16414779.3072 | -1 |  | 0.4 | 6153.04 | 21387.2582 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Sui Gas Road Pk2 | 1706 | 682.4 | [5 empty] | LIVE - 100% Completed | 100% | 682.4 | 15218766.4574 | 2282814.9686 | 12935951.4888 | -0.85 |  | 0.4 | 6565.41 | 13851.4086 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Arif Town, Shahzad Colony | 1478 | 591.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 591.2 | 12384519.9748 | 12384519.9748 |  | -1 |  |  | 2283.6572 | 14563.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260296 | No Initiation Date | Sukkur | Sukkur | Sukkur Ind Area | 350 | 140 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 11770055.9292 | 11770055.9292 |  |  |  |  | 2834.75 | 13112.713 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 months | Jun-2026 | Not started yet | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I260296 | No Initiation Date | Sukkur | Sukkur | Sukkur Township P-2_KingCrystl2 | 1516 | 606.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 50% |  | 7990896.3184 | 4594765.3831 |  |  |  |  | 667.7 | 9542.9276 | Hybrid | 50% | NOT LIVE |  | 50% | 0.5 | 2026-03-01 | 92 | 93 | 45 | In Progress | 3 months | Jun-2026 | Work in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I260296 | No Initiation Date | Sukkur | Sukkur | Sukkur Township Pocket 1 | 2046 | 818.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 10% |  | 12123929.355 | 11093395.3598 |  |  |  |  | 789.935 | 14829.9598 | Hybrid | 10% | NOT LIVE |  | 10% | 0.1 | 2026-03-01 | 92 | 93 | 45 | In Progress | 3 months | Jun-2026 | Work in Progress | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Awan Housing Society | 272 | 108.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 108.8 | 3495322.8978 | 3495322.8978 |  | -0.85 |  |  | 723.6103 | 4517.1 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Azizabad | 508 | 203.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 203.2 | 3972112.1 | 3972112.1 |  | -1 |  |  | 481.85 | 5012.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00437 | 2022-12-29 | Lahore | Lahore Misc Areas | Sultan Town | 494 | 247 | [5 empty] | LIVE - 100% Completed | 100% | 247 | 6033905.157 | 905085.7735 | 5128819.3834 | -0.51 |  | 0.5 | 1380.5924 | 4947.8223 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00437 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Sum Sum Tower | 384 | 153.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 153.6 | 2418004.947 | 2418004.947 | 0 | -1 |  | 0.4 | 380.5489 | 728.653 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 46204 | Jul-2026 | Permission Issue | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I240705 | 2026-07-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Canal View | 168 | 67.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 67.2 | 2728584.1847 | 2728584.1847 |  | -0.85 |  |  | 627.9895 | 2632.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | Surti_Humaira_Jami | 1516 | 606.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 12216807.595 | 12216807.595 |  |  |  |  | 1971.42 | 12424.9077 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Cheema Town, Permi Town | 766 | 306.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 306.4 | 6990484.9012 | 6990484.9012 |  | -1 |  |  | 1203.4823 | 8656.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240538 | 2024-02-29 | Haripur | Haripur Ph2 | T & T Colony | 726 | 290.4 | Dropped | 0 | 0 | 0 |  | REMOVE BUDGET (P) | 0% | 290.4 | 12519929.4645 | 0 | 12519929.4645 | -0.5 |  | 0.4 | 3094.65 | 12442.0131 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I240538 | Timeline not applicable
I250734 | No Initiation Date | Bahawalpur | Bahwalpur (P2)-B | Taha Town | 428 | 171.2 | Not Live Yet |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 171.2 | 3779141.6265 | 3779141.6265 |  |  |  |  | 731.5378 | 2773.7472 | Hybrid | 0% | Not Live |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 months | Jun-2026 | NOC pending by society | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
INT-23-00447 | 2022-12-29 | Peshawar | Peshawar Misc Areas | Tajabad P01 | 1262 | 631 | 11 | 5 | 5 | 1 | P,1 Tajj Abad Street ,1,2,3,4,5,6,7,8 Till Bord bazar Bridge | LIVE - 100% Completed | 100% | 631 | 15176910.21 | 2276536.5315 | 12900373.6785 | -1 |  | 0.5 | 2910.65 | 17379.3085 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00447 | Timeline not applicable
INT-23-00447 | 2022-12-29 | Peshawar | Peshawar Misc Areas | Tajabad P02 | 500 | 250 |  |  |  |  | P,2 Tajj Abad Street ,1,2,3,4, | NOT LIVE - RETAIN BUDGET | 0% | 250 | 6487992.91 | 6487992.91 | 0 | -1 |  | 0.5 | 1413.35 | 5902.254 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 122 | 123 | 75 | Yet to Start | 4 Months | Jul-2026 | Permission issue /Need to retain | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | INT-23-00447 | 2026-07-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Chief Residencia Housing Societ | 258 | 103.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 103.2 | 6097056.7846 | 6097056.7846 |  | -0.85 |  |  | 1622.7504 | 4503.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250208 | 2024-09-14 | Wahh | Wah Cantt | Tameer e Hayat Colony | 716 | 286.4 | 0 |  |  |  |  | REMOVE BUDGET (P) | 0% | 286.4 | 5951202.724 | 0 | 5951202.724 | -0.85 |  | 0.4 | 1017.75 | 5530.474 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I250208 | Timeline not applicable
I240700 | 2024-05-15 | Gujranwala | Gujranwala Ph3 | Tanveer Town & Ratta Rd | 1692 | 676.8 | [5 empty] | LIVE - 100% Completed | 100% | 676.8 | 20271848.75 | 3040777.3125 | 17231071.4375 | -0.85 |  | 0.4 | 3601.8 | 16003.75 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240700 | Timeline not applicable
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Commercial Area, Kothi Mohallah | 1296 | 518.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 518.4 | 13461119.1502 | 13461119.1502 |  | -1 |  |  | 2416.5986 | 17768.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260105 | No Initiation Date | Lahore | Al Hafeez Garden & Tariq Garden | Tariq Garden | 1498 | 599.2 | [5 empty] | REMOVE BUDGET (P) | 0% |  | 37367326.2798 | 0 |  |  |  |  | 18395 | 14267.5 | Buried | 100% | Not Live |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | need to remove--Permission Issue by society end | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | #N/A | Timeline not applicable
I250203 | 2024-09-13 | Gujranwala | Gujranwala | Tariq Garden & Makki Road Area | 970 | 388 | [5 empty] | NOT LIVE - RETAIN BUDGET | 90% | 388 | 9236314.051 | 2170533.802 | 7065780.2491 | -0.85 |  | 0.4 | 1359.6 | 17843.6011 | Hybrid | 90% | NOT LIVE |  | 90% | 0.9 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46082 | Mar-2026 | Civil Work Completion | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250203 | 2026-03-01
I260295 | No Initiation Date | Karachi | Model Town_Sh Faisal_Faisal Cant | TariqBinZayed | 1156 | 462.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 11984167.1091 | 11984167.1091 |  |  |  |  | 2006.3986 | 6954.8022 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 months | Oct-2026 | Not started yet, permission issue | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I260061 | No Initiation Date | Jhelum | Jhelum (P4) | Thatti Gujran & Mughlan | 448 | 179.2 |  |  | Yes |  |  | NOT LIVE - RETAIN BUDGET | 0% |  | 1625589.9159 | 1625589.9159 |  |  |  |  | 0 | 5593.3807 | Arial | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 Months | Jun-2026 | Railway crossing required even on Aerial network | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Faiz Colony | 676 | 270.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 270.4 | 5951423.6045 | 5951423.6045 |  | -0.85 |  |  | 1015.213 | 7630 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Feeders/Transportations | Sadiqabad | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 59647628 | 59647628 |  | -1 |  |  | 19218 | #REF! |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I240538 | 2024-02-29 | Haripur | Haripur Ph2 | TIP Housing | 1214 | 485.6 | 121 | 113 | 1 | 7 |  | LIVE - 100% Completed | 100% | 485.6 | 18232668.045 | 2734900.2068 | 15497767.8383 | -1 |  | 0.4 | 2360.95 | 12552.3745 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240538 | Timeline not applicable
I240678 | 2024-05-16 | Sialkot | Sialkot | Towards Chitti Sheikh | 404 | 161.6 |  | 0 | 0 | 0 | Not Lived Yet | NOT LIVE - RETAIN BUDGET | 70% | 161.6 | 8050523.377 | 3260461.9677 | 4790061.4093 | -1 |  | 0.4 | 2159.8732 | 8485.6173 | Hybrid | 70% | NOT LIVE |  | 70% | 0.7 | 2026-03-01 | 0 | 1 | -47 | In Progress | 46054 | Mar-2026 | Civil work 70% done, rem 30% TBD | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240678 | 2026-03-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Towards Ugoki Mor | 1078 | 431.2 |  | 0 | 0 | 0 | Not Lived Yet | NOT LIVE - RETAIN BUDGET | 0% | 431.2 | 25859974.2556 | 25859974.2556 | 0 | -1 |  | 0.4 | 7387.0555 | 11616.2779 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 0 | 1 | -47 | Yet to Start | 46054 | Mar-2026 | Cable plan pending | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240678 | 2026-03-01
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-6 Sec 02 | 470 | 235 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 235 | 3364308.2472 | 3364308.2472 | 0 | -1 |  | 0.5 | 1078.8614 | 390.0021 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | INT-23-00764 | Feedback Awaited
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-6 Sec 03 | 1040 | 520 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 520 | 6814929.913 | 6814929.913 | 0 | -0.85 |  | 0.5 | 2117.9993 | 589.8668 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 | 1 |  |  |  | INT-23-00764 | Feedback Awaited
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-6 Sec 04 | 936 | 468 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 468 | 6348483.772 | 6348483.772 | 0 | -1 |  | 0.5 | 2072.1516 | 743.9441 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | INT-23-00764 | Feedback Awaited
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-6 Sec 05 | 540 | 270 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 270 | 3256311.3161 | 3256311.3161 | 0 | -1 |  | 0.5 | 1026.8523 | 320.6521 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 | 2 |  |  |  | INT-23-00764 | Feedback Awaited
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-6 Sec 06 | 1080 | 540 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 540 | 6309520.0149 | 6309520.0149 | 0 | -1 |  | 0.5 | 2029.5789 | 665.6933 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | INT-23-00764 | Feedback Awaited
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-6 Sec 07 | 1080 | 540 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 540 | 6492834.1078 | 6492834.1078 | 0 | 0 |  | 0.5 | 2204.7451 | 583.8976 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | INT-23-00764 | Feedback Awaited
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-6 Sec 08 | 1224 | 612 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 612 | 7351292.461 | 7351292.461 | 0 | -1 |  | 0.5 | 2000.7713 | 560.5594 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | INT-23-00764 | Feedback Awaited
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-6 Sec 09 | 1224 | 612 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 612 | 7621697.3073 | 7621697.3073 | 0 | -0.5 |  | 0.5 | 2244.7333 | 485.4446 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | INT-23-00764 | Feedback Awaited
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-6 Sec 10 | 1224 | 612 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 612 | 6933108.5876 | 6933108.5876 | 0 | -1 |  | 0.5 | 1800.829 | 559.0182 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | INT-23-00764 | Feedback Awaited
INT-23-00764 | 2023-06-01 | Karachi | Askari (1-6) Karachi | Askari-6 Sec 11 | 936 | 468 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 468 | 4778406.0854 | 4778406.0854 | 0 | -0.85 |  | 0.5 | 1228.9388 | 389.8874 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start | Not Given By BUH | Feedback Awaited | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | INT-23-00764 | Feedback Awaited
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Gulshen I Azmat, Maqbool City | 332 | 132.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 132.8 | 4961184.7087 | 4961184.7087 |  | -0.85 |  |  | 1054.9918 | 5596.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Gulshen I Iqbal | 178 | 71.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 71.2 | 2442215.8 | 2442215.8 |  | -1 |  |  | 510.6 | 2131.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Haider Colony | 1446 | 578.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 578.4 | 11856018.7503 | 11856018.7503 |  | -0.85 |  |  | 2032.4722 | 15145 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Haq Town | 1116 | 446.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 446.4 | 9914684.4283 | 9914684.4283 |  | -1 |  |  | 1575.9983 | 13145 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Heaven City | 278 | 111.2 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 111.2 | 3575324.5041 | 3575324.5041 |  | -0.85 |  |  | 922.1996 | 3047.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Hussainabad & Ghafoorabad | 1284 | 513.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 513.6 | 12326456.3431 | 12326456.3431 |  | -1 |  |  | 2557.5179 | 14392.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Indus Town | 2010 | 804 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 804 | 7359667.7268 | 7359667.7268 |  | -0.85 |  |  | 898.6913 | 10525.71 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Izhar Enclave,Unknown1,Unknown2 | 362 | 144.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 144.8 | 8398147.4501 | 8398147.4501 |  | -1 |  |  | 2372.5362 | 6106.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Jinnah Town, Mohallah Islampura | 804 | 321.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 321.6 | 8765822.9126 | 8765822.9126 |  | -0.5 |  |  | 1815.1122 | 11152.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Mehar Farid Colony | 1034 | 413.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 413.6 | 8907744.3468 | 8907744.3468 |  | -1 |  |  | 1648.7543 | 10431.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Model Avenue | 644 | 257.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 257.6 | 9143813.7457 | 9143813.7457 |  | #DIV/0! |  |  | 2213.3026 | 11021.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240188 | 2023-09-27 | Feeders/Transportations | Islamabad DHA Ph1 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 900000 | 450000 | 450000 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240188 | Timeline not applicable
I240189 | 2023-09-27 | Feeders/Transportations | Quetta Cantt | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3050000 | 1525000 | 1525000 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240189 | Timeline not applicable
I240190 | 2023-09-27 | Feeders/Transportations | Sialkot Cantt | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 6000000 | 3000000 | 3000000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240190 | Timeline not applicable
I240435 | 2024-01-18 | Feeders/Transportations | Top City Islamabad | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3740000 | 1870000 | 1870000 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240435 | Timeline not applicable
I240437 | 2024-01-18 | Feeders/Transportations | Askari Lahore | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 4275000 | 2137500 | 2137500 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240437 | Timeline not applicable
I240438 | 2024-01-09 | Feeders/Transportations | Chinar Bagh Lahore | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3280000 | 1640000 | 1640000 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240438 | Timeline not applicable
I240440 | 2024-01-19 | Feeders/Transportations | Al Jalil & Al khalil LHE | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3340000 | 1670000 | 1670000 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240440 | Timeline not applicable
I240442 | 2024-01-19 | Feeders/Transportations | Chitral Ph1 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 4250000 | 2125000 | 2125000 | 0 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240442 | Timeline not applicable
I240518 | 2024-02-27 | Feeders/Transportations | Naval Anchorage and other Areas (ISB) | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1590000 | 795000 | 795000 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240518 | Timeline not applicable
I240519 | 2024-02-27 | Feeders/Transportations | Royal Palm & Canal View | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3675000 | 1837500 | 1837500 | -0.85 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240519 | Timeline not applicable
I240537 | 2024-02-29 | Feeders/Transportations | Abbottabad Ph2 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 540000 | 270000 | 270000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET |  | 2 |  |  |  | I240537 | Timeline not applicable
I240538 | 2024-02-29 | Feeders/Transportations | Haripur Ph2 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3960000 | 1980000 | 1980000 | -0.5 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240538 | Timeline not applicable
I240539 | 2024-02-28 | Feeders/Transportations | Swat Ph2 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 810000 | 405000 | 405000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240539 | Timeline not applicable
I240540 | 2024-02-28 | Feeders/Transportations | Mardan Ph2 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3900000 | 1950000 | 1950000 | -0.5 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240540 | Timeline not applicable
I240557 | 2024-03-08 | Feeders/Transportations | Jhelum- Kala Gojran | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 685000 | 342500 | 342500 | -0.85 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240557 | Timeline not applicable
I240678 | 2024-05-16 | Feeders/Transportations | Sialkot | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 7000000 | 3500000 | 3500000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240678 | Timeline not applicable
I240680 | 2024-05-16 | Feeders/Transportations | RahimYar Khan Ph2 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 2200000 | 1100000 | 1100000 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240680 | Timeline not applicable
I240679 | No Initiation Date | Feeders/Transportations | Sargodha | Transportation | [7 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240679 | Timeline not applicable
I240681 | No Initiation Date | Feeders/Transportations | Quetta | Transportation | [7 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240681 | Timeline not applicable
I240682 | 2024-05-16 | Feeders/Transportations | Faisalabad Ph4 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 13515000 | 6757500 | 6757500 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240682 | Timeline not applicable
I240683 | 2024-05-15 | Feeders/Transportations | Okara | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1200000 | 600000 | 600000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240683 | Timeline not applicable
I240684 | 2024-05-16 | Feeders/Transportations | Askari RWP (4-7-10) | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 710000 | 355000 | 355000 | 0 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240684 | Timeline not applicable
I240700 | 2024-05-15 | Feeders/Transportations | Gujranwala Ph3 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 9570000 | 4785000 | 4785000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240700 | Timeline not applicable
I240702 | 2024-05-15 | Feeders/Transportations | Hyderabad | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3880000 | 1940000 | 1940000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240702 | Timeline not applicable
INT-23-00764 | 2023-06-01 | Feeders/Transportations | Askari (1-6) Karachi | Feeder | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 63674960 | 31837480 | 31837480 | -1 |  |  | 17085 |  |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00764 | Timeline not applicable
I240704 | 2024-05-15 | Feeders/Transportations | Multan Ph3 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 6400000 | 3200000 | 3200000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240704 | Timeline not applicable
I240705 | 2024-05-15 | Feeders/Transportations | Karachi Ph5 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 8080000 | 4040000 | 4040000 | -0.85 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240705 | Timeline not applicable
I240782 | No Initiation Date | Feeders/Transportations | Torkhan Border | Transportation | [7 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 | [7 empty] | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I240782 | Timeline not applicable
I250114 | 2024-08-08 | Feeders/Transportations | Bahadurabad (KTTC) | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 655000 | 327500 | 327500 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250114 | Timeline not applicable
I250201 | 2024-09-13 | Feeders/Transportations | ISB DHA Ph4 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 525000 | 262500 | 262500 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET |  | 2 |  |  |  | I250201 | Timeline not applicable
I250202 | 2024-09-13 | Feeders/Transportations | Haripur Hazara | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 810000 | 405000 | 405000 | -0.85 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250202 | Timeline not applicable
I250203 | 2024-09-13 | Feeders/Transportations | Gujranwala | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 450000 | 225000 | 225000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250203 | Timeline not applicable
I250205 | 2024-09-12 | Feeders/Transportations | Jhelum Ph2 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 2100000 | 1050000 | 1050000 | -1 |  |  |  | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250205 | Timeline not applicable
I250206 | 2024-09-12 | Feeders/Transportations | Daska | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 7110000 | 3555000 | 3555000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250206 | Timeline not applicable
I250207 | 2024-09-12 | Feeders/Transportations | Abbottabad | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 990000 | 495000 | 495000 | -0.5 |  |  |  | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250207 | Timeline not applicable
I250208 | 2024-09-14 | Feeders/Transportations | Wah Cantt | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1080000 | 540000 | 540000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250208 | Timeline not applicable
I250209 | 2024-09-14 | Feeders/Transportations | Rawalpindi | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 2610000 | 1305000 | 1305000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250209 | Timeline not applicable
I250210 | 2024-09-14 | Feeders/Transportations | Sargodha | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3980000 | 1990000 | 1990000 | -1 |  |  |  | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250210 | Timeline not applicable
I250211 | 2024-09-14 | Feeders/Transportations | Okara | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1170000 | 585000 | 585000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250211 | Timeline not applicable
I250212 | 2024-09-14 | Feeders/Transportations | Mingora | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 6120000 | 3060000 | 3060000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250212 | Timeline not applicable
I250213 | 2024-09-14 | Feeders/Transportations | Mardan | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1500000 | 750000 | 750000 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250213 | Timeline not applicable
I250298 | 2024-10-17 | Feeders/Transportations | ISB DHA Ph-5 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1125000 | 562500 | 562500 | -0.85 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250298 | Timeline not applicable
I250307 | No Initiation Date | Feeders/Transportations | DHA KHI - Common Corridor Project | Transportation | [7 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250307 | Timeline not applicable
I250326 | 2024-11-05 | Feeders/Transportations | Askari Multan | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 540000 | 270000 | 270000 | -0.85 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250326 | Timeline not applicable
I250327 | 2024-11-05 | Feeders/Transportations | Islamabad | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 8075000 | 4037500 | 4037500 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250327 | Timeline not applicable
I250374 | No Initiation Date | Feeders/Transportations | Faisalabad | Transportation | [7 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250374 | Timeline not applicable
I250375 | 2024-11-25 | Feeders/Transportations | Bahawalpur (P3) | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 750000 | 375000 | 375000 | -0.765 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250375 | Timeline not applicable
I250376 | 2024-11-25 | Feeders/Transportations | Islamabad Ph3 (P2) | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3062500 | 1531250 | 1531250 | -0.85 |  |  |  | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250376 | Timeline not applicable
I250377 | 2024-11-25 | Feeders/Transportations | Peshawar (P2) | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 4775000 | 2387500 | 2387500 | #DIV/0! | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250377 | Timeline not applicable
I250378 | 2024-11-25 | Feeders/Transportations | Sahiwal (P2) | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 750000 | 375000 | 375000 | #DIV/0! |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250378 | Timeline not applicable
I250379 | 2024-11-25 | Feeders/Transportations | Wahh Estate | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 600000 | 300000 | 300000 | #DIV/0! |  |  |  | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250379 | Timeline not applicable
I250380 | 2024-11-27 | Feeders/Transportations | Gulshan-e-Maymar | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 | 0 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250380 | Timeline not applicable
I250681 | 2025-03-26 | Feeders/Transportations | CTC Lahore | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 540000 | 270000 | 270000 | -0.5 |  |  |  | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET |  | 2 |  |  |  | I250681 | Timeline not applicable
I250734 | No Initiation Date | Feeders/Transportations | Bahwalpur (P2)-B | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 4025000 | 4025000 |  | -1 |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I250737 | 2025-04-16 | Feeders/Transportations | ISB-BT-Ph-8 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1620000 | 810000 | 810000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I250737 | Timeline not applicable
I260060 | No Initiation Date | Feeders/Transportations | DHA Gujranwala | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 90000 | 90000 |  | 0 |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260061 | No Initiation Date | Feeders/Transportations | Jhelum (P4) | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1300000 | 1300000 |  | -0.85 |  |  | 0 |  |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260068 | 2025-07-17 | Feeders/Transportations | DHA PH 1-5 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1895000 | 947500 | 1326500 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET |  | 2 |  |  |  | I260068 | Timeline not applicable
I260068 | 2025-07-17 | Feeders/Transportations | DHA PH 7-8 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 0 | 0 | 0 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | I260068 | Timeline not applicable
I260105 | No Initiation Date | Feeders/Transportations | Al Hafeez Garden & Tariq Garden | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 900000 | 900000 |  | -1 |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260105 | No Initiation Date | Feeders/Transportations | Al Hafeez Garden & Tariq Garden | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 720000 | 720000 |  | -0.765 |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260159 | No Initiation Date | Feeders/Transportations | Faisalabad Citi Hosuing Extension | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 960000 | 960000 |  | -1 |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260160 | No Initiation Date | Feeders/Transportations | Khyban-e-Amin, High court & Al Rehman PH4 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1620000 | 1620000 |  | -0.85 |  |  | 0 |  |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260180 | No Initiation Date | Feeders/Transportations | Gujranwala Makki Road | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 2640000 | 2640000 |  | -1 |  |  | 0 |  |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260208 | No Initiation Date | Feeders/Transportations | LHE - DHA Phase 6, EME, Rahbar | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 2725000 | 2725000 |  | -1 |  |  | 0 |  |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260294 | No Initiation Date | Feeders/Transportations | Darussalam_LucknowSociety_DadabhoyTown | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 510000 | 510000 |  | -1 |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260295 | No Initiation Date | Feeders/Transportations | Model Town_Sh Faisal_Faisal Cant | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 4315000 | 4315000 |  | -1 |  |  | 0 |  |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260296 | No Initiation Date | Feeders/Transportations | Sukkur | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 5400000 | 5400000 |  | -1 |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260298 | No Initiation Date | Feeders/Transportations | Petaro Garrison, Hyderabad | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 175000 | 175000 |  | -1 |  |  | 0 |  |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
I260361 | No Initiation Date | Feeders/Transportations | Lhr MW City & Al Hafeez Ph-1 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 3600000 | 3600000 |  | -1 |  |  | 0 |  |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
INT-21-00315 | 2020-12-30 | Feeders/Transportations | Gujranwala Ph2 | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 6262500 | 3131250 | 3131250 | -1 |  |  |  | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-21-00315 | Timeline not applicable
INT-23-00435 | 2022-12-29 | Feeders/Transportations | Karachi Misc Areas | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1650000 | 825000 | 825000 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00435 | Timeline not applicable
INT-23-00436 | 2022-12-29 | Feeders/Transportations | Hyderabad Misc Areas | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 284000 | 142000 | 142000 | 0 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET |  | 2 |  |  |  | INT-23-00436 | Timeline not applicable
INT-23-00437 | 2022-12-29 | Feeders/Transportations | Lahore Misc Areas | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 2587500 | 1293750 | 1293750 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00437 | Timeline not applicable
INT-23-00438 | 2022-12-29 | Feeders/Transportations | Bahawalpur | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 375000 | 187500 | 187500 | 0 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00438 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Feeders/Transportations | Multan Misc. Areas | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 4087500 | 2043750 | 2043750 | -1 |  |  |  | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00439 | Timeline not applicable
INT-23-00440 | 2022-12-29 | Feeders/Transportations | Sargodha | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 867500 | 433750 | 433750 | -0.85 |  |  |  | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00440 | Timeline not applicable
INT-23-00441 | 2022-12-29 | Feeders/Transportations | Faisalabad Misc Areas | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1200000 | 600000 | 600000 | -0.85 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00441 | Timeline not applicable
INT-23-00442 | 2022-12-29 | Feeders/Transportations | Sahiwal Misc Areas | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 525000 | 262500 | 262500 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00442 | Timeline not applicable
INT-23-00444 | 2022-12-29 | Feeders/Transportations | Islamabad Misc Areas | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1895000 | 947500 | 947500 | #DIV/0! |  |  |  | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00444 | Timeline not applicable
INT-23-00445 | 2022-12-29 | Feeders/Transportations | Rawalpindi Misc Areas | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 587000 | 293500 | 293500 | #DIV/0! |  |  | 1 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00445 | Timeline not applicable
INT-23-00446 | 2022-12-29 | Feeders/Transportations | Wah Cant Misc Ares | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1920000 | 960000 | 960000 | #DIV/0! |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00446 | Timeline not applicable
INT-23-00447 | 2022-12-29 | Feeders/Transportations | Peshawar Misc Areas | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1987500 | 993750 | 993750 | -1 |  |  | 0 | 0 |  | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00447 | Timeline not applicable
INT-23-00764 | 2023-06-01 | Feeders/Transportations | Askari (1-6) Karachi | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 1515000 | 757500 | 757500 | -1 | [5 empty] | 50% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | INT-23-00764 | Timeline not applicable
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Model City Housing | 746 | 298.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 298.4 | 7483306.9238 | 7483306.9238 |  | #DIV/0! |  |  | 1567.5819 | 9090 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | University Town | 278 | 111.2 | [5 empty] | LIVE - 100% Completed | 100% | 111.2 | 7377581.9884 | 1106637.2983 | 6270944.6901 | -1 |  | 0.4 | 5118.3405 | 3376.8755 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
I250327 | 2024-11-05 | Islamabad | Islamabad | University Town P1 | 1232 | 492.8 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 492.8 | 32405235.65 | 32405235.65 | 0 | -1 |  | 0.4 | 15014.739 | 218 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46113 | Apr-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250327 | 2026-04-01
I250327 | 2024-11-05 | Islamabad | Islamabad | University Town P2 | 1528 | 611.2 | 0 |  |  |  |  | NOT LIVE - RETAIN BUDGET | 0% | 611.2 | 31889374.417 | 31889374.417 | 0 | -0.85 |  | 0.4 | 14364.927 | 10655.025 | Buried | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46113 | Apr-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250327 | 2026-04-01
I260296 | No Initiation Date | Sukkur | Sukkur | Unknonwn_1 | 402 | 160.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 95% |  | 2664905.7008 | 512994.3474 |  |  |  |  | 0 | 4891.0246 | Arial | 95% | NOT LIVE |  | 95% | 0.95 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Outside work almost done | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Unknown 01 | 84 | 42 |  |  |  |  | Unspecified area | REMOVE BUDGET (P) | 0% | 42 | 1499928.7388 | 0 | 1499928.7388 | -1 |  | 0.5 | 475.2893 | 1449.988 | Arial |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove from Budget | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | INT-23-00439 | Timeline not applicable
I260296 | No Initiation Date | Sukkur | Sukkur | Unknown 03 | 180 | 72 | [5 empty] | NOT LIVE - RETAIN BUDGET | 95% |  | 1604977.2113 | 308958.1132 |  |  |  |  | 0 | 2745.2928 | Arial | 95% | NOT LIVE |  | 95% | 0.95 | 2026-03-01 | 31 | 32 | -16 | In Progress | 1 Month | Apr-2026 | Outside work almost done | Not Live - Work in Progress (WIP) | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-04-01
I260296 | No Initiation Date | Sukkur | Sukkur | Unknown 11 | 670 | 268 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% |  | 11492216.9454 | 11492216.9454 |  |  |  |  | 2551.85 | 5219.745 | Arial | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 3 months | Jun-2026 | Not started yet | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-06-01
I250206 | 2024-09-12 | Daska | Daska | Unknown Society _ 4 | 528 | 211.2 |  |  |  |  | Please confirm Society name | REMOVE BUDGET (T) | 0% | 211.2 | 8310750.5242 | 0 | 8310750.5242 | -1 | Daska Housing | 0.4 | 1925.2664 | 6265.2639 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to Remove (after 6 months) | Temporary Budget Removal | REMOVE BUDGET (T) |  |  |  | 0 |  | I250206 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Unknown Society _ 5 | 288 | 115.2 |  |  |  |  | Please confirm Society name | NOT LIVE - RETAIN BUDGET | 0% | 115.2 | 3704453.0308 | 3704453.0308 | 0 | -1 |  | 0.4 | 652.5678 | 3582.664 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 61 | 62 | 14 | Yet to Start | 46143 | May-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-05-01
I250206 | 2024-09-12 | Daska | Daska | Unknown Society _3 | 508 | 203.2 |  |  |  |  | Please confirm Society name | NOT LIVE - RETAIN BUDGET | 0% | 203.2 | 5421261.2707 | 5421261.2707 | 0 | -1 |  | 0.4 | 961.5604 | 4603.4006 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 61 | 62 | 14 | Yet to Start | 46143 | May-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-05-01
I250206 | 2024-09-12 | Daska | Daska | Unknown Society 10 | 664 | 265.6 |  |  |  |  | Please confirm Society name | NOT LIVE - RETAIN BUDGET | 0% | 265.6 | 7256045.75 | 7256045.75 | 0 | -0.85 | Ramzan Town | 0.4 | 1327.1 | 6130.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 0 | 1 | -47 | Yet to Start | 46054 | Mar-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-03-01
I250206 | 2024-09-12 | Daska | Daska | Unknown Society 13 | 362 | 144.8 |  |  |  |  | Please confirm Society name | LIVE - 100% Completed | 100% | 144.8 | 4411121.25 | 661668.1875 | 3749453.0625 | -1 | Madina Housing | 0.4 | 810.75 | 4038.25 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250206 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Unknown Society 14-P1 | 124 | 49.6 |  |  |  |  | Please confirm Society name | NOT LIVE - RETAIN BUDGET | 0% | 49.6 | 1925057.75 | 1925057.75 | 0 | -0.85 | Shaid Town | 0.4 | 309.35 | 1497.85 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 0 | 1 | -47 | Yet to Start | 46054 | Mar-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  | 6449875.3208 |  | I250206 | 2026-03-01
I250206 | 2024-09-12 | Daska | Daska | Unknown Society 14-P2 | 874 | 349.6 |  |  |  |  | Please confirm Society name | REMOVE BUDGET (P) | 0% | 349.6 | 11993795.2035 | 0 | 11993795.2035 | -1 | Probable Grace City Area | 0.4 | 2656.2754 | 9666.2584 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to Remove | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I250206 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Unknown Society 14-P3 | 462 | 184.8 |  |  |  |  | Please confirm Society name | REMOVE BUDGET (P) | 0% | 184.8 | 4187359.746 | 0 | 4187359.746 | -0.85 | Probable Grace City Area | 0.4 | 612.95 | 4460.2 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to Remove | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I250206 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Unknown Society 14-P4 | 464 | 185.6 |  |  |  |  | Please confirm Society name | REMOVE BUDGET (P) | 0% | 185.6 | 5342626.5 | 0 | 5342626.5 | -1 | Probable Grace City Area | 0.4 | 1006.25 | 5206.95 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to Remove | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I250206 | Timeline not applicable
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Model Town, Arfat Town | 652 | 260.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 260.8 | 7915908.0246 | 7915908.0246 |  | #DIV/0! |  |  | 1601.1815 | 10115 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250206 | 2024-09-12 | Daska | Daska | Unknown Society 20 | 424 | 169.6 |  |  |  |  | Please confirm Society name | SWAPPED | 0% | 169.6 | 4694817.25 | 0 | 4694817.25 | -0.85 | City Town-P2 | 0.4 | 833.75 | 4094.8 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Meraj Housing | Swap Cases | SWAPPED |  |  | Meraj Housing | 22604832.2609 | 542 | I250206 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Unknown Society 21 | 128 | 51.2 |  |  |  |  | Please confirm Society name | REMOVE BUDGET (P) | 0% | 51.2 | 1875315 | 0 | 1875315 | -1 |  | 0.4 | 319.7 | 1310.8 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to Remove | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I250206 | Timeline not applicable
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Muhajir Colony, Old Sadiqabad | 1126 | 450.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 450.4 | 9767085.7874 | 9767085.7874 |  | #DIV/0! |  |  | 1575.9983 | 14133.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Mujahid Colony, Tipu Sultan | 876 | 350.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 350.4 | 8621467.7303 | 8621467.7303 |  | #DIV/0! |  |  | 1597.3926 | 12190 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250206 | 2024-09-12 | Daska | Daska | Unknown Society 9 | 408 | 163.2 |  |  |  |  | Please confirm Society name | NOT LIVE - RETAIN BUDGET | 0% | 163.2 | 5943218.75 | 5943218.75 | 0 | -0.85 | Farrukh Lodge-Rehman Colony | 0.4 | 1317.9 | 4158.6 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 61 | 62 | 14 | Yet to Start | 46143 | May-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 | 2 |  |  |  | I250206 | 2026-05-01
I250206 | 2024-09-12 | Daska | Daska | Unknown Society_11 | 522 | 208.8 |  |  |  |  | Please confirm Society name | NOT LIVE - RETAIN BUDGET | 0% | 208.8 | 6842778.0172 | 6842778.0172 | 0 | -1 | Al Haram Town | 0.4 | 1365.2825 | 6189.4275 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-06-01
I250206 | 2024-09-12 | Daska | Daska | Unknown Society_12 | 244 | 97.6 |  |  |  |  | Please confirm Society name | NOT LIVE - RETAIN BUDGET | 0% | 97.6 | 5130305.0279 | 5130305.0279 | 0 | -0.85 | One City | 0.4 | 1231.036 | 3722.7148 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 61 | 62 | 14 | Yet to Start | 46143 | May-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-05-01
I250206 | 2024-09-12 | Daska | Daska | Unknown Society_22 | 418 | 167.2 |  |  |  |  | Please confirm Society name | SWAPPED | 0% | 167.2 | 4623068.25 | 0 | 4623068.25 | -1 |  | 0.4 | 792.35 | 4278 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Meraj Housing | Swap Cases | SWAPPED |  |  | Meraj Housing | 22604832.2609 | 542 | I250206 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Unknown Society_23 | 956 | 382.4 |  |  |  |  | Please confirm Society name | NOT LIVE - RETAIN BUDGET | 0% | 382.4 | 9924048 | 9924048 | 0 | -0.85 | Alipur Ghuman | 0.4 | 1559.4 | 10893 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 0 | 1 | -47 | Yet to Start | 46054 | Mar-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 | 1 |  |  |  | I250206 | 2026-03-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Muncipal Town, Illyas Colony, | 2052 | 820.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 820.8 | 18481669.7453 | 18481669.7453 |  | #DIV/0! |  |  | 3480.3366 | 23233.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Mustafa , Zafar, Bismillah, Kar | 1122 | 448.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 448.8 | 8641126.0835 | 8641126.0835 |  | #DIV/0! |  |  | 1364.7487 | 14246.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Noor Colony,Zamindara Housing | 970 | 388 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 388 | 9420139.8448 | 9420139.8448 |  | #DIV/0! |  |  | 1695.9401 | 13485 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Public Colony & Commercial Area | 594 | 237.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 237.6 | 7634406.7734 | 7634406.7734 |  | #DIV/0! |  |  | 1883.5193 | 6782.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Rao Town | 950 | 380 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 380 | 7853530.5747 | 7853530.5747 |  | #DIV/0! |  |  | 1227.3025 | 12367.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Rehman Avenue | 262 | 104.8 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 104.8 | 3837716.5939 | 3837716.5939 |  | -1 |  |  | 889.3305 | 3167.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 1 | 300 | 120 |  |  |  |  | Please confirm Society name | NOT LIVE - RETAIN BUDGET | 0% | 120 | 3026231.25 | 3026231.25 | 0 | -1 |  | 0.4 | 488.75 | 2704.25 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 0 | 1 | -47 | Yet to Start | 46082 | Mar-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 | 2 |  |  |  | I250206 | 2026-03-01
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 15 | 246 | 98.4 |  |  |  |  | Please confirm Society name | NOT LIVE - RETAIN BUDGET | 0% | 98.4 | 3975135 | 3975135 | 0 | -0.85 | Makkah City | 0.4 | 817.65 | 3839.6 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-06-01
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 16 | 102 | 40.8 |  |  |  |  | Please confirm Society name | NOT LIVE - RETAIN BUDGET | 0% | 40.8 | 1806180.75 | 1806180.75 | 0 | -1 | Al Rehmat City | 0.4 | 341.55 | 1448.55 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 | 1 |  |  |  | I250206 | 2026-06-01
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 17 | 208 | 83.2 |  |  |  |  | Please confirm Society name | SWAPPED | 0% | 83.2 | 2299604 | 0 | 2299604 | -0.85 |  | 0.4 | 366.85 | 1911.1 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Meraj Housing | Swap Cases | SWAPPED |  |  | Meraj Housing | 22604832.2609 | 542 | I250206 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 18 | 154 | 61.6 |  |  |  |  | Please confirm Society name | SWAPPED | 0% | 61.6 | 2190435 | 0 | 2190435 | -1 | Green Valley-P2 | 0.4 | 411.7 | 1274.55 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Meraj Housing | Swap Cases | SWAPPED |  | 1 | Meraj Housing | 22604832.2609 | 542 | I250206 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 19 | 94 | 37.6 |  |  |  |  | Please confirm Society name | SWAPPED | 0% | 37.6 | 1473900.75 | 0 | 1473900.75 | -1 |  | 0.4 | 209.3 | 919.3 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Meraj Housing | Swap Cases | SWAPPED |  |  | Meraj Housing | 22604832.2609 | 542 | I250206 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 2 | 338 | 135.2 |  |  |  |  | Please confirm Society name | REMOVE BUDGET (P) | 0% | 135.2 | 3785193.25 | 0 | 3785193.25 | -0.85 | Ramzan City | 0.4 | 627.9 | 2966.7 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to Remove | Permenant Budget Removal | REMOVE BUDGET (P) |  | 1 |  | 0 |  | I250206 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 24 | 66 | 26.4 |  |  |  |  | Please confirm Society name | SWAPPED | 0% | 26.4 | 1047427.5 | 0 | 1047427.5 | -1 |  | 0.4 | 143.75 | 587.25 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Swapped with Meraj Housing | Swap Cases | SWAPPED |  |  | Meraj Housing | 22604832.2609 | 542 | I250206 | Timeline not applicable
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 6 | 372 | 148.8 |  |  |  |  | Please confirm Society name | NOT LIVE - RETAIN BUDGET | 0% | 148.8 | 4301761.5 | 4301761.5 | 0 | -0.85 | Khalid Town | 0.4 | 754.4 | 3913.55 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 31 | 32 | -16 | Yet to Start | 46113 | Apr-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-04-01
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 7 | 876 | 350.4 |  |  |  |  | Please confirm Society name | NOT LIVE - RETAIN BUDGET | 0% | 350.4 | 10274856 | 10274856 | 0 | -1 | Canal View | 0.4 | 1830.8 | 11832 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 0 | 1 | -47 | Yet to Start | 46082 | Mar-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-03-01
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 8 | 330 | 132 |  |  |  |  | Please confirm Society name | NOT LIVE - RETAIN BUDGET | 0% | 132 | 3310606.625 | 3310606.625 | 0 | -0.85 | Apna Town | 0.4 | 434.7 | 3130.55 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 61 | 62 | 14 | Yet to Start | 46143 | May-2026 | Need to Retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I250206 | 2026-05-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Rustam Colony & Mohallah | 686 | 274.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 274.4 | 7898760.1591 | 7898760.1591 |  | -1 |  |  | 1695.929 | 8743.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Satellite Town, Aziz Town, Gill | 1360 | 544 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 544 | 13099619.642 | 13099619.642 |  | -1 |  |  | 2408.9958 | 17915 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Village garden | 148 | 74 | 0 | 0 | 0 | 0 | On hold | NOT LIVE - RETAIN BUDGET | 100% | 74 | 1696577.2834 | 254486.5925 | 1442090.6909 | -0.85 |  | 0.5 | 348.45 | 1478.0011 | Hybrid | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 0 | 1 | -47 | Completed | 45703 | Mar-2026 | NOC Issue by Society/Work Completed | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | INT-23-00439 | 2026-03-01
I240540 | 2024-02-28 | Mardan | Mardan Ph2 | VIP Housing | 188 | 75.2 | 188 |  |  |  |  | ON Hold due to Railway Permission | 100% | 75.2 | 1584160.3 | 237624.045 | 1346536.255 | -0.85 |  | 0.4 | 0 | 2584.33 | Hybrid | 100% | NOT LIVE |  | 100% | 1 | 2026-03-01 | 31 | 32 | -16 | Completed | 1 Month | Apr-2026 | Railway crossing halting the process of activation (work done on arial) | Not Live - Permission Issues | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240540 | 2026-04-01
INT-23-00437 | 2022-12-29 | Lahore | Lahore Misc Areas | Wafaqi Colony | 2678 | 1339 | [5 empty] | LIVE - 100% Completed | 100% | 1339 | 11605724 | 1740858.6 | 9864865.4 | -1 |  | 0.5 | 1885.95 | 8747.85 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00437 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Wafay Citi GG Block | 4322 | 1728.8 | [5 empty] | LIVE - 100% Completed | 100% | 1728.8 | 44742841.1717 | 6711426.1757 | 38031414.9959 | -0.5 |  | 0.4 | 0 | 22231.5829 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
INT-21-00315 | 2020-12-30 | Gujranwala | Gujranwala Ph2 | Waffay Block Rem.Area | 3768 | 1507.2 | [5 empty] | LIVE - 100% Completed | 100% | 1507.2 | 55531073.8722 | 8329661.0808 | 47201412.7913 | -1 |  | 0.4 | 37423.8199 | 27024.616 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-21-00315 | Timeline not applicable
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Wapda Colony | 674 | 269.6 | 383 | 250 | 28 | 1 |  | LIVE - 100% Completed | 100% | 269.6 | 16137692.5004 | 2420653.8751 | 13717038.6253 | -1 |  | 0.4 | 1693.835 | 3624.6257 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Due to permission issue some part Live on Aerial | Live - Permission Awaited | LIVE - 100% Completed |  | 1 |  |  |  | I240702 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Wapda Town | 710 | 284 |  | 0 | 0 | 5 | Occupancy : 100 | LIVE - 100% Completed | 100% | 284 | 11002646.071 | 1650396.9107 | 9352249.1604 | -1 |  | 0.4 | 2313.2876 | 7788.5884 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Siraj Colony,Sukh Chain Housing | 304 | 121.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 121.6 | 5188456.369 | 5188456.369 |  | -1 |  |  | 1298.8241 | 4335 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I250377 | 2024-11-25 | Peshawar | Peshawar (P2) | Warsak Rd Ext. P1 | 394 | 157.6 | 50 | 44 | 3 | 3 | Sufiyan Garden,Sudais Garden,Uzair Town, | NOT LIVE - RETAIN BUDGET | 0% | 157.6 | 8663253.8075 | 8663253.8075 | 0 | #DIV/0! |  | 0.4 | 2041.25 | 5047.856 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250377 | 2026-06-01
I250377 | 2024-11-25 | Peshawar | Peshawar (P2) | Warsak Rd Ext. P2 | 154 | 61.6 | 2092 | 1274 | 404 | 414 | Main Peer Bala Village Main Michini warsak road | REMOVE BUDGET (P) | 0% | 61.6 | 3045173.69 | 0 | 3045173.69 | #DIV/0! |  | 0.4 | 635.95 | 1661.5695 | Hybrid |  | NOT LIVE |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable | Need to remove | Permenant Budget Removal | REMOVE BUDGET (P) |  |  |  | 0 |  | I250377 | Timeline not applicable
I250377 | 2024-11-25 | Peshawar | Peshawar (P2) | Warsak Rd Ext. P3 | 918 | 367.2 |  | 0 | 0 | 0 | Main Warsak Road Patwar Bala Main Michini Warsak Road | NOT LIVE - RETAIN BUDGET | 0% | 367.2 | 10124541.118 | 10124541.118 | 0 | #DIV/0! |  | 0.4 | 1659.45 | 6827.7165 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250377 | 2026-06-01
I250377 | 2024-11-25 | Peshawar | Peshawar (P2) | Warsak Rd Ext. P4 | 1006 | 402.4 |  | 2 | 0 | 0 | Main Mathra Bazar and round About villages,Kamal abad,Dhery Koroona,Khair abad, | NOT LIVE - RETAIN BUDGET | 0% | 402.4 | 14189027.5305 | 14189027.5305 | 0 | #DIV/0! |  | 0.4 | 2563.35 | 10205.16 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250377 | 2026-06-01
I250377 | 2024-11-25 | Peshawar | Peshawar (P2) | Warsak Rd Ext. P5 | 616 | 246.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 246.4 | 8532523.025 | 8532523.025 | 0 | #DIV/0! |  | 0.4 | 1483.5 | 5761.92 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 92 | 93 | 45 | Yet to Start | 46174 | Jun-2026 | Need to retain | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | 2 |  |  |  |  | I250377 | 2026-06-01
I250377 | 2024-11-25 | Peshawar | Peshawar (P2) | Warsak Rd Ext. P6 | 350 | 140 | [5 empty] | LIVE - 100% Completed | 100% | 140 | 6962073.065 | 1044310.9598 | 5917762.1052 | #DIV/0! |  | 0.4 | 1580.1 | 4249.602 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250377 | Timeline not applicable
I250377 | 2024-11-25 | Peshawar | Peshawar (P2) | Warsak Rd Ext. P7 | 778 | 311.2 | [5 empty] | LIVE - 100% Completed | 100% | 311.2 | 11923490.85 | 1788523.6275 | 10134967.2225 | #DIV/0! |  | 0.4 | 2037.8 | 10567.02 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Buried work done only on main warsak road | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250377 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Water Board Society | 120 | 48 | [5 empty] | LIVE - 100% Completed | 100% | 48 | 4472205.75 | 670830.8625 | 3801374.8875 | -0.85 |  | 0.4 | 874 | 1125.2 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable | Live - Completed | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I240704 | 2024-05-15 | Multan | Multan Ph3 | Western Fort | 232 | 92.8 | 78 | 8 | 3 | 67 |  | LIVE - 100% Completed | 100% | 92.8 | 9006140.7411 | 1350921.1112 | 7655219.6299 | -1 |  | 0.4 | 4313.0839 | 3433.2068 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240704 | Timeline not applicable
I240684 | 2024-05-16 | Rawalpindi | Askari RWP (4-7-10) | Willoughby Road appartments | 1328 | 531.2 | 23 | 9 | 2 | 12 |  | LIVE - 100% Completed | 100% | 531.2 | 12761912.419 | 1914286.8628 | 10847625.5562 | 0 |  | 0.4 | 3249.7605 | 1671.922 | Buried | 15% | LIVE | Buried | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240684 | Timeline not applicable
INT-23-00437 | 2022-12-29 | Lahore | Lahore Misc Areas | Wocland | 148 | 74 | [5 empty] | LIVE - 100% Completed | 100% | 74 | 1617776.1294 | 242666.4194 | 1375109.71 | 0 |  | 0.5 | 263.6216 | 996.859 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00437 | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Writers Colony | 574 | 287 | 370 | 40 | 51 | 279 |  | LIVE - 100% Completed | 100% | 287 | 5823823.33 | 873573.4995 | 4950249.8305 | -1 |  | 0.5 | 1100 | 6236.45 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Ya Rehman Society | 182 | 72.8 | [5 empty] | LIVE - 100% Completed | 100% | 72.8 | 3688574.5461 | 553286.1819 | 3135288.3642 | -1 |  | 0.4 | 733.6391 | 2132.2014 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240705 | Timeline not applicable
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Younas Town | 148 | 59.2 |  | 23 | 44 | 87 | Occupancy : 250 | LIVE - 100% Completed | 100% | 59.2 | 2691677.574 | 403751.6361 | 2287925.9379 | -1 |  | 0.4 | 525.55 | 1405.721 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
I250210 | 2024-09-14 | Sargodha | Sargodha | Z Block NST & Services Colony | 970 | 388 | 50 | 1 |  | 49 | Live | LIVE - 100% Completed | 100% | 388 | 8437067.896 | 1265560.1844 | 7171507.7116 | -1 |  | 0.4 | 952.2 | 7663.75 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I250210 | Timeline not applicable
I240679 | 2024-05-16 | Sargodha | Sargodha | Zafar Colony | 550 | 220 | 55 | 2 | 2 | 51 | Live | LIVE - 100% Completed | 100% | 220 | 1342145 | 201321.75 | 1140823.25 | -1 |  | 0.4 | 0 | 8045 | Arial | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240679 | Timeline not applicable
I240678 | 2024-05-16 | Sialkot | Sialkot | Zafarwal | 434 | 173.6 |  | 0 | 0 | 0 | Not Lived Yet | NOT LIVE - RETAIN BUDGET | 0% | 173.6 | 5673595.6817 | 5673595.6817 | 0 | -1 |  | 0.4 | 1222.0605 | 3476.1264 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 0 | 1 | -47 | Yet to Start | March-26 | Mar-2026 | Need to retain/NOC Issue | Not Live - Others Reasons | NOT LIVE - RETAIN BUDGET | 1 |  |  |  |  | I240678 | 2026-03-01
I240678 | 2024-05-16 | Sialkot | Sialkot | Zahoor Elahi Road | 968 | 387.2 |  | 45 | 7 | 378 |  | LIVE - 100% Completed | 100% | 387.2 | 10837958.1447 | 1625693.7217 | 9212264.423 | -1 |  | 0.4 | 2033.3492 | 7826.7012 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240678 | Timeline not applicable
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Tibba Qadirabad | 1226 | 490.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 490.4 | 8760356.4376 | 8760356.4376 |  | -1 |  |  | 1079.5939 | 14020 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Feeders/Transportations | Sadiqabad | Transportation | 0 | 0 | [5 empty] | FEEDER ETC WORK - RETAIN BUDGET | 0% | 0 | 8940000 | 8940000 |  | -1 |  |  | 0 | 0 |  | 100% |  |  | 0% | 0 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Yet to Start |  | Timeline not applicable |  | Feeders/Trans | FEEDER ETC WORK - RETAIN BUDGET | [5 empty] | #N/A | Timeline not applicable
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Zakariya Villas | 440 | 220 | 317 | 57 | 63 | 197 |  | LIVE - 100% Completed | 100% | 220 | 6539221.53 | 980883.2295 | 5558338.3005 | -0.5 |  | 0.5 | 1959.6 | 4684.95 | Hybrid | 15% | LIVE | Hybrid | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | INT-23-00439 | Timeline not applicable
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Warriach Town & Arian Colony | 1316 | 526.4 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 526.4 | 10868097.6052 | 10868097.6052 |  | -1 |  |  | 2083.0561 | 12592.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Zakria Garden,Unknown 3-4, | 1040 | 416 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 416 | 12946321.6235 | 12946321.6235 |  | -1 |  |  | 2986.6636 | 12438.75 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
UI2560607 | No Initiation Date | Sadiqabad | Sadiqabad | Zamzam Garden,Jeevan City | 684 | 273.6 | [5 empty] | NOT LIVE - RETAIN BUDGET | 0% | 273.6 | 7575550.226 | 7575550.226 |  | -1 |  |  | 1640.7652 | 7817.5 | Hybrid | 0% | NOT LIVE |  | 0% | 0 | 2026-03-01 | 214 | 215 | 167 | Yet to Start | 6 Months | Oct-2026 | These Projects have not been started yet, proceedings shall be done post eid | Not Live - Work to be initiated | NOT LIVE - RETAIN BUDGET | [5 empty] | #N/A | 2026-10-01
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Zuabir Colony | 394 | 157.6 |  | 3 | 6 | 39 | Occupancy : 200 | LIVE - 100% Completed | 100% | 157.6 | 6574598.0606 | 986189.7091 | 5588408.3515 | -1 |  | 0.4 | 1067 | 5501.9539 | Hybrid | 15% | LIVE | Arial | 100% | 1 | 2026-03-01 | None | Duration Doesn't Exsists | No ETA | Completed |  | Timeline not applicable |  | Live - As per Plan | LIVE - 100% Completed | [5 empty] | I240682 | Timeline not applicable
Formulas:
Days Remaining = IFERROR(Table8[[#This Row],[Timeline - Monthwise]]-TODAY(),"No ETA")

## KPI
S.No | Category | KPI Name | What it Tells | Excel Formula (Concept)
1 | Execution | Total Projects | Overall scale of operations | 1150
2 | Execution | Live Projects | Revenue-active deployments | 525
3 | Execution | Not Live Projects | Work completed but not activated | 625
4 | Execution | Avg Completion % | Overall execution progress | 43.47%
5 | Execution | Projects ≥80% Complete | Near-finish pipeline | 579
6 | Financial | Total Allocated Budget | Planned CAPEX | 22095709754.6035
7 | Financial | Total Revised Budget | Updated CAPEX view | 10815617066.9371
8 | Financial | Budget Variance | Over/under spend
9 | Financial | CAPEX at Risk | Money stuck in near-complete, not-live projects
10 | Financial | Cost Efficiency | Spend effectiveness
11 | Risk | Delayed Projects | Execution delays
12 | Risk | Projects Delayed >10 Days | Severe delays
13 | Risk | Near Complete Not Live | Activation bottlenecks
14 | Risk | High CAPEX Not Live | Financial exposure (all stalled)
15 | Risk | Zero Progress Projects | Execution failure / inactivity | 745
16 | Commercial | Total Homes Passed (HP) | Network deployment scale | 1444140
17 | Commercial | Active Customers | Monetized base | 13574
18 | Commercial | Conversion % | Deployment → revenue efficiency | 0.9399%
19 | Commercial | Revenue Potential Blocked | Customers stuck due to non-activation | 104840
20 | Commercial | Time to Live | Delay between completion & activation | -214

## Dashboard - Surface
|  | Approved SF Expansion Feasibilities Report |  |  |  |  | Total Network | Expected Home Passes | Sellable Capacity | Active Home Passes
[6 empty] | Total Network (HP) | 1444140 | 600881.5
Number of Feasibility | 97 | Live Areas | 525 | Not Live Areas | 625 | Total Areas | 1150
Live vs Non Live Ratio |  |  |  | Standardized Comment Box |  |  |  |  | Timeline Box |  |  |  |  | 513
[9 empty] | Month |  | Quarter | Number of Areas |  | Quarter - Total
|  |  |  | Comments | Count of Areas |  |  |  | 2026-01-01 |  | Q1 |  |  | 37
|  |  |  | LIVE - 100% Completed | 512 |  |  |  | 2026-02-01
|  |  |  | LIVE - 25% Completed | 1 |  |  |  | 2026-03-01 |  |  | 37
|  |  |  | LIVE - 50% Completed | 6 |  |  |  | 2026-04-01 |  | Q2 | 61 |  | 151
|  |  |  | LIVE - 60% Completed | 3 |  |  |  | 2026-05-01 |  |  | 26
|  |  |  | LIVE - 80% Completed | 5 | Buried | 253 |  | 2026-06-01 |  |  | 64
|  |  |  | NOT LIVE - RETAIN BUDGET | 533 |  |  |  | 2026-07-01 |  | Q3 | 33 |  | 33
|  |  |  | REMOVE BUDGET (P) | 43 |  |  |  | 2026-08-01
|  |  |  | REMOVE BUDGET (T) | 19 |  |  |  | 2026-09-01
|  |  |  | SWAPPED | 28 | Hybrid | 804 |  | 2026-10-01 |  | Q4 | 292 |  | 292
|  |  |  | Grand Total | 1150 |  |  |  | 2026-11-01
2026-12-01
[9 empty] | 2027-01-01 |  | Q1 |  |  | 0
[6 empty] | Arial | 93 |  | 2027-02-01
2027-03-01
[9 empty] | 2027-04-01 |  | Q2 |  |  | 0
2027-05-01
Orignally Approved Areas - Arial,Buried,Hybrid |  |  |  | City Names |  |  |  |  | 2027-06-01
[9 empty] | 2027-07-01 |  | Q3 |  |  | 0
2027-08-01
2027-09-01
[9 empty] | 2027-10-01 |  | Q4 |  |  | 0
2027-11-01
2027-12-01
[12 empty] | Feedback Awaited | 45
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## City Names (hidden)
Number of CEMs | 34
Row Labels | Count of Fesibility Name
Abbottabad | 8
Bahawalpur | 30
Chitral | 2
Daska | 43
Dera Ghazi Khan | 31
Faisalabad | 42
Gujranwala | 72
Hafizabad | 28
Haripur | 15
Hyderabad | 29
Islamabad | 71
Jhang | 21
Jhelum | 27
Karachi | 116
Kasur | 35
Lahore | 157
Lalamusa | 8
Mandi Bahauddin | 25
Mardan | 27
Multan | 83
Narowal | 30
Okara | 7
Peshawar | 25
Quetta | 4
Rahim Yar Khan | 10
Rawalpindi | 16
Sadiqabad | 44
Sahiwal | 9
Sargodha | 30
Sialkot | 36
Swat | 41
Torkhan Border | 1
Wahh | 12
Sukkur | 15
Grand Total | 1150

## Dashboard - Feasibility
Approved SF Expansion Feasibilities Report - Area Focused
Number of Feasibility | 97
Live Areas | 525
Not Live Areas | 625
Total Network (HP) | 1444140
Expected HP | 600881.5
Fesibility Name | Area / Section / Pocket / Society (Original Name) | Remarks Grouped | Total HP | Expected Customers Based on Market Share (%) | Expected Customers Based on Completion of Work
Abbottabad | Gulfam Town_Mera Muzzafar | Live - As per Plan | 450 | 180 | 180
| Malikpura | Live - As per Plan | 714 | 285.6 | 285.6
| Salhad | Swap Cases | 700 | 280 | 280
Abbottabad Ph2 | Al Mansoor Town Ext. | Live - As per Plan | 440 | 176 | 176
| Jhangi Qazian | Live - As per Plan | 420 | 168 | 168
| Jhangi Saeedan Extension | Live - As per Plan | 482 | 192.8 | 192.8
| Kaghan Colony Extension | Live - As per Plan | 302 | 120.8 | 120.8
| Kareenpura Extension | Live - As per Plan | 182 | 72.8 | 72.8
Al Hafeez Garden & Tariq Garden | Al Hafeez Garden Ph-5 | Not Live - Work in Progress (WIP) | 1450 | 580
| Al Hafeez Gdn Ph-2 | Live - As per Plan | 1404 | 561.6
| Al Raheem Gdn Ph-2 Extn. | Not Live - Work to be initiated | 1150 | 460
| Tariq Garden | Permenant Budget Removal | 1498 | 599.2
Al Jalil & Al khalil LHE | Al Hamra | Not Live - Work in Progress (WIP) | 424 | 169.6 | 169.6
| Al Jalil Housing P2 | Live - As per Plan | 2232 | 892.8 | 892.8
| Al Jalil Housing P3 | Live - As per Plan | 2210 | 884 | 884
| Al Jalil Housing P4 | Not Live - Work to be initiated | 2106 | 842.4 | 842.4
| Al Kabeer Ph-2-Pk1 | Live - As per Plan | 2268 | 907.2 | 907.2
| Al Kabeer Ph-2-Pk2 | Not Live - Work in Progress (WIP) | 3086 | 1234.4 | 1234.4
| Al Kabeer Ph-2-Pk3 | Not Live - Work to be initiated | 776 | 310.4 | 310.4
| Al Kabeer Town Ph-1 | Live - As per Plan | 512 | 204.8 | 204.8
| Central Park Housing-P1 | Permenant Budget Removal | 1526 | 610.4 | 610.4
| Central Park Housing-P2 | Permenant Budget Removal | 1200 | 480 | 480
| Central Park Housing-P3 | Permenant Budget Removal | 1206 | 482.4 | 482.4
Askari (1-6) Karachi | Akari-1 | Live - As per Plan | 320 | 160 | 160
| Akari-2 | Live - As per Plan | 240 | 120 | 120
| Akari-3 | Live - As per Plan | 970 | 485 | 485
| Askari-4 | Live - As per Plan | 1612 | 806 | 806
| Askari-5 P1 | Live - As per Plan | 728 | 364 | 364
| Askari-5 P2 | Live - As per Plan | 3460 | 1730 | 1730
| Askari-5G | Live - As per Plan | 282 | 141 | 141
| Askari-5H | Not Live - Work to be initiated | 216 | 108 | 108
| Askari-5J | Live - As per Plan | 1300 | 650 | 650
| Askari-6 Sec 01 | Live - As per Plan | 566 | 283 | 283
| Askari-6 Sec 02 | Not Live - Work to be initiated | 470 | 235 | 235
| Askari-6 Sec 03 | Not Live - Work to be initiated | 1040 | 520 | 520
| Askari-6 Sec 04 | Not Live - Work to be initiated | 936 | 468 | 468
| Askari-6 Sec 05 | Not Live - Work to be initiated | 540 | 270 | 270
| Askari-6 Sec 06 | Not Live - Work to be initiated | 1080 | 540 | 540
| Askari-6 Sec 07 | Not Live - Work to be initiated | 1080 | 540 | 540
| Askari-6 Sec 08 | Not Live - Work to be initiated | 1224 | 612 | 612
| Askari-6 Sec 09 | Not Live - Work to be initiated | 1224 | 612 | 612
| Askari-6 Sec 10 | Not Live - Work to be initiated | 1224 | 612 | 612
| Askari-6 Sec 11 | Not Live - Work to be initiated | 936 | 468 | 468
Askari Lahore | Askari-1 | Live - As per Plan | 720 | 288 | 288
| Askari-10 P1 | Live - As per Plan | 3018 | 1207.2 | 1207.2
| Askari-10 P2 | Live - As per Plan | 1734 | 693.6 | 693.6
| Askari-10 Sec-S | Live - As per Plan | 216 | 86.4 | 43.2
| Askari-11 P1 | Not Live - Work to be initiated | 972 | 388.8 | 388.8
| Askari-11 P2 | Not Live - Work to be initiated | 1628 | 651.2 | 651.2
| Askari-11 P3 | Not Live - Work to be initiated | 960 | 384 | 384
| Askari-2 | Live - As per Plan | 228 | 91.2 | 91.2
| Askari-5 | Live - As per Plan | 1104 | 441.6 | 441.6
| Askari-9 | Live - As per Plan | 828 | 331.2 | 331.2
Askari Multan | Askari-1 | Live - As per Plan | 182 | 72.8 | 72.8
| Askari-2 | Live - As per Plan | 292 | 116.8 | 116.8
| Askari-3 | Live - As per Plan | 506 | 202.4 | 202.4
Askari RWP (4-7-10) | Askari-10 | Live - As per Plan | 372 | 148.8 | 148.8
| Askari-4 | Live - As per Plan | 864 | 345.6 | 345.6
| Askari-7 P1 | Swap Cases | 472 | 188.8 | 188.8
| Askari-7 P2 | Swap Cases | 964 | 385.6 | 385.6
| Nazeer Apt. | Live - As per Plan | 54 | 21.6 | 21.6
| Willoughby Road appartments | Live - As per Plan | 1328 | 531.2 | 531.2
Askari Sialkot | Askari-I | Live - As per Plan | 272 | 163.2 | 163.2
| Askari-II | Live - As per Plan | 500 | 300 | 300
Bahadurabad (KTTC) | Bahadurabad & Sharfabad | Live - As per Plan | 2446 | 978.4 | 978.4
Bahawalpur | Japan Town | Live - As per Plan | 486 | 243 | 243
Bahawalpur (P3) | Asif & Hassan Town | Live - As per Plan | 1740 | 696 | 696
| Cheema Town Ph-2 | Live - As per Plan | 700 | 280 | 280
| Japan Town | Live - As per Plan | 486 | 194.4 | 194.4
| Medical Colony | Live - As per Plan | 432 | 172.8 | 172.8
Bahwalpur (P2)-B | 3 Marla Scheme | Not Live - Work in Progress (WIP) | 1730 | 692 | 692
| Alibad_Colony | Live - As per Plan | 278 | 111.2 | 111.2
| AlNoor Exct-Haram-Garden Ph-4 | Live - As per Plan | 298 | 119.2 | 119.2
| Al-Rahim Garden & Crystal Homes | Live - As per Plan | 484 | 193.6 | 193.6
| Anwarabad Colony | Not Live - Work in Progress (WIP) | 332 | 132.8 | 132.8
| Askari | Live - As per Plan | 108 | 43.2 | 43.2
| Band Road Extension & Makhdumpu | Not Live - Work in Progress (WIP) | 2086 | 834.4 | 834.4
| Fauji Basti | Not Live - Work in Progress (WIP) | 1206 | 482.4 | 482.4
| Green and Al-hafeez Town | Not Live - Work in Progress (WIP) | 1886 | 754.4 | 754.4
| Habib Colony | Live - As per Plan | 518 | 207.2 | 207.2
| Haseeb Town,Fahad Colony & Dila | Not Live - Work in Progress (WIP) | 3180 | 1272 | 1272
| Islamia Colony PK1 | Not Live - Work in Progress (WIP) | 1158 | 463.2 | 463.2
| Islamia Colony PK2 | Not Live - Work in Progress (WIP) | 2030 | 812 | 812
| Islamia Colony PK3 | Not Live - Work in Progress (WIP) | 1498 | 599.2 | 599.2
| Khakwani Colony | Live - As per Plan | 708 | 283.2 | 283.2
| Model Town C Extension | Not Live - Work in Progress (WIP) | 750 | 300 | 300
| Mohallah Aam Khass and Noor Sha | Not Live - Work in Progress (WIP) | 830 | 332 | 332
| New_Muslim town | Live - As per Plan | 892 | 356.8 | 356.8
| Paragon Ideal Homes | Not Live - Permission Issues | 824 | 329.6 | 329.6
| Safari Garden Phase 1 | Not Live - Permission Issues | 204 | 81.6 | 81.6
| Safari Garden Phase 2 | Not Live - Permission Issues | 308 | 123.2 | 123.2
| Shahdara & Habib Colony | Not Live - Permission Issues | 1746 | 698.4 | 698.4
| Small Industrial Estate | Not Live - Permission Issues | 700 | 280 | 280
| State and Middle Town | Live - As per Plan | 934 | 373.6 | 373.6
| Taha Town | Not Live - Permission Issues | 428 | 171.2 | 171.2
Buffer Zone Khi | P1 | Live - As per Plan | 2246 | 673.8 | 673.8
| P1 | Not Live - Work to be initiated | 2246 | 673.8
| P2 | Live - As per Plan | 1880 | 564 | 564
| P2 | Not Live - Work to be initiated | 1880 | 564
| P3 | Live - As per Plan | 1774 | 532.2 | 532.2
| P3 | Not Live - Work to be initiated | 1774 | 532.2
| P4 | Live - As per Plan | 3244 | 973.2 | 973.2
| P4 | Not Live - Work to be initiated | 3244 | 973.2
| P5 | Live - As per Plan | 6000 | 1800 | 1800
| P5 | Not Live - Work to be initiated | 6000 | 1800
| P6 | Live - As per Plan | 3298 | 989.4 | 989.4
| P6 | Not Live - Work to be initiated | 3298 | 989.4
Chinar Bagh Lahore | Chinar_Bagh_P01 | Live - As per Plan | 694 | 277.6 | 277.6
| Chinar_Bagh_P02 | Live - As per Plan | 962 | 384.8 | 384.8
| Chinar_Bagh_P03 | Live - As per Plan | 898 | 359.2 | 359.2
| Eden Lane Villas 2 | Permenant Budget Removal | 814 | 325.6 | 325.6
| Rehman Garden-2 Pk-1 | Not Live - Work in Progress (WIP) | 2366 | 946.4 | 946.4
| Rehman Garden-2 Pk-2 | Not Live - Work in Progress (WIP) | 1540 | 616 | 616
| Rehman Garden-2 Pk-3 | Not Live - Work to be initiated | 1118 | 447.2 | 447.2
| Rehman Garden-2 Pk-4 | Not Live - Work to be initiated | 824 | 329.6 | 329.6
| Rehman Garden-2 Pk-5 | Not Live - Work to be initiated | 1320 | 528 | 528
| Rehman Garden-2 Pk-6 | Not Live - Work to be initiated | 984 | 393.6 | 393.6
| Rehman Garden-2 Pk-7 | Not Live - Work to be initiated | 846 | 338.4 | 338.4
| Rehman Garden-2 Pk-8 | Not Live - Work to be initiated | 944 | 377.6 | 377.6
Chitral Ph1 | Bakarabad & Jughoor | Not Live - Work to be initiated | 714 | 285.6 | 285.6
| Chitral City | Live - As per Plan | 3118 | 1247.2 | 623.6
CTC Lahore | Ali Park & Nadirabad P1 | Not Live - Work in Progress (WIP) | 1424 | 569.6 | 569.6
| Ali Park & Nadirabad P2 | Not Live - Work in Progress (WIP) | 1512 | 604.8 | 604.8
| Gulshan e Ali | Not Live - Work in Progress (WIP) | 934 | 373.6 | 373.6
Darussalam_LucknowSociety_DadabhoyTown | Darussalam Society | Not Live - Work in Progress (WIP) | 1074 | 429.6
| Lucknow Society | Not Live - Work to be initiated | 1322 | 528.8
| Dadabhoy Town | Not Live - Work to be initiated | 662 | 264.8
Daska | Barkat Town | Live - As per Plan | 592 | 236.8 | 236.8
| Bhatti Colony | Swap Cases | 536 | 214.4 | 214.4
| Civil Lines | Not Live - Work to be initiated | 598 | 239.2 | 239.2
| Faisal_Town | Swap Cases | 320 | 128 | 128
| Garden Town | Not Live - Work to be initiated | 1288 | 515.2 | 515.2
| Ghalotian Mor | Not Live - Work to be initiated | 456 | 182.4 | 182.4
| Gulistan_town | Not Live - Work to be initiated | 1100 | 440 | 440
| Gulshan Colony | Not Live - Work to be initiated | 752 | 300.8 | 300.8
| Habibpura | Not Live - Work to be initiated | 778 | 311.2 | 311.2
| Islampura | Swap Cases | 1132 | 452.8 | 452.8
| Model Town | Not Live - Work to be initiated | 556 | 222.4 | 222.4
| Punjab Small Ind. Estate | Not Live - Work to be initiated | 196 | 78.4 | 78.4
| Qazi Town | Not Live - Work to be initiated | 460 | 184 | 184
| Rehmanpura | Swap Cases | 652 | 260.8 | 260.8
| Sambrial_Road | Not Live - Work to be initiated | 256 | 102.4 | 102.4
| Shahabpura | Not Live - Work to be initiated | 946 | 378.4 | 378.4
| Unknown Society _ 4 | Temporary Budget Removal | 528 | 211.2 | 211.2
| Unknown Society _ 5 | Not Live - Work to be initiated | 288 | 115.2 | 115.2
| Unknown Society _3 | Not Live - Work to be initiated | 508 | 203.2 | 203.2
| Unknown Society 10 | Not Live - Work to be initiated | 664 | 265.6 | 265.6
| Unknown Society 13 | Live - As per Plan | 362 | 144.8 | 144.8
| Unknown Society 14-P1 | Not Live - Work to be initiated | 124 | 49.6 | 49.6
| Unknown Society 14-P2 | Permenant Budget Removal | 874 | 349.6 | 349.6
| Unknown Society 14-P3 | Permenant Budget Removal | 462 | 184.8 | 184.8
| Unknown Society 14-P4 | Permenant Budget Removal | 464 | 185.6 | 185.6
| Unknown Society 20 | Swap Cases | 424 | 169.6 | 169.6
| Unknown Society 21 | Permenant Budget Removal | 128 | 51.2 | 51.2
| Unknown Society 9 | Not Live - Work to be initiated | 408 | 163.2 | 163.2
| Unknown Society_11 | Not Live - Work to be initiated | 522 | 208.8 | 208.8
| Unknown Society_12 | Not Live - Work to be initiated | 244 | 97.6 | 97.6
| Unknown Society_22 | Swap Cases | 418 | 167.2 | 167.2
| Unknown Society_23 | Not Live - Work to be initiated | 956 | 382.4 | 382.4
| Unkown Society 1 | Not Live - Work to be initiated | 300 | 120 | 120
| Unkown Society 15 | Not Live - Work to be initiated | 246 | 98.4 | 98.4
| Unkown Society 16 | Not Live - Work to be initiated | 102 | 40.8 | 40.8
| Unkown Society 17 | Swap Cases | 208 | 83.2 | 83.2
| Unkown Society 18 | Swap Cases | 154 | 61.6 | 61.6
| Unkown Society 19 | Swap Cases | 94 | 37.6 | 37.6
| Unkown Society 2 | Permenant Budget Removal | 338 | 135.2 | 135.2
| Unkown Society 24 | Swap Cases | 66 | 26.4 | 26.4
| Unkown Society 6 | Not Live - Work to be initiated | 372 | 148.8 | 148.8
| Unkown Society 7 | Not Live - Work to be initiated | 876 | 350.4 | 350.4
| Unkown Society 8 | Not Live - Work to be initiated | 330 | 132 | 132
DG Khan | Adam Housing-P1 | Not Live - Work to be initiated | 554 | 249.3 | 249.3
| Adam Housing-P2 | Not Live - Work to be initiated | 428 | 192.6 | 192.6
| Al Hussain Garden | Not Live - Work to be initiated | 228 | 102.6 | 102.6
| Al Inam Gardens | Not Live - Work to be initiated | 316 | 142.2 | 142.2
| Al Rasool Town | Not Live - Work to be initiated | 310 | 139.5 | 139.5
| Canal View | Not Live - Work to be initiated | 582 | 261.9 | 261.9
| CPC Colony | Not Live - Work to be initiated | 346 | 155.7 | 155.7
| Dream City | Not Live - Work to be initiated | 532 | 239.4 | 239.4
| Ejaz Town | Not Live - Work to be initiated | 690 | 310.5 | 310.5
| Garden Town | Not Live - Work to be initiated | 488 | 219.6 | 219.6
| Gul zameen Colony | Not Live - Work to be initiated | 196 | 88.2 | 88.2
| Gulberg housing Society | Not Live - Work to be initiated | 1166 | 524.7 | 524.7
| Indus Smart City | Not Live - Work to be initiated | 148 | 66.6 | 66.6
| K Gaardens | Not Live - Work to be initiated | 360 | 162 | 162
| Khayaban e Sarwar | Not Live - Work to be initiated | 1110 | 499.5 | 499.5
| Khayaban i Abid | Not Live - Work to be initiated | 242 | 108.9 | 108.9
| Main Area P1 | Not Live - Work to be initiated | 3176 | 1429.2 | 1429.2
| Main Area P2 | Not Live - Work to be initiated | 3656 | 1645.2 | 1645.2
| Main Area P3 | Not Live - Work to be initiated | 1776 | 799.2 | 799.2
| Model Town | Not Live - Work to be initiated | 1012 | 455.4 | 455.4
| New Defence | Not Live - Work to be initiated | 930 | 418.5 | 418.5
| New Model Town | Not Live - Work to be initiated | 398 | 179.1 | 179.1
| NMC Colony 1 | Not Live - Work to be initiated | 296 | 133.2 | 133.2
| Part of New Defence | Not Live - Work to be initiated | 262 | 117.9 | 117.9
| Railway Civil Lines P1 | Not Live - Work to be initiated | 596 | 268.2 | 268.2
| Railway Civil Lines P2 | Not Live - Work to be initiated | 570 | 256.5 | 256.5
| Royal city | Not Live - Work to be initiated | 166 | 74.7 | 74.7
| Royal Pearl Enclave | Not Live - Work to be initiated | 1768 | 795.6 | 795.6
| Sana Valley | Not Live - Work to be initiated | 424 | 190.8 | 190.8
| Usmania Village | Not Live - Work to be initiated | 230 | 103.5 | 103.5
| Zam Zam City | Not Live - Work to be initiated | 262 | 117.9 | 117.9
DHA Gujranwala | DHA Sector A ( Villas ) | Not Live - Work in Progress (WIP) | 528 | 264
DHA KHI - Common Corridor Project | DKTCC (Remaining Areas) | Live - As per Plan | 19009 | 7603.6 | 7603.6
DHA Multan | Additional Cost | Not Live - Work to be initiated | 0 | 0 | 0
| Block M | Not Live - Work to be initiated | 2576 | 1545.6 | 1545.6
| Block Q | Not Live - Work to be initiated | 2914 | 1748.4 | 1748.4
| Block R | Not Live - Work to be initiated | 2466 | 1479.6 | 1479.6
| DHA Rumanza-P1 | Not Live - Work to be initiated | 724 | 434.4 | 434.4
| DHA Villas | Not Live - Work to be initiated | 618 | 370.8 | 370.8
DHA PH 1-5 | DHA PH-4 KK | Not Live - Work in Progress (WIP) | 1106 | 553 | 553
| DHA PH-5 M | Live - As per Plan | 926 | 463 | 463
| Ph-1 G & H Block | Not Live - Work in Progress (WIP) | 930 | 465 | 465
| Ph-1 K Block | Not Live - Work in Progress (WIP) | 252 | 126 | 126
| Ph-2 Q Block | Not Live - Work in Progress (WIP) | 286 | 143 | 143
| Ph-2 T Block | Not Live - Work in Progress (WIP) | 234 | 117 | 117
| Ph-3 XX Block | Not Live - Work in Progress (WIP) | 162 | 81 | 81
| Ph-3 Y & Z Block | Not Live - Work in Progress (WIP) | 700 | 350 | 350
| Ph-4 K Commercial | Not Live - Work in Progress (WIP) | 580 | 290 | 290
| Ph-5 K Commercial | Not Live - Work in Progress (WIP) | 282 | 141 | 141
DHA PH 7-8 | PH-7-P1 | Not Live - Work in Progress (WIP) | 4170 | 2085 | 2085
| PH-7-P2 | Not Live - Work in Progress (WIP) | 3496 | 1748 | 1748
| PH-7-P3 | Not Live - Work in Progress (WIP) | 6980 | 3490 | 3490
| PH-7-P5 | Not Live - Work in Progress (WIP) | 5536 | 2768 | 2768
| Ph-8-IVY-P1 | Temporary Budget Removal | 2918 | 1459 | 1459
| Ph-8-IVY-P2 | Temporary Budget Removal | 3820 | 1910 | 1910
| PH-8-P1 | Not Live - Work in Progress (WIP) | 1992 | 996 | 996
| PH-8-P2 | Not Live - Work in Progress (WIP) | 2412 | 1206 | 1206
| PH-8-P3 | Not Live - Work in Progress (WIP) | 1386 | 693 | 693
| PH-8-P4 | Not Live - Work in Progress (WIP) | 1420 | 710 | 710
| PH-8-P5 | Not Live - Work in Progress (WIP) | 930 | 465 | 465
| PH-8-P6 | Not Live - Work in Progress (WIP) | 842 | 421 | 421
| PH-8-P7 | Temporary Budget Removal | 980 | 490 | 490
| PH-8-P8 | Temporary Budget Removal | 802 | 401 | 401
Faisalabad | Fesco Abdullahpur | Live - As per Plan | 50 | 20 | 20
| Fesco Colony 132 KV | Live - As per Plan | 24 | 9.6 | 9.6
| NAYAB Colony Directors Residencies | Live - As per Plan | 4 | 1.6 | 1.6
| Officers Colony Canal Road | Live - As per Plan | 90 | 36 | 36
Faisalabad Citi Hosuing Extension | P4-Citi Housing | Not Live - Work in Progress (WIP) | 2926 | 1755.6
| P1, Extended Part | Not Live - Work in Progress (WIP) | 386 | 231.6
Faisalabad Misc Areas | CITI Housing PH-2_Main | Live - As per Plan | 2620 | 1310 | 1310
| Eden Orchards | Live - As per Plan | 1778 | 889 | 889
| Kaleem Shaheed Colony-2 | Live - As per Plan | 842 | 421 | 421
Faisalabad Ph4 | Al Barkat Villas | Swap Cases | 190 | 76 | 76
| Al Rehmat Villa | Live - As per Plan | 228 | 91.2 | 91.2
| Bilal City | Live - As per Plan | 170 | 68 | 68
| Canal Burg | Live - As per Plan | 206 | 82.4 | 82.4
| Canal Garden_Canal Rd | Live - As per Plan | 342 | 136.8 | 136.8
| Canal Park | Live - As per Plan | 140 | 56 | 56
| CITI Housing D Block | Live - As per Plan | 524 | 209.6 | 209.6
| Eden Villas | Live - As per Plan | 1088 | 435.2 | 435.2
| FDA City_P1 | Live - As per Plan | 3278 | 1311.2 | 1311.2
| FDA City_P2 | Live - As per Plan | 3476 | 1390.4 | 1390.4
| FDA City_P3 | Live - As per Plan | 5098 | 2039.2 | 2039.2
| Green Village | Live - As per Plan | 60 | 24 | 24
| Gulshan e Haram-II | Live - As per Plan | 346 | 138.4 | 138.4
| Gulshan e Makkah | Live - As per Plan | 460 | 184 | 184
| Haneef Garden | Live - As per Plan | 78 | 31.2 | 31.2
| Iqbal Stadium Comm.Area | Live - As per Plan | 106 | 42.4 | 42.4
| Jalvi Market | Live - As per Plan | 524 | 209.6 | 209.6
| Khy-e-Manzoor | Swap Cases | 432 | 172.8 | 172.8
| Layllpur Garden | Live - As per Plan | 482 | 192.8 | 192.8
| M3-Ind.Estate_P1 | Permenant Budget Removal | 322 | 128.8 | 128.8
| M3-Ind.Estate_P2 | Permenant Budget Removal | 298 | 119.2 | 119.2
| Madina Town | Live - As per Plan | 2346 | 938.4 | 938.4
| Meadows_I | Live - As per Plan | 144 | 57.6 | 57.6
| Mujahid Town_Ali Town | Live - As per Plan | 334 | 133.6 | 133.6
| Naimat Colony | Live - As per Plan | 1434 | 573.6 | 573.6
| Nawab City | Live - As per Plan | 350 | 140 | 140
| Royal Villas EXT. | Live - As per Plan | 298 | 119.2 | 119.2
| Samanabad | Live - As per Plan | 2792 | 1116.8 | 1116.8
| Satellite Town | Live - As per Plan | 1610 | 644 | 644
| Shehzad Colony | Live - As per Plan | 414 | 165.6 | 165.6
| Wapda Town | Live - As per Plan | 710 | 284 | 284
| Younas Town | Live - As per Plan | 148 | 59.2 | 59.2
| Zuabir Colony | Live - As per Plan | 394 | 157.6 | 157.6
Gujranwala | Tariq Garden & Makki Road Area | Not Live - Work in Progress (WIP) | 970 | 388 | 388
Gujranwala Makki Road | PK-01 | Not Live - Work in Progress (WIP) | 5402 | 2160.8
| PK-02 | Not Live - Work in Progress (WIP) | 7946 | 3178.4
Gujranwala Ph2 | Al mansoorah colony | Live - As per Plan | 492 | 196.8 | 196.8
| Aman Society | Live - As per Plan | 96 | 38.4 | 38.4
| Aurangzaib Town | Live - As per Plan | 594 | 237.6 | 237.6
| Civil Lines | Live - As per Plan | 1248 | 499.2 | 499.2
| DC Colony ext.PK_1 | Live - As per Plan | 1230 | 492 | 492
| DC Colony ext.PK_2 | Live - As per Plan | 722 | 288.8 | 288.8
| G magnolia Remaining Part | Live - As per Plan | 1520 | 608 | 608
| Garjakh Road | Not Live - Work in Progress (WIP) | 3480 | 1392 | 1392
| Ghordor Road P1 | Live - As per Plan | 3824 | 1529.6 | 1529.6
| Ghordor Road P2 | Live - As per Plan | 4278 | 1711.2 | 1711.2
| Ghordor Road P3 | Live - As per Plan | 3376 | 1350.4 | 1350.4
| Ghordor Road P4 | Live - As per Plan | 2012 | 804.8 | 804.8
| Green Valley Ph-6 | Live - As per Plan | 442 | 176.8 | 176.8
| Gulshan Aziz Colony | Live - As per Plan | 388 | 155.2 | 155.2
| Hafizabad Road | Live - As per Plan | 4144 | 1657.6 | 1657.6
| Jalil Town | Live - As per Plan | 1492 | 596.8 | 596.8
| Jinnah Road | Live - As per Plan | 6232 | 2492.8 | 2492.8
| Jinnah Road 2 | Not Live - Work in Progress (WIP) | 3502 | 1400.8 | 1400.8
| Kashmir Colony 1 & 2 | Not Live - Others Reasons | 2096 | 838.4 | 838.4
| Master Citi Pk-1 | Live - As per Plan | 1678 | 671.2 | 671.2
| Master Citi Pk-2 | Live - As per Plan | 3232 | 1292.8 | 1292.8
| Master Citi Pk-3 | Live - As per Plan | 2608 | 1043.2 | 1043.2
| Nowshehra Road | Not Live - Work in Progress (WIP) | 3950 | 1580 | 1580
| Nowshehra Sansi Road | Not Live - Work in Progress (WIP) | 2714 | 1085.6 | 1085.6
| P1 muslim town | Live - As per Plan | 636 | 254.4 | 254.4
| P2 muslim town | Live - As per Plan | 440 | 176 | 176
| Qasim Town | Live - As per Plan | 1774 | 709.6 | 709.6
| Shalimar Town | Live - As per Plan | 598 | 239.2 | 239.2
| Sialkot By Pass | Live - As per Plan | 1586 | 634.4 | 634.4
| Sialkot Road | Live - As per Plan | 3022 | 1208.8 | 1208.8
| Sui Gas Road Pk1 | Live - As per Plan | 3292 | 1316.8 | 1316.8
| Sui Gas Road Pk2 | Live - As per Plan | 1706 | 682.4 | 682.4
| University Town | Live - As per Plan | 278 | 111.2 | 111.2
| Wafay Citi GG Block | Live - As per Plan | 4322 | 1728.8 | 1728.8
| Waffay Block Rem.Area | Live - As per Plan | 3768 | 1507.2 | 1507.2
Gujranwala Ph3 | Ajwa City_P1 | Live - As per Plan | 2202 | 880.8 | 880.8
| Ajwa City_P2 | Not Live - Work in Progress (WIP) | 3046 | 1218.4 | 1218.4
| Civil Line Area BOQ | Live - As per Plan | 1728 | 691.2 | 691.2
| Civil lines Lower End | Live - As per Plan | 280 | 112 | 112
| Disposal Road | Live - As per Plan | 814 | 325.6 | 325.6
| Fazal Town | Live - As per Plan | 544 | 217.6 | 217.6
| Garden Town_P1 | Live - As per Plan | 2208 | 883.2 | 883.2
| Garden Town_P2 | Live - As per Plan | 892 | 356.8 | 356.8
| Garden Town_P3 | Live - As per Plan | 1132 | 452.8 | 452.8
| Ghorrdo Road | Live - As per Plan | 1276 | 510.4 | 510.4
| GT Rd Pocket 06 | Live - As per Plan | 636 | 254.4 | 254.4
| GT Rd Pocket 07 | Live - As per Plan | 1006 | 402.4 | 402.4
| GT Rd Pocket 08 | Live - As per Plan | 980 | 392 | 392
| GT Rd Pocket 09 | Live - As per Plan | 1388 | 555.2 | 555.2
| GT Rd Pocket 10 | Live - As per Plan | 1400 | 560 | 560
| GT Rd Pocket 11 | Not Live - Others Reasons | 1466 | 586.4 | 586.4
| GT Rd Pocket 12 | Not Live - Others Reasons | 1084 | 433.6 | 433.6
| Hafizabad Road | Live - As per Plan | 234 | 93.6 | 93.6
| Khokhar k_BOQ | Not Live - Work in Progress (WIP) | 1920 | 768 | 768
| Parao Road | Live - As per Plan | 2006 | 802.4 | 802.4
| Pasrur Rd & Skt Bypass | Live - As per Plan | 3576 | 1430.4 | 1430.4
| SKT Rd Pocket 01 | Not Live - Work in Progress (WIP) | 1660 | 664 | 664
| SKT Rd Pocket 02 | Not Live - Work in Progress (WIP) | 3386 | 1354.4 | 1354.4
| SKT Rd Pocket 03 | Not Live - Work in Progress (WIP) | 986 | 394.4 | 394.4
| SKT Rd Pocket 04 | Not Live - Work in Progress (WIP) | 750 | 300 | 300
| SKT Rd Pocket 05 | Live - As per Plan | 424 | 169.6 | 169.6
| Sui Gas Road | Live - As per Plan | 5620 | 2248 | 2248
| Tanveer Town & Ratta Rd | Live - As per Plan | 1692 | 676.8 | 676.8
Gulshan-e-Maymar | Sector P, U, V & SPECHS | Not Live - Work in Progress (WIP) | 1262 | 504.8 | 504.8
| Sector Q | Not Live - Work in Progress (WIP) | 204 | 81.6 | 81.6
| Sector R | Not Live - Others Reasons | 1036 | 414.4 | 414.4
| Sector S | Live - As per Plan | 172 | 68.8 | 68.8
| Sector T | Live - As per Plan | 382 | 152.8 | 152.8
| Sector W, ZA & Colonies | Live - As per Plan | 1912 | 764.8 | 764.8
| Sector X | Not Live - Others Reasons | 2072 | 828.8 | 828.8
| Sector Y | Not Live - Others Reasons | 598 | 239.2 | 239.2
| Sector Z | Live - As per Plan | 1644 | 657.6 | 657.6
Hafizabad | Akhtar Town & Tarrar Road | Not Live - Work to be initiated | 1390 | 625.5 | 625.5
| Al Kareem City | Not Live - Work to be initiated | 1606 | 722.7 | 722.7
| Alipur Chatta Road Pocket 1 | Not Live - Work to be initiated | 666 | 299.7 | 299.7
| Alipur Chatta Road Pocket 2 | Not Live - Work to be initiated | 1622 | 729.9 | 729.9
| Anarkali Bazar | Not Live - Work to be initiated | 362 | 162.9 | 162.9
| Azam Garden | Not Live - Work to be initiated | 446 | 200.7 | 200.7
| Canal & Officer & Faisal | Not Live - Work to be initiated | 1310 | 589.5 | 589.5
| Defence Colony | Not Live - Work to be initiated | 996 | 448.2 | 448.2
| Gulberg | Not Live - Work to be initiated | 210 | 94.5 | 94.5
| Hassan Town | Not Live - Work to be initiated | 2056 | 925.2 | 925.2
| HVTR & MB & POR & JBR | Not Live - Work to be initiated | 2656 | 1195.2 | 1195.2
| Iqbal Garden | Not Live - Work to be initiated | 372 | 167.4 | 167.4
| Kassoki Road P1 | Not Live - Work to be initiated | 1050 | 472.5 | 472.5
| Kassoki Road P2 | Not Live - Work to be initiated | 1096 | 493.2 | 493.2
| Kot Hashmat 1 & Kot Hashmat 2 | Not Live - Work to be initiated | 920 | 414 | 414
| Madina Town | Not Live - Work to be initiated | 238 | 107.1 | 107.1
| Makkah Town & Ali Town | Not Live - Work to be initiated | 2248 | 1011.6 | 1011.6
| Qazipura_Qadirabad Srndg Area | Not Live - Work to be initiated | 806 | 362.7 | 362.7
| Sattellite Town | Not Live - Work to be initiated | 512 | 230.4 | 230.4
| Shalimar_Al Hamra Town | Not Live - Work to be initiated | 540 | 243 | 243
| Sukheke Hafizabad Road | Not Live - Work to be initiated | 2214 | 996.3 | 996.3
| Sultan Residencia Park | Not Live - Work to be initiated | 464 | 208.8 | 208.8
| Sunny Garden | Not Live - Work to be initiated | 580 | 261 | 261
| Tulip City | Not Live - Work to be initiated | 908 | 408.6 | 408.6
| Unknown Society 2 & Iqbal Town | Not Live - Work to be initiated | 296 | 133.2 | 133.2
| Unknown Society 5 | Not Live - Work to be initiated | 500 | 225 | 225
| Zahoor Orchard | Not Live - Work to be initiated | 426 | 191.7 | 191.7
| Zahoor Orchard Town | Not Live - Work to be initiated | 736 | 331.2 | 331.2
Haripur Hazara | Makhan_Malikyar_Kalas | Live - As per Plan | 350 | 140 | 140
| Roshan_Noor ext._Madina_Uni | Live - As per Plan | 680 | 272 | 272
| Sarai Saleh | Not Live - Work to be initiated | 714 | 285.6 | 285.6
Haripur Ph2 | Darvesh P1 | Live - As per Plan | 300 | 120 | 120
| Darvesh P2 | Live - As per Plan | 684 | 273.6 | 273.6
| Gulzar Colony & Main Rd | Live - As per Plan | 424 | 169.6 | 169.6
| Kangra Colony P1 | Live - As per Plan | 978 | 391.2 | 391.2
| Kangra Colony P2 | Live - As per Plan | 1168 | 467.2 | 467.2
| Main KKH & Lari Adda | Live - As per Plan | 782 | 312.8 | 312.8
| Model Town | Live - As per Plan | 398 | 159.2 | 159.2
| Noor Colony | Live - As per Plan | 846 | 338.4 | 338.4
| Pak China Phosphate Colony | Not Live - Work to be initiated | 200 | 80 | 80
| Roshanabad | Live - As per Plan | 208 | 83.2 | 83.2
| T & T Colony | Permenant Budget Removal | 726 | 290.4 | 290.4
| TIP Housing | Live - As per Plan | 1214 | 485.6 | 485.6
Hyderabad | Abdullah Sports Tower Ext | Not Live - Work in Progress (WIP) | 96 | 38.4 | 38.4
| Barrage Colony | Live - Permission Awaited | 608 | 243.2 | 243.2
| Barrage Officer Colony | Live - Permission Awaited | 114 | 45.6 | 45.6
| Bismillah City & Ext | Live - As per Plan | 1042 | 416.8 | 416.8
| Fazal Sun City | Not Live - Permission Issues | 3446 | 1378.4 | 1378.4
| Gulshan e Bakhtawar Ext | Live - Permission Awaited | 502 | 200.8 | 50.2
| Hyd Cantt P01 | Live - Permission Awaited | 190 | 76 | 76
| Hyd Cantt P02 | Live - Permission Awaited | 368 | 147.2 | 147.2
| Hyd Cantt P03 | Live - Permission Awaited | 56 | 22.4 | 22.4
| Ink City 02 P01 | Live - As per Plan | 174 | 69.6 | 69.6
| Ink City 02 P02 | Permenant Budget Removal | 90 | 36 | 36
| Ink City 02 P03 | Live - As per Plan | 216 | 86.4 | 86.4
| Khursheed Town | Permenant Budget Removal | 300 | 120 | 120
| Latifabad No 04 | Not Live - Work in Progress (WIP) | 888 | 355.2 | 355.2
| Latifabad No 09 | Swap Cases | 1316 | 526.4 | 526.4
| Latifabad No 10 | Live - Permission Awaited | 1912 | 764.8 | 764.8
| Marvi Town & Marvi Garden | Live - As per Plan | 592 | 236.8 | 236.8
| MB Shora Colony | Live - Permission Awaited | 902 | 360.8 | 288.64
| New Wahdat Colony | Not Live - Work in Progress (WIP) | 706 | 282.4 | 282.4
| Saima Down Town | Live - As per Plan | 436 | 174.4 | 139.52
| Sarfaraz Colony | Live - Permission Awaited | 242 | 96.8 | 96.8
| Site Area & Shanghai Tower | Live - As per Plan | 270 | 108 | 108
| SSGC Housing | Live - As per Plan | 370 | 148 | 148
| Wapda Colony | Live - Permission Awaited | 674 | 269.6 | 269.6
Hyderabad Misc Areas | Fortune Arcade | Not Live - Work to be initiated | 46 | 18.4 | 18.4
| Indus Society | Live - As per Plan | 212 | 84.8 | 84.8
| Palm Village | Live - As per Plan | 1248 | 499.2 | 499.2
| Shah Nawaz Grand City | Live - As per Plan | 186 | 74.4 | 74.4
ISB DHA Ph4 | DHA Ph-4 P1 | Live - As per Plan | 2138 | 855.2 | 855.2
| DHA Ph-4 P2 | Permenant Budget Removal | 1982 | 792.8 | 792.8
ISB DHA Ph-5 | P1 | Live - As per Plan | 598 | 239.2 | 239.2
| P2 | Live - As per Plan | 816 | 326.4 | 326.4
| P3 | Live - As per Plan | 1148 | 459.2 | 459.2
| P4 | Live - As per Plan | 850 | 340 | 340
| P5 | Live - As per Plan | 1116 | 446.4 | 357.12
ISB-BT-Ph-8 | Bahria P10 | Not Live - Work to be initiated | 2892 | 1156.8 | 1156.8
| Bahria P25 | Not Live - Work to be initiated | 1092 | 436.8 | 436.8
| Bahria P26 | Not Live - Work to be initiated | 2298 | 919.2 | 919.2
| Bahria P3 | Not Live - Work in Progress (WIP) | 994 | 397.6 | 397.6
| Bahria P6 | Not Live - Work to be initiated | 1910 | 764 | 764
| Bahria P8 | Not Live - Work to be initiated | 2144 | 857.6 | 857.6
| Bahria P9 | Not Live - Work to be initiated | 2312 | 924.8 | 924.8
Islamabad | G-11 P1 | Not Live - Work to be initiated | 1444 | 577.6 | 577.6
| G-11 P2 | Not Live - Work to be initiated | 1944 | 777.6 | 777.6
| G-11 P3 | Not Live - Work to be initiated | 2684 | 1073.6 | 1073.6
| G-11 P4 | Not Live - Work to be initiated | 3684 | 1473.6 | 1473.6
| H13_Mainly Hostels | Live - As per Plan | 908 | 363.2 | 363.2
| Mumtaz City P1 | Not Live - Work to be initiated | 2016 | 806.4 | 806.4
| Mumtaz City P2 | Not Live - Work to be initiated | 1100 | 440 | 440
| N.Blue Ar. & Other Buildings | Live - As per Plan | 2404 | 961.6 | 961.6
| PAF Tarnol-P1 | Live - As per Plan | 1550 | 620 | 372
| PAF Tarnol-P2 | Live - As per Plan | 1444 | 577.6 | 346.56
| PHA G-11 & I12 | Not Live - Work to be initiated | 4674 | 1869.6 | 1869.6
| University Town P1 | Not Live - Work to be initiated | 1232 | 492.8 | 492.8
| University Town P2 | Not Live - Work to be initiated | 1528 | 611.2 | 611.2
Islamabad DHA Ph1 | DHA_Ph-1_P1 | Live - As per Plan | 930 | 372 | 372
| DHA_Ph-1_P2 | Temporary Budget Removal | 1258 | 503.2 | 503.2
| DHA_Ph-1_P3 | Temporary Budget Removal | 1112 | 444.8 | 444.8
Islamabad Misc Areas | CTD_ANF_Police Lines_H11 | Not Live - Others Reasons | 522 | 261 | 261
| E-16 | Live - As per Plan | 726 | 363 | 363
| Hostel City | Live - As per Plan | 394 | 197 | 197
| I-10 P1 | Live - As per Plan | 1220 | 610 | 610
| I-10 P2 | Live - As per Plan | 812 | 406 | 406
| I-10 P3 | Live - As per Plan | 1192 | 596 | 596
| I-10 P4 | Live - As per Plan | 1810 | 905 | 905
| I-10 P5 | Live - As per Plan | 2218 | 1109 | 1109
| I-11 Aerial | Live - As per Plan | 418 | 209 | 209
| I-11P1 | Live - As per Plan | 570 | 285 | 285
| I-11P2 | Live - As per Plan | 1504 | 752 | 752
| I-9 P1 | Live - As per Plan | 1222 | 611 | 611
| I-9 P2 | Live - As per Plan | 794 | 397 | 397
| I-9 P3 | Live - As per Plan | 752 | 376 | 376
| I-9 P4 | Live - As per Plan | 836 | 418 | 418
Islamabad Ph3 (P2) | B-17 Blk-D extn | Live - As per Plan | 588 | 235.2 | 235.2
| B-17 BlockD | Live - As per Plan | 1124 | 449.6 | 449.6
| B-17 BlockF-P1 | Live - As per Plan | 1978 | 791.2 | 791.2
| B-17 BlockF-P2 | Live - As per Plan | 2512 | 1004.8 | 1004.8
| E-17 | Live - As per Plan | 876 | 350.4 | 350.4
| Emaar P1 | Permenant Budget Removal | 324 | 129.6 | 129.6
| Emaar P2 | Permenant Budget Removal | 356 | 142.4 | 142.4
| Emaar P3 | Temporary Budget Removal | 462 | 184.8 | 184.8
| Faisal Town P2 | Live - As per Plan | 1516 | 606.4 | 606.4
| Faisal Town P3 | Live - As per Plan | 2208 | 883.2 | 883.2
| Faisal Town P4 | Live - As per Plan | 1434 | 573.6 | 573.6
| FMC_Partial | Live - As per Plan | 3146 | 1258.4 | 1258.4
| Hostel City_Extn | Live - As per Plan | 278 | 111.2 | 111.2
| I-14-P1 | Live - As per Plan | 1978 | 791.2 | 791.2
| I-14-P2 | Live - As per Plan | 1606 | 642.4 | 642.4
| I-14-P3 | Live - As per Plan | 1710 | 684 | 684
| I-14-P4 | Live - As per Plan | 1848 | 739.2 | 739.2
Jhang | Al Karam City Phase 1 | Not Live - Work to be initiated | 602 | 270.9 | 270.9
| Ali Town | Not Live - Work to be initiated | 1610 | 724.5 | 724.5
| Chaudary Colony | Not Live - Work to be initiated | 1020 | 459 | 459
| Civil Lines | Not Live - Work to be initiated | 950 | 427.5 | 427.5
| Ghaziabad | Not Live - Work to be initiated | 2296 | 1033.2 | 1033.2
| Gulshan Colony | Not Live - Work to be initiated | 1372 | 617.4 | 617.4
| Khokar Colony | Not Live - Work to be initiated | 244 | 109.8 | 109.8
| Lalazar Colony | Not Live - Work to be initiated | 532 | 239.4 | 239.4
| Madina Colony | Not Live - Work to be initiated | 814 | 366.3 | 366.3
| Officers Colony | Not Live - Work to be initiated | 330 | 148.5 | 148.5
| Paradise City | Not Live - Work to be initiated | 602 | 270.9 | 270.9
| Samanabad | Not Live - Work to be initiated | 1302 | 585.9 | 585.9
| Satellite Town_PK1 | Not Live - Work to be initiated | 1770 | 796.5 | 796.5
| Satellite Town_PK2 | Not Live - Work to be initiated | 920 | 414 | 414
| Satellite Town_PK3 | Not Live - Work to be initiated | 746 | 335.7 | 335.7
| Shadab Colony | Not Live - Work to be initiated | 490 | 220.5 | 220.5
| Shah Block | Not Live - Work to be initiated | 270 | 121.5 | 121.5
| Sultan Colony | Not Live - Work to be initiated | 630 | 283.5 | 283.5
| Unknown Society 3 | Not Live - Work to be initiated | 266 | 119.7 | 119.7
| Unknown-1 | Not Live - Work to be initiated | 270 | 121.5 | 121.5
| Unknown-2 | Not Live - Work to be initiated | 324 | 145.8 | 145.8
Jhelum (P4) | Bagga | Live - As per Plan | 228 | 91.2
| Chitan | Live - As per Plan | 294 | 117.6
| Eid Gah | Live - As per Plan | 206 | 82.4
| Gharmala | Live - As per Plan | 202 | 80.8
| Gujjar pur | Not Live - Others Reasons | 126 | 50.4
| Kantrila | Permenant Budget Removal | 238 | 95.2
| Kantrili | Permenant Budget Removal | 208 | 83.2
| Kotli Allahyar | Live - As per Plan | 266 | 106.4
| Saeela | Live - As per Plan | 694 | 277.6
| Gharmala Monan | Permenant Budget Removal | 132 | 52.8
| Jahangir | Permenant Budget Removal | 214 | 85.6
| Jhakkarr | Permenant Budget Removal | 448 | 179.2
| Chak Hafizan | Permenant Budget Removal | 168 | 67.2
| Chak Doulat | Permenant Budget Removal | 154 | 61.6
| Ranjha Mahira | Permenant Budget Removal | 532 | 212.8
| Muftian | Permenant Budget Removal | 130 | 52
| Chak Akka | Permenant Budget Removal | 1976 | 790.4
| Thatti Gujran & Mughlan | Not Live - Others Reasons | 448 | 179.2
Jhelum- Kala Gojran | Kala Gujran_P1 | Live - As per Plan | 680 | 272 | 272
| Kala Gujran_P2 | Live - As per Plan | 422 | 168.8 | 168.8
Jhelum Ph2 | Bagh Mohalla & Naya Mohallla | Live - As per Plan | 1252 | 500.8 | 500.8
| Bala Gujjran | Live - As per Plan | 246 | 98.4 | 98.4
| Chal Jamal | Swap Cases | 312 | 124.8 | 124.8
| Citi Housing Block D_E_F Extn. | Not Live - Work to be initiated | 1426 | 570.4 | 570.4
| Kharala | Live - As per Plan | 640 | 256 | 256
| Makhdoomabad | Live - As per Plan | 726 | 290.4 | 290.4
| Shamas Pur | Swap Cases | 198 | 79.2 | 79.2
Karachi Misc Areas | Falaknaz Pebbles | Live - As per Plan | 108 | 54 | 54
| FB Area Block-22 | Live - As per Plan | 326 | 163 | 163
| Gulshan Block-19 | Live - As per Plan | 768 | 384 | 384
| MBCHS | Live - As per Plan | 720 | 360 | 360
| Model Colony | Live - As per Plan | 1302 | 651 | 651
| Muslim Khatri CHS | Live - As per Plan | 352 | 176 | 176
| PIB Colony | Not Live - Work to be initiated | 2248 | 1124 | 1124
| Soomra Society | Live - As per Plan | 548 | 274 | 274
Karachi Ph5 | AbrazulMinal_KingsBridgeView | Not Live - Permission Issues | 1400 | 560 | 560
| AFOHS PK-1 | Live - As per Plan | 984 | 393.6 | 393.6
| AFOHS PK-2 | Live - As per Plan | 478 | 191.2 | 191.2
| AFOHS PK-3 | Not Live - Work to be initiated | 1256 | 502.4 | 502.4
| Al Rahim City Ph-1 | Live - As per Plan | 488 | 195.2 | 195.2
| Al Rahim City Ph-2 | Live - As per Plan | 480 | 192 | 192
| Amynabad | Live - As per Plan | 290 | 116 | 116
| Callachi Society | Live - As per Plan | 1626 | 650.4 | 325.2
| Chandni Chowk | Not Live - Permission Issues | 1390 | 556 | 556
| Custom Preventive CHS | Live - Permission Awaited | 258 | 103.2 | 103.2
| Diamond City_Wasi Country Park | Not Live - Permission Issues | 1154 | 461.6 | 461.6
| F.B Area Block-21 | Not Live - Permission Issues | 2160 | 864 | 864
| Gulshan Block-4A | Live - As per Plan | 580 | 232 | 232
| Khayaban-e-Patni CHS | Swap Cases | 212 | 84.8 | 84.8
| Kings_ASF_ Tower_P01 | Not Live - Permission Issues | 2016 | 806.4 | 806.4
| Kings_ASF_ Tower_P02 | Not Live - Permission Issues | 2016 | 806.4 | 806.4
| Kokan CHS | Swap Cases | 346 | 138.4 | 138.4
| Madras CHS | Live - As per Plan | 734 | 293.6 | 293.6
| NIPA Society | Not Live - Permission Issues | 284 | 113.6 | 113.6
| Oasis Park Residencia | Not Live - Work to be initiated | 346 | 138.4 | 138.4
| Pak Ideal CHS P1 | Live - As per Plan | 452 | 180.8 | 180.8
| Pak Ideal CHS P2 | Live - As per Plan | 448 | 179.2 | 179.2
| PiliBheet Society | Live - As per Plan | 728 | 291.2 | 291.2
| Pioneer Fountain_KHI UNI | Live - As per Plan | 262 | 104.8 | 104.8
| Redline | Not Live - Work in Progress (WIP) | 310 | 124 | 124
| Sadabad Society | Not Live - Permission Issues | 348 | 139.2 | 139.2
| Saima Villas | Live - As per Plan | 1342 | 536.8 | 536.8
| Scheme33_MalirCantt_MDU_P01 | Live - As per Plan | 2356 | 942.4 | 942.4
| Scheme33_MalirCantt_MDU_P02 | Live - As per Plan | 1320 | 528 | 528
| Scheme33_MalirCantt_MDU_P03 | Live - As per Plan | 1238 | 495.2 | 495.2
| Scheme33_MalirCantt_MDU_P04 | Live - As per Plan | 1104 | 441.6 | 441.6
| Sum Sum Tower | Not Live - Permission Issues | 384 | 153.6 | 153.6
| Water Board Society | Live - As per Plan | 120 | 48 | 48
| Ya Rehman Society | Live - As per Plan | 182 | 72.8 | 72.8
Kasur | Abdul Khaliq Colony | Not Live - Work to be initiated | 82 | 32.8 | 32.8
| Ali Ahmed Shah Colony | Not Live - Work to be initiated | 712 | 284.8 | 284.8
| Al-Kareem Garden | Not Live - Work to be initiated | 440 | 176 | 176
| Al-Majeed Housing Scheme | Not Live - Work to be initiated | 460 | 184 | 184
| Azhar Colony Khara Road and Bas | Not Live - Work to be initiated | 1660 | 664 | 664
| Defence Colony | Not Live - Work to be initiated | 632 | 252.8 | 252.8
| Dhorr Kot Road & Kot Fateh Din | Not Live - Work to be initiated | 2180 | 872 | 872
| Gulberg | Not Live - Work to be initiated | 1394 | 557.6 | 557.6
| Haji Park Bypass | Not Live - Work to be initiated | 328 | 131.2 | 131.2
| Haji Park Commercial | Not Live - Work to be initiated | 114 | 45.6 | 45.6
| Haji Park Phase 1 | Not Live - Work to be initiated | 390 | 156 | 156
| Hamza Town | Not Live - Work to be initiated | 204 | 81.6 | 81.6
| Ideal Garden Housing | Not Live - Work to be initiated | 388 | 155.2 | 155.2
| Kasur Raiwand Road | Not Live - Work to be initiated | 902 | 360.8 | 360.8
| Khara Road | Not Live - Work to be initiated | 1968 | 787.2 | 787.2
| Khara Road and Nafees Colony | Not Live - Work to be initiated | 2524 | 1009.6 | 1009.6
| Madina Town | Not Live - Work to be initiated | 136 | 54.4 | 54.4
| Main Kasur P-1 | Not Live - Work to be initiated | 2010 | 804 | 804
| Main Kasur P-2 | Not Live - Work to be initiated | 3350 | 1340 | 1340
| Main Kasur P-3 | Not Live - Work to be initiated | 424 | 169.6 | 169.6
| Main Kasur P-4 | Not Live - Work to be initiated | 1954 | 781.6 | 781.6
| Main Kasur P-5 | Not Live - Work to be initiated | 1158 | 463.2 | 463.2
| Maqbool Town | Not Live - Work to be initiated | 126 | 50.4 | 50.4
| Munir Shaheed Colony | Not Live - Work to be initiated | 682 | 272.8 | 272.8
| Mustafa Park | Not Live - Work to be initiated | 186 | 74.4 | 74.4
| Nadeem Park | Not Live - Work to be initiated | 354 | 141.6 | 141.6
| New City | Not Live - Work to be initiated | 940 | 376 | 376
| Officer Colony | Not Live - Work to be initiated | 204 | 81.6 | 81.6
| Peeru wala Road | Not Live - Work to be initiated | 1370 | 548 | 548
| Qadirabad , NoorShah Wali and K | Not Live - Work to be initiated | 4836 | 1934.4 | 1934.4
| Road Kot | Not Live - Work to be initiated | 1406 | 562.4 | 562.4
| Saeedabad | Not Live - Work to be initiated | 2064 | 825.6 | 825.6
| Saif City | Not Live - Work to be initiated | 376 | 150.4 | 150.4
| Saleem Town Ph-1 | Not Live - Work to be initiated | 1420 | 568 | 568
| Tariq Colony | Not Live - Work to be initiated | 1330 | 532 | 532
Khyban-e-Amin, High court & Al Rehman PH4 | PK01 | Not Live - Work in Progress (WIP) | 4706 | 1882.4
| PK02 | Not Live - Others Reasons | 938 | 375.2
| PK03 | Not Live - Work in Progress (WIP) | 2990 | 1196
| PK04 | Not Live - Work in Progress (WIP) | 2590 | 1036
| PK05 | Not Live - Others Reasons | 1756 | 702.4
| High Court Society | Live - As per Plan | 776 | 310.4
| Al Rehman Garden 4 | Not Live - Work in Progress (WIP) | 978 | 391.2
Lahore Misc Areas | Al-Hamd Society | Live - As per Plan | 264 | 132 | 132
| Al-Raheems Homes | Live - As per Plan | 120 | 60 | 60
| BOR | Live - As per Plan | 788 | 394 | 394
| Cavalry Ext Aerial | Live - As per Plan | 1792 | 896 | 896
| Cavalry Ext Hybrid | Live - As per Plan | 1792 | 896 | 896
| Dream Avenue | Live - As per Plan | 506 | 253 | 253
| Fazaiya Society P1 | Live - As per Plan | 1470 | 735 | 735
| Fazaiya Society P2 | Live - As per Plan | 1492 | 746 | 746
| Judicial Colony Ph 2 | Live - As per Plan | 466 | 233 | 233
| Mansoora | Live - As per Plan | 140 | 70 | 70
| Misc. Areas | Live - As per Plan | 400 | 200 | 200
| Sultan Town | Live - As per Plan | 494 | 247 | 247
| Wafaqi Colony | Live - As per Plan | 2678 | 1339 | 1339
| Wocland | Live - As per Plan | 148 | 74 | 74
Lahore Ph5 | Abid Market | Not Live - Work in Progress (WIP) | 656 | 262.4 | 262.4
| Etihad Town | Live - As per Plan | 2606 | 1042.4 | 1042.4
| Ferozpur Road | Not Live - Work in Progress (WIP) | 2278 | 911.2 | 911.2
| Ilyas Colony | Not Live - Others Reasons | 616 | 246.4 | 246.4
| Jail Road Bird Wood & Waris Co | Live - Permission Awaited | 454 | 181.6 | 90.8
| Jinnah Colony Aerial | Live - As per Plan | 216 | 86.4 | 86.4
| Lawarance Road & China Road | Not Live - Permission Issues | 372 | 148.8 | 148.8
| LC_P1 | Live - As per Plan | 1818 | 727.2 | 727.2
| LC_P2 | Live - As per Plan | 742 | 296.8 | 296.8
| LC_P3 | Live - As per Plan | 790 | 316 | 316
| LC_P4 | Live - As per Plan | 828 | 331.2 | 331.2
| LC_P5 | Live - As per Plan | 862 | 344.8 | 344.8
| LC_P6 | Live - As per Plan | 1176 | 470.4 | 470.4
| LC_P7 | Live - As per Plan | 908 | 363.2 | 363.2
| LDA_Ph-1 | Live - As per Plan | 1956 | 782.4 | 782.4
| LDA_Ph-2 | Live - As per Plan | 1970 | 788 | 788
| LDA_Ph-3 | Live - As per Plan | 2082 | 832.8 | 832.8
| Mall Road | Live - As per Plan | 820 | 328 | 328
| N LHR City P1 | Live - As per Plan | 1940 | 776 | 776
| N LHR City P2 | Live - As per Plan | 1560 | 624 | 624
| PAEC T.Buried | Live - As per Plan | 1364 | 545.6 | 545.6
| Park View_Hybrid_P1 | Permenant Budget Removal | 1266 | 506.4 | 506.4
| Park View_T.B_P2 | Permenant Budget Removal | 2378 | 951.2 | 951.2
| Park View_T.B_P3 | Permenant Budget Removal | 1510 | 604 | 604
| Park View_T.B_P4 | Permenant Budget Removal | 3186 | 1274.4 | 1274.4
| Rehan Gardens Ph 1&2 | Not Live - Work to be initiated | 538 | 215.2 | 215.2
| Sherwani_Shadab Hsng Scty | Live - As per Plan | 1362 | 544.8 | 544.8
| Township_A2_P01 | Live - As per Plan | 1338 | 535.2 | 535.2
| Township_A2_P02 | Live - As per Plan | 2004 | 801.6 | 801.6
| Township_B1_P01 | Live - As per Plan | 766 | 306.4 | 306.4
| Township_B1_P02 | Live - As per Plan | 928 | 371.2 | 371.2
| Township_B1_P03 | Live - As per Plan | 1378 | 551.2 | 551.2
| Township_B1_P04 | Live - As per Plan | 1354 | 541.6 | 541.6
| Township_B2_P01 | Live - As per Plan | 434 | 173.6 | 173.6
| Township_B2_P02 | Live - As per Plan | 620 | 248 | 248
| Township_C1_BL03 | Live - As per Plan | 558 | 223.2 | 223.2
| Township_C2_BL03 | Live - As per Plan | 558 | 223.2 | 223.2
Lalamusa | Darbari, Qureshi Muhallah,Shad | Not Live - Work to be initiated | 1678 | 755.1 | 755.1
| Dhamah,Lalazar & Railway Colony | Not Live - Work to be initiated | 532 | 239.4 | 239.4
| Eid Gah, Rehmat Abbas,Kaira Muh | Not Live - Work to be initiated | 2802 | 1260.9 | 1260.9
| Gunjra Road,Bagh e Syedan & Bud | Not Live - Work to be initiated | 1600 | 720 | 720
| Karimpura, Hajipura, SabriMuhal | Not Live - Work to be initiated | 1876 | 844.2 | 844.2
| Mehar Muhallah,Weraowala,Sadiqa | Not Live - Work to be initiated | 1454 | 654.3 | 654.3
| Syda Gol,Faisalpur,Jogi&Qasbah& | Not Live - Work to be initiated | 3950 | 1777.5 | 1777.5
| Thirkian,Asghar Town,Ahmad Town | Not Live - Work to be initiated | 1096 | 493.2 | 493.2
LHE - DHA Phase 6, EME, Rahbar | Rahbr-Sec-1-P1 | Not Live - Work in Progress (WIP) | 1190 | 476
| Rahbr-Sec-1-P2 | Not Live - Work in Progress (WIP) | 952 | 380.8
| Rahbr-Sec-2-P1 | Not Live - Work in Progress (WIP) | 2848 | 1139.2
| Rahbr-Sec-2-P2 | Not Live - Work in Progress (WIP) | 2836 | 1134.4
Lhr MW City & Al Hafeez Ph-1 | Pocket-1 | Not Live - Work in Progress (WIP) | 1948 | 779.2
| Pocket-2 | Not Live - Work in Progress (WIP) | 828 | 331.2
| Pocket-3 | Not Live - Work in Progress (WIP) | 2042 | 816.8
| Pocket-4 | Not Live - Work in Progress (WIP) | 2728 | 1091.2
| Pocket-5 | Not Live - Others Reasons | 2654 | 1061.6
| Pocket-6 | Not Live - Work in Progress (WIP) | 986 | 394.4
| Pocket-7 | Not Live - Work in Progress (WIP) | 1778 | 711.2
| Al Hafeez Garden Ph-1 | Not Live - Others Reasons | 1406 | 562.4
Mandi Bahauddin | Al-Rehman, Eiffel, Sultan Town | Not Live - Work to be initiated | 1566 | 704.7 | 704.7
| Arshad Town and Model Town | Not Live - Work to be initiated | 2134 | 960.3 | 960.3
| Bangali Town | Not Live - Work to be initiated | 750 | 337.5 | 337.5
| District Complex, Complex City | Not Live - Work to be initiated | 250 | 112.5 | 112.5
| Gillani Town,Tariqabad,Sufipura | Not Live - Work to be initiated | 3164 | 1423.8 | 1423.8
| Gulberg Town | Not Live - Work to be initiated | 326 | 146.7 | 146.7
| Gurrah Muhallah | Not Live - Work to be initiated | 3690 | 1660.5 | 1660.5
| Hajipura | Not Live - Work to be initiated | 788 | 354.6 | 354.6
| Hamza Ali town | Not Live - Work to be initiated | 548 | 246.6 | 246.6
| Jinnah City | Not Live - Work to be initiated | 224 | 100.8 | 100.8
| Kachehri Area | Not Live - Work to be initiated | 2708 | 1218.6 | 1218.6
| Manzoorabad | Not Live - Work to be initiated | 412 | 185.4 | 185.4
| Paradise Complex | Not Live - Work to be initiated | 134 | 60.3 | 60.3
| Qila Gujjran, Rehmanpura | Not Live - Work to be initiated | 1708 | 768.6 | 768.6
| Ranger Colony | Not Live - Work to be initiated | 382 | 171.9 | 171.9
| Royal Palm City | Not Live - Work to be initiated | 312 | 140.4 | 140.4
| Sattelite Town | Not Live - Work to be initiated | 736 | 331.2 | 331.2
| Shalimar City | Not Live - Work to be initiated | 562 | 252.9 | 252.9
| Sufi City Housing Scheme PK-1 | Not Live - Work to be initiated | 1542 | 693.9 | 693.9
| Sufi City Housing Scheme PK-2 | Not Live - Work to be initiated | 2672 | 1202.4 | 1202.4
| Tajpura, Shalimar & Amin Twn | Not Live - Work to be initiated | 2636 | 1186.2 | 1186.2
| Unkown Area 2 | Not Live - Work to be initiated | 1338 | 602.1 | 602.1
| Unkown Area 3 | Not Live - Work to be initiated | 1152 | 518.4 | 518.4
| Unkown Area 4 | Not Live - Work to be initiated | 940 | 423 | 423
| Unkown Area 6 | Not Live - Work to be initiated | 2806 | 1262.7 | 1262.7
Mardan | Bismillah Town | Live - As per Plan | 512 | 204.8 | 204.8
| Gulberg Town | Live - As per Plan | 552 | 220.8 | 220.8
| Gulshan Town Ph1 | Live - As per Plan | 376 | 150.4 | 150.4
| Mohabatabad P1 | Swap Cases | 340 | 136 | 136
| Mohabatabad P2 | Swap Cases | 456 | 182.4 | 182.4
| Orchird Villas | Live - As per Plan | 286 | 114.4 | 114.4
Mardan Ph2 | Abdullah Colony & Nawa Killy | Live - As per Plan | 394 | 157.6 | 157.6
| Bari Chum | Live - As per Plan | 1134 | 453.6 | 453.6
| Bicket Gunj | Live - As per Plan | 654 | 261.6 | 261.6
| Cantt | Live - As per Plan | 314 | 125.6 | 125.6
| Center Colony | Live - As per Plan | 288 | 115.2 | 115.2
| Daman & Kilo Town | Live - As per Plan | 612 | 244.8 | 244.8
| Defence Housing | Live - As per Plan | 50 | 20 | 20
| Gaju_Khaksar_Shams Gunj | Live - As per Plan | 1262 | 504.8 | 504.8
| Green Acres P1 | Live - As per Plan | 966 | 386.4 | 386.4
| Green Acres P2 | Live - As per Plan | 500 | 200 | 200
| Guli Bagh | Live - As per Plan | 1122 | 448.8 | 448.8
| Katcheri Road | Live - As per Plan | 444 | 177.6 | 177.6
| Labour Colony | Permenant Budget Removal | 458 | 183.2 | 183.2
| Maqam Mandi | Live - As per Plan | 120 | 48 | 48
| Muslimabad | Live - As per Plan | 2262 | 904.8 | 904.8
| New Bagh Colony | Live - As per Plan | 524 | 209.6 | 209.6
| New Surkh Dheri | Live - As per Plan | 480 | 192 | 192
| Pohan Colony | Live - As per Plan | 460 | 184 | 184
| Shamsi Rd | Live - As per Plan | 462 | 184.8 | 184.8
| Sharifabad | Permenant Budget Removal | 300 | 120 | 120
| VIP Housing | Not Live - Permission Issues | 188 | 75.2 | 75.2
Mingora | Between Fizaghat & Sangota | Not Live - Work to be initiated | 62 | 24.8 | 24.8
| Airport (Ghanshal village) P01 | Live - As per Plan | 500 | 200 | 200
| Ingaroderai-Takhtaband P01 | Live - As per Plan | 2350 | 940 | 940
| Ingaroderai-Takhtaband P02 | Live - As per Plan | 1080 | 432 | 432
| Ingaroderai-Takhtaband P03 | Live - As per Plan | 946 | 378.4 | 378.4
| Kabal P01 | Live - As per Plan | 104 | 41.6 | 41.6
| Kabal P02 | Live - As per Plan | 132 | 52.8 | 52.8
| Kabal P03 | Live - As per Plan | 422 | 168.8 | 168.8
| Kabal P04 | Live - As per Plan | 150 | 60 | 60
| Kabal P05 | Live - As per Plan | 508 | 203.2 | 203.2
| Kabal P06 | Live - As per Plan | 162 | 64.8 | 64.8
| Kabal P07 | Live - As per Plan | 180 | 72 | 72
| Kabal P08 | Live - As per Plan | 462 | 184.8 | 184.8
| Kabal P09 | Live - As per Plan | 1228 | 491.2 | 491.2
| Odigram P01 | Live - As per Plan | 536 | 214.4 | 214.4
| Odigram P02 | Live - As per Plan | 1110 | 444 | 444
| Odigram P03 | Live - As per Plan | 1086 | 434.4 | 434.4
| Odigram P04 | Live - As per Plan | 426 | 170.4 | 170.4
| Odigram P05 | Live - As per Plan | 114 | 45.6 | 45.6
| Odigram P06 | Live - As per Plan | 764 | 305.6 | 305.6
| Shagai & Akhon Baba P01 | Not Live - Work to be initiated | 818 | 327.2 | 327.2
| Shagai & Akhon Baba P02 | Not Live - Work in Progress (WIP) | 704 | 281.6 | 281.6
| Shia Bagh & BUH Qambar P01 | Live - As per Plan | 714 | 285.6 | 285.6
| Shia Bagh & BUH Qambar P02 | Live - As per Plan | 450 | 180 | 180
Model Town_Sh Faisal_Faisal Cant | Model Colony | Not Live - Work to be initiated | 1302 | 520.8
| SHFT Pocket-1 | Not Live - Work to be initiated | 658 | 263.2
| SHFT Pocket-2 | Not Live - Work to be initiated | 1814 | 725.6
| SHFT Pocket-3 | Not Live - Work to be initiated | 1438 | 575.2
| SHFT Pocket-4 | Not Live - Work to be initiated | 810 | 324
| SHFT Pocket-5 | Not Live - Work to be initiated | 1628 | 651.2
| TariqBinZayed | Not Live - Work to be initiated | 1156 | 462.4
| Gulshan-e-Rafi | Not Live - Work to be initiated | 712 | 284.8
| Salman Gardens | Not Live - Work to be initiated | 382 | 152.8
| Anwar-e-Ibrahim | Not Live - Work to be initiated | 558 | 223.2
| Rafi Gardens_Gulshan e Muneer | Not Live - Work to be initiated | 890 | 356
| M.Ali Shaheed Society_Maaz Town | Not Live - Work to be initiated | 596 | 238.4
| Punjabi Sodagran Society | Not Live - Work to be initiated | 450 | 180
| Shamsi Society | Not Live - Work to be initiated | 1744 | 697.6
| Bilal Town | Not Live - Work to be initiated | 2212 | 884.8
| Alfalah Society | Not Live - Work to be initiated | 1330 | 532
| Rafah-e-Aam Society | Not Live - Work to be initiated | 834 | 333.6
| Hansabad | Not Live - Work to be initiated | 528 | 211.2
| Bagh-e-Malir | Not Live - Work to be initiated | 792 | 316.8
| Gulshan-e-Tayyaba | Not Live - Work to be initiated | 488 | 195.2
| Gohar Green | Not Live - Work to be initiated | 1906 | 762.4
| Kazimabad | Not Live - Work to be initiated | 1154 | 461.6
| Surti_Humaira_Jami | Not Live - Work to be initiated | 1516 | 606.4
| Alamgir&Jannat ul Barkat | Not Live - Work to be initiated | 1020 | 408
| Pak Kausar Town | Not Live - Work to be initiated | 1034 | 413.6
| Darakhshan Society PK1 | Not Live - Work to be initiated | 222 | 88.8
| Darakhshan Society PK2 | Not Live - Work to be initiated | 2078 | 831.2
| Millat Garden | Not Live - Work to be initiated | 610 | 244
Multan Misc. Areas | Al Khalil Housing Scheme | Live - As per Plan | 140 | 70 | 70
| Allabad, AliTown & IslamPura | Live - As per Plan | 1024 | 512 | 512
| AlQuresh Phase 1 | Live - As per Plan | 1366 | 683 | 683
| AlQuresh Phase 2 | Not Live - Permission Issues | 1420 | 710 | 710
| Aslam, Mujtuba & Canal Colony | Live - As per Plan | 1036 | 518 | 518
| Bahadurpur | Live - As per Plan | 1306 | 653 | 653
| Bast Shor Kot | Live - As per Plan | 508 | 254 | 254
| Bilal Colony & Mukhtyar Town | Live - As per Plan | 1444 | 722 | 722
| Bodla Town | Live - As per Plan | 1514 | 757 | 757
| Bukhari Villas | Live - As per Plan | 476 | 238 | 238
| Canal Cantt Views | Live - As per Plan | 1048 | 524 | 524
| Chah Hadi Wala | Live - As per Plan | 384 | 192 | 192
| Citi Housing Sector A | Live - As per Plan | 526 | 263 | 263
| Citi Housing Sector B | Live - As per Plan | 1082 | 541 | 541
| Citi Housing Sector C | Live - As per Plan | 1274 | 637 | 637
| Defence Housing Society | Swap Cases | 518 | 259 | 259
| Defence villas | Live - As per Plan | 272 | 136 | 136
| Gulberg & New Gulberg | Live - As per Plan | 1084 | 542 | 542
| Gulistan-i-Ashar | Not Live - Work to be initiated | 1012 | 506 | 506
| Gulraiz Town | Live - As per Plan | 720 | 360 | 360
| Gulshan e Faiz | Live - As per Plan | 1328 | 664 | 664
| Gulshan e Iqbal | Live - As per Plan | 216 | 108 | 108
| Gulshen-i-Sardar | Live - As per Plan | 228 | 114 | 114
| Inam City | Permenant Budget Removal | 148 | 74 | 74
| Khan Village II | Live - As per Plan | 454 | 227 | 227
| Khayaban e Kubra | Live - As per Plan | 170 | 85 | 85
| Lasani Colony | Live - As per Plan | 816 | 408 | 408
| Mohsin Town & Rasheed Avenue | Live - As per Plan | 428 | 214 | 214
| Muslim Town | Live - As per Plan | 502 | 251 | 251
| New Naqshband Colony | Live - As per Plan | 990 | 495 | 495
| Qaiserabad | Live - As per Plan | 944 | 472 | 472
| Qasim Pur Colony | Live - As per Plan | 996 | 498 | 498
| Qasim Villas & Shams Colony | Live - As per Plan | 452 | 226 | 226
| Rehman Colony | Live - As per Plan | 334 | 167 | 167
| Sadiqabad latifabad Wahidabad | Live - As per Plan | 2080 | 1040 | 1040
| Shamsi Colony | Live - As per Plan | 252 | 126 | 126
| Unknown 01 | Permenant Budget Removal | 84 | 42 | 42
| Village garden | Not Live - Permission Issues | 148 | 74 | 74
| Writers Colony | Live - As per Plan | 574 | 287 | 287
| Zakariya Villas | Live - As per Plan | 440 | 220 | 220
Multan Ph3 | Adam Housing | Swap Cases | 1130 | 452 | 452
| Al Nawab Rehman Villas AlKareem | Live - As per Plan | 1470 | 588 | 588
| Ali Town | Live - As per Plan | 1486 | 594.4 | 594.4
| Bhutta Colony | Live - As per Plan | 94 | 37.6 | 37.6
| Buch Villas Extn. | Live - As per Plan | 464 | 185.6 | 185.6
| Canal View Multan | Live - As per Plan | 564 | 225.6 | 225.6
| Citi Housing Jinnah Block-P1 | Live - As per Plan | 2128 | 851.2 | 851.2
| Citi Housing Jinnah Block-P2 | Live - As per Plan | 2024 | 809.6 | 809.6
| Citi Housing Sector D | Live - As per Plan | 1256 | 502.4 | 502.4
| Dewan ka Bagh | Live - As per Plan | 1598 | 639.2 | 639.2
| Dream Valley | Live - As per Plan | 118 | 47.2 | 47.2
| Fatima Jinnah Town A | Live - As per Plan | 940 | 376 | 376
| Fatima Jinnah Town B | Live - As per Plan | 1158 | 463.2 | 463.2
| Fatima Jinnah Town C | Live - As per Plan | 502 | 200.8 | 200.8
| Fatima Jinnah Town D | Live - As per Plan | 1472 | 588.8 | 588.8
| Fatima Jinnah Town E | Live - As per Plan | 716 | 286.4 | 286.4
| Fatima Jinnah Town F | Live - As per Plan | 928 | 371.2 | 371.2
| Fatima Jinnah Town G | Live - As per Plan | 650 | 260 | 260
| Fatima Jinnah Town H | Live - As per Plan | 1004 | 401.6 | 401.6
| Fatima Jinnah Town J | Live - As per Plan | 572 | 228.8 | 228.8
| Green Fort Housing Society | Live - As per Plan | 1094 | 437.6 | 437.6
| Gulshan-i-Ghafoor | Live - As per Plan | 108 | 43.2 | 43.2
| Gulshen e Yousaf & Stadium | Live - As per Plan | 1684 | 673.6 | 673.6
| Ibrahim Garden | Permenant Budget Removal | 174 | 69.6 | 69.6
| Marhaba Canal View | Permenant Budget Removal | 1078 | 431.2 | 431.2
| Multan Golf City | Not Live - Others Reasons | 370 | 148 | 148
| Nawab Bhatta Colony | Live - As per Plan | 1050 | 420 | 420
| Nayab Grace City | Live - As per Plan | 554 | 221.6 | 221.6
| Nayyab City & Extension | Live - As per Plan | 1196 | 478.4 | 478.4
| Posh AVenue | Live - As per Plan | 68 | 27.2 | 27.2
| Royal Residencia | Live - As per Plan | 614 | 245.6 | 245.6
| Sadiqabad latifabad Wahidabad | Live - As per Plan | 2080 | 832 | 832
| Sayyam City | Live - As per Plan | 376 | 150.4 | 150.4
| Western Fort | Live - As per Plan | 232 | 92.8 | 92.8
Muridky, Kalasha Kako, Shadra | Ajnianwala | Not Live - Work to be initiated | 1998 | 799.2 | 799.2
| Bahrrian Wala | Not Live - Work to be initiated | 698 | 279.2 | 279.2
| Chalk no.12 | Not Live - Work to be initiated | 1355 | 542 | 542
| Feroz Wattowan-i | Not Live - Work to be initiated | 1428 | 571.2 | 571.2
| Ferozewala | Not Live - Work to be initiated | 36000 | 14400 | 14400
| Ghang | Not Live - Work to be initiated | 1457 | 582.8 | 582.8
| Jandiala Sher Khan | Not Live - Work to be initiated | 1478 | 591.2 | 591.2
| Jatri Kohna | Not Live - Work to be initiated | 1428 | 571.2 | 571.2
| Kala Shah Kaku | Not Live - Work to be initiated | 11500 | 4600 | 4600
| Kaloke | Not Live - Work to be initiated | 2317 | 926.8 | 926.8
| KOT Abdul Malik | Not Live - Work to be initiated | 14800 | 5920 | 5920
| Kot Sondha | Not Live - Work to be initiated | 2463 | 985.2 | 985.2
| Kurkle Androon | Not Live - Work to be initiated | 573 | 229.2 | 229.2
| Lahore Jaranwala Road | Not Live - Work to be initiated | 16400 | 6560 | 6560
| Mirza Virkan | Not Live - Work to be initiated | 1264 | 505.6 | 505.6
| Muradey Kalan | Not Live - Work to be initiated | 460 | 184 | 184
| Muridke | Not Live - Work to be initiated | 32100 | 12840 | 12840
| Nazri Lubana | Not Live - Work to be initiated | 497 | 198.8 | 198.8
| Nokhar | Not Live - Work to be initiated | 1122 | 448.8 | 448.8
| Rakh Hiran Minara | Not Live - Work to be initiated | 4466 | 1786.4 | 1786.4
| Safdarabad | Not Live - Work to be initiated | 13000 | 5200 | 5200
| Shahdara Town | Not Live - Work to be initiated | 64000 | 25600 | 25600
Narowal | Abdullah City | Not Live - Work to be initiated | 396 | 158.4 | 158.4
| Al-Hamra City | Not Live - Work to be initiated | 230 | 92 | 92
| Al-Rafeh Garden | Not Live - Work to be initiated | 248 | 99.2 | 99.2
| Al-Raheem Residencia | Not Live - Work to be initiated | 370 | 148 | 148
| Al-Reheem Garden | Not Live - Work to be initiated | 1060 | 424 | 424
| Al-Rehmanpura and Zafarwal Road | Not Live - Work to be initiated | 962 | 384.8 | 384.8
| Bismilllah Society | Not Live - Work to be initiated | 616 | 246.4 | 246.4
| Circular Road | Not Live - Work to be initiated | 2074 | 829.6 | 829.6
| Civil Lines | Not Live - Work to be initiated | 2220 | 888 | 888
| Doctor's Colony | Not Live - Work to be initiated | 1434 | 573.6 | 573.6
| Garden Town | Not Live - Work to be initiated | 582 | 232.8 | 232.8
| Green City Park | Not Live - Work to be initiated | 448 | 179.2 | 179.2
| Habib Garden | Not Live - Work to be initiated | 248 | 99.2 | 99.2
| Hayat Town | Not Live - Work to be initiated | 638 | 255.2 | 255.2
| Katchery Road and Allama Iqbal | Not Live - Work to be initiated | 888 | 355.2 | 355.2
| Khayaban-e-Nawab | Not Live - Work to be initiated | 562 | 224.8 | 224.8
| Manik Road Mohala Hussainabad | Not Live - Work to be initiated | 524 | 209.6 | 209.6
| MOh Bijli Ghar | Not Live - Work to be initiated | 970 | 388 | 388
| Moh Meera Shah Hussain | Not Live - Work to be initiated | 4458 | 1783.2 | 1783.2
| Mohala Hajver Nagar Open Area | Not Live - Work to be initiated | 762 | 304.8 | 304.8
| Mushtaq Town | Not Live - Work to be initiated | 1750 | 700 | 700
| Narowal Bypass to Nawab Town (C | Not Live - Work to be initiated | 1356 | 542.4 | 542.4
| Nisari Muhallah & Muslim Town S | Not Live - Work to be initiated | 1008 | 403.2 | 403.2
| Pan peer Road Societies | Not Live - Work to be initiated | 1868 | 747.2 | 747.2
| Pasrur Bypass , City Commercial | Not Live - Work to be initiated | 1348 | 539.2 | 539.2
| Punjab Housing & NPS | Not Live - Work to be initiated | 908 | 363.2 | 363.2
| Rana Shami Town & Satellite Tow | Not Live - Work to be initiated | 420 | 168 | 168
| Sadeeqpura | Not Live - Work to be initiated | 296 | 118.4 | 118.4
| Samanabad-College Area | Not Live - Work to be initiated | 3420 | 1368 | 1368
| Usman Trade City | Not Live - Work to be initiated | 368 | 147.2 | 147.2
Naval Anchorage and other Areas (ISB) | 18_P1 | Live - As per Plan | 888 | 444 | 444
| 18_P2 | Temporary Budget Removal | 278 | 139 | 139
| C-18 | Live - As per Plan | 832 | 416 | 416
| Naval ANchorage | Live - As per Plan | 1726 | 863 | 863
| Roshan Pakistan | Live - As per Plan | 1180 | 590 | 590
Okara | 1-4L | Live - As per Plan | 708 | 283.2 | 283.2
| Ayub Park | Live - As per Plan | 1368 | 547.2 | 547.2
| Bajwa Colony, Samad Pura Road,S | Live - As per Plan | 2438 | 975.2 | 975.2
| Dubai Town | Live - As per Plan | 738 | 295.2 | 295.2
| Farid Town | Live - As per Plan | 2470 | 988 | 988
| Karmawala | Live - As per Plan | 30 | 12 | 12
| Sher Rabbani Town & Ghaziabad | Live - As per Plan | 1710 | 684 | 684
PAF Base Chaklala | PAF Base Chaklala | Not Live - Work to be initiated | 2830 | 1132 | 1132
Palm City Lahore | Palm City | Not Live - Work in Progress (WIP) | 732 | 293
Peshawar (P2) | City Side P01 | Not Live - Work to be initiated | 1048 | 419.2 | 419.2
| City Side P02 | Live - As per Plan | 976 | 390.4 | 390.4
| City Side P03 | Live - As per Plan | 1060 | 424 | 424
| Misc.Areas Warsak | Live - As per Plan | 1584 | 633.6 | 633.6
| OPF Colony | Live - As per Plan | 788 | 315.2 | 315.2
| Warsak Rd Ext. P1 | Not Live - Work to be initiated | 394 | 157.6 | 157.6
| Warsak Rd Ext. P2 | Permenant Budget Removal | 154 | 61.6 | 61.6
| Warsak Rd Ext. P3 | Not Live - Work to be initiated | 918 | 367.2 | 367.2
| Warsak Rd Ext. P4 | Not Live - Work to be initiated | 1006 | 402.4 | 402.4
| Warsak Rd Ext. P5 | Not Live - Work to be initiated | 616 | 246.4 | 246.4
| Warsak Rd Ext. P6 | Live - As per Plan | 350 | 140 | 140
| Warsak Rd Ext. P7 | Live - As per Plan | 778 | 311.2 | 311.2
Peshawar Misc Areas | Askari 01 | Live - As per Plan | 214 | 107 | 107
| Askari 02 | Live - As per Plan | 364 | 182 | 182
| Askari 03 | Live - As per Plan | 52 | 26 | 26
| Askari 04 | Live - As per Plan | 84 | 42 | 42
| Askari 05 | Not Live - Others Reasons | 142 | 71 | 71
| Charkhana P01 | Live - As per Plan | 4508 | 2254 | 2254
| Charkhana P02 | Live - As per Plan | 2780 | 1390 | 1390
| Charkhana P03 | Live - As per Plan | 2992 | 1496 | 1496
| Officer & Professor Colony_PU | Live - As per Plan | 336 | 168 | 168
| OPF Colony | Live - As per Plan | 788 | 394 | 394
| Ring Road P01 | Live - As per Plan | 2236 | 1118 | 1118
| Tajabad P01 | Live - As per Plan | 1262 | 631 | 631
| Tajabad P02 | Not Live - Permission Issues | 500 | 250 | 250
Petaro Garrison, Hyderabad | Petaro | Live - As per Plan | 740 | 296
PSW to Torkham Border | PSW to Torkham Border | Live - As per Plan | 0 | 0 | 0
Quetta | Killi Payen | Live - As per Plan | 400 | 160 | 160
| Sabzal Road | Not Live - Permission Issues | 800 | 320 | 320
Quetta Cantt | Cantt_P1 | Live - As per Plan | 1108 | 554 | 554
| Cantt_P2 | Live - As per Plan | 4717 | 2358.5 | 2358.5
RahimYar Khan Ph2 | ALi + Fort + Madina | Live - As per Plan | 312 | 124.8 | 124.8
| Atta Housing + Canal + Paradise | Live - Permission Awaited | 786 | 314.4 | 188.64
| Dastgeer Colony | Temporary Budget Removal | 378 | 151.2 | 151.2
| Fahad Town | Live - As per Plan | 328 | 131.2 | 131.2
| Gulberg+Ahmed+Air view | Live - As per Plan | 576 | 230.4 | 230.4
| Ittehad Garden P1 | Live - As per Plan | 712 | 284.8 | 284.8
| Ittehad Garden P2 | Live - As per Plan | 1000 | 400 | 400
| Ittehad Town & Other | Temporary Budget Removal | 268 | 107.2 | 107.2
| Niazi Colony | Live - As per Plan | 2506 | 1002.4 | 1002.4
| Rehmat Colony | Temporary Budget Removal | 1620 | 648 | 648
Rawalpindi | Gulshanabad P01 | Swap Cases | 1758 | 703.2 | 703.2
| Gulshanabad P02 | Swap Cases | 1470 | 588 | 588
| Gulshanabad P03 | Swap Cases | 916 | 366.4 | 366.4
| Jhelum Road Buildings | Live - As per Plan | 1082 | 432.8 | 432.8
| Metro Homes | Not Live - Work to be initiated | 528 | 211.2 | 211.2
| Samarzar Housing Society | Not Live - Work to be initiated | 1824 | 729.6 | 729.6
| Sanobar City | Swap Cases | 1454 | 581.6 | 581.6
Rawalpindi Misc Areas | Afzal Town Expansion(Aerial) | Live - As per Plan | 1428 | 714 | 714
| Ayub Park | Live - As per Plan | 16 | 8 | 8
Royal Palm & Canal View | Canal View | Not Live - Permission Issues | 1950 | 780 | 780
| P1 | Not Live - Permission Issues | 1030 | 412 | 412
| P2 | Not Live - Permission Issues | 1566 | 626.4 | 626.4
| P3 | Not Live - Permission Issues | 2314 | 925.6 | 925.6
| P9 | Not Live - Permission Issues | 1908 | 763.2 | 763.2
Sadiqabad | Abid Colony | Not Live - Work to be initiated | 474 | 189.6 | 189.6
| Ajmal Town,Faisal Town | Not Live - Work to be initiated | 1160 | 464 | 464
| Akbar Town & Laghari Colony | Not Live - Work to be initiated | 902 | 360.8 | 360.8
| Al Haram City, Hamza City Overs | Not Live - Work to be initiated | 378 | 151.2 | 151.2
| Al Hassan, Jamal City, Al Noor | Not Live - Work to be initiated | 460 | 184 | 184
| Ali Tiown & New Ali Town | Not Live - Work to be initiated | 348 | 139.2 | 139.2
| Allama Iqbal Town, Aslam Town, | Not Live - Work to be initiated | 1924 | 769.6 | 769.6
| Amir Canal View, Canal Residenc | Not Live - Work to be initiated | 262 | 104.8 | 104.8
| Arif Town, Shahzad Colony | Not Live - Work to be initiated | 1478 | 591.2 | 591.2
| Awan Housing Society | Not Live - Work to be initiated | 272 | 108.8 | 108.8
| Azizabad | Not Live - Work to be initiated | 508 | 203.2 | 203.2
| Canal View | Not Live - Work to be initiated | 168 | 67.2 | 67.2
| Cheema Town, Permi Town | Not Live - Work to be initiated | 766 | 306.4 | 306.4
| Chief Residencia Housing Societ | Not Live - Work to be initiated | 258 | 103.2 | 103.2
| Commercial Area, Kothi Mohallah | Not Live - Work to be initiated | 1296 | 518.4 | 518.4
| Faiz Colony | Not Live - Work to be initiated | 676 | 270.4 | 270.4
| Gulshen I Azmat, Maqbool City | Not Live - Work to be initiated | 332 | 132.8 | 132.8
| Gulshen I Iqbal | Not Live - Work to be initiated | 178 | 71.2 | 71.2
| Haider Colony | Not Live - Work to be initiated | 1446 | 578.4 | 578.4
| Haq Town | Not Live - Work to be initiated | 1116 | 446.4 | 446.4
| Heaven City | Not Live - Work to be initiated | 278 | 111.2 | 111.2
| Hussainabad & Ghafoorabad | Not Live - Work to be initiated | 1284 | 513.6 | 513.6
| Indus Town | Not Live - Work to be initiated | 2010 | 804 | 804
| Izhar Enclave,Unknown1,Unknown2 | Not Live - Work to be initiated | 362 | 144.8 | 144.8
| Jinnah Town, Mohallah Islampura | Not Live - Work to be initiated | 804 | 321.6 | 321.6
| Mehar Farid Colony | Not Live - Work to be initiated | 1034 | 413.6 | 413.6
| Model Avenue | Not Live - Work to be initiated | 644 | 257.6 | 257.6
| Model City Housing | Not Live - Work to be initiated | 746 | 298.4 | 298.4
| Model Town, Arfat Town | Not Live - Work to be initiated | 652 | 260.8 | 260.8
| Muhajir Colony, Old Sadiqabad | Not Live - Work to be initiated | 1126 | 450.4 | 450.4
| Mujahid Colony, Tipu Sultan | Not Live - Work to be initiated | 876 | 350.4 | 350.4
| Muncipal Town, Illyas Colony, | Not Live - Work to be initiated | 2052 | 820.8 | 820.8
| Mustafa , Zafar, Bismillah, Kar | Not Live - Work to be initiated | 1122 | 448.8 | 448.8
| Noor Colony,Zamindara Housing | Not Live - Work to be initiated | 970 | 388 | 388
| Public Colony & Commercial Area | Not Live - Work to be initiated | 594 | 237.6 | 237.6
| Rao Town | Not Live - Work to be initiated | 950 | 380 | 380
| Rehman Avenue | Not Live - Work to be initiated | 262 | 104.8 | 104.8
| Rustam Colony & Mohallah | Not Live - Work to be initiated | 686 | 274.4 | 274.4
| Satellite Town, Aziz Town, Gill | Not Live - Work to be initiated | 1360 | 544 | 544
| Siraj Colony,Sukh Chain Housing | Not Live - Work to be initiated | 304 | 121.6 | 121.6
| Tibba Qadirabad | Not Live - Work to be initiated | 1226 | 490.4 | 490.4
| Warriach Town & Arian Colony | Not Live - Work to be initiated | 1316 | 526.4 | 526.4
| Zakria Garden,Unknown 3-4, | Not Live - Work to be initiated | 1040 | 416 | 416
| Zamzam Garden,Jeevan City | Not Live - Work to be initiated | 684 | 273.6 | 273.6
Sahiwal (P2) | Golf City | Not Live - Work to be initiated | 286 | 114.4 | 114.4
| Montgomery Society | Live - As per Plan | 188 | 75.2 | 75.2
| Muhall Noor & Park Salamat Park | Not Live - Work in Progress (WIP) | 916 | 366.4 | 366.4
| Peoples & Bitholdi Colony | Live - As per Plan | 2948 | 1179.2 | 1179.2
| Razaq Royal Ph-3_P1 | Not Live - Work to be initiated | 774 | 309.6 | 309.6
| Razaq Royal Ph-3_P2 | Not Live - Work to be initiated | 286 | 114.4 | 114.4
| Sitara City | Permenant Budget Removal | 156 | 62.4 | 62.4
Sahiwal Misc Areas | Bhutto Colony | Live - As per Plan | 1860 | 930 | 930
| Chak 89 | Live - As per Plan | 916 | 458 | 458
Sargodha | Al Freed Garden Phase 1 | Swap Cases | 480 | 192 | 192
| Al Freed Garden Phase 2 | Swap Cases | 670 | 268 | 268
| Atta Muhammad Coloy HH To 47 Ch | Live - As per Plan | 214 | 107 | 107
| Awan Chowk To Gulberg City | Live - As per Plan | 640 | 320 | 320
| Aziz,Imran,Nawab,Gondl,Fjr,Srwr | Live - As per Plan | 1432 | 572.8 | 572.8
| Bajwa Colony | Not Live - Work in Progress (WIP) | 340 | 136 | 136
| Bashir,Chuna Bhati,Jamil | Live - As per Plan | 1038 | 415.2 | 415.2
| Chak 43 NB,Ali & Yousuf Park | Live - As per Plan | 832 | 332.8 | 332.8
| Factory_Area | Not Live - Work in Progress (WIP) | 350 | 140 | 140
| Fazil Town FDT To Khizar Masjio | Live - As per Plan | 784 | 392 | 392
| Ghani Park FDT To Steel Welding | Live - As per Plan | 386 | 193 | 193
| Govt Central Model School To Th | Live - As per Plan | 688 | 344 | 344
| Green valley | Swap Cases | 288 | 115.2 | 115.2
| Gulberg City | Permenant Budget Removal | 792 | 316.8 | 316.8
| Islampura | Live - As per Plan | 2800 | 1120 | 1120
| Istiqlalabad | Live - As per Plan | 1800 | 720 | 720
| Kachari Road To Awan Colony Dep | Live - As per Plan | 220 | 110 | 110
| Kacheela House To Gujjar House | Live - As per Plan | 336 | 168 | 168
| Liaquat Colony | Live - As per Plan | 450 | 180 | 180
| Milatabad | Swap Cases | 766 | 306.4 | 306.4
| New Raza Garden | Not Live - Work in Progress (WIP) | 1128 | 451.2 | 451.2
| Raza Gardan Phase 1 & 2 | Not Live - Work in Progress (WIP) | 1116 | 446.4 | 446.4
| Rehmanpura | Live - As per Plan | 1800 | 720 | 720
| Remount Depot | Swap Cases | 206 | 82.4 | 82.4
| RPO Office TO Session Court Roa | Live - As per Plan | 252 | 126 | 126
| Sabar Wall Colony | Not Live - Work in Progress (WIP) | 1662 | 664.8 | 664.8
| Salman Pura - Saleem Park | Not Live - Work in Progress (WIP) | 622 | 248.8 | 248.8
| SGD Bhalwal Road TO Fatima Jinn | Live - As per Plan | 586 | 293 | 293
| Z Block NST & Services Colony | Live - As per Plan | 970 | 388 | 388
| Zafar Colony | Live - As per Plan | 550 | 220 | 220
Sialkot | Amir Street Cap Rd & Model Town | Not Live - Work to be initiated | 210 | 84 | 84
| Ayan Garden | Live - As per Plan | 56 | 22.4 | 22.4
| Bograh Ext | Not Live - Work to be initiated | 528 | 211.2 | 211.2
| Bonkan | Live - As per Plan | 550 | 220 | 220
| Camp Gujran | Not Live - Work to be initiated | 556 | 222.4 | 222.4
| Capital Rd & Model Town Ext | Live - As per Plan | 358 | 143.2 | 143.2
| Christian Town & Muslim Town | Live - As per Plan | 868 | 347.2 | 347.2
| Circular Road | Live - As per Plan | 628 | 251.2 | 251.2
| CITI Housing E_F_G | Live - As per Plan | 1894 | 757.6 | 757.6
| Citi Housing Sec-A_Sectn-1 | Live - As per Plan | 1426 | 570.4 | 570.4
| Diamond Citi P2 | Live - As per Plan | 2282 | 912.8 | 912.8
| Fatehgarh | Live - As per Plan | 232 | 92.8 | 92.8
| Fatehger Ext | Not Live - Work to be initiated | 2120 | 848 | 848
| Gohaddpur to Ghaniabad | Not Live - Work to be initiated | 470 | 188 | 188
| Hunterpura Ext | Not Live - Work to be initiated | 534 | 213.6 | 213.6
| Jallianwala | Live - As per Plan | 620 | 248 | 248
| Kashmir Rd Jani Shop st | Not Live - Work to be initiated | 386 | 154.4 | 154.4
| Kent Housing Ext. | Live - As per Plan | 184 | 73.6 | 73.6
| Khadim Ali Rd | Live - As per Plan | 240 | 96 | 96
| Marala Road & Muradpur | Live - As per Plan | 604 | 241.6 | 241.6
| Nihalchand & Greenwood St | Live - As per Plan | 980 | 392 | 392
| Peerwali | Live - As per Plan | 978 | 391.2 | 391.2
| Rangpura Road | Live - As per Plan | 632 | 252.8 | 252.8
| Rizwan Colony Deen Pura | Live - As per Plan | 170 | 68 | 68
| Roras Road | Live - As per Plan | 1092 | 436.8 | 436.8
| Shahabpura Main Rd | Live - As per Plan | 440 | 176 | 176
| Towards Chitti Sheikh | Not Live - Work in Progress (WIP) | 404 | 161.6 | 161.6
| Towards Ugoki Mor | Not Live - Work in Progress (WIP) | 1078 | 431.2 | 431.2
| Zafarwal | Not Live - Others Reasons | 434 | 173.6 | 173.6
| Zahoor Elahi Road | Live - As per Plan | 968 | 387.2 | 387.2
Sialkot Cantt | Cantt Commercial | Live - As per Plan | 1382 | 691 | 691
| Cantt.P_1 | Live - As per Plan | 748 | 374 | 374
| Cantt.P_2 | Live - As per Plan | 884 | 442 | 442
| Cantt.P_3 | Live - As per Plan | 562 | 281 | 281
Sukkur | Barrage Colony | Not Live - Work in Progress (WIP) | 964 | 385.6
| NewSukkurCityTownship | Not Live - Work to be initiated | 762 | 304.8
| Unknown 11 | Not Live - Work to be initiated | 670 | 268
| Sukkur Township Pocket 1 | Not Live - Work in Progress (WIP) | 2046 | 818.4
| Sukkur Township P-2_KingCrystl2 | Not Live - Work in Progress (WIP) | 1516 | 606.4
| Golimar Area | Not Live - Work in Progress (WIP) | 292 | 116.8
| Sachal Township_Kings Crystal | Not Live - Work in Progress (WIP) | 1864 | 745.6
| Shikarpur Rd | Not Live - Work in Progress (WIP) | 1058 | 423.2
| 100 Feet Rd P1 | Not Live - Work in Progress (WIP) | 1472 | 588.8
| 100 Feet Rd P2 | Not Live - Work in Progress (WIP) | 2416 | 966.4
| Sukkur Ind Area | Not Live - Work to be initiated | 350 | 140
| Unknonwn_1 | Not Live - Work in Progress (WIP) | 402 | 160.8
| Unknown 03 | Not Live - Work in Progress (WIP) | 180 | 72
| Main City P1 | Not Live - Work to be initiated | 2372 | 948.8
| Main City P2 | Not Live - Work to be initiated | 2494 | 997.6
Swat | Derai P1 | Live - As per Plan | 1032 | 412.8 | 412.8
| Derai P2 | Live - As per Plan | 848 | 339.2 | 339.2
| Derai P3 | Live - As per Plan | 512 | 204.8 | 204.8
| Saidu Ext | Live - As per Plan | 864 | 345.6 | 345.6
Swat Ph2 | Aman kot | Not Live - Work in Progress (WIP) | 2538 | 1015.2 | 812.16
| Gul Kada | Live - As per Plan | 816 | 326.4 | 261.12
| Kanju Road P01 | Live - As per Plan | 758 | 303.2 | 303.2
| Kanju Road P02 | Live - As per Plan | 1222 | 488.8 | 488.8
| Khwaja abad | Live - As per Plan | 860 | 344 | 275.2
| Landikas_Rang Mohalla | Live - As per Plan | 3236 | 1294.4 | 1294.4
| Main Bazar Mingora | Live - As per Plan | 3102 | 1240.8 | 1240.8
| Makan Bagh | Live - As per Plan | 522 | 208.8 | 208.8
| Rahimabad_Qambar | Live - As per Plan | 1758 | 703.2 | 703.2
| River Area_Hayatabad | Live - As per Plan | 1394 | 557.6 | 557.6
| Saidu Sharif P1 | Live - As per Plan | 568 | 227.2 | 227.2
| Saidu Sharif P2 | Live - As per Plan | 818 | 327.2 | 327.2
Top City Islamabad | Block-A | Live - As per Plan | 2270 | 1135 | 1135
| Block-B | Live - As per Plan | 1576 | 788 | 788
| Block-C | Live - As per Plan | 2308 | 1154 | 1154
| Block-D | Live - As per Plan | 1548 | 774 | 774
Wah Cant Misc Ares | Block N & O New City Ph2 | Temporary Budget Removal | 1008 | 504 | 504
| Block P New City Ph2 | Temporary Budget Removal | 614 | 307 | 307
| Block Q New City Ph2 | Temporary Budget Removal | 304 | 152 | 152
| Block R & S New City Ph2 | Temporary Budget Removal | 1548 | 774 | 774
| Block U & V New City Ph2 | Temporary Budget Removal | 554 | 277 | 277
| Block W & Y New City Ph2 | Temporary Budget Removal | 570 | 285 | 285
| Block Y & Z New City Ph2 | Temporary Budget Removal | 554 | 277 | 277
Wah Cantt | Gulistan Colony | Permenant Budget Removal | 1750 | 700 | 700
| Gulshan e Anwar T.Buried | Live - As per Plan | 730 | 292 | 292
| Tameer e Hayat Colony | Permenant Budget Removal | 716 | 286.4 | 286.4
Wahh Estate | Estate Area P2 | Live - As per Plan | 618 | 247.2 | 247.2
| Estate Area P3 | Not Live - Others Reasons | 1538 | 615.2 | 615.2
Grand Total |  |  | 1444140 | 600881.5 | 544448.26
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Dashboard - Financials
Approved SF Expansion Feasibilities Report - Financial Focused
*Actual data as per 18th march 2026
Number of Feasibility | 97
Total Areas | 1150
Live Areas | 525
Not Live Areas | 625
Total Network (HP) | 1444140
Expected HP | 600881.5
Allocated Budget | 22095709754.6035
Budget Requirement - Remaining Work | 10815617066.937
Actual | 3364041920.48
Net Savings | 7916050767.1865
Budget Position
Grand Total | 22095709754.6035 | 3364041920.48 | 10815617066.937 | 7916050767.1865
| Allocated Budget | Actual Incurred | Budget Requirement - Remaining Work | Net Savings
CEM Number
100 | 518998173.5488 |  | 518998173.5488
102 | 320950492.9885 |  | 320950492.9885
103 | 264880241.6587 |  | 264880241.6587
104 | 201467753.5922 |  | 121062257.0655
105 | 469213284.4801 |  | 468309111.9401
106 | 537922932.5858 |  | 537922932.5858
107 | 207441341.7189 |  | 207441341.7189
108 | 399657325.7902 |  | 399657325.7902
109 | 324998966.7491 |  | 297374054.5754
110 | 299162106.9635 |  | 299162106.9635
111 | 16500000 |  | 16500000
112 | 419021550.1714 |  | 419021550.1714
I240188 | 108159630.7859 | 32303880.19 | 11498885.0486 | 64356865.5473
I240189 | 128620785.1659 | 48635713.89 | 21340967.7749 | 58644103.5011
I240190 | 133827375.6403 | 23221417.91 | 26296056.346 | 84309901.3843
I240435 | 248499863.0449 | 67652364.56 | 48350596.4567 | 132496902.0281
I240437 | 285986428.2027 | 32014191.35 | 184971902.5387 | 69000334.314
I240438 | 197850142.5434 | 81236523.64 | 104793760.5573 | 11819858.3461
I240440 | 380747283.5319 | 26049440.1 | 159745472.0109 | 194952371.421
I240442 | 120824652.0098 | 12671694.77 | 76638796.3372 | 31514160.9025
I240459 | 12138005.0092 | 48327875.35 | 2044350.7514 | -38234221.0922
I240518 | 112050607.2667 | 2778864.87 | 21773385.3528 | 87498357.0439
I240519 | 297581509.3071 | 5337898.44 | 288482669.3071 | 3760941.56
I240537 | 23356438.4126 | 21906186.89 | 4885213.2619 | -3434961.7393
I240538 | 202480325.6595 | 30224939.89 | 54534892.0622 | 117720493.7073
I240539 | 262661971.296 | 50550348.66 | 57684009.8485 | 154427612.7875
I240540 | 199830616.2584 | 20154770.02 | 42586587.5914 | 137089258.647
I240557 | 20127458.866 | 48265829.91 | 3524168.8299 | -31662539.8739
I240678 | 414713991.8042 | 34886785.31 | 152230808.948 | 227596397.5463
I240679 | 10311892.5 | 12874810.53 | 1546783.875 | -4109701.905
I240680 | 133968445.702 | 11241888.84 | 26413140.4864 | 96313416.3756
I240681 | 12569175 | 108843250.32 | 3940750.625 | -100214825.945
I240682 | 626675307.4316 | 44345651.27 | 109372171.7964 | 472957484.3651
I240683 | 79640275.4625 | 16462578.98 | 19732647.4194 | 43445049.0631
I240684 | 69792468.609 | 47923740.83 | 11572754.1965 | 10295973.5825
I240700 | 672588564.2608 | 30109710.57 | 188492147.7914 | 453986705.8994
I240701 | 15078455 | 41959381.04 | 3456160.75 | -30337086.79
I240702 | 233184378.5853 | 135166472.02 | 70072569.4468 | 27945337.1184
I240703 | 861306256.5102 | 110534224.46 | 175479694.4926 | 575292337.5576
I240704 | 640727539.3732 | 106291079.56 | 140079366.2711 | 394357093.5421
I240705 | 526845585.3829 | 99528764.94 | 269705372.1079 | 157611448.335
I240782 | 125214350 | 6399057.12 | 18782152.5 | 100033140.38
I250114 | 38144251.6233 | 9911416.85 | 6187837.7435 | 22044997.0298
I250201 | 47592961.2205 | 2914326.93 | 5280950.325 | 39397683.9655
I250202 | 27034446.9509 | 6064833.29 | 14359302.7588 | 6610310.9021
I250203 | 13662314.051 | 10830900 | 4383533.802 | -1552119.7509
I250205 | 115636928.0112 | 9650887.11 | 71675134.6087 | 34310906.2925
I250206 | 348988241.8392 | 37654769.53 | 205439097.5198 | 105894374.7895
I250207 | 31957072.7085 | 8876461.53 | 4387124.4197 | 18693486.7588
I250208 | 52865210.1145 | 12376240.33 | 8860835.4782 | 31628134.3064
I250209 | 130681950.7051 | 54634503.47 | 45821094.2533 | 30226352.9818
I250210 | 192623788.984 | 18557157.07 | 66093216.8521 | 107973415.0619
I250211 | 49430718.9 | 37329299.21 | 8942270.335 | 3159149.355
I250212 | 285944485.0685 | 21624782.49 | 81451595.6257 | 182868106.9527
I250213 | 49354039.3976 | 15484688.63 | 9947099.1246 | 23922251.643
I250298 | 88120170.7877 | 80833806.33 | 20187657.4254 | -12901292.9677
I250307 | 517994073.7885 | 50504525.19 | 77699111.0683 | 389790437.5302
I250326 | 26408470.3052 | 29990113.6 | 5128258.0458 | -8709901.3406
I250327 | 531867730.3593 | 18753966.2 | 411918493.31 | 101195270.8494
I250374 | 1724390 | 0 | 258658.5 | 1465731.5
I250375 | 57537758.4162 | 13863425.15 | 12987621.2624 | 30686712.0038
I250376 | 557042160.9296 | 72610872.22 | 121661639.2974 | 362769649.4121
I250377 | 210835494.6044 | 12761740.29 | 104307030.861 | 93766723.4534
I250378 | 111427799.5419 | 15200321.67 | 61902973.5707 | 34324504.3013
I250379 | 47229040.8433 | 115955842.06 | 27225969.81 | -95952771.0267
I250380 | 283707294.9974 | 11888900.15 | 57607536.5487 | 214210858.2987
I250681 | 95594354.869 | 11082543.43 | 42571281.5245 | 41940529.9144
I250734 | 214988457.4045 | 21098168.35 | 107087908.3243 | 86802380.7303
I250737 | 376403670.2508 | 24952501.79 | 341774417.7819 | 9676750.679
I260060 | 25004869.5 | 6618364.34 | 14514110.425 | 3872394.735
I260061 | 107159247.7709 | 139597248.9 | 56991589.0122 | -89429590.1413
I260068 | 1635462937.7955 | 28887112.17 | 409664367.7508 | 1196911457.8747
I260105 | 119641188.284 | 0 | 57419495.0842 | 62221693.1998
I260159 | 67815324.28 | 10238475.59 | 11893548.642 | 45683300.048
I260160 | 321563528.2352 | 18804849.37 | 252828684.6428 | 49929994.2224
I260179 | 17688934.5 | 245384.52 | 6139742.675 | 11303807.305
I260180 | 122128866.5312 | 6234786.98 | 65452719.6348 | 50441359.9164
I260208 | 187392787.0047 | 107220 | 187392787.0047 | -107220
I260294 | 41609589.6381 | 288024.22 | 30104596.5174 | 11216968.9007
I260295 | 433500061.6578 | 878211.4 | 433500061.6578 | -878211.4
I260296 | 272350044.0914 | 17232581.84 | 209378129.515 | 45739332.7364
I260298 | 10770638.8012 | 1254241.51 | 4585627.5702 | 4930769.721
I260361 | 307110957.408 | 5283860.51 | 285527412.6165 | 16299684.2815
INT-21-00315 | 761753116.5258 | 283234406.96 | 185636291.9326 | 292882417.6332
INT-23-00435 | 108087915.9045 | 77881903.39 | 41650286.1468 | -11444273.6324
INT-23-00436 | 51381436.4933 | 17417582.61 | 13172063.2545 | 20791790.6288
INT-23-00437 | 200389603.1767 | 42295320.28 | 42061889.2765 | 116032393.6202
INT-23-00438 | 13329311.807 | 121795.99 | 2371656.771 | 10835859.0459
INT-23-00439 | 484250707.8032 | 190240587.93 | 100760924.4531 | 193249195.4201
INT-23-00440 | 53663374.8325 | 4688155.21 | 14757455.7249 | 34217763.8976
INT-23-00441 | 124440455.3157 | 20306046.74 | 23648885.2974 | 80485523.2783
INT-23-00442 | 42564737.5882 | 2854816.24 | 14401866.6382 | 25308054.71
INT-23-00444 | 175798350.6184 | 195619264.95 | 44427721.8334 | -64248636.165
INT-23-00445 | 36865953.56 | 40582736.6 | 11492136.034 | -15208919.074
INT-23-00446 | 167455820.522 | 0 | 11762446.4 | 155693374.122
INT-23-00447 | 214116397.2736 | 112052637.19 | 54253229.9227 | 47810530.1609
INT-23-00764 | 350042372.1435 | 57769975.94 | 133371866.5379 | 158900529.6656
Grand Total
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Note on C42: Bilal Aslam: Fixed shall remain constant even when filters applied.

## Standardized Comments (hidden)
Number of CEMs | 10
Row Labels | Count of Fesibility Name
LIVE - 100% Completed | 512
LIVE - 25% Completed | 1
LIVE - 50% Completed | 6
LIVE - 60% Completed | 3
LIVE - 80% Completed | 5
NOT LIVE - RETAIN BUDGET | 533
REMOVE BUDGET (P) | 43
REMOVE BUDGET (T) | 19
SWAPPED | 28
Grand Total | 1150

## Swap Details (hidden)
[5 empty] | 16264 | 6557.4 | 217677010.1385 |  |  |  | 132625520.93 | 5144
CEM Number | CEM Initiation Date | City Name | Fesibility Name | Area / Section / Pocket / Society (Original Name) | Total H.P | Customers According to % (Market Share) | Allocated Budget | Total Civil works - Buried | Total Civil works - Arial | Swapped With - | Swapped/Removal Budget | HP - Revised
I250207 | 2024-09-12 | Abbottabad | Abbottabad | Salhad | 700 | 280 | 13746943.2437 | 2963.1422 | 19896.0444 | Banda Jaat & Iqbal Road | 0 | ?
I250206 | 2024-09-12 | Daska | Daska | Bhatti Colony | 536 | 214.4 | 5635736.0276 | 992.4627 | 4986.8027 | Meraj Housing | 22604832.2609 | 542
I250206 | 2024-09-12 | Daska | Daska | Faisal_Town | 320 | 128 | 5536549 | 1147.7 | 4422.5 | Meraj Housing | 22604832.2609 | 542
I250206 | 2024-09-12 | Daska | Daska | Islampura | 1132 | 452.8 | 8329511.368 | 961.4 | 9642.5 | Meraj Housing | 22604832.2609 | 542
I250206 | 2024-09-12 | Daska | Daska | Rehmanpura | 652 | 260.8 | 6639116.496 | 1094.8 | 6366 | Meraj Housing | 22604832.2609 | 542
I250206 | 2024-09-12 | Daska | Daska | Unknown Society 20 | 424 | 169.6 | 4694817.25 | 833.75 | 4094.8 | Meraj Housing | 22604832.2609 | 542
I250206 | 2024-09-12 | Daska | Daska | Unknown Society_22 | 418 | 167.2 | 4623068.25 | 792.35 | 4278 | Meraj Housing | 22604832.2609 | 542
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 17 | 208 | 83.2 | 2299604 | 366.85 | 1911.1 | Meraj Housing | 22604832.2609 | 542
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 18 | 154 | 61.6 | 2190435 | 411.7 | 1274.55 | Meraj Housing | 22604832.2609 | 542
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 19 | 94 | 37.6 | 1473900.75 | 209.3 | 919.3 | Meraj Housing | 22604832.2609 | 542
I250206 | 2024-09-12 | Daska | Daska | Unkown Society 24 | 66 | 26.4 | 1047427.5 | 143.75 | 587.25 | Meraj Housing | 22604832.2609 | 542
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Al Barkat Villas | 190 | 76 | 3623949.247 | 809.6 | 1873.2538 | City Walk | 4637080.9375 | 254
I240682 | 2024-05-16 | Faisalabad | Faisalabad Ph4 | Khy-e-Manzoor | 432 | 172.8 | 5761950.425 | 1139.65 | 4442.475 | Pine Garden | 0 | ?!
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Latifabad No 09 | 1316 | 526.4 | 15091680.8626 | 2605.9 | 11969.4064 | Latifabad #2 | 7901516.3743 | 858
I250205 | 2024-09-12 | Jhelum | Jhelum Ph2 | Chal Jamal | 312 | 124.8 | 5688152.996 | 1657.15 | 5093.85 | Gharmala, Gharmala Monan & Chittan | 5811629.0927 | 628
I250205 | 2024-09-12 | Jhelum | Jhelum Ph2 | Shamas Pur | 198 | 79.2 | 2131177.996 | 409.4 | 1628.35 | Gharmala, Gharmala Monan & Chittan | 5811629.0927 | 628
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Khayaban-e-Patni CHS | 212 | 84.8 | 4887798.4991 | 1079.9494 | 2731.3402 | Hansa | 9247425.9799 | 0
I240705 | 2024-05-15 | Karachi | Karachi Ph5 | Kokan CHS | 346 | 138.4 | 11269033.0773 | 2155.1646 | 5318.6079 | Hansa | 9247425.9799 | 0
I250213 | 2024-09-14 | Mardan | Mardan | Mohabatabad P1 | 340 | 136 | 4566394 | 845.25 | 3726.45 | new muhabbatabad | 0 | ?
I250213 | 2024-09-14 | Mardan | Mardan | Mohabatabad P2 | 456 | 182.4 | 5853007.9 | 1220.15 | 4251.57 | new muhabbatabad | 0 | ?
INT-23-00439 | 2022-12-29 | Multan | Multan Misc. Areas | Defence Housing Society | 518 | 259 | 12724227.8253 | 6884.6077 | 6437.5466 | Pace City and White House Scoiety | 11729454.64 | 844
I240684 | 2024-05-16 | Rawalpindi | Askari RWP (4-7-10) | Askari-7 P1 | 472 | 188.8 | 6238771.269 | 1938.3435 | 1150.534 | Askari 12 | 6355978.3 | 160
I240684 | 2024-05-16 | Rawalpindi | Askari RWP (4-7-10) | Askari-7 P2 | 964 | 385.6 | 14207822.697 | 4421.6685 | 3298.834 | Askari 12 | 6355978.3 | 160
I250209 | 2024-09-14 | Rawalpindi | Rawalpindi | Gulshanabad P01 | 1758 | 703.2 | 17094645.258 | 2826.7 | 19588.601 | G-16 developed part only | 54483572 | 1606
I250209 | 2024-09-14 | Rawalpindi | Rawalpindi | Gulshanabad P02 | 1470 | 588 | 16562638.7071 | 3055.55 | 20330.0372 | G-16 developed part only | 54483572 | 1606
I250209 | 2024-09-14 | Rawalpindi | Rawalpindi | Gulshanabad P03 | 916 | 366.4 | 11424746.21 | 2458.7 | 10956.3015 | G-16 developed part only | 54483572 | 1606
I250209 | 2024-09-14 | Rawalpindi | Rawalpindi | Sanobar City | 1454 | 581.6 | 11170103.204 | 1561.7 | 12560.364 | G-16 developed part only | 54483572 | 1606
I250210 | 2024-09-14 | Sargodha | Sargodha | Remount Depot | 206 | 82.4 | 13163801.0798 | 3986.2481 | 6688.1052 | Grand A-1 City | 9854031.3448 | 252
Summary - Swaps
|  | Cost | Allocated Budget | 217677010.1385
|  | Cost | Swapped Budget | 132625520.93
|  | Revenue | Allocated Budget | 16264
|  | Revenue | Swapped Budget | 5144
|  | Cost | Dip | -39.07%
|  | Revenue | Dip | -68.37%

## Actuals (hidden)
Number of Total Areas | 18581034211.0381 | 8480651043.2293 | 10135167167.7449 |  |  | Number of Total Areas | 22095709754.6035 | 10815617066.937 | 10712793241.4577
Row Labels | Sum of Allocated Budget | Sum of Revised Budget | Sum of Difference |  |  | Row Labels | Sum of Allocated Budget | Sum of Revised Budget | Sum of Difference
Abbottabad | 46635361.121 | 4933262.6816 | 41702098.4394 |  |  | Abbottabad | 46635361.121 | 4933262.6816 | 41702098.4394
Bahawalpur | 234720343.2277 | 78068026.9577 | 48751767.1897 |  |  | Bahawalpur | 234720343.2277 | 78068026.9577 | 48751767.1897
Chitral | 107457482.0098 | 69955211.3372 | 37502270.6725 |  |  | Chitral | 107457482.0098 | 69955211.3372 | 37502270.6725
Daska | 238190943.4392 | 150040448.3198 | 88150495.1195 |  |  | Daska | 238190943.4392 | 150040448.3198 | 88150495.1195
Dera Ghazi Khan | 415670312.3488 | 415670312.3488 |  |  |  | Dera Ghazi Khan | 415670312.3488 | 415670312.3488
Faisalabad | 715131057.0272 | 91398554.2358 | 567810727.1535 |  |  | Faisalabad | 715131057.0272 | 91398554.2358 | 567810727.1535
Gujranwala | 1642979885.176 | 591739195.3929 | 1015816807.0546 |  |  | Feeders/Transportations | 3514675543.5655 | 2334966023.7077 | 1193072844.2577
Hafizabad | 252576804.9885 | 252576804.9885 |  |  |  | Gujranwala | 1642979885.176 | 591739195.3929 | 1015816807.0546
Haripur | 166186302.6104 | 37229959.821 | 128956342.7894 |  |  | Hafizabad | 252576804.9885 | 252576804.9885
Hyderabad | 247184920.0797 | 62007415.8715 | 178992492.9772 |  |  | Haripur | 166186302.6104 | 37229959.821 | 128956342.7894
Islamabad | 1899278927.2637 | 853745637.8312 | 1040417112.7484 |  |  | Hyderabad | 247184920.0797 | 62007415.8715 | 178992492.9772
Jhang | 190914712.4087 | 190914712.4087 |  |  |  | Islamabad | 1899278927.2637 | 853745637.8312 | 1040417112.7484
Jhelum | 172926785.0482 | 71668192.8508 | 51090933.4386 |  |  | Jhang | 190914712.4087 | 190914712.4087
Karachi | 2148258237.7282 | 912013069.8938 | 1144334678.187 |  |  | Jhelum | 172926785.0482 | 71668192.8508 | 51090933.4386
Kasur | 277182368.4801 | 276278195.9401 |  |  |  | Karachi | 2148258237.7282 | 912013069.8938 | 1144334678.187
Lahore | 4687149709.8115 | 2183279055.3426 | 2378935957.8479 |  |  | Kasur | 277182368.4801 | 276278195.9401
Lalamusa | 151789539.3189 | 151789539.3189 |  |  |  | Lahore | 4687149709.8115 | 2183279055.3426 | 2378935957.8479
Mandi Bahauddin | 303045745.7902 | 303045745.7902 |  |  |  | Lalamusa | 151789539.3189 | 151789539.3189
Mardan | 198763325.656 | 27323021.716 | 171440303.94 |  |  | Mandi Bahauddin | 303045745.7902 | 303045745.7902
Multan | 1277748684.2307 | 444024103.3454 | 806099668.7116 |  |  | Mardan | 198763325.656 | 27323021.716 | 171440303.94
Narowal | 274744690.9635 | 274744690.9635 |  |  |  | Multan | 1277748684.2307 | 444024103.3454 | 806099668.7116
Okara | 102458798.3625 | 15368819.7544 | 87089978.6081 |  |  | Narowal | 274744690.9635 | 274744690.9635
Peshawar | 307075969.798 | 99622299.7437 | 207453670.0543 |  |  | Okara | 102458798.3625 | 15368819.7544 | 87089978.6081
Quetta | 135338960.1659 | 22356218.3999 | 112982741.7661 |  |  | Peshawar | 307075969.798 | 99622299.7437 | 207453670.0543
Rahim Yar Khan | 111071445.702 | 14964640.4864 | 96106805.2156 |  |  | Quetta | 135338960.1659 | 22356218.3999 | 112982741.7661
Rawalpindi | 177277562.8741 | 47104579.4838 | 130172983.3904 |  |  | Rahim Yar Khan | 111071445.702 | 14964640.4864 | 96106805.2156
Sadiqabad | 350433922.1714 | 350433922.1714 |  |  |  | Rawalpindi | 177277562.8741 | 47104579.4838 | 130172983.3904
Sahiwal | 85781337.1301 | 42199240.2089 | 39901741.9701 |  |  | Sadiqabad | 350433922.1714 | 350433922.1714
Sargodha | 193303052.3165 | 50749454.452 | 142553597.8645 |  |  | Sahiwal | 85781337.1301 | 42199240.2089 | 39901741.9701
Sialkot | 483284928.4537 | 141873994.0454 | 341410934.4083 |  |  | Sargodha | 193303052.3165 | 50749454.452 | 142553597.8645
Swat | 465926299.3645 | 93712460.2242 | 364292663.1616 |  |  | Sialkot | 483284928.4537 | 141873994.0454 | 341410934.4083
Torkhan Border | 125214350 | 18782152.5 | 106432197.5 |  |  | Swat | 465926299.3645 | 93712460.2242 | 364292663.1616
Wahh | 210791285.8799 | 19469858.8882 | 191321426.9917 |  |  | Torkhan Border | 125214350 | 18782152.5 | 106432197.5
Sukkur | 184540160.0914 | 121568245.515 |  |  |  | Wahh | 210791285.8799 | 19469858.8882 | 191321426.9917
Grand Total | 18581034211.0381 | 8480651043.2293 | 9519720397.1999 |  |  | Sukkur | 184540160.0914 | 121568245.515
[6 empty] | Grand Total | 22095709754.6035 | 10815617066.937 | 10712793241.4577
CEMz | Orders | Details | Budget | Actual | Commitment | Assigned | Available |  | Row Labels | Sum of Actual | Row Labels | Sum of Actual
I240188 | I240188000 | StormFiber Expansion – DHA | 6606972.94 | 6606972.94 |  | 6606972.94 |  |  | I240188 | 32303880.19 | I240188 | 32303880.19
I240188 | I240188001 | Cabinets & Accessories - | 8597643.82 | 52195.56 |  | 52195.56 | 8545448.26 |  | I240189 | 48635713.89 | I240189 | 48635713.89
I240188 | I240188002 | Consumable & Accessories | 2553619.57 | 23156.47 |  | 23156.47 | 2530463.1 |  | I240190 | 23221417.91 | I240190 | 23221417.91
I240188 | I240188003 | Cables - (Feeder Access | 4367822.49 | 741397.52 |  | 741397.52 | 3626424.97 |  | I240435 | 67652364.56 | I240435 | 67652364.56
I240188 | I240188004 | Enclosures - (Feeder Ac | 1011367.55 | 1269.94 |  | 1269.94 | 1010097.61 |  | I240437 | 32014191.35 | I240437 | 32014191.35
I240188 | I240188005 | Splitters - (Access & Dis | 1628109.57 | 18464.24 |  | 18464.24 | 1609645.33 |  | I240438 | 81236523.64 | I240438 | 81236523.64
I240188 | I240188006 | Duct - (HDPE / GI with | 3795143.99 |  |  |  | 3795143.99 |  | I240440 | 26049440.1 | I240440 | 26049440.1
I240188 | I240188007 | Handholes - (HH / Chamb | 8004000 |  |  |  | 8004000 |  | I240442 | 12671694.77 | I240442 | 12671694.77
I240188 | I240188008 | FDT Foundation | 40000 |  |  |  | 40000 |  | I240459 | 48327875.35 | I240459 | 48327875.35
I240188 | I240188009 | Infrastructure Laying - | 5764812.02 | 212290 | 4102970 | 4315260 | 1449552.02 |  | I240518 | 2778864.87 | I240518 | 2778864.87
I240188 | I240188010 | Cable Hauling - (Aerial | 2679920.4 | 10770 |  | 10770 | 2669150.4 |  | I240519 | 5337898.44 | I240519 | 5337898.44
I240188 | I240188011 | Building Attachments - | 990000 |  |  |  | 990000 |  | I240537 | 21906186.89 | I240537 | 21906186.89
I240188 | I240188012 | Transportation - (Vehic | 900000 |  |  |  | 900000 |  | I240538 | 30224939.89 | I240538 | 30224939.89
I240188 | I240188013 | Tool Kit - (Access) | 150000 | 109800 |  | 109800 | 40200 |  | I240539 | 50550348.66 | I240539 | 50550348.66
I240188 | I240188014 | Tool Kit - (Dev.) | 80000 |  |  |  | 80000 |  | I240540 | 20154770.02 | I240540 | 20154770.02
I240188 | I240188015 | Cable prepartion Tools - | 150000 |  |  |  | 150000 |  | I240557 | 48265829.91 | I240557 | 48265829.91
I240188 | I240188016 | Splice Machine | 800000 |  |  |  | 800000 |  | I240678 | 34886785.31 | I240678 | 34886785.31
I240188 | I240188017 | Cleavers | 400000 |  |  |  | 400000 |  | I240679 | 12874810.53 | I240679 | 12874810.53
I240188 | I240188018 | VFLS | 100000 |  |  |  | 100000 |  | I240680 | 11241888.84 | I240680 | 11241888.84
I240188 | I240188019 | PON Power Meters. | 600000 |  |  |  | 600000 |  | I240681 | 108843250.32 | I240681 | 108843250.32
I240188 | I240188020 | CATV Transmission Equipmen | 2094400 | 894755.6 |  | 894755.6 | 1199644.4 |  | I240682 | 44345651.27 | I240682 | 44345651.27
I240188 | I240188021 | PON cards | 2156000 |  |  |  | 2156000 |  | I240683 | 16462578.98 | I240683 | 16462578.98
I240188 | I240188022 | Bolan | 3600000 |  |  |  | 3600000 |  | I240684 | 47923740.83 | I240684 | 47923740.83
I240188 | I240189000 | StormFiber Expansion – Que | 23632807.92 | 23632807.92 |  | 23632807.92 |  |  | I240700 | 30109710.57 | I240700 | 30109710.57
I240189 | I240189001 | Cabinets & Accessories - | 3498481.35 | 416841.66 |  | 416841.66 | 3081639.69 |  | I240701 | 41959381.04 | I240701 | 41959381.04
I240189 | I240189002 | Consumable & Accessories | 2357620.89 | 1822312.18 |  | 1822312.18 | 535308.71 |  | I240702 | 135166472.02 | I240702 | 135166472.02
I240189 | I240189003 | Cables - (Feeder Access | 21840678.17 | 3295504.31 |  | 3295504.31 | 18545173.86 |  | I240703 | 110534224.46 | I240703 | 110534224.46
I240189 | I240189004 | Enclosures - (Feeder Ac | 913937.53 | 51921.69 |  | 51921.69 | 862015.84 |  | I240704 | 106291079.56 | I240704 | 106291079.56
I240189 | I240189005 | Splitters - (Access & Dis | 972582.45 | 127163.68 |  | 127163.68 | 845418.77 |  | I240705 | 99528764.94 | I240705 | 99528764.94
I240189 | I240189006 | Duct - (HDPE / GI with | 24188045.12 |  |  |  | 24188045.12 |  | I240782 | 6399057.12 | I240782 | 6399057.12
I240189 | I240189007 | Handholes - (HH / Chamb | 4112000 |  |  |  | 4112000 |  | I250114 | 9911416.85 | I250114 | 9911416.85
I240189 | I240189008 | Poles | 168000 |  |  |  | 168000 |  | I250201 | 2914326.93 | I250201 | 2914326.93
I240189 | I240189009 | FDT Foundation | 100000 |  |  |  | 100000 |  | I250202 | 6064833.29 | I250202 | 6064833.29
I240189 | I240189010 | Infrastructure Laying - | 26376051.33 |  |  |  | 26376051.33 |  | I250203 | 10830900 | I250203 | 10830900
I240189 | I240189011 | Cable Hauling - (Aerial | 3384838.5 |  |  |  | 3384838.5 |  | I250205 | 9650887.11 | I250205 | 9650887.11
I240189 | I240189012 | Building Attachments - | 1844500 |  |  |  | 1844500 |  | I250206 | 37654769.53 | I250206 | 37654769.53
I240189 | I240189013 | Transportation - (Vehic | 3050000 | 233720 |  | 233720 | 2816280 |  | I250207 | 8876461.53 | I250207 | 8876461.53
I240189 | I240189014 | Tool Kit - (Access) | 150000 | 126830 |  | 126830 | 23170 |  | I250208 | 12376240.33 | I250208 | 12376240.33
I240189 | I240189015 | Tool Kit - (Dev.) | 120000 |  |  |  | 120000 |  | I250209 | 54634503.47 | I250209 | 54634503.47
I240189 | I240189016 | Cable prepartion Tools - | 450000 | 2499.99 |  | 2499.99 | 447500.01 |  | I250210 | 18557157.07 | I250210 | 18557157.07
I240189 | I240189017 | Splice Machine | 1400000 | 737898.01 |  | 737898.01 | 662101.99 |  | I250211 | 37329299.21 | I250211 | 37329299.21
I240189 | I240189018 | Cleavers | 240000 | 190000 |  | 190000 | 50000 |  | I250212 | 21624782.49 | I250212 | 21624782.49
I240189 | I240189019 | VFLs | 120000 |  |  |  | 120000 |  | I250213 | 15484688.63 | I250213 | 15484688.63
I240189 | I240189020 | OTDR - For Core / FTTH b | 1075000 |  |  |  | 1075000 |  | I250298 | 80833806.33 | I250298 | 80833806.33
I240189 | I240189021 | PON Power Meters. | 480000 | 192174.13 |  | 192174.13 | 287825.87 |  | I250307 | 50504525.19 | I250307 | 50504525.19
I240189 | I240189022 | CATV Transmission Equipmen | 2372402.25 | 894755.6 |  | 894755.6 | 1477646.65 |  | I250326 | 29990113.6 | I250326 | 29990113.6
I240189 | I240189023 | PON Cards | 3407400 |  |  |  | 3407400 |  | I250327 | 18753966.2 | I250327 | 18753966.2
I240189 | I240189024 | Bolan | 4335120.73 | 16386.78 |  | 16386.78 | 4318733.95 |  | I250374 | 0 | I250374 | 0
I240189 | I240190000 | StormFiber Expansion – Sia | 40527705.86 | 40527705.86 |  | 40527705.86 |  |  | I250375 | 13863425.15 | I250375 | 13863425.15
I240190 | I240190001 | Cabinets & Accessories - | 4326752.64 | 253812.83 |  | 253812.83 | 4072939.81 |  | I250376 | 72610872.22 | I250376 | 72610872.22
I240190 | I240190002 | Consumable & Accessories | 1657151.4 | 1354458.88 |  | 1354458.88 | 302692.52 |  | I250377 | 12761740.29 | I250377 | 12761740.29
I240190 | I240190003 | Cables - (Feeder Access | 12392349.47 | 4056681.19 |  | 4056681.19 | 8335668.28 |  | I250378 | 15200321.67 | I250378 | 15200321.67
I240190 | I240190004 | Enclosures - (Feeder Ac | 653599.8 | 111050.93 |  | 111050.93 | 542548.87 |  | I250379 | 115955842.06 | I250379 | 115955842.06
I240190 | I240190005 | Splitters - (Access & Dis | 789646.42 | 34641.72 |  | 34641.72 | 755004.7 |  | I250380 | 11888900.15 | I250380 | 11888900.15
I240190 | I240190006 | Duct - (HDPE / GI with | 39249550.46 | 18541.86 |  | 18541.86 | 39231008.6 |  | I250681 | 11082543.43 | I250681 | 11082543.43
I240190 | I240190007 | Handholes - (HH / Chamb | 7293500 |  |  |  | 7293500 |  | I250734 | 21098168.35 | I250734 | 21098168.35
I240190 | I240190008 | Poles | 560000 |  |  |  | 560000 |  | I250737 | 24952501.79 | I250737 | 24952501.79
I240190 | I240190009 | FDT Foundation | 100000 |  |  |  | 100000 |  | I260060 | 6618364.34 | I260060 | 6618364.34
I240190 | I240190010 | Infrastructure Laying - | 15558347.5 |  |  |  | 15558347.5 |  | I260061 | 139597248.9 | I260061 | 139597248.9
I240190 | I240190011 | Cable Hauling - (Aerial | 4713513.6 |  |  |  | 4713513.6 |  | I260068 | 28887112.17 | I260068 | 28887112.17
I240190 | I240190012 | Building Attachments - | 782998.68 |  |  |  | 782998.68 |  | I260105 | 0 | I260105 | 0
I240190 | I240190013 | Transportation - (Vehic | 6000000 | 171050 |  | 171050 | 5828950 |  | I260159 | 10238475.59 | I260159 | 10238475.59
I240190 | I240190014 | Tool Kit - (Access) | 300000 | 308400 |  | 308400 | 8400.00- |  | I260160 | 18804849.37 | I260160 | 18804849.37
I240190 | I240190015 | Tool Kit - (Dev.) | 80000 |  |  |  | 80000 |  | I260179 | 245384.52 | I260179 | 245384.52
I240190 | I240190016 | Cable prepartion Tools - | 150000 | 152480.62 |  | 152480.62 | 2480.62- |  | I260180 | 6234786.98 | I260180 | 6234786.98
I240190 | I240190017 | Splice Machine | 792000 |  |  |  | 792000 |  | I260208 | 107220 | I260208 | 107220
I240190 | I240190018 | Cleavers | 400000 |  |  |  | 400000 |  | I260294 | 288024.22 | I260294 | 288024.22
I240190 | I240190019 | VFLs | 100000 |  |  |  | 100000 |  | I260295 | 878211.4 | I260295 | 878211.4
I240190 | I240190020 | PON Power Meters. | 600000 | 96045.46 |  | 96045.46 | 503954.54 |  | I260296 | 17232581.84 | I260296 | 17232581.84
I240190 | I240190021 | CATV Transmission Equipmen | 2094400 | 1802598.63 |  | 1802598.63 | 291801.37 |  | I260298 | 1254241.51 | I260298 | 1254241.51
I240190 | I240190022 | PON Cards | 5390000 |  |  |  | 5390000 |  | I260361 | 5283860.51 | I260361 | 5283860.51
I240190 | I240190023 | Bolan | 5240900.6 | 288005.86 |  | 288005.86 | 4952894.74 |  | INT-21-00315 | 283234406.96 | INT-21-00315 | 283234406.96
I240190 | I240435000 | StormFiber Expansion – Top | 14573649.93 | 14573649.93 |  | 14573649.93 |  |  | INT-23-00435 | 77881903.39 | INT-23-00435 | 77881903.39
I240435 | I240435001 | Cabinets & Accessories - | 11966911.04 | 716514.71 |  | 716514.71 | 11250396.33 |  | INT-23-00436 | 17417582.61 | INT-23-00436 | 17417582.61
I240435 | I240435002 | Consumable & Accessories | 2779361.65 | 1363192.39 |  | 1363192.39 | 1416169.26 |  | INT-23-00437 | 42295320.28 | INT-23-00437 | 42295320.28
I240435 | I240435003 | Cables - (Feeder Access | 29970939.44 | 3979863.61 |  | 3979863.61 | 25991075.83 |  | INT-23-00438 | 121795.99 | INT-23-00438 | 121795.99
I240435 | I240435004 | Enclosures - (Feeder Ac | 679142.77 | 159447.21 |  | 159447.21 | 519695.56 |  | INT-23-00439 | 190240587.93 | INT-23-00439 | 190240587.93
I240435 | I240435005 | Splitters - (Access & Dis | 4753039.41 | 180325.15 |  | 180325.15 | 4572714.26 |  | INT-23-00440 | 4688155.21 | INT-23-00440 | 4688155.21
I240435 | I240435006 | Duct - (HDPE / GI with | 2255374.9 | 775037.36 |  | 775037.36 | 1480337.54 |  | INT-23-00441 | 20306046.74 | INT-23-00441 | 20306046.74
I240435 | I240435007 | Handholes - (HH / Chamb | 620000 |  |  |  | 620000 |  | INT-23-00442 | 2854816.24 | INT-23-00442 | 2854816.24
I240435 | I240435008 | FDT Foundation | 90000 |  | 60000 | 60000 | 30000 |  | INT-23-00444 | 195619264.95 | INT-23-00444 | 195619264.95
I240435 | I240435009 | Infrastructure Laying - | 1387875.99 | 26499.99 | 768700 | 795199.99 | 592676 |  | INT-23-00445 | 40582736.6 | INT-23-00445 | 40582736.6
I240435 | I240435010 | Cable Hauling - (Aerial | 6644239 | 875000 | 1437875 | 2312875 | 4331364 |  | INT-23-00446 | 0 | INT-23-00446 | 0
I240435 | I240435011 | Building Attachments - | 1796855 |  |  |  | 1796855 |  | INT-23-00447 | 112052637.19 | INT-23-00447 | 112052637.19
I240435 | I240435012 | Transportation - (Vehic | 3740000 |  |  |  | 3740000 |  | INT-23-00764 | 57769975.94 | INT-23-00764 | 57769975.94
I240435 | I240435013 | Tool Kit - (Access) | 240000 | 190700 |  | 190700 | 49300 |  | Grand Total | 3364041920.48 | Grand Total | 3364041920.48
I240435 | I240435014 | Tool Kit - (Dev.) | 200000 |  |  |  | 200000
I240435 | I240435015 | Cable prepartion Tools - | 480000 | 232090.13 |  | 232090.13 | 247909.87
I240435 | I240435016 | Splice Machine | 2800000 | 401479.67 |  | 401479.67 | 2398520.33
I240435 | I240435017 | Cleavers | 320000 |  |  |  | 320000
I240435 | I240435018 | VFLs | 160000 |  |  |  | 160000
I240435 | I240435019 | OTDR - For Core / FTTH b | 700000 |  |  |  | 700000
I240435 | I240435020 | PON Power Mtr. | 640000 | 96087.07 |  | 96087.07 | 543912.93
I240435 | I240435021 | CATV Transmission Equipmen | 3407400 |  |  |  | 3407400
I240435 | I240435022 | OLT | 2697525 |  |  |  | 2697525
I240435 | I240435023 | PON Cards | 5111100 |  |  |  | 5111100
I240435 | I240435024 | Bolan | 17930875 | 1995240.00- | 17677125 | 15681885 | 2248990
I240435 | I240435025 | Switch | 851850 |  |  |  | 851850
I240435 | I240435026 | OLT connectivity SFPs Mult | 32938.2 |  |  |  | 32938.2
I240435 | I240435027 | Uplink SFPs for POP connec | 13814.6 | 13087.66 |  | 13087.66 | 726.94
I240435 | I240437000 | StormFiber Expansion – Ask | 58643039.61 | 58643039.61 |  | 58643039.61
I240437 | I240437001 | Cabinets & Accessories - | 16674157.71 | 790087.3 |  | 790087.3 | 15884070.41
I240437 | I240437002 | Consumable & Accessories | 3288517.68 | 637970.8 |  | 637970.8 | 2650546.88
I240437 | I240437003 | Cables - (Feeder Access | 29851148.54 | 2099045.05 |  | 2099045.05 | 27752103.49
I240437 | I240437004 | Enclosures - (Feeder Ac | 2247971.97 | 234476.25 |  | 234476.25 | 2013495.72
I240437 | I240437005 | Splitters - (Access & Dis | 7023232.87 | 165950.97 |  | 165950.97 | 6857281.9
I240437 | I240437006 | Duct - (HDPE / GI with | 44976229.59 | 2300795.08 |  | 2300795.08 | 42675434.51
I240437 | I240437007 | Handholes - (HH / Chamb | 15720000 |  |  |  | 15720000
I240437 | I240437008 | FDT Foundation | 60000 |  |  |  | 60000
I240437 | I240437009 | Infrastructure Laying - | 73804037.72 |  | 10400000 | 10400000 | 63404037.72
I240437 | I240437010 | Cable Hauling - (Aerial | 14222806.37 |  |  |  | 14222806.37
I240437 | I240437011 | Building Attachments - | 13985509.56 |  |  |  | 13985509.56
I240437 | I240437012 | Transportation - (Vehic | 4350000 |  |  |  | 4350000
I240437 | I240437013 | Tool Kit - (Access) | 360000 | 375660 |  | 375660 | 15660.00-
I240437 | I240437014 | Tool Kit - (Dev.) | 150000 |  |  |  | 150000
I240437 | I240437015 | Cable prepartion Tools - | 318332.3 | 15438.5 |  | 15438.5 | 302893.8
I240437 | I240437016 | Splice Machine | 2100000 |  |  |  | 2100000
I240437 | I240437017 | Cleavers | 480000 | 92658.18 |  | 92658.18 | 387341.82
I240437 | I240437018 | VFLs | 180000 |  |  |  | 180000
I240437 | I240437019 | OTDR - For Core / FTTH b | 700000 |  |  |  | 700000
I240437 | I240437020 | PON Power Mtr. | 720000 |  |  |  | 720000
I240437 | I240437021 | CATV Transmission Equipmen | 1945057.5 | 1802598.64 |  | 1802598.64 | 142458.86
I240437 | I240437022 | OLT | 2697525 |  |  |  | 2697525
I240437 | I240437023 | PON Cards | 5962950 |  |  |  | 5962950
I240437 | I240437024 | Bolan | 6561957.32 | 100446.24 |  | 100446.24 | 6461511.08
I240437 | I240438000 | StormFiber Expansion – Chi | 23399064.34 | 23399064.34 |  | 23399064.34
I240438 | I240438001 | Cabinets & Accessories - | 20184693.22 | 158984.29 |  | 158984.29 | 20025708.93
I240438 | I240438002 | Consumable & Accessories | 5081433.68 | 893424.2 |  | 893424.2 | 4188009.48
I240438 | I240438003 | Cables - (Feeder Access | 41821723.39 | 753944.01 |  | 753944.01 | 41067779.38
I240438 | I240438004 | Enclosures - (Feeder Ac | 3150138.58 | 761.99 |  | 761.99 | 3149376.59
I240438 | I240438005 | Splitters - (Access & Dis | 8875705.23 | 18673.35 |  | 18673.35 | 8857031.88
I240438 | I240438006 | Duct - (HDPE / GI with | 46781981.36 | 9500000.00- |  | 9500000.00- | 56281981.36
I240438 | I240438007 | Handholes - (HH / Chamb | 7936500 |  |  |  | 7936500
I240438 | I240438008 | Poles | 570000 |  |  |  | 570000
I240438 | I240438009 | FDT Foundation | 310000 |  |  |  | 310000
I240438 | I240438010 | Infrastructure Laying - | 22229016.9 | 23927324 |  | 23927324 | 1698307.10-
I240438 | I240438011 | Cable Hauling - (Aerial | 11667317 |  |  |  | 11667317
I240438 | I240438012 | Building Attachments - | 812000 |  |  |  | 812000
I240438 | I240438013 | Transportation - (Vehic | 3280000 |  |  |  | 3280000
I240438 | I240438014 | Tool Kit - (Access) | 300000 | 276400 |  | 276400 | 23600
I240438 | I240438015 | Tool Kit - (Dev.) | 100000 |  |  |  | 100000
I240438 | I240438016 | Cable prepartion Tools - | 240000 |  |  |  | 240000
I240438 | I240438017 | Splice Machine | 1400000 |  |  |  | 1400000
I240438 | I240438018 | Cleavers | 400000 |  |  |  | 400000
I240438 | I240438019 | VFLs | 160000 |  |  |  | 160000
I240438 | I240438020 | OTDR - For Core / FTTH b | 675000 |  |  |  | 675000
I240438 | I240438021 | PON Power Mtr. | 560000 |  |  |  | 560000
I240438 | I240438022 | CATV Transmission Equipmen | 1817280 | 1802598.64 |  | 1802598.64 | 14681.36
I240438 | I240438023 | PON Cards | 8518500 |  |  |  | 8518500
I240438 | I240438024 | Carry with Ladder | 5000000 |  | 2179000 | 2179000 | 2821000
I240438 | I240438025 | Bolan | 1800000 |  |  |  | 1800000
I240438 | I240440000 | StormFiber Expansion – Lah | 53404413.16 | 53404413.16 |  | 53404413.16
I240440 | I240440001 | Cabinets & Accessories - | 31966433.41 | 745233.67 |  | 745233.67 | 31221199.74
I240440 | I240440002 | Consumable & Accessories | 5807873.75 | 613571.9 |  | 613571.9 | 5194301.85
I240440 | I240440003 | Cables - (Feeder Access | 50046994.2 | 1325259.2 |  | 1325259.2 | 48721735
I240440 | I240440004 | Enclosures - (Feeder Ac | 2499128.73 | 106529.8 |  | 106529.8 | 2392598.93
I240440 | I240440005 | Splitters - (Access & Dis | 10305147.05 | 51837.81 |  | 51837.81 | 10253309.24
I240440 | I240440006 | Duct - (HDPE / GI with | 66749136.4 | 5471840.14 |  | 5471840.14 | 61277296.26
I240440 | I240440007 | Handholes - (HH / Chamb | 31767000 | 2893500 | 3161000 | 6054500 | 25712500
I240440 | I240440008 | FDT Foundation | 250137.91 | 49499.56 |  | 49499.56 | 200638.35
I240440 | I240440009 | Infrastructure Laying - | 92504854.79 | 32780.00- | 9856125 | 9823345 | 82681509.79
I240440 | I240440010 | Cable Hauling - (Aerial | 10058474.58 |  |  |  | 10058474.58
I240440 | I240440011 | Building Attachments - | 2287998.12 |  |  |  | 2287998.12
I240440 | I240440012 | Transportation - (Vehic | 3340000 |  |  |  | 3340000
I240440 | I240440013 | Tool Kit - (Access) | 375000 | 345000 |  | 345000 | 30000
I240440 | I240440014 | Tool Kit - (Dev.) | 300000 |  |  |  | 300000
I240440 | I240440015 | Cable prepartion Tools - | 900000 |  |  |  | 900000
I240440 | I240440016 | Splice Machine | 4800000 | 1164174.57 |  | 1164174.57 | 3635825.43
I240440 | I240440017 | Cleavers | 400000 |  |  |  | 400000
I240440 | I240440018 | VFLs | 220000 |  |  |  | 220000
I240440 | I240440019 | OTDR - For Core / FTTH b | 1400000 |  |  |  | 1400000
I240440 | I240440020 | PON Power Mtr. | 1320000 | 48043.54 |  | 48043.54 | 1271956.46
I240440 | I240440021 | CATV Transmission Equipmen | 4784557.5 | 4506496.55 |  | 4506496.55 | 278060.95
I240440 | I240440022 | PON Cards | 10222200 |  |  |  | 10222200
I240440 | I240440023 | Carry with ladder | 5000000 |  | 2179000 | 2179000 | 2821000
I240440 | I240440024 | Bolan | 3600000 |  |  |  | 3600000
I240440 | I240442000 | StormFiber Expansion – Chi | 8728453.36 | 8728453.36 |  | 8728453.36
I240442 | I240442001 | Cabinets & Accessories - | 6623469.65 | 200451.49 |  | 200451.49 | 6423018.16
I240442 | I240442002 | Consumable & Accessories | 1591400 | 1192701.02 |  | 1192701.02 | 398698.98
I240442 | I240442003 | Cables - (Feeder Access | 25537960.93 | 4378626.7 |  | 4378626.7 | 21159334.23
I240442 | I240442004 | Enclosures - (Feeder Ac | 608686.44 | 114283.33 |  | 114283.33 | 494403.11
I240442 | I240442005 | Splitters - (Access & Dis | 532123.63 | 77130.52 |  | 77130.52 | 454993.11
I240442 | I240442006 | Duct - (HDPE / GI with | 27293801.75 |  |  |  | 27293801.75
I240442 | I240442007 | Handholes - (HH / Cham | 3088500 |  |  |  | 3088500
I240442 | I240442008 | Poles | 1344000 |  | 112000 | 112000 | 1232000
I240442 | I240442009 | FDT Foundation | 80000 |  | 40000 | 40000 | 40000
I240442 | I240442010 | Infrastructure Laying - | 35424288 | 555000 |  | 555000 | 34869288
I240442 | I240442011 | Cable Hauling - (Aerial | 5721245.1 | 1515640 | 794760 | 2310400 | 3410845.1
I240442 | I240442012 | Transportation - (Vehic | 4250000 | 257000 |  | 257000 | 3993000
I240442 | I240442013 | Tool Kit - (Access) | 180000 | 103250 |  | 103250 | 76750
I240442 | I240442014 | Tool Kit - (Dev.) | 50000 | 50000 |  | 50000
I240442 | I240442015 | Cable prepartion Tools - | 120000 |  |  |  | 120000
I240442 | I240442016 | Splice Machine | 700000 | 525000 |  | 525000 | 175000
I240442 | I240442017 | Cleavers | 240000 |  |  |  | 240000
I240442 | I240442018 | VFLs | 120000 |  |  |  | 120000
I240442 | I240442019 | OTDR - For Core / FTTH b | 675000 | 365000 |  | 365000 | 310000
I240442 | I240442020 | PON Power Mtr. | 250000 | 96087.06 |  | 96087.06 | 153912.94
I240442 | I240442021 | CATV Transmission Equipmen | 3080857.5 |  |  |  | 3080857.5
I240442 | I240442022 | Bolan | 3600000 | 935.3 |  | 935.3 | 3599064.7
I240442 | I240442023 | Carry with ladder | 1800000 |  |  |  | 1800000
I240442 | I240442024 | OLT | 2697525 |  |  |  | 2697525
I240442 | I240442025 | PON cards | 2555550 |  |  |  | 2555550
I240442 | I240442026 | Switch | 851850 |  |  |  | 851850
I240442 | I240459000 | STORMFIBER EXPANSION – ASK | 3240589.35 | 3240589.35 |  | 3240589.35
I240459 | I240459001 | Cabinets & Accessories - | 1082081.97 | 1366.53 |  | 1366.53 | 1080715.44
I240459 | I240459002 | Consumable & Accessories | 240174.35 | 121723.47 |  | 121723.47 | 118450.88
I240459 | I240459003 | Cables - (Feeder Access | 1305899.39 | 38696.11 |  | 38696.11 | 1267203.28
I240459 | I240459004 | Enclosures - (Feeder Ac | 179889.04 | 499.37 |  | 499.37 | 179389.67
I240459 | I240459005 | Splitters - (Access & Dis | 538311.13 |  |  |  | 538311.13
I240459 | I240459006 | Duct - (HDPE / GI with | 3035121.56 |  |  |  | 3035121.56
I240459 | I240459007 | Handholes - (HH / Chamb | 657000 |  |  |  | 657000
I240459 | I240459008 | FDT Foundation | 50000 |  |  |  | 50000
I240459 | I240459009 | Infrastructure Laying - | 1176342.4 |  |  |  | 1176342.4
I240459 | I240459010 | Cable Hauling - (Aerial | 561858.4 |  |  |  | 561858.4
I240459 | I240459011 | Tool Kit - (Access) | 150000 | 84030 |  | 84030 | 65970
I240459 | I240459012 | Tool Kit - (Dev.) | 160000 |  |  |  | 160000
I240459 | I240459013 | Cable preparation Tools | 300000 |  |  |  | 300000
I240459 | I240459015 | Cleavers | 160000 | 57000 |  | 57000 | 103000
I240459 | I240459016 | VFLs | 80000 |  |  |  | 80000
I240459 | I240459017 | OTDR - For Core / FTTH b | 700000 |  |  |  | 700000
I240459 | I240459018 | PON Power Mtr. | 320000 |  |  |  | 320000
I240459 | I240459019 | CATV Transmission Equipmen | 2129625 | 1802598.64 |  | 1802598.64 | 327026.36
I240459 | I240459020 | PON Cards | 851850 |  |  |  | 851850
I240459 | I240518000 | StormFiber Expansion – Mis | 46221961.23 | 46221961.23 |  | 46221961.23
I240518 | I240518001 | Cabinets & Accessories - | 7758642.19 | 277271.48 |  | 277271.48 | 7481370.71
I240518 | I240518002 | Consumable & Accessories | 1752844.96 | 86255.61 |  | 86255.61 | 1666589.35
I240518 | I240518003 | Cables - (Feeder Access | 6214392.81 | 2304511.27 |  | 2304511.27 | 3909881.54
I240518 | I240518004 | Enclosures - (Feeder Ac | 985071.12 | 20716.73 |  | 20716.73 | 964354.39
I240518 | I240518005 | Splitters - (Access & Dis | 3801893.17 | 79354.62 |  | 79354.62 | 3722538.55
I240518 | I240518006 | Duct - (HDPE / GI with | 17220507.85 |  |  |  | 17220507.85
I240518 | I240518007 | Handholes - (HH / Chamb | 10027500 |  |  |  | 10027500
I240518 | I240518008 | FDT Foundation | 68615.78 |  |  |  | 68615.78
I240518 | I240518009 | Infrastructure Laying - | 8356874.55 |  | 24145 | 24145 | 8332729.55
I240518 | I240518010 | Cable Hauling - (Aerial | 3542940.4 |  |  |  | 3542940.4
I240518 | I240518011 | Building Attachments - | 1937502 |  |  |  | 1937502
I240518 | I240518012 | Transportation - (Vehic | 1590000 |  |  |  | 1590000
I240518 | I240518013 | Tool Kit - (Access) | 150000 |  |  |  | 150000
I240518 | I240518014 | Tool Kit - (Dev.) | 160000 |  |  |  | 160000
I240518 | I240518015 | Cable preparation Tools | 300000 |  |  |  | 300000
I240518 | I240518016 | Splice Machine | 1600000 | 10755.16 |  | 10755.16 | 1589244.84
I240518 | I240518017 | Cleavers | 480000 |  |  |  | 480000
I240518 | I240518018 | VFLs | 120000 |  |  |  | 120000
I240518 | I240518019 | OTDR - For Core / FTTH b | 1400000 |  |  |  | 1400000
I240518 | I240518020 | PON Power Mtr. | 720000 |  |  |  | 720000
I240518 | I240518021 | CATV Transmission Equipeme | 1064812.5 |  |  |  | 1064812.5
I240518 | I240518022 | PON Cards | 1703700 |  |  |  | 1703700
I240518 | I240518023 | Bolan | 3599429.56 | 0.01- | 1949700 | 1949699.99 | 1649729.57
I240518 | I240519001 | Cabinets & Accessories - | 13373000 |  |  |  | 13373000
I240519 | I240519002 | Consumable & Accessories | 2738100 |  |  |  | 2738100
I240519 | I240519003 | Cables - (Feeder Access | 32864149.71 |  |  |  | 32864149.71
I240519 | I240519004 | Enclosures - (Feeder Ac | 1971797.46 |  |  |  | 1971797.46
I240519 | I240519005 | Splitters - (Access & Dis | 6030985.48 |  |  |  | 6030985.48
I240519 | I240519006 | Duct - (HDPE / GI with | 54747638.94 |  |  |  | 54747638.94
I240519 | I240519007 | Handholes - (HH / Chamb | 21660000 |  |  |  | 21660000
I240519 | I240519008 | FDT Foundation | 225000 |  |  |  | 225000
I240519 | I240519009 | Infrastructure Laying - | 102021741.43 |  |  |  | 102021741.43
I240519 | I240519010 | Cable Hauling - (Aerial | 8911103.5 |  |  |  | 8911103.5
I240519 | I240519011 | Building Attachments - | 49363491.54 |  |  |  | 49363491.54
I240519 | I240519012 | Transportation - (Vehic | 3675000 |  |  |  | 3675000
I240519 | I240519013 | Tool Kit - (Access) | 450000 |  |  |  | 450000
I240519 | I240519014 | Tool Kit - (Dev.) | 400000 |  |  |  | 400000
I240519 | I240519015 | Cable preparation Tools | 750000 |  |  |  | 750000
I240519 | I240519016 | Splice Machine | 4000000 |  |  |  | 4000000
I240519 | I240519017 | Cleavers | 480000 |  |  |  | 480000
I240519 | I240519018 | VFLs | 200000 |  |  |  | 200000
I240519 | I240519019 | OTDR - For Core / FTTH b | 1400000 |  |  |  | 1400000
I240519 | I240519020 | PON Power Mtr. | 1200000 |  |  |  | 1200000
I240519 | I240519021 | CATV Transmission Equipeme | 8348130 |  |  |  | 8348130
I240519 | I240519022 | PON Cards | 5111100 |  |  |  | 5111100
I240519 | I240519023 | OLT | 2697525 |  |  |  | 2697525
I240519 | I240519024 | Switch | 851850 |  |  |  | 851850
I240519 | I240519025 | OLT connectivity SFPs Mult | 32938.2 |  |  |  | 32938.2
I240519 | I240519026 | Uplink SFPs for POP connec | 98814.6 |  |  |  | 98814.6
I240519 | I240519027 | Bolan | 9000000 |  |  |  | 9000000
I240519 | I240537000 | StormFiber Expansion – Abb | 5337898.44 | 5337898.44 |  | 5337898.44
I240537 | I240537001 | Cabinets & Accessories - | 3701341.05 | 463518.8 |  | 463518.8 | 3237822.25
I240537 | I240537002 | Consumable & Accessories | 938337.48 | 769486.74 |  | 769486.74 | 168850.74
I240537 | I240537003 | Cables - (Feeder Access | 6084143.95 | 3209255.47 |  | 3209255.47 | 2874888.48
I240537 | I240537004 | Enclosures - (Feeder Ac | 257101.69 | 243196.38 |  | 243196.38 | 13905.31
I240537 | I240537005 | Splitters - (Access & Dis | 757776.9 | 19188.75 |  | 19188.75 | 738588.15
I240537 | I240537006 | Duct - (HDPE / GI with | 1329172.72 |  |  |  | 1329172.72
I240537 | I240537007 | Handholes - (HH / Chamb | 154000 |  |  |  | 154000
I240537 | I240537008 | Poles | 840000 |  |  |  | 840000
I240537 | I240537009 | FDT Foundation | 30000 |  |  |  | 30000
I240537 | I240537010 | Infrastructure Laying - | 46519.3 |  |  |  | 46519.3
I240537 | I240537011 | Cable Hauling - (Aerial | 2318548 | 2222860 | 77140 | 2300000 | 18548
I240537 | I240537012 | Building Attachments - | 1046460 |  |  |  | 1046460
I240537 | I240537013 | Transportation - (Vehic | 540000 |  |  |  | 540000
I240537 | I240537014 | Tool Kit - (Access) | 150000 | 148850 |  | 148850 | 1150
I240537 | I240537015 | Tool Kit - (Dev.) | 80000 | 25000 |  | 25000 | 55000
I240537 | I240537016 | Cable preparation Tools | 150000 |  |  |  | 150000
I240537 | I240537017 | Splice Machine | 796270.19 | 766499.86 |  | 766499.86 | 29770.33
I240537 | I240537018 | Cleavers | 240000 | 19000 |  | 19000 | 221000
I240537 | I240537019 | VFLs | 60000 |  |  |  | 60000
I240537 | I240537020 | PON Power Mtr. | 360000 | 48043.53 |  | 48043.53 | 311956.47
I240537 | I240537021 | CATV Transmission Equipmen | 965430 | 901299.31 |  | 901299.31 | 64130.69
I240537 | I240537022 | PON Cards | 1703700 |  |  |  | 1703700
I240537 | I240537023 | Bolan | 3900000 |  | 1949700 | 1949700 | 1950300
I240537 | I240538000 | StormFiber Expansion – Har | 13069988.05 | 13069988.05 |  | 13069988.05
I240538 | I240538001 | Cabinets & Accessories - | 14585209.98 | 590561.85 |  | 590561.85 | 13994648.13
I240538 | I240538002 | Consumable & Accessories | 3390190.61 | 739274.79 |  | 739274.79 | 2650915.82
I240538 | I240538003 | Cables - (Feeder Access | 31444645.43 | 5324914.09 |  | 5324914.09 | 26119731.34
I240538 | I240538004 | Enclosures - (Feeder Ac | 2172672.05 | 285110.54 |  | 285110.54 | 1887561.51
I240538 | I240538005 | Splitters - (Access & Dis | 5183772.95 | 535788.77 |  | 535788.77 | 4647984.18
I240538 | I240538006 | Duct - (HDPE / GI with | 44451537.66 | 16025.23 |  | 16025.23 | 44435512.43
I240538 | I240538007 | Handholes - (HH / Chamb | 4834000 | 187000 |  | 187000 | 4647000
I240538 | I240538008 | Poles | 3300000 |  |  |  | 3300000
I240538 | I240538009 | FDT Foundation | 360000 | 14000 |  | 14000 | 346000
I240538 | I240538010 | Infrastructure Laying - | 34774340 | 471250 |  | 471250 | 34303090
I240538 | I240538011 | Cable Hauling - (Aerial | 7952802.5 | 2124580 | 1872460 | 3997040 | 3955762.5
I240538 | I240538012 | Building Attachments - | 32767000 |  |  |  | 32767000
I240538 | I240538013 | Transportation - (Vehic | 3960000 |  |  |  | 3960000
I240538 | I240538014 | Tool Kit - (Access) | 225000 | 24251.42 |  | 24251.42 | 200748.58
I240538 | I240538015 | Tool Kit - (Dev.) | 160000 |  |  |  | 160000
I240538 | I240538016 | Cable preparation Tools | 300000 | 6732.85 |  | 6732.85 | 293267.15
I240538 | I240538017 | Splice Machine | 1600000 |  |  |  | 1600000
I240538 | I240538018 | Cleavers | 240000 |  |  |  | 240000
I240538 | I240538019 | VFLs | 100000 |  |  |  | 100000
I240538 | I240538020 | OTDR - For Core / FTTH b | 675000 |  |  |  | 675000
I240538 | I240538021 | PON Power Mtr. | 600000 |  |  |  | 600000
I240538 | I240538022 | CATV Transmission Equipmen | 2058637.5 |  |  |  | 2058637.5
I240538 | I240538023 | PON cards | 4259250 |  |  |  | 4259250
I240538 | I240538024 | Carry with ladder | 2500000 | 205000 | 2254000 | 2459000 | 41000
I240538 | I240538025 | Bolan | 3900000 |  |  |  | 3900000
I240538 | I240539000 | StormFiber Expansion – Swa | 19700450.35 | 19700450.35 |  | 19700450.35
I240539 | I240539001 | Cabinets & Accessories - | 26228265.86 | 3991826.99 |  | 3991826.99 | 22236438.87
I240539 | I240539002 | Consumable & Accessories | 7066994.71 | 5405693.08 |  | 5405693.08 | 1661301.63
I240539 | I240539003 | Cables - (Feeder Access | 55327638.71 | 11686421.75 |  | 11686421.75 | 43641216.96
I240539 | I240539004 | Enclosures - (Feeder Ac | 3435692.42 | 972295.99 |  | 972295.99 | 2463396.43
I240539 | I240539005 | Splitters - (Access & Dis | 8847995.54 | 1740268.07 |  | 1740268.07 | 7107727.47
I240539 | I240539006 | Duct - (HDPE / GI with | 39540802.63 | 1109527.02 |  | 1109527.02 | 38431275.61
I240539 | I240539007 | Handholes - (HH / Chamb | 3608000 |  |  |  | 3608000
I240539 | I240539008 | Poles | 4710000 |  |  |  | 4710000
I240539 | I240539009 | FDT Foundation | 540000 |  |  |  | 540000
I240539 | I240539010 | Infrastructure Laying - | 40151148 |  |  |  | 40151148
I240539 | I240539011 | Cable Hauling - (Aerial | 15900781 |  |  |  | 15900781
I240539 | I240539012 | Building Attachments - | 36715452 |  |  |  | 36715452
I240539 | I240539013 | Transportation - (Vehic | 810000 | 143000 |  | 143000 | 667000
I240539 | I240539014 | Tool Kit - (Access) | 450000 | 163250 |  | 163250 | 286750
I240539 | I240539015 | Tool Kit - (Dev.) | 320000 | 25000 |  | 25000 | 295000
I240539 | I240539016 | Cable preparation Tools | 556182.98 | 43217.28 |  | 43217.28 | 512965.7
I240539 | I240539017 | Splice Machine | 3200000 | 698788.47 |  | 698788.47 | 2501211.53
I240539 | I240539018 | Cleavers | 480000 | 91735.68 |  | 91735.68 | 388264.32
I240539 | I240539019 | VFLs | 200000 | 2686.81 |  | 2686.81 | 197313.19
I240539 | I240539020 | OTDR - For Core / FTTH b | 675000 |  |  |  | 675000
I240539 | I240539021 | PON Power Mtr. | 1200000 | 93043.53 |  | 93043.53 | 1106956.47
I240539 | I240539022 | CATV Transmission Equipmen | 3308017.5 |  |  |  | 3308017.5
I240539 | I240539023 | PON Cards | 8518500 |  |  |  | 8518500
I240539 | I240539024 | Bolan | 7200000 |  |  |  | 7200000
I240539 | I240539025 | Carry with Ladder | 2500000 |  |  |  | 2500000
I240539 | I240540000 | StormFiber Expansion – Mar | 24383593.99 | 24383593.99 |  | 24383593.99
I240540 | I240540001 | Cabinets & Accessories - | 22163060.61 | 1553128.2 |  | 1553128.2 | 20609932.41
I240540 | I240540002 | Consumable & Accessories | 8587251.35 | 2379826.99 |  | 2379826.99 | 6207424.36
I240540 | I240540003 | Cables - (Feeder Access | 54650932.71 | 6587884.69 |  | 6587884.69 | 48063048.02
I240540 | I240540004 | Enclosures - (Feeder Ac | 2814859.14 | 594313.2 |  | 594313.2 | 2220545.94
I240540 | I240540005 | Splitters - (Access & Dis | 7666707.98 | 775387.89 |  | 775387.89 | 6891320.09
I240540 | I240540006 | Duct - (HDPE / GI with | 26938132.71 |  | 48400 | 48400 | 26889732.71
I240540 | I240540007 | Handholes - (HH / Chamb | 4222000 |  |  |  | 4222000
I240540 | I240540008 | Poles | 3320000 | 20000 | 280000 | 300000 | 3020000
I240540 | I240540009 | FDT Foundation | 660000 |  | 200000 | 200000 | 460000
I240540 | I240540010 | Infrastructure Laying - | 23772456.35 | 2519000 | 3030075 | 5549075 | 18223381.35
I240540 | I240540011 | Cable Hauling - (Aerial | 16463355 | 1455120 | 1488880 | 2944000 | 13519355
I240540 | I240540012 | Building Attachments - | 306000 |  |  |  | 306000
I240540 | I240540013 | Transportation - (Vehic | 3900000 |  |  |  | 3900000
I240540 | I240540014 | Tool Kit - (Access) | 375000 | 106860 |  | 106860 | 268140
I240540 | I240540015 | Tool Kit - (Dev.) | 224000 | 2686.85 |  | 2686.85 | 221313.15
I240540 | I240540016 | Cable preparation Tools | 450000 |  |  |  | 450000
I240540 | I240540017 | Splice Machine | 2400000 | 7459.61 |  | 7459.61 | 2392540.39
I240540 | I240540018 | Cleavers | 400000 |  |  |  | 400000
I240540 | I240540019 | VFLs | 160000 |  |  |  | 160000
I240540 | I240540020 | OTDR - For Core / FTTH b | 675000 |  |  |  | 675000
I240540 | I240540021 | PON Power Mtr. | 960000 | 48022.73 |  | 48022.73 | 911977.27
I240540 | I240540022 | CATV Transmission Equipmen | 3024067.5 | 894755.6 |  | 894755.6 | 2129311.9
I240540 | I240540023 | PON Cards | 6814800 |  |  |  | 6814800
I240540 | I240540024 | Bolan | 5400000 |  |  |  | 5400000
I240540 | I240540025 | Carry with Ladder | 2500000 |  |  |  | 2500000
I240540 | I240557000 | StormFiber Expansion – Kal | 3210324.26 | 3210324.26 |  | 3210324.26
I240557 | I240557001 | Cabinets & Accessories - | 1678992.86 | 19567.78 |  | 19567.78 | 1659425.08
I240557 | I240557002 | Consumable & Accessories | 397800 | 12412.56 |  | 12412.56 | 385387.44
I240557 | I240557003 | Cables - (Feeder Access | 4627848.8 | 90981.87 |  | 90981.87 | 4536866.93
I240557 | I240557004 | Enclosures - (Feeder Ac | 295462 | 10314.99 |  | 10314.99 | 285147.01
I240557 | I240557005 | Splitters - (Access & Dis | 682656.45 | 32135.79 |  | 32135.79 | 650520.66
I240557 | I240557006 | Duct - (HDPE / GI with | 4334773.33 |  |  |  | 4334773.33
I240557 | I240557007 | Handholes - (HH / Chamb | 726000 |  |  |  | 726000
I240557 | I240557008 | Poles | 300000 |  |  |  | 300000
I240557 | I240557009 | FDT Foundation | 40000 |  |  |  | 40000
I240557 | I240557010 | Infrastructure Laying - | 770400 |  |  |  | 770400
I240557 | I240557011 | Cable Hauling - (Aerial | 1701415 |  |  |  | 1701415
I240557 | I240557012 | Building Attachments - | 669500 |  |  |  | 669500
I240557 | I240557013 | Transportation - (Vehic | 685000 |  |  |  | 685000
I240557 | I240557014 | Tool Kit - (Access) | 75000 | 27660 |  | 27660 | 47340
I240557 | I240557015 | Tool Kit - (Dev.) | 50000 |  |  |  | 50000
I240557 | I240557016 | Cable prepartion Tools - | 150000 | 360 |  | 360 | 149640
I240557 | I240557017 | Cleavers | 80000 | 45464.73 |  | 45464.73 | 34535.27
I240557 | I240557018 | VFLs | 20000 |  |  |  | 20000
I240557 | I240557019 | PON Power Mtr. | 240000 | 211161.39 |  | 211161.39 | 28838.61
I240557 | I240678000 | StormFiber Expansion – Dev | 47815770.8 | 47815770.8 |  | 47815770.8
I240678 | I240678001 | Cabinets & Accessories - | 37183752.84 | 3575414.79 |  | 3575414.79 | 33608338.05
I240678 | I240678002 | Consumable & Accessories | 8085881.63 | 2515398.83 |  | 2515398.83 | 5570482.8
I240678 | I240678003 | Cables - (Feeder Access | 67180622.96 | 6491792.46 |  | 6491792.46 | 60688830.5
I240678 | I240678004 | Enclosures - (Feeder Ac | 3828548.51 | 441610.69 |  | 441610.69 | 3386937.82
I240678 | I240678005 | Splitters - (Access & Dis | 13750628.63 | 1389015.3 |  | 1389015.3 | 12361613.33
I240678 | I240678006 | Duct - (HDPE / GI with | 83407258.87 | 2004456.7 |  | 2004456.7 | 81402802.17
I240678 | I240678007 | Handholes - (HH / Chamb | 21128500 | 198000 | 33000 | 231000 | 20897500
I240678 | I240678008 | Poles | 3450000 |  |  |  | 3450000
I240678 | I240678009 | FDT Foundation | 775000 | 34000 |  | 34000 | 741000
I240678 | I240678010 | Infrastructure Laying - | 95860589.3 | 435625 | 744600 | 1180225 | 94680364.3
I240678 | I240678011 | Cable Hauling - (Aerial | 18579414.35 | 7775370 | 1320720 | 9096090 | 9483324.35
I240678 | I240678012 | Building Attachments - ( | 5040000 |  |  |  | 5040000
I240678 | I240678013 | Transportation - (Vehic | 7000000 |  |  |  | 7000000
I240678 | I240678014 | Tool Kit - (Access) | 525000 | 520810 |  | 520810 | 4190
I240678 | I240678015 | Tool Kit - (Dev.) | 800000 |  |  |  | 800000
I240678 | I240678016 | Cable prepartion Tools - | 750000 | 113032.78 |  | 113032.78 | 636967.22
I240678 | I240678017 | Splice Machine | 3972270.19 | 749191.22 |  | 749191.22 | 3223078.97
I240678 | I240678018 | Cleavers | 1120000 | 76000 |  | 76000 | 1044000
I240678 | I240678019 | VFLs | 380000 |  |  |  | 380000
I240678 | I240678020 | OTDR - For Core / FTTH b | 1750000 |  |  |  | 1750000
I240678 | I240678021 | PON Power Mtr. | 2280000 | 192338.98 |  | 192338.98 | 2087661.02
I240678 | I240678022 | CATV Transmission Equipmen | 1930860 | 1789511.2 |  | 1789511.2 | 141348.8
I240678 | I240678023 | PON Cards | 7666650 | 3531787.99 |  | 3531787.99 | 4134862.01
I240678 | I240678024 | OLT | 2697525 | 1803964.62 |  | 1803964.62 | 893560.38
I240678 | I240678025 | OLT connectivity SFPs Mult | 16469.1 |  |  |  | 16469.1
I240678 | I240678026 | Uplink SFPs for POP connec | 49407.3 | 32163.49 |  | 32163.49 | 17243.81
I240678 | I240678027 | Bolan | 6906205.97 | 465755.97 | 6457700 | 6923455.97 | 17250.00-
I240678 | I240678028 | Carry | 7500000 | 205000 | 6612000 | 6817000 | 683000
I240678 | I240679000 | StormFiber Expansion – Dev | 546545.29 | 546545.29 |  | 546545.29
I240679 | I240679001 | Cabinets & Accessories - | 2989446.12 | 181712.03 |  | 181712.03 | 2807734.09
I240679 | I240679002 | Consumable & Accessories | 628165.42 | 124111.08 |  | 124111.08 | 504054.34
I240679 | I240679003 | Cables - (Feeder Access | 4618605.71 | 297815.21 |  | 297815.21 | 4320790.5
I240679 | I240679004 | Enclosures - (Feeder Ac | 19051.64 | 18236.9 |  | 18236.9 | 814.74
I240679 | I240679005 | Splitters - (Access & Dis | 1440955.86 | 58563.68 |  | 58563.68 | 1382392.18
I240679 | I240679006 | CATV Transmission Equipmen | 3265425 | 894755.6 |  | 894755.6 | 2370669.4
I240679 | I240679007 | PON Cards | 4259250 |  |  |  | 4259250
I240679 | I240679008 | Carry | 5000000 |  |  |  | 5000000
I240679 | I240679009 | Bolan | 3600000 |  |  |  | 3600000
I240679 | I240679010 | Access tool kits | 375000 | 19000 |  | 19000 | 356000
I240679 | I240679011 | Clever | 400000 |  |  |  | 400000
I240679 | I240679012 | PON Meters | 960000 |  |  |  | 960000
I240679 | I240679013 | VFL | 160000 |  |  |  | 160000
I240679 | I240679014 | DEV Tool Kits and Cable pr | 600000 |  |  |  | 600000
I240679 | I240679015 | OTDR | 975000 |  |  |  | 975000
I240679 | I240679016 | Splicing Machines | 2400000 |  |  |  | 2400000
I240679 | I240680000 | StormFiber Expansion – Dev | 11280616.03 | 11280616.03 |  | 11280616.03
I240680 | I240680001 | Cabinets & Accessories - | 14998426.84 | 32797.6 |  | 32797.6 | 14965629.24
I240680 | I240680002 | Consumable & Accessories | 3134578.96 | 345001.25 |  | 345001.25 | 2789577.71
I240680 | I240680003 | Cables - (Feeder Access | 15702401.45 | 4477907.44 |  | 4477907.44 | 11224494.01
I240680 | I240680004 | Enclosures - (Feeder Ac | 2011153.03 | 43616.83 |  | 43616.83 | 1967536.2
I240680 | I240680005 | Splitters - (Access & Dis | 5403288.6 | 47033.22 |  | 47033.22 | 5356255.38
I240680 | I240680006 | Duct - (HDPE / GI with | 24367006.63 | 108332.7 |  | 108332.7 | 24258673.93
I240680 | I240680007 | Handholes - (HH / Chamb | 6597980 |  |  |  | 6597980
I240680 | I240680008 | FDT Foundation | 360000 |  |  |  | 360000
I240680 | I240680009 | Infrastructure Laying - | 38789036.21 |  | 4850000 | 4850000 | 33939036.21
I240680 | I240680010 | Cable Hauling - (Aerial | 6164985 |  |  |  | 6164985
I240680 | I240680011 | Building Attachments - | 2819654 |  |  |  | 2819654
I240680 | I240680012 | Transportation - (Vehic | 2200000 | 458900 |  | 458900 | 1741100
I240680 | I240680013 | Tool Kit - (Access) | 375000 | 250560 |  | 250560 | 124440
I240680 | I240680014 | Tool Kit - (Dev.) | 160000 |  |  |  | 160000
I240680 | I240680015 | Cable prepartion Tools - | 300000 |  |  |  | 300000
I240680 | I240680016 | Splice Machine | 1600000 | 422322.78 |  | 422322.78 | 1177677.22
I240680 | I240680017 | Cleavers | 400000 |  |  |  | 400000
I240680 | I240680018 | VFLs | 160000 |  |  |  | 160000
I240680 | I240680019 | OTDR - For Core / FTTH b | 1350000 |  |  |  | 1350000
I240680 | I240680020 | PON Power Mtr. | 600000 |  |  |  | 600000
I240680 | I240680021 | CATV Transmission Equipmen | 3208635 | 894755.6 |  | 894755.6 | 2313879.4
I240680 | I240680022 | PON Cards | 4259250 |  |  |  | 4259250
I240680 | I240680023 | Bolan | 3900000 |  | 1949700 | 1949700 | 1950300
I240680 | I240680024 | Carry | 5000000 | 410000 | 4508000 | 4918000 | 82000
I240680 | I240681000 | StormFiber Expansion – Dev | 3750661.42 | 3750661.42 |  | 3750661.42
I240681 | I240681001 | Cables - (Feeder Access | 1430095 | 74445.45 |  | 74445.45 | 1355649.55
I240681 | I240681002 | Enclosures - (Feeder Ac | 44000 |  |  |  | 44000
I240681 | I240681003 | Duct - (HDPE / GI with | 1797702.58 | 183332.6 |  | 183332.6 | 1614369.98
I240681 | I240681004 | Handholes - (HH / Chamb | 880000 |  | 480000 | 480000 | 400000
I240681 | I240681005 | Infrastructure Laying - | 960000 | 20080 |  | 20080 | 939920
I240681 | I240681006 | PON cards | 851850 |  |  |  | 851850
I240681 | I240681007 | Access tool Kits | 75000 | 71040 |  | 71040 | 3960
I240681 | I240681008 | PON Meter | 120000 |  |  |  | 120000
I240681 | I240681009 | VFL | 25000 |  |  |  | 25000
I240681 | I240681010 | Splice Machine | 800000 |  |  |  | 800000
I240681 | I240681011 | Dev Tool / Cable Prep Kit | 225000 |  |  |  | 225000
I240681 | I240682000 | StormFiber Expansion – Dev | 108487352.27 | 108494352.27 |  | 108494352.27 | 7000.00-
I240682 | I240682001 | Cabinets & Accessories - | 47659285.97 | 1915814.15 |  | 1915814.15 | 45743471.82
I240682 | I240682002 | Consumable & Accessories | 11566992.44 | 2835867.54 |  | 2835867.54 | 8731124.9
I240682 | I240682003 | Cables - (Feeder Access | 101449885.88 | 14005849.2 |  | 14005849.2 | 87444036.68
I240682 | I240682004 | Enclosures - (Feeder Ac | 6296601.23 | 301972.35 |  | 301972.35 | 5994628.88
I240682 | I240682005 | Splitters - (Access & Dis | 14967539.69 | 1167052.22 |  | 1167052.22 | 13800487.47
I240682 | I240682006 | Duct - (HDPE / GI with | 137383079.4 | 1407413.9 |  | 1407413.9 | 135975665.5
I240682 | I240682007 | Handholes - (HH / Chamb | 20083000 |  |  |  | 20083000
I240682 | I240682008 | Poles | 1740000 |  |  |  | 1740000
I240682 | I240682009 | FDT Foundation | 975000 | 2049.79 |  | 2049.79 | 972950.21
I240682 | I240682010 | Infrastructure Laying - | 81717210.1 | 237700 | 15775000 | 16012700 | 65704510.1
I240682 | I240682011 | Cable Hauling - (Aerial | 30772482 | 3767505 | 1544775 | 5312280 | 25460202
I240682 | I240682012 | Building Attachments - | 31215600 |  |  |  | 31215600
I240682 | I240682013 | Transportation - (Vehic | 13515000 |  |  |  | 13515000
I240682 | I240682014 | Tool Kit - (Access) | 1050000 | 636620 |  | 636620 | 413380
I240682 | I240682015 | Tool Kit - (Dev.) | 250000 |  |  |  | 250000
I240682 | I240682016 | Cable prepartion Tools - | 883330 | 2955.23 |  | 2955.23 | 880374.77
I240682 | I240682017 | Splice Machine | 3996046.22 |  |  |  | 3996046.22
I240682 | I240682018 | Cleavers | 1120000 | 76856 |  | 76856 | 1043144
I240682 | I240682019 | VFLs | 400000 |  |  |  | 400000
I240682 | I240682020 | OTDR - For Core / FTTH b | 1750000 |  |  |  | 1750000
I240682 | I240682021 | PON Power Mtr. | 2280000 |  |  |  | 2280000
I240682 | I240682022 | CATV Transmission Equipmen | 4174065 |  |  |  | 4174065
I240682 | I240682023 | OLT | 2697525 |  |  |  | 2697525
I240682 | I240682024 | PON Cards | 12777750 | 10218403.39 |  | 10218403.39 | 2559346.61
I240682 | I240682025 | Bolan | 11700000 |  | 5849100 | 5849100 | 5850900
I240682 | I240682026 | Carry | 5000000 | 205000 | 4433000 | 4638000 | 362000
I240682 | I240682027 | OLT connectivity SFPs Mult | 32938.2 | 30773.25 |  | 30773.25 | 2164.95
I240682 | I240682028 | Uplink SFPs for POP connec | 98814.6 |  |  |  | 98814.6
I240682 | I240683000 | StormFiber Expansion – Dev | 7533819.25 | 7533819.25 |  | 7533819.25
I240683 | I240683001 | Cabinets & Accessories - | 8229032.22 | 2060399.54 |  | 2060399.54 | 6168632.68
I240683 | I240683002 | Consumable & Accessories | 1645427.72 | 296981.68 |  | 296981.68 | 1348446.04
I240683 | I240683003 | Cables - (Feeder Access | 9749703.98 | 2872124.95 |  | 2872124.95 | 6877579.03
I240683 | I240683004 | Enclosures - (Feeder Ac | 1173936.01 | 260835.76 |  | 260835.76 | 913100.25
I240683 | I240683005 | Splitters - (Access & Dis | 2083311.61 | 1427843.93 |  | 1427843.93 | 655467.68
I240683 | I240683006 | Duct - (HDPE / GI with | 18436995.56 | 23366 |  | 23366 | 18413629.56
I240683 | I240683007 | Handholes - (HH / Chamb | 2728000 |  |  |  | 2728000
I240683 | I240683008 | FDT Foundation | 120000 |  |  |  | 120000
I240683 | I240683009 | Infrastructure Laying - | 22575861 |  |  |  | 22575861
I240683 | I240683010 | Cable Hauling - (Aerial | 4084643.5 |  |  |  | 4084643.5
I240683 | I240683011 | Transportation - (Vehic | 1200000 |  |  |  | 1200000
I240683 | I240683012 | Tool Kit - (Access) | 225000 | 240550 |  | 240550 | 15550.00-
I240683 | I240683013 | Tool Kit - (Dev.) | 100000 |  |  |  | 100000
I240683 | I240683014 | Cable prepartion Tools - | 300000 |  |  |  | 300000
I240683 | I240683015 | Splice Machine | 1600000 |  |  |  | 1600000
I240683 | I240683016 | Cleavers | 240000 | 19937.49 |  | 19937.49 | 220062.51
I240683 | I240683017 | VFLs | 100000 |  |  |  | 100000
I240683 | I240683019 | PON Power Mtr. | 600000 | 144130.6 |  | 144130.6 | 455869.4
I240683 | I240683020 | CATV Transmission Equipmen | 2115427.5 |  |  |  | 2115427.5
I240683 | I240683021 | PON Cards | 3407400 |  |  |  | 3407400
I240683 | I240683022 | Bolan | 3900000 |  | 1949700 | 1949700 | 1950300
I240683 | I240684000 | StormFiber Expansion – Dev | 9116409.03 | 9116409.03 |  | 9116409.03
I240684 | I240684001 | Cabinets & Accessories - | 4921637.15 | 345760.87 |  | 345760.87 | 4575876.28
I240684 | I240684002 | Consumable & Accessories | 950950 | 16635.36 |  | 16635.36 | 934314.64
I240684 | I240684003 | Cables - (Feeder Access | 7116138.74 | 739508.68 |  | 739508.68 | 6376630.06
I240684 | I240684004 | Enclosures - (Feeder Ac | 558009.5 | 10073.9 |  | 10073.9 | 547935.6
I240684 | I240684005 | Splitters - (Access & Dis | 1811746.74 | 98657.98 |  | 98657.98 | 1713088.76
I240684 | I240684006 | Duct - (HDPE / GI with | 12344361.37 | 463227.89 |  | 463227.89 | 11881133.48
I240684 | I240684007 | Handholes - (HH / Chamb | 3078000 |  |  |  | 3078000
I240684 | I240684008 | FDT Foundation
I240684 | I240684009 | Infrastructure Laying - | 20036939.44 | 681190 | 1484790 | 2165980 | 17870959.44
I240684 | I240684010 | Cable Hauling - (Aerial | 1469010.8 | 190449.4 | 41100 | 231549.4 | 1237461.4
I240684 | I240684011 | Building Attachments - | 7680276 | 203350 | 508105 | 711455 | 6968821
I240684 | I240684012 | Transportation - (Vehic | 710000 |  |  |  | 710000
I240684 | I240684013 | Tool Kit - (Access) | 8890.32 |  |  |  | 8890.32
I240684 | I240684014 | Tool Kit - (Dev.) | 50000 |  |  |  | 50000
I240684 | I240684015 | Cable prepartion Tools - | 150000 |  |  |  | 150000
I240684 | I240684016 | Splice Machine | 800000 |  |  |  | 800000
I240684 | I240684017 | Cleavers | 80000 |  |  |  | 80000
I240684 | I240684018 | VFLs | 20000 |  |  |  | 20000
I240684 | I240684019 | PON Power Mtr. | 120000 |  |  |  | 120000
I240684 | I240684020 | CATV Transmission Equipmen | 3208635 |  |  |  | 3208635
I240684 | I240684021 | Bolan or Karvan | 1800000 |  |  |  | 1800000
I240684 | I240700000 | StormFiber Expansion – Dev | 45174886.75 | 45174886.75 |  | 45174886.75
I240700 | I240700001 | Cabinets & Accessories - | 71267692.6 | 3186663.05 |  | 3186663.05 | 68081029.55
I240700 | I240700002 | Consumable & Accessories | 15273318.65 | 2033845.8 |  | 2033845.8 | 13239472.85
I240700 | I240700003 | Cables - (Feeder Access | 86906988.2 | 8159778.36 |  | 8159778.36 | 78747209.84
I240700 | I240700004 | Enclosures - (Feeder Ac | 9210100.26 | 462887.93 |  | 462887.93 | 8747212.33
I240700 | I240700005 | Splitters - (Access & Dis | 20061276.8 | 837181.43 |  | 837181.43 | 19224095.37
I240700 | I240700006 | Duct - (HDPE / GI with | 134648607.51 | 3474736.02 |  | 3474736.02 | 131173871.49
I240700 | I240700007 | Handholes - (HH / Chamb | 38478000 |  |  |  | 38478000
I240700 | I240700008 | FDT Foundation | 1260000 | 200000 |  | 200000 | 1060000
I240700 | I240700009 | Infrastructure Laying - | 170146748.4 | 1304800 | 4235000 | 5539800 | 164606948.4
I240700 | I240700010 | Cable Hauling - (Aerial | 26331117.5 | 2352785 | 8897215 | 11250000 | 15081117.5
I240700 | I240700011 | Building Attachments - | 17834752 |  |  |  | 17834752
I240700 | I240700012 | Transportation - (Vehic | 9570000 |  |  |  | 9570000
I240700 | I240700013 | Tool Kit - (Access) | 1350000 | 661590 |  | 661590 | 688410
I240700 | I240700014 | Tool Kit - (Dev.) | 300000 | 75000 |  | 75000 | 225000
I240700 | I240700015 | Cable prepartion Tools - | 900000 |  |  |  | 900000
I240700 | I240700016 | Splice Machine | 4788586.61 | 728825.78 |  | 728825.78 | 4059760.83
I240700 | I240700017 | Cleavers | 1440000 | 212743.15 |  | 212743.15 | 1227256.85
I240700 | I240700018 | VFLs | 480000 | 16120.86 |  | 16120.86 | 463879.14
I240700 | I240700019 | OTDR - For Core / FTTH b | 2425000 | 836000 |  | 836000 | 1589000
I240700 | I240700020 | PON Power Mtr. | 2880000 | 140.17 |  | 140.17 | 2879859.83
I240700 | I240700021 | CATV Transmission Equipmen | 5139495 |  |  |  | 5139495
I240700 | I240700022 | OLT | 2697525 |  |  |  | 2697525
I240700 | I240700023 | PON Cards | 21296250 |  |  |  | 21296250
I240700 | I240700024 | Carry with ladder | 17500000 | 615000 | 15478000 | 16093000 | 1407000
I240700 | I240700025 | Bolan | 7500000 |  | 3899400 | 3899400 | 3600600
I240700 | I240700026 | OLT connectivity SFPs Mult | 32938.2 | 30773.25 |  | 30773.25 | 2164.95
I240700 | I240700027 | Uplink SFPs for POP connec | 98814.6 |  |  |  | 98814.6
I240700 | I240700028 | Switch | 851850 |  |  |  | 851850
I240700 | I240701000 | StormFiber Expansion – Dev | 4920839.77 | 4920839.77 |  | 4920839.77
I240701 | I240701001 | Cabinets & Accessories - | 1593154.89 | 1600801.89 |  | 1600801.89 | 7647.00-
I240701 | I240701002 | Consumable & Accessories | 897591.23 | 405559.91 |  | 405559.91 | 492031.32
I240701 | I240701003 | Cables - (Feeder Access | 6208490.46 | 1909333.56 |  | 1909333.56 | 4299156.9
I240701 | I240701004 | Enclosures - (Feeder Ac | 16072 | 5491.26 |  | 5491.26 | 10580.74
I240701 | I240701005 | Splitters - (Access & Dis | 1590111.85 | 115830.04- |  | 115830.04- | 1705941.89
I240701 | I240701006 | Infrastructure Laying - | 143654.45 |  |  |  | 143654.45
I240701 | I240701007 | PON Cards | 2555550 | 814503.89 |  | 814503.89 | 1741046.11
I240701 | I240701008 | Bolan | 3900000 |  |  |  | 3900000
I240701 | I240701009 | Access Tool Kits | 150000 | 99200 |  | 99200 | 50800
I240701 | I240701010 | PON Meter | 360000 |  |  |  | 360000
I240701 | I240701011 | Clevers | 160000 |  |  |  | 160000
I240701 | I240701012 | Splicing Machine | 800000 |  |  |  | 800000
I240701 | I240701013 | Cable prepration Tools (Ca | 150000 |  |  |  | 150000
I240701 | I240701014 | Dev Tool Kit | 50000 |  |  |  | 50000
I240701 | I240701015 | VFL | 60000 |  |  |  | 60000
I240701 | I240701016 | EDFA | 965430 |  |  |  | 965430
I240701 | I240702000 | StormFiber Expansion – Dev | 37124490.55 | 37124490.53 |  | 37124490.53 | 0.02
I240702 | I240702001 | Cabinets & Accessories - | 28614505.46 | 476292.33 |  | 476292.33 | 28138213.13
I240702 | I240702002 | Consumable & Accessories | 6064600 | 708034.34 |  | 708034.34 | 5356565.66
I240702 | I240702003 | Cables - (Feeder Access | 32211448.1 | 5934485.25 |  | 5934485.25 | 26276962.85
I240702 | I240702004 | Enclosures - (Feeder Ac | 1621585.98 | 121260.72 |  | 121260.72 | 1500325.26
I240702 | I240702005 | Splitters - (Access & Dis | 7850771.94 | 151971.03 |  | 151971.03 | 7698800.91
I240702 | I240702006 | Duct - (HDPE / GI with | 47554277.84 | 2041984.17 |  | 2041984.17 | 45512293.67
I240702 | I240702007 | Handholes - (HH / Chamb | 4792305 | 724950 | 982399 | 1707349 | 3084956
I240702 | I240702008 | Poles | 3360000 |  |  |  | 3360000
I240702 | I240702009 | FDT Foundation | 780000 |  |  |  | 780000
I240702 | I240702010 | Infrastructure Laying - | 32173833.6 | 7515010 | 3274850 | 10789860 | 21383973.6
I240702 | I240702011 | Cable Hauling - (Aerial | 11075544.56 |  | 2282790 | 2282790 | 8792754.56
I240702 | I240702012 | Building Attachments - | 15663516 |  |  |  | 15663516
I240702 | I240702013 | Transportation - (Vehic | 3880000 |  |  |  | 3880000
I240702 | I240702014 | Tool Kit - (Access) | 375000 | 233690 |  | 233690 | 141310
I240702 | I240702015 | Tool Kit - (Dev.) | 150000 |  |  |  | 150000
I240702 | I240702016 | Cable prepartion Tools - | 450000 | 164286.71 |  | 164286.71 | 285713.29
I240702 | I240702017 | Splice Machine | 2400000 | 637069.22 |  | 637069.22 | 1762930.78
I240702 | I240702018 | Cleavers | 400000 | 38000 |  | 38000 | 362000
I240702 | I240702019 | VFLs | 160000 |  |  |  | 160000
I240702 | I240702020 | OTDR - For Core / FTTH b | 1350000 |  |  |  | 1350000
I240702 | I240702021 | PON Power Mtr. | 960000 |  |  |  | 960000
I240702 | I240702022 | CATV Transmission Equipmen | 3024067.5 |  |  |  | 3024067.5
I240702 | I240702023 | PON Cards | 8518500 | 705871.29 |  | 705871.29 | 7812628.71
I240702 | I240702024 | Carry with ladder | 7500000 |  | 6537000 | 6537000 | 963000
I240702 | I240702025 | Bolan | 3900000 |  | 1949700 | 1949700 | 1950300
I240702 | I240703000 | StormFiber Expansion – Dev | 115713566.96 | 115713566.96 |  | 115713566.96
I240703 | I240703001 | Cabinets & Accessories - | 88562225.64 | 5264183.85 |  | 5264183.85 | 83298041.79
I240703 | I240703002 | Consumable & Accessories | 17154771.21 | 4588972.2 |  | 4588972.2 | 12565799.01
I240703 | I240703003 | Cables - (Feeder Access | 102651091.64 | 14983086.97 |  | 14983086.97 | 87668004.67
I240703 | I240703004 | Enclosures - (Feeder Ac | 7445340.67 | 964117.03 |  | 964117.03 | 6481223.64
I240703 | I240703005 | Splitters - (Access & Dis | 24403340.36 | 1460671.9 |  | 1460671.9 | 22942668.46
I240703 | I240703006 | Duct - (HDPE / GI with | 113718233.09 | 1622640.33 |  | 1622640.33 | 112095592.76
I240703 | I240703007 | Handholes - (HH / Chamb | 47802000 |  | 5949500 | 5949500 | 41852500
I240703 | I240703008 | Poles | 480000 |  |  |  | 480000
I240703 | I240703009 | FDT Foundation | 1140000 | 20000 | 90000 | 110000 | 1030000
I240703 | I240703010 | Infrastructure Laying - | 195171841.36 | 79600 | 22262800 | 22342400 | 172829441.36
I240703 | I240703011 | Cable Hauling - (Aerial | 36101113.5 | 448450 |  | 448450 | 35652663.5
I240703 | I240703012 | Building Attachments - | 48795828 | 66640 |  | 66640 | 48729188
I240703 | I240703013 | Transportation - (Vehic | 9350000 | 268500 |  | 268500 | 9081500
I240703 | I240703014 | Tool Kit - (Access) | 900000 | 893610 |  | 893610 | 6390
I240703 | I240703015 | Tool Kit - (Dev.) | 500000 | 50000 |  | 50000 | 450000
I240703 | I240703016 | Cable prepartion Tools - | 1500000 | 106331.14 |  | 106331.14 | 1393668.86
I240703 | I240703017 | Splice Machine | 3996046.22 | 815448.06 |  | 815448.06 | 3180598.16
I240703 | I240703018 | Cleavers | 960000 |  |  |  | 960000
I240703 | I240703019 | VFLs | 440000 |  |  |  | 440000
I240703 | I240703020 | OTDR - For Core / FTTH b | 4175000 | 402000 |  | 402000 | 3773000
I240703 | I240703021 | PON Power Mtr. | 2280000 | 288261.24 |  | 288261.24 | 1991738.76
I240703 | I240703022 | CATV Transmission Equipmen | 8646277.5 | 894755.6 |  | 894755.6 | 7751521.9
I240703 | I240703023 | OLT | 2697525 | 1803964.63 |  | 1803964.63 | 893560.37
I240703 | I240703024 | PON Cards | 17037000 | 17126221.76 |  | 17126221.76 | 89221.76-
I240703 | I240703025 | Switch | 851850 |  |  |  | 851850
I240703 | I240703026 | Carry with ladder | 10000000 | 270000 | 6687000 | 6957000 | 3043000
I240703 | I240703027 | Bolan | 16200000 | 412254.12 | 16206200 | 16618454.12 | 418454.12-
I240703 | I240704000 | StormFiber Expansion – Dev | 57704515.61 | 57704515.63 |  | 57704515.63 | 0.02-
I240704 | I240704001 | Cabinets & Accessories - | 59097303.75 | 1796696.11 |  | 1796696.11 | 57300607.64
I240704 | I240704002 | Consumable & Accessories | 11787481.21 | 2242803.52 |  | 2242803.52 | 9544677.69
I240704 | I240704003 | Cables - (Feeder Access | 86201126.02 | 4742594 |  | 4742594 | 81458532.02
I240704 | I240704004 | Enclosures - (Feeder Ac | 6478111.25 | 508241.97 |  | 508241.97 | 5969869.28
I240704 | I240704005 | Splitters - (Access & Dis | 20780571.03 | 701423.72 |  | 701423.72 | 20079147.31
I240704 | I240704006 | Duct - (HDPE / GI with | 166226840.67 | 6297696.25 |  | 6297696.25 | 159929144.42
I240704 | I240704007 | Handholes - (HH / Chamb | 28118000 | 136000 |  | 136000 | 27982000
I240704 | I240704008 | FDT Foundation | 94881.74 |  | 18000 | 18000 | 76881.74
I240704 | I240704009 | Infrastructure Laying - | 133132883.3 | 5650675 | 3780000 | 9430675 | 123702208.3
I240704 | I240704010 | Cable Hauling - (Aerial | 26568246 | 1778300 | 2221700 | 4000000 | 22568246
I240704 | I240704011 | Building Attachments - | 8620640 |  |  |  | 8620640
I240704 | I240704012 | Transportation - (Vehic | 6400000 | 8000 |  | 8000 | 6392000
I240704 | I240704013 | Tool Kit - (Access) | 1050000 | 1123470 |  | 1123470 | 73470.00-
I240704 | I240704014 | Tool Kit - (Dev.) | 300000 |  |  |  | 300000
I240704 | I240704015 | Cable prepartion Tools - | 750000 | 52792.04 |  | 52792.04 | 697207.96
I240704 | I240704016 | Splice Machine | 4800000 | 1681989.59 |  | 1681989.59 | 3118010.41
I240704 | I240704017 | Cleavers | 1112000 | 57000 |  | 57000 | 1055000
I240704 | I240704018 | VFLs | 380000 |  |  |  | 380000
I240704 | I240704019 | OTDR - For Core / FTTH b | 1750000 | 365000 |  | 365000 | 1385000
I240704 | I240704020 | PON Power Mtr. | 2280000 | 144068.19 |  | 144068.19 | 2135931.81
I240704 | I240704021 | CATV Transmission Equipmen | 4174065 | 894755.6 |  | 894755.6 | 3279309.4
I240704 | I240704022 | OLT | 2697525 | 1803964.62 |  | 1803964.62 | 893560.38
I240704 | I240704023 | PON Cards | 11074050 | 9882198.05 |  | 9882198.05 | 1191851.95
I240704 | I240704024 | Switch | 851850 |  |  |  | 851850
I240704 | I240704025 | Carry with Ladder | 12500000 | 270000 | 11045000 | 11315000 | 1185000
I240704 | I240704026 | Bolan | 5850000 |  | 3899400 | 3899400 | 1950600
I240704 | I240705000 | StormFiber Expansion – Dev | 66153410.9 | 66153410.9 |  | 66153410.9
I240705 | I240705001 | Cabinets & Accessories - | 38859485.6 | 1013063.3 |  | 1013063.3 | 37846422.3
I240705 | I240705002 | Consumable & Accessories | 8845136.33 | 283964.07 |  | 283964.07 | 8561172.26
I240705 | I240705003 | Cables - (Feeder Access | 73877986.36 | 1711894.56 |  | 1711894.56 | 72166091.8
I240705 | I240705004 | Enclosures - (Feeder Ac | 6256625.44 | 180827.17 |  | 180827.17 | 6075798.27
I240705 | I240705005 | Splitters - (Access & Dis | 15774882.52 | 70209.75 |  | 70209.75 | 15704672.77
I240705 | I240705006 | Duct - (HDPE / GI with | 98328198.3 | 882579.09 |  | 882579.09 | 97445619.21
I240705 | I240705007 | Handholes - (HH / Chamb | 25802000 | 8020000 | 1396000 | 9416000 | 16386000
I240705 | I240705008 | Poles | 420000 |  |  |  | 420000
I240705 | I240705009 | FDT Foundation | 675000 | 100000 | 275000 | 375000 | 300000
I240705 | I240705010 | Infrastructure Laying - | 129376466.56 | 5837099 | 4341746 | 10178845 | 119197621.56
I240705 | I240705011 | Cable Hauling - (Aerial | 21106153.43 | 83760 | 1050 | 84810 | 21021343.43
I240705 | I240705012 | Building Attachments - | 32405912 |  |  |  | 32405912
I240705 | I240705013 | Transportation - (Vehic | 8080000 | 71500 |  | 71500 | 8008500
I240705 | I240705014 | Tool Kit - (Access) | 420000 | 322950 |  | 322950 | 97050
I240705 | I240705015 | Tool Kit - (Dev.) | 250000 |  |  |  | 250000
I240705 | I240705016 | Cable prepartion Tools - | 600000 |  |  |  | 600000
I240705 | I240705017 | Splice Machine | 2800000 | 481917.17 |  | 481917.17 | 2318082.83
I240705 | I240705018 | Cleavers | 560000 | 38000 |  | 38000 | 522000
I240705 | I240705019 | VFLs | 300000 |  |  |  | 300000
I240705 | I240705020 | OTDR - For Core / FTTH b | 2325000 |  |  |  | 2325000
I240705 | I240705021 | PON Power Mtr. | 1280000 |  |  |  | 1280000
I240705 | I240705022 | CATV Transmission Equipmen | 5139495 | 2684266.81 |  | 2684266.81 | 2455228.19
I240705 | I240705023 | OLT | 2697525 | 1803964.62 |  | 1803964.62 | 893560.38
I240705 | I240705024 | PON Cards | 11925900 | 8512941.77 |  | 8512941.77 | 3412958.23
I240705 | I240705025 | OLT connectivity SFPs Mult | 32938.2 | 30773.26 |  | 30773.26 | 2164.94
I240705 | I240705026 | Uplink SFPs for POP connec | 98814.6 |  |  |  | 98814.6
I240705 | I240705027 | Carry with lader | 12500000 |  | 10895000 | 10895000 | 1605000
I240705 | I240705028 | Bolan | 5400000 |  |  |  | 5400000
I240705 | I240782000 | LH Infrastructure developm | 67399054.37 | 67399054.37 |  | 67399054.37
I240782 | I240782001 | Cabinets & Accessories - | 795954.5 | 70215.49 |  | 70215.49 | 725739.01
I240782 | I240782002 | Cables - (Feeder Access | 10628985.93 | 114746.3 |  | 114746.3 | 10514239.63
I240782 | I240782003 | Enclosures - (Feeder Ac | 229144.67 | 10363.28 |  | 10363.28 | 218781.39
I240782 | I240782004 | Duct - (HDPE / GI with | 16733918.58 | 25342.23 |  | 25342.23 | 16708576.35
I240782 | I240782005 | Infrastructure Laying - | 4497110 | 110000 |  | 110000 | 4387110
I240782 | I240782006 | Admin / Supervision Charge | 2925183.22 | 535974 |  | 535974 | 2389209.22
I240782 | I240782007 | Transportation - (Vehic | 1600000 | 378000 |  | 378000 | 1222000
I240782 | I240782008 | Tool Kit - (Dev.) | 160000 | 25000 |  | 25000 | 135000
I240782 | I240782009 | Cable prepartion Tools - | 300000 |  |  |  | 300000
I240782 | I240782010 | Splice Machine | 1600000 | 721876.21 |  | 721876.21 | 878123.79
I240782 | I240782011 | Cleavers | 160000 |  |  |  | 160000
I240782 | I240782012 | VFLs | 40000 |  |  |  | 40000
I240782 | I240782013 | OTDR - For Core / FTTH b | 3000000 |  |  |  | 3000000
I240782 | I240782014 | Optical Power Mtr & Source | 510000 |  |  |  | 510000
I240782 | I240782015 | Fiber Identifier | 320000 |  |  |  | 320000
I240782 | I240782016 | Others (Blades for Tools) | 40000 |  |  |  | 40000
I240782 | I240782017 | Hilux / Double Cabin | 14000000 | 198 |  | 198 | 13999802
I240782 | I250114000 | StormFiber Expansion – Jin | 4407341.61 | 4407341.61 |  | 4407341.61
I250114 | I250114001 | Cabinets & Accessories - | 3641000 |  |  |  | 3641000
I250114 | I250114002 | Consumable & Accessories | 816110.5 | 28248.13 |  | 28248.13 | 787862.37
I250114 | I250114003 | Cables - (Feeder Access | 12293354.39 | 286483.65 |  | 286483.65 | 12006870.74
I250114 | I250114004 | Enclosures - (Feeder Ac | 594500.03 |  |  |  | 594500.03
I250114 | I250114005 | Splitters - (Access & Dis | 1408991.76 |  |  |  | 1408991.76
I250114 | I250114006 | Duct - (HDPE / GI with | 5826354.25 | 1272786.28 |  | 1272786.28 | 4553567.97
I250114 | I250114007 | Handholes - (HH / Chamb | 645260 |  |  |  | 645260
I250114 | I250114008 | FDT Foundation | 50000 |  |  |  | 50000
I250114 | I250114009 | Infrastructure Laying - | 3481542.98 | 2274000 |  | 2274000 | 1207542.98
I250114 | I250114010 | Cable Hauling - (Aerial | 1607710.5 |  |  |  | 1607710.5
I250114 | I250114011 | Building Attachments - | 2417000.34 |  |  |  | 2417000.34
I250114 | I250114012 | Existing Aerial Cable Cutt | 300000 |  |  |  | 300000
I250114 | I250114013 | Transportation - (Vehic | 655000 | 6500 |  | 6500 | 648500
I250114 | I250201000 | StormFiber Expansion – Dev | 6043398.79 | 6043398.79 |  | 6043398.79
I250201 | I250201001 | Cabinets & Accessories | 5752200.56 | 10651.77 |  | 10651.77 | 5741548.79
I250201 | I250201002 | Consumable & Accessories | 1266539.85 | 722434.3 |  | 722434.3 | 544105.55
I250201 | I250201003 | Cables - (Feeder Access | 3311062.82 | 957700.85 |  | 957700.85 | 2353361.97
I250201 | I250201004 | Enclosures - (Feeder Ac | 631236.49 | 1777.89 |  | 1777.89 | 629458.6
I250201 | I250201005 | Splitters - (Access & Dis | 2515669.22 | 4788.33 |  | 4788.33 | 2510880.89
I250201 | I250201006 | Duct - (HDPE / GI with | 3274348.49 | 14400 |  | 14400 | 3259948.49
I250201 | I250201007 | Handholes - (HH / Chamb | 144000 |  |  |  | 144000
I250201 | I250201008 | FDT Foundation | 75000 |  | 50000 | 50000 | 25000
I250201 | I250201009 | Infrastructure Laying - | 7418190 |  | 1168400 | 1168400 | 6249790
I250201 | I250201010 | Cable Hauling - (Aeria | 813765 |  | 840780 | 840780 | 27015.00-
I250201 | I250201011 | Building Attachments - ( | 12125000 |  |  |  | 12125000
I250201 | I250201012 | Transportation - (Vehic | 525000 |  |  |  | 525000
I250201 | I250201013 | PON Cards | 1419750 |  |  |  | 1419750
I250201 | I250201014 | Carry with Ladder
I250201 | I250201015 | Tool Kits Access | 150000 |  |  |  | 150000
I250201 | I250201016 | Clevers | 160000 |  |  |  | 160000
I250201 | I250201017 | PON Metres | 360000 |  |  |  | 360000
I250201 | I250201018 | VFL | 60000 |  |  |  | 60000
I250201 | I250201019 | Tool Kit - Dev | 75000 |  |  |  | 75000
I250201 | I250201020 | Splicing Machine | 800000 |  |  |  | 800000
I250201 | I250201021 | Bolan | 1949700 |  | 1949700 | 1949700
I250201 | I250202000 | StormFiber Expansion – Dev | 1202573.79 | 1202573.79 |  | 1202573.79
I250202 | I250202001 | Cabinets & Accessories | 3940084.52 | 29997.96 |  | 29997.96 | 3910086.56
I250202 | I250202002 | Consumable & Accessories | 958100 | 211837.17 |  | 211837.17 | 746262.83
I250202 | I250202003 | Cables - (Feeder Access | 5821006.37 | 1947579.72 |  | 1947579.72 | 3873426.65
I250202 | I250202004 | Enclosures - (Feeder Ac | 487432.47 | 89355.6 |  | 89355.6 | 398076.87
I250202 | I250202005 | Splitters - (Access & Dis | 1282154.12 | 137902.64 |  | 137902.64 | 1144251.48
I250202 | I250202006 | Duct - (HDPE / GI with | 3601748.68 |  |  |  | 3601748.68
I250202 | I250202007 | Handholes - (HH / Chamb | 712000 |  | 17000 | 17000 | 695000
I250202 | I250202008 | Poles | 600000 |  |  |  | 600000
I250202 | I250202009 | FDT Foundation | 76000 |  |  |  | 76000
I250202 | I250202010 | Infrastructure Laying - | 5284890.26 |  |  |  | 5284890.26
I250202 | I250202011 | Cable Hauling - (Aeria | 2291559.38 | 2109540 | 242220 | 2351760 | 60200.62-
I250202 | I250202012 | Transportation - (Vehic | 810000 |  |  |  | 810000
I250202 | I250202013 | Tool Kit - (Access) | 75000 | 59900 |  | 59900 | 15100
I250202 | I250202014 | Tool Kit - (Dev.) | 80000 | 25000 |  | 25000 | 55000
I250202 | I250202015 | Cable prepartion Tools - | 116897.37 | 26134.27 |  | 26134.27 | 90763.1
I250202 | I250202016 | Splice Machine | 800000 | 721876.2 |  | 721876.2 | 78123.8
I250202 | I250202017 | Cleavers | 160000 |  |  |  | 160000
I250202 | I250202018 | VFLs | 40000 | 2687 |  | 2687 | 37313
I250202 | I250202019 | OTDR - For Core / FTTH bo | 950000 |  |  |  | 950000
I250202 | I250202020 | PON Power Mtr. | 240000 | 48022.73 |  | 48022.73 | 191977.27
I250202 | I250202021 | CATV Transmission Equipmen | 3208635 |  |  |  | 3208635
I250202 | I250202022 | PON Cards | 709875 |  |  |  | 709875
I250202 | I250202023 | Carry with Ladder | 2500000 | 205000 | 2254000 | 2459000 | 41000
I250202 | I250202024 | PON Cards | 709875 |  |  |  | 709875
I250202 | I250203000 | StormFiber Expansion – Dev | 450000 | 450000 |  | 450000
I250203 | I250203001 | Cabinets & Accessories | 1695000 |  |  |  | 1695000
I250203 | I250203002 | Consumable & Accessories | 362000 |  |  |  | 362000
I250203 | I250203003 | Cables - (Feeder Access | 2768692.85 |  |  |  | 2768692.85
I250203 | I250203004 | Enclosures - (Feeder Ac | 229500 |  |  |  | 229500
I250203 | I250203005 | Splitters - (Access & Dis | 645237.85 |  |  |  | 645237.85
I250203 | I250203006 | Duct - (HDPE / GI with | 2229390.8 |  |  |  | 2229390.8
I250203 | I250203007 | Handholes - (HH / Chamb | 440000 |  |  |  | 440000
I250203 | I250203008 | Poles | 150000 |  |  |  | 150000
I250203 | I250203009 | FDT Foundation | 30000 |  |  |  | 30000
I250203 | I250203010 | Infrastructure Laying - | 3049500 |  |  |  | 3049500
I250203 | I250203011 | Cable Hauling - (Aeria | 1162992.55 |  |  |  | 1162992.55
I250203 | I250203012 | Transportation - (Vehic | 450000 |  |  |  | 450000
I250203 | I250205000 | StormFiber Expansion – Dev | 10830900 | 10830900 |  | 10830900
I250205 | I250205001 | Cabinets & Accessories | 8529000 |  |  |  | 8529000
I250205 | I250205002 | Consumable & Accessories | 1930050 |  |  |  | 1930050
I250205 | I250205003 | Cables - (Feeder Access | 17276463.74 |  |  |  | 17276463.74
I250205 | I250205004 | Enclosures - (Feeder Ac | 1256400 |  |  |  | 1256400
I250205 | I250205005 | Splitters - (Access & Dis | 3529012.07 |  |  |  | 3529012.07
I250205 | I250205006 | Duct - (HDPE / GI with | 28667662.5 |  |  |  | 28667662.5
I250205 | I250205007 | Handholes - (HH / Chamb | 7182000 | 16500 |  | 16500 | 7165500
I250205 | I250205008 | FDT Foundation | 200000 |  |  |  | 200000
I250205 | I250205009 | Infrastructure Laying - | 26065313.04 |  | 2100000 | 2100000 | 23965313.04
I250205 | I250205010 | Cable Hauling - (Aeria | 4570126.66 |  |  |  | 4570126.66
I250205 | I250205011 | Building Attachments - ( | 304000 |  |  |  | 304000
I250205 | I250205012 | Transportation - (Vehic | 2100000 |  |  |  | 2100000
I250205 | I250205013 | Tool Kit - (Access) | 150000 | 140435 |  | 140435 | 9565
I250205 | I250205014 | Tool Kit - (Dev.) | 72000 |  |  |  | 72000
I250205 | I250205015 | Cable preparation Tools | 150000 |  |  |  | 150000
I250205 | I250205016 | Splice Machine | 800000 |  |  |  | 800000
I250205 | I250205017 | Cleavers | 160000 |  |  |  | 160000
I250205 | I250205018 | VFLs | 60000 |  |  |  | 60000
I250205 | I250205019 | OTDR - For Core / FTTH b | 950000 |  |  |  | 950000
I250205 | I250205020 | PON Power Mtr. | 360000 |  |  |  | 360000
I250205 | I250205021 | CATV Transmission Equipmen | 3208635 |  |  |  | 3208635
I250205 | I250205022 | PON Cards | 1419750 |  |  |  | 1419750
I250205 | I250205023 | Carry with ladder | 2500000 | 205000 | 2254000 | 2459000 | 41000
I250205 | I250205024 | Bolan | 1950000 |  | 1949700 | 1949700 | 300
I250205 | I250206000 | StormFiber Expansion – Dev | 9288952.11 | 9288952.11 |  | 9288952.11
I250206 | I250206001 | Cabinets & Accessories | 43253000 | 655194.81 |  | 655194.81 | 42597805.19
I250206 | I250206002 | Consumable & Accessories | 8706550 | 707135.96 |  | 707135.96 | 7999414.04
I250206 | I250206003 | Cables - (Feeder Access | 66041515.58 | 17108501.53 |  | 17108501.53 | 48933014.05
I250206 | I250206004 | Enclosures - (Feeder Ac | 5425800 | 881225.15 |  | 881225.15 | 4544574.85
I250206 | I250206005 | Splitters - (Access & Dis | 15632654.71 | 384624.05 |  | 384624.05 | 15248030.66
I250206 | I250206006 | Duct - (HDPE / GI with | 74618061.81 | 8363009.05 |  | 8363009.05 | 66255052.76
I250206 | I250206007 | Handholes - (HH / Chamb | 12298000 | 1983000 | 264000 | 2247000 | 10051000
I250206 | I250206008 | Poles | 6600000 |  |  |  | 6600000
I250206 | I250206009 | FDT Foundation | 1100000 | 60000 | 20000 | 80000 | 1020000
I250206 | I250206010 | Infrastructure Laying - | 32107395.79 | 5084131 | 171000 | 5255131 | 26852264.79
I250206 | I250206011 | Cable Hauling - (Aeria | 18557639.63 | 191500 |  | 191500 | 18366139.63
I250206 | I250206012 | Transportation - (Vehic | 7110000 |  |  |  | 7110000
I250206 | I250206013 | Tool Kit - (Access) | 600000 | 261230 |  | 261230 | 338770
I250206 | I250206014 | Tool Kit - (Dev.) | 186666 |  |  |  | 186666
I250206 | I250206015 | Cable preparation Tools | 450000 |  |  |  | 450000
I250206 | I250206016 | Splice Machine | 2400000 | 959501.19 |  | 959501.19 | 1440498.81
I250206 | I250206017 | Cleavers | 640000 |  |  |  | 640000
I250206 | I250206018 | VFLs | 60000 |  |  |  | 60000
I250206 | I250206019 | OTDR - For Core / FTTH b | 1225000 | 365000 |  | 365000 | 860000
I250206 | I250206020 | PON Power Mtr. | 1320000 | 48043.54 |  | 48043.54 | 1271956.46
I250206 | I250206021 | CATV Transmission Equipmen | 6232702.5 |  |  |  | 6232702.5
I250206 | I250206022 | OLT | 1987650 |  |  |  | 1987650
I250206 | I250206023 | PON Cards | 7098750 |  |  |  | 7098750
I250206 | I250206024 | Switch | 851850 |  |  |  | 851850
I250206 | I250206025 | OLT connectivity SFPs Mult | 32938.2 | 30773.25 |  | 30773.25 | 2164.95
I250206 | I250206026 | Uplink SFPs for POP connec | 98814.6 |  |  |  | 98814.6
I250206 | I250206027 | Carry with Ladder | 10000000 | 410000 | 4508000 | 4918000 | 5082000
I250206 | I250206028 | Bolan | 3900000 | 1500 | 1949700 | 1951200 | 1948800
I250206 | I250207001 | Cabinets & Accessories | 4097000 | 160400 |  | 160400 | 3936600
I250207 | I250207002 | Consumable & Accessories | 921200 |  |  |  | 921200
I250207 | I250207003 | Cables - (Feeder Access | 6706225.22 |  |  |  | 6706225.22
I250207 | I250207004 | Enclosures - (Feeder Ac | 574500.62 |  |  |  | 574500.62
I250207 | I250207005 | Splitters - (Access & Dis | 1532826.72 |  |  |  | 1532826.72
I250207 | I250207006 | Duct - (HDPE / GI with | 5064560.56 |  |  |  | 5064560.56
I250207 | I250207007 | Handholes - (HH / Chamb | 792000 | 117500 |  | 117500 | 674500
I250207 | I250207008 | Poles | 600000 |  |  |  | 600000
I250207 | I250207009 | FDT Foundation | 90000 |  |  |  | 90000
I250207 | I250207010 | Infrastructure Laying - | 7778175 | 5857280 |  | 5857280 | 1920895
I250207 | I250207011 | Cable Hauling - (Aeria | 2810656 | 87000 | 1313000 | 1400000 | 1410656
I250207 | I250207012 | Transportation - (Vehic | 990000 |  |  |  | 990000
I250207 | I250207013 | Tool Kit - (Access) | 75000 | 74710 |  | 74710 | 290
I250207 | I250207014 | Tool Kit - (Dev.) | 80000 |  |  |  | 80000
I250207 | I250207015 | Cable preparation Tools | 150000 |  |  |  | 150000
I250207 | I250207016 | Splice Machine | 1600000 |  |  |  | 1600000
I250207 | I250207017 | Cleavers | 160000 |  |  |  | 160000
I250207 | I250207018 | VFLs | 20000 |  |  |  | 20000
I250207 | I250207019 | OTDR - For Core / FTTH b | 950000 |  |  |  | 950000
I250207 | I250207020 | PON Power Mtr. | 240000 |  |  |  | 240000
I250207 | I250207021 | CATV Transmission Equipmen | 3208635 |  |  |  | 3208635
I250207 | I250207022 | PON Cards | 709875 |  |  |  | 709875
I250207 | I250207023 | Carry with Ladder | 2500000 | 274000 | 2254000 | 2528000 | 28000.00-
I250207 | I250208000 | StormFiber Expansion – Dev | 2465971.53 | 2465971.53 |  | 2465971.53
I250208 | I250208001 | Cabinets & Accessories | 3365028.47 | 84490.02 |  | 84490.02 | 3280538.45
I250208 | I250208002 | Consumable & Accessories | 1186100 | 11730.31 |  | 11730.31 | 1174369.69
I250208 | I250208003 | Cables - (Feeder Access | 7108035.17 | 302841.58 |  | 302841.58 | 6805193.59
I250208 | I250208004 | Enclosures - (Feeder Ac | 679800 | 49203.66 |  | 49203.66 | 630596.34
I250208 | I250208005 | Splitters - (Access & Dis | 2227497.85 | 46072.03 |  | 46072.03 | 2181425.82
I250208 | I250208006 | Duct - (HDPE / GI with | 9609646.27 | 3156968.31 |  | 3156968.31 | 6452677.96
I250208 | I250208007 | Handholes - (HH / Chamb | 2750000 |  |  |  | 2750000
I250208 | I250208008 | Poles | 600000 |  |  |  | 600000
I250208 | I250208009 | FDT Foundation | 120000 |  |  |  | 120000
I250208 | I250208010 | Infrastructure Laying - | 14828375.39 | 7876879 | 618000 | 8494879 | 6333496.39
I250208 | I250208011 | Cable Hauling - (Aeria | 2214755.43 |  |  |  | 2214755.43
I250208 | I250208012 | Building Attachments - ( | 1830000 |  |  |  | 1830000
I250208 | I250208013 | Transportation - (Vehic | 1080000 |  |  |  | 1080000
I250208 | I250208014 | Tool Kit - (Access) | 150000 |  |  |  | 150000
I250208 | I250208015 | Tool Kit - (Dev.) | 75000 |  |  |  | 75000
I250208 | I250208016 | Cable prepartion Tools - | 150000 |  |  |  | 150000
I250208 | I250208017 | Splice Machine | 800000 |  |  |  | 800000
I250208 | I250208018 | Cleavers | 160000 |  |  |  | 160000
I250208 | I250208019 | VFLs | 60000 |  |  |  | 60000
I250208 | I250208020 | OTDR - For Core / FTTH bo | 950000 |  |  |  | 950000
I250208 | I250208021 | PON Power Mtr. | 600000 |  |  |  | 600000
I250208 | I250208022 | CATV Transmission Equipmen | 4301842.5 |  |  |  | 4301842.5
I250208 | I250208023 | PON Cards | 1419750 |  |  |  | 1419750
I250208 | I250208024 | Carry with ladder | 5000000 | 205000 | 2254000 | 2459000 | 2541000
I250208 | I250209001 | Cabinets & Accessories | 15970000 | 643055.42 |  | 643055.42 | 15326944.58
I250209 | I250209002 | Consumable & Accessories | 3267750 |  |  |  | 3267750
I250209 | I250209003 | Cables - (Feeder Access | 24601656.08 | 9574770.31 |  | 9574770.31 | 15026885.77
I250209 | I250209004 | Enclosures - (Feeder Ac | 1949400 |  |  |  | 1949400
I250209 | I250209005 | Splitters - (Access & Dis | 6156930.17 |  |  |  | 6156930.17
I250209 | I250209006 | Duct - (HDPE / GI with | 23285017 | 11184083.07 |  | 11184083.07 | 12100933.93
I250209 | I250209007 | Handholes - (HH / Chamb | 4774000 | 132000 | 92500 | 224500 | 4549500
I250209 | I250209008 | Poles | 1800000 |  |  |  | 1800000
I250209 | I250209009 | FDT Foundation | 330000 |  | 125000 | 125000 | 205000
I250209 | I250209010 | Infrastructure Laying - | 38858250 | 12022300 | 7362000 | 19384300 | 19473950
I250209 | I250209011 | Cable Hauling - (Aeria | 6135947.46 | 5100 | 409770 | 414870 | 5721077.46
I250209 | I250209012 | Building Attachments - ( | 943000 |  |  |  | 943000
I250209 | I250209013 | Transportation - (Vehic | 2610000 |  |  |  | 2610000
I250209 | I250209014 | Tool Kit - (Access) | 450000 |  |  |  | 450000
I250209 | I250209015 | Tool Kit - (Dev.) | 320000 |  |  |  | 320000
I250209 | I250209016 | Cable prepartion Tools - | 450000 |  |  |  | 450000
I250209 | I250209017 | Splice Machine | 2400000 |  |  |  | 2400000
I250209 | I250209018 | Cleavers | 720000 |  |  |  | 720000
I250209 | I250209019 | VFLs | 180000 |  |  |  | 180000
I250209 | I250209020 | OTDR - For Core / FTTH bo | 1900000 |  |  |  | 1900000
I250209 | I250209021 | PON Power Mtr. | 1080000 |  |  |  | 1080000
I250209 | I250209022 | CATV Transmission Equipmen | 5267272.5 |  |  |  | 5267272.5
I250209 | I250209023 | PON Cards | 4259250 |  |  |  | 4259250
I250209 | I250209024 | Carry with ladder | 7500000 | 2441022 | 4558000 | 6999022 | 500978
I250209 | I250209025 | Bolan | 11700000 |  | 1949700 | 1949700 | 9750300
I250209 | I250209026 | OLT | 1987650 |  |  |  | 1987650
I250209 | I250209027 | Switch | 851850 |  |  |  | 851850
I250209 | I250209028 | OLT connectivity SFPs Mult | 32938.2 |  |  |  | 32938.2
I250209 | I250209029 | Uplink SFPs for POP connec | 98814.6 |  |  |  | 98814.6
I250209 | I250210000 | StormFiber Expansion – Dev | 19275228.09 | 19275228.09 |  | 19275228.09
I250210 | I250210001 | Cabinets & Accessories | 20546212.72 | 1144655.53 |  | 1144655.53 | 19401557.19
I250210 | I250210002 | Consumable & Accessories | 4629078.18 | 1211456.39 |  | 1211456.39 | 3417621.79
I250210 | I250210003 | Cables - (Feeder Access | 37622625.5 | 8266509.66 |  | 8266509.66 | 29356115.84
I250210 | I250210004 | Enclosures - (Feeder Ac | 2741064.91 | 195871.06 |  | 195871.06 | 2545193.85
I250210 | I250210005 | Splitters - (Access & Dis | 8648521.66 | 246958.5 |  | 246958.5 | 8401563.16
I250210 | I250210006 | Duct - (HDPE / GI with | 29887327.68 | 4338057.48 |  | 4338057.48 | 25549270.2
I250210 | I250210007 | Handholes - (HH / Chamb | 7326000 |  | 105000 | 105000 | 7221000
I250210 | I250210008 | Poles | 780000 |  |  |  | 780000
I250210 | I250210009 | FDT Foundation | 425000 |  |  |  | 425000
I250210 | I250210010 | Infrastructure Laying - | 31159920.45 | 750000 | 1826200 | 2576200 | 28583720.45
I250210 | I250210011 | Cable Hauling - (Aeria | 9878373.86 |  |  |  | 9878373.86
I250210 | I250210012 | Building Attachments - ( | 830000 |  |  |  | 830000
I250210 | I250210013 | Transportation - (Vehic | 3980000 |  |  |  | 3980000
I250210 | I250210014 | Tool Kit - (Access) | 300000 | 253650 | 34400 | 288050 | 11950
I250210 | I250210015 | Tool Kit - (Dev.) | 300000 |  |  |  | 300000
I250210 | I250210016 | Cable prepartion Tools - | 600000 |  |  |  | 600000
I250210 | I250210017 | Splice Machine | 3200000 | 3585.06 |  | 3585.06 | 3196414.94
I250210 | I250210018 | Cleavers | 320000 | 38000 |  | 38000 | 282000
I250210 | I250210019 | VFLs | 160000 |  |  |  | 160000
I250210 | I250210020 | OTDR - For Core / FTTH b | 950000 |  |  |  | 950000
I250210 | I250210021 | PON Power Mtr. | 1440000 |  |  |  | 1440000
I250210 | I250210022 | CATV Transmission Equipmen | 5267272.5 |  |  |  | 5267272.5
I250210 | I250210023 | OLT | 1987650 |  |  |  | 1987650
I250210 | I250210024 | PON Cards | 4259250 |  |  |  | 4259250
I250210 | I250210025 | Switch | 851850 |  |  |  | 851850
I250210 | I250210026 | OLT connectivity SFPs Mult | 32938.2 |  |  |  | 32938.2
I250210 | I250210027 | Uplink SFPs for POP connec | 98814.6 |  |  |  | 98814.6
I250210 | I250210028 | Carry with Ladder | 4731635.93 | 410000 | 4508000 | 4918000 | 186364.07-
I250210 | I250210029 | Bolan | 3900000 |  | 1949700 | 1949700 | 1950300
I250210 | I250211001 | Cabinets & Accessories | 8931000 | 1698413.39 |  | 1698413.39 | 7232586.61
I250211 | I250211002 | Consumable & Accessories | 1960600 | 682837.88 |  | 682837.88 | 1277762.12
I250211 | I250211003 | Cables - (Feeder Access | 8611849.5 | 2668132.3 |  | 2668132.3 | 5943717.2
I250211 | I250211004 | Enclosures - (Feeder Ac | 1139100 | 189766.89 |  | 189766.89 | 949333.11
I250211 | I250211005 | Splitters - (Access & Dis | 3579600 | 1024520.66 |  | 1024520.66 | 2555079.34
I250211 | I250211006 | Duct - (HDPE / GI with | 7757104.4 | 2162686.29 |  | 2162686.29 | 5594418.11
I250211 | I250211007 | Handholes - (HH / Chamb | 1628000 |  |  |  | 1628000
I250211 | I250211008 | Poles | 450000 |  |  |  | 450000
I250211 | I250211009 | FDT Foundation | 150000 |  |  |  | 150000
I250211 | I250211010 | Infrastructure Laying - | 5742250 | 2262000 | 3450000 | 5712000 | 30250
I250211 | I250211011 | Cable Hauling - (Aeria | 3181215 | 459900 | 1540100 | 2000000 | 1181215
I250211 | I250211012 | Transportation - (Vehic | 1170000 |  |  |  | 1170000
I250211 | I250211013 | Tool Kit - (Access) | 150000 | 149740 |  | 149740 | 260
I250211 | I250211014 | Tool Kit - (Dev.) | 75000 |  |  |  | 75000
I250211 | I250211015 | Cable prepartion Tools - | 150000 |  |  |  | 150000
I250211 | I250211016 | Splice Machine | 800000 |  |  |  | 800000
I250211 | I250211017 | Cleavers | 160000 | 19000 |  | 19000 | 141000
I250211 | I250211018 | VFLs | 60000 |  |  |  | 60000
I250211 | I250211019 | PON Power Mtr. | 360000 |  |  |  | 360000
I250211 | I250211020 | CATV Transmission Equipmen | 3208635 |  |  |  | 3208635
I250211 | I250211021 | PON Cards | 2129625 |  |  |  | 2129625
I250211 | I250211022 | Carry with Ladder | 5000000 | 205000 | 2254000 | 2459000 | 2541000
I250211 | I250212000 | StormFiber Expansion – Dev | 27505715.19 | 27505715.19 |  | 27505715.19
I250212 | I250212001 | Cabinets & Accessories | 34555196.47 | 941180.2 |  | 941180.2 | 33614016.27
I250212 | I250212002 | Consumable & Accessories | 7810450 | 1663404.32 |  | 1663404.32 | 6147045.68
I250212 | I250212003 | Cables - (Feeder Access | 48236629.33 | 5843760.82 |  | 5843760.82 | 42392868.51
I250212 | I250212004 | Enclosures - (Feeder Ac | 5448457.69 | 364394.32 |  | 364394.32 | 5084063.37
I250212 | I250212005 | Splitters - (Access & Dis | 11563085.75 | 295572.4 |  | 295572.4 | 11267513.35
I250212 | I250212006 | Duct - (HDPE / GI with | 40537242.42 | 8415162.19 |  | 8415162.19 | 32122080.23
I250212 | I250212007 | Handholes - (HH / Chamb | 10384000 |  |  |  | 10384000
I250212 | I250212008 | Poles | 7500000 |  |  |  | 7500000
I250212 | I250212009 | FDT Foundation | 810000 | 80000 |  | 80000 | 730000
I250212 | I250212010 | Infrastructure Laying - | 62850175 | 2174500 | 6772500 | 8947000 | 53903175
I250212 | I250212011 | Cable Hauling - (Aeria | 19938867.85 |  | 271344 | 271344 | 19667523.85
I250212 | I250212012 | Transportation - (Vehic | 6120000 | 143200 |  | 143200 | 5976800
I250212 | I250212013 | Tool Kit - (Access) | 300000 |  |  |  | 300000
I250212 | I250212014 | Tool Kit - (Dev.) | 225000 |  |  |  | 225000
I250212 | I250212015 | Cable prepartion Tools - | 450000 |  |  |  | 450000
I250212 | I250212016 | Splice Machine | 2384665.37 | 769746.94 |  | 769746.94 | 1614918.43
I250212 | I250212017 | Cleavers | 320000 |  |  |  | 320000
I250212 | I250212018 | VFLs | 140000 |  |  |  | 140000
I250212 | I250212019 | OTDR - For Core / FTTH b | 975000 |  |  |  | 975000
I250212 | I250212020 | PON Power Mtr. | 840000 |  |  |  | 840000
I250212 | I250212021 | CATV Transmission Equipmen | 4174065 |  |  |  | 4174065
I250212 | I250212022 | PON Cards | 4969125 |  |  |  | 4969125
I250212 | I250212023 | carry with ladder | 5000000 | 205000 | 2254000 | 2459000 | 2541000
I250212 | I250212024 | Bolan | 3900000 |  | 1949700 | 1949700 | 1950300
I250212 | I250213000 | StormFiber Expansion – Dev | 728861.3 | 728861.3 |  | 728861.3
I250213 | I250213001 | Cabinets & Accessories - | 5055036.58 | 625323.62 |  | 625323.62 | 4429712.96
I250213 | I250213002 | Consumable & Accessories | 1094730.85 | 238791.12 |  | 238791.12 | 855939.73
I250213 | I250213003 | Cables - (Feeder Access | 7144328.21 | 1484713.16 |  | 1484713.16 | 5659615.05
I250213 | I250213004 | Enclosures - (Feeder Ac | 617403.19 | 89501.36 |  | 89501.36 | 527901.83
I250213 | I250213005 | Splitters - (Access & Dis | 1709959.95 | 175183.77 |  | 175183.77 | 1534776.18
I250213 | I250213006 | Duct - (HDPE / GI with | 11399813.48 | 15413.11 |  | 15413.11 | 11384400.37
I250213 | I250213007 | Handholes - (HH / Chamb | 1892000 |  |  |  | 1892000
I250213 | I250213008 | Poles | 540000 |  |  |  | 540000
I250213 | I250213009 | FDT Foundation | 150000 |  |  |  | 150000
I250213 | I250213010 | Infrastructure Laying - | 14821023.99 | 20000 |  | 20000 | 14801023.99
I250213 | I250213011 | Cable Hauling - (Aerial | 2671082 |  |  |  | 2671082
I250213 | I250213012 | Building Attachments - | 30000 |  |  |  | 30000
I250213 | I250213013 | Transportation - (Vehic | 1500000 |  |  |  | 1500000
I250213 | I250213014 | Tool Kit - (Access) | 150000 | 46470 |  | 46470 | 103530
I250213 | I250213015 | Tool Kit - (Dev.) | 133333.34 |  |  |  | 133333.34
I250213 | I250213016 | Cable prepartion Tools - | 300000 |  |  |  | 300000
I250213 | I250213017 | Splice Machine | 1600000 |  |  |  | 1600000
I250213 | I250213018 | Cleavers | 160000 |  |  |  | 160000
I250213 | I250213019 | VFLs | 80000 |  |  |  | 80000
I250213 | I250213020 | OTDR - For Core / FTTH b | 950000 |  |  |  | 950000
I250213 | I250213021 | PON Power Mtr. | 480000 |  |  |  | 480000
I250213 | I250213022 | CATV Transmission Equipmen | 3208635 |  |  |  | 3208635
I250213 | I250213023 | PON Card | 709875 |  |  |  | 709875
I250213 | I250213024 | Carry with Ladder | 2500000 | 274000 | 2254000 | 2528000 | 28000.00-
I250213 | I250298000 | StormFiber Expansion – Dev | 12515292.49 | 12515292.49 |  | 12515292.49
I250298 | I250298001 | Cabinets & Accessories - | 10712833.2 | 214336.58 |  | 214336.58 | 10498496.62
I250298 | I250298002 | Consumable & Accessories | 1658850 | 1408196.09 |  | 1408196.09 | 250653.91
I250298 | I250298003 | Cables - (Feeder Access | 17353741.92 | 3689615.09 |  | 3689615.09 | 13664126.83
I250298 | I250298004 | Enclosures - (Feeder Ac | 1237933.36 | 33775.12 |  | 33775.12 | 1204158.24
I250298 | I250298005 | Splitters - (Access & Dis | 3383603.4 | 23998.36 |  | 23998.36 | 3359605.04
I250298 | I250298006 | Duct - (HDPE / GI with | 6093027.3 | 36403.64 |  | 36403.64 | 6056623.66
I250298 | I250298007 | Handholes - (HH / Chamb | 1496000 |  |  |  | 1496000
I250298 | I250298008 | FDT Foundation | 63853.57 | 40000 |  | 40000 | 23853.57
I250298 | I250298009 | Infrastructure Laying - | 16450000 |  | 16450000 | 16450000
I250298 | I250298010 | Cable Hauling - (Aerial | 5498043 |  | 1800000 | 1800000 | 3698043
I250298 | I250298011 | Building Attachments - | 5605999.76 |  |  |  | 5605999.76
I250298 | I250298012 | Transportation - (Vehic | 1125000 |  |  |  | 1125000
I250298 | I250307000 | StormFiber Expansion-DKTCC | 75387481.45 | 75387481.45 |  | 75387481.45
I250307 | I250307001 | Cabinets & Accessories - | 78629750 |  |  |  | 78629750
I250307 | I250307002 | Consumable & Accessories | 18531525 |  |  |  | 18531525
I250307 | I250307003 | Cables - (Feeder Access | 62868432.88 |  |  |  | 62868432.88
I250307 | I250307004 | Enclosures - (Feeder Ac | 15541942.2 |  |  |  | 15541942.2
I250307 | I250307005 | Splitters - (Access & Dis | 16866196 |  |  |  | 16866196
I250307 | I250307006 | Duct - (HDPE / GI with | 108775007.54 | 11913725.39 | 68977.48 | 11982702.87 | 96792304.67
I250307 | I250307007 | Handholes - (HH / Chamb | 3210999.21 |  | 82333.16 | 82333.16 | 3128666.05
I250307 | I250307008 | FDT Foundation | 225000 |  |  |  | 225000
I250307 | I250307009 | Infrastructure Laying - | 42874175.36 | 23306777.62 | 4037466.86 | 27344244.48 | 15529930.88
I250307 | I250307010 | Cable Hauling - (Aerial | 23740711.08 | 1773480 |  | 1773480 | 21967231.08
I250307 | I250307011 | Building Attachments - | 71344696.8 | 311642 |  | 311642 | 71033054.8
I250307 | I250307012 | Tool Kit - (Access) | 375000 | 254080 |  | 254080 | 120920
I250307 | I250307013 | Tool Kit - (Dev.) | 240000 |  |  |  | 240000
I250307 | I250307014 | Cable prepartion Tools - | 450000 |  |  |  | 450000
I250307 | I250307015 | Splice Machine | 2400000 |  |  |  | 2400000
I250307 | I250307016 | Cleavers | 640000 |  |  |  | 640000
I250307 | I250307017 | VFLs | 160000 |  |  |  | 160000
I250307 | I250307018 | OTDR - For Core / FTTH b | 5524999.97 |  |  |  | 5524999.97
I250307 | I250307019 | PON Power Mtr. | 960000 |  |  |  | 960000
I250307 | I250307020 | CATV Transmission Equipmen | 2885000 |  |  |  | 2885000
I250307 | I250326000 | StormFiber Expansion – Ask | 12898820.18 | 12944820.18 |  | 12944820.18 | 46000.00-
I250326 | I250326001 | Cabinets & Accessories - | 2162444.23 | 40763.5 |  | 40763.5 | 2121680.73
I250326 | I250326002 | Consumable & Accessories | 402150 | 123906.62 |  | 123906.62 | 278243.38
I250326 | I250326003 | Cables - (Feeder Access | 2312990.01 | 363906.79 |  | 363906.79 | 1949083.22
I250326 | I250326004 | Enclosures - (Feeder Acc | 78263.38 | 19832.1 |  | 19832.1 | 58431.28
I250326 | I250326005 | Splitters - (Access & Dist | 557576.4 | 10090.97 |  | 10090.97 | 547485.43
I250326 | I250326006 | Duct - (HDPE / GI with C | 3823847.48 | 4549.26 |  | 4549.26 | 3819298.22
I250326 | I250326007 | Handholes - (HH / Chambe | 1672000 |  |  |  | 1672000
I250326 | I250326008 | FDT Foundation | 75000 |  |  |  | 75000
I250326 | I250326009 | Infrastructure Laying - | 440444.78 |  |  |  | 440444.78
I250326 | I250326010 | Cable Hauling - (Aerial | 971933.85 |  |  |  | 971933.85
I250326 | I250326011 | Building Attachments - ( | 523000 |  |  |  | 523000
I250326 | I250326012 | Transportation - (Vehicl | 540000 |  |  |  | 540000
I250326 | I250326013 | Tool Kit - (Access) | 75000 |  |  |  | 75000
I250326 | I250326014 | Cleavers | 80000 |  |  |  | 80000
I250326 | I250326015 | VFLs | 20000 |  |  |  | 20000
I250326 | I250326016 | PON Power Mtr. | 120000 |  |  |  | 120000
I250326 | I250326017 | PON Card | 695375 |  |  |  | 695375
I250326 | I250326018 | Carry | 2500000 |  |  |  | 2500000
I250326 | I250327000 | StormFiber Expansion – Dev | 29427064.36 | 29427064.36 |  | 29427064.36
I250327 | I250327001 | Cabinets & Accessories - | 39408342.71 | 1149530.83 |  | 1149530.83 | 38258811.88
I250327 | I250327002 | Consumable & Accessories | 7294700 | 21300.92 |  | 21300.92 | 7273399.08
I250327 | I250327003 | Cables - (Feeder Access | 33848033.66 | 2951833.32 |  | 2951833.32 | 30896200.34
I250327 | I250327004 | Enclosures - (Feeder Acc | 4960090.44 | 16277.45 |  | 16277.45 | 4943812.99
I250327 | I250327005 | Splitters - (Access & Dist | 14135870.99 | 156461.71 |  | 156461.71 | 13979409.28
I250327 | I250327006 | Duct - (HDPE / GI with C | 123429636.41 | 2873524.88 |  | 2873524.88 | 120556111.53
I250327 | I250327007 | Handholes - (HH / Chambe | 45228000 | 55500 |  | 55500 | 45172500
I250327 | I250327008 | FDT Foundation | 265275.81 |  |  |  | 265275.81
I250327 | I250327009 | Infrastructure Laying - | 174983237 | 9113250.48 | 40263277.83 | 49376528.31 | 125606708.69
I250327 | I250327010 | Cable Hauling - (Aerial | 8552208.87 | 590000 |  | 590000 | 7962208.87
I250327 | I250327011 | Building Attachments - ( | 40862250 | 1058280 |  | 1058280 | 39803970
I250327 | I250327012 | Transportation - (Vehicl | 8075000 |  |  |  | 8075000
I250327 | I250327013 | Tool Kit - (Access) | 450000 |  |  |  | 450000
I250327 | I250327014 | Tool Kit - (Dev.) | 480000 |  |  |  | 480000
I250327 | I250327015 | Cable prepartion Tools - | 900000 |  |  |  | 900000
I250327 | I250327016 | Splice Machine | 3200000 | 751924.86 |  | 751924.86 | 2448075.14
I250327 | I250327017 | Cleavers | 480000 |  |  |  | 480000
I250327 | I250327018 | VFLs | 240000 |  |  |  | 240000
I250327 | I250327019 | PON Power Mtr. | 1440000 |  |  |  | 1440000
I250327 | I250327020 | CATV Transmission Equipmen | 3908007.5 |  |  |  | 3908007.5
I250327 | I250327021 | OLT | 1947050 |  |  |  | 1947050
I250327 | I250327022 | PON Cards | 9735250 |  |  |  | 9735250
I250327 | I250327023 | Switch | 834450 |  |  |  | 834450
I250327 | I250327024 | Uplink SFPs for POP connec | 72597.15 |  |  |  | 72597.15
I250327 | I250327025 | OLT connectivity SFPs Mult | 24199.05 | 16081.75 |  | 16081.75 | 8117.3
I250327 | I250327026 | Carry | 10000000 |  |  |  | 10000000
I250327 | I250327027 | Bolan | 3600000 |  |  |  | 3600000
I250327 | I250374001 | Cabinets & Accessories - | 243000 |  |  |  | 243000
I250374 | I250374002 | Consumable & Accessories | 20430 |  |  |  | 20430
I250374 | I250374003 | Cables - (Feeder Access | 614999.7 |  |  |  | 614999.7
I250374 | I250374004 | Enclosures - (Feeder Ac | 17500 |  |  |  | 17500
I250374 | I250374005 | Splitters - (Access & Dis | 135000 |  |  |  | 135000
I250374 | I250374006 | Cable Hauling - (Aeria | 434000 |  |  |  | 434000
I250374 | I250375001 | Cabinets & Accessories - | 6827000 |  |  |  | 6827000
I250375 | I250375002 | Consumable & Accessories | 1344100 |  |  |  | 1344100
I250375 | I250375003 | Cables - (Feeder Access | 8369153.6 |  |  |  | 8369153.6
I250375 | I250375004 | Enclosures - (Feeder Ac | 805800 |  |  |  | 805800
I250375 | I250375005 | Splitters - (Access & Dis | 2413432.73 |  |  |  | 2413432.73
I250375 | I250375006 | Duct - (HDPE / GI with | 12879222.65 |  |  |  | 12879222.65
I250375 | I250375007 | Handholes - (HH / Chamb | 2214000 |  |  |  | 2214000
I250375 | I250375008 | FDT Foundation | 125000 |  |  |  | 125000
I250375 | I250375009 | Infrastructure Laying - | 16493059.73 | 11893750 | 640000 | 12533750 | 3959309.73
I250375 | I250375010 | Cable Hauling - (Aerial | 2698989.71 |  |  |  | 2698989.71
I250375 | I250375011 | Building Attachments - | 2618000 |  |  |  | 2618000
I250375 | I250375012 | Transportation - (Vehic | 750000 |  |  |  | 750000
I250375 | I250375013 | Tool Kit - (Access) | 225000 |  |  |  | 225000
I250375 | I250375014 | Tool Kit - (Dev.) | 50000 |  |  |  | 50000
I250375 | I250375015 | Cable preparation Tools | 150000 |  |  |  | 150000
I250375 | I250375016 | Splice Machine | 800000 |  |  |  | 800000
I250375 | I250375017 | Cleavers | 160000 |  |  |  | 160000
I250375 | I250375018 | VFLs | 60000 |  |  |  | 60000
I250375 | I250375019 | PON Power Mtr. | 360000 |  |  |  | 360000
I250375 | I250375020 | EDFA | 945200 | 894755.6 |  | 894755.6 | 50444.4
I250375 | I250375021 | PON Cards | 2502000 |  |  |  | 2502000
I250375 | I250375022 | Bolan | 5000000 |  |  |  | 5000000
I250375 | I250376001 | Cabinets & Accessories - | 35065000 | 1074919.55 |  | 1074919.55 | 33990080.45
I250376 | I250376002 | Consumable & Accessories | 6908300 | 74032.38 |  | 74032.38 | 6834267.62
I250376 | I250376003 | Cables - (Feeder Access | 68660060.35 | 870328.95 |  | 870328.95 | 67789731.4
I250376 | I250376004 | Enclosures - (Feeder Ac | 6240400 | 304636.82 |  | 304636.82 | 5935763.18
I250376 | I250376005 | Splitters - (Access & Dis | 15112710 | 648487.39 |  | 648487.39 | 14464222.61
I250376 | I250376006 | Duct - (HDPE / GI with | 140414796.34 | 53092.08 |  | 53092.08 | 140361704.26
I250376 | I250376007 | Handholes - (HH / Chamb | 31272000 | 374500 | 462500 | 837000 | 30435000
I250376 | I250376008 | FDT Foundation | 450000 |  |  |  | 450000
I250376 | I250376009 | Infrastructure Laying - | 200056203.18 | 28087535 | 1660540 | 29748075 | 170308128.18
I250376 | I250376010 | Cable Hauling - (Aerial | 19360681.06 | 26160 | 9000 | 35160 | 19325521.06
I250376 | I250376011 | Building Attachments - | 17159000 | 44000 | 4200 | 48200 | 17110800
I250376 | I250376012 | Transportation - (Vehic | 2712500 |  |  |  | 2712500
I250376 | I250376013 | Tool Kit - (Access) | 1125000 | 328780 |  | 328780 | 796220
I250376 | I250376014 | Tool Kit - (Dev.) | 300000 |  |  |  | 300000
I250376 | I250376015 | Cable preparation Tools | 900000 |  |  |  | 900000
I250376 | I250376016 | Splice Machine | 4800000 | 737898 |  | 737898 | 4062102
I250376 | I250376017 | Cleavers | 1200000 |  |  |  | 1200000
I250376 | I250376018 | VFLs | 420000 |  |  |  | 420000
I250376 | I250376019 | OTDR - For Core / FTTH b | 4350000 |  |  |  | 4350000
I250376 | I250376020 | PON Power Mtr. | 2520000 |  |  |  | 2520000
I250376 | I250376021 | CATV Transmission Equipmen | 5031800 |  |  |  | 5031800
I250376 | I250376022 | OLT | 1946000 |  |  |  | 1946000
I250376 | I250376023 | PON Cards | 12510000 |  |  |  | 12510000
I250376 | I250376024 | Switch | 834000 |  |  |  | 834000
I250376 | I250376025 | OLT connectivity SFPs Mult | 32248 | 30773.26 |  | 30773.26 | 1474.74
I250376 | I250376026 | Uplink SFPs for POP connec | 96744 |  |  |  | 96744
I250376 | I250376027 | Carry | 6000000 |  |  |  | 6000000
I250376 | I250376028 | Bolan | 10000000 |  |  |  | 10000000
I250376 | I250377000 | StormFiber Expansion – New | 41030648.34 | 41030648.34 |  | 41030648.34
I250377 | I250377001 | Cabinets & Accessories - | 18588920.44 | 542110.93 |  | 542110.93 | 18046809.51
I250377 | I250377002 | Consumable & Accessories | 4130700 | 1598265.73 |  | 1598265.73 | 2532434.27
I250377 | I250377003 | Cables - (Feeder Access | 30413868.4 | 6261087.49 |  | 6261087.49 | 24152780.91
I250377 | I250377004 | Enclosures - (Feeder Ac | 2682938.79 | 62808.53 |  | 62808.53 | 2620130.26
I250377 | I250377005 | Splitters - (Access & Dis | 6789809.71 | 105858.88 |  | 105858.88 | 6683950.83
I250377 | I250377006 | Duct - (HDPE / GI with | 34974948.35 | 372387.37 |  | 372387.37 | 34602560.98
I250377 | I250377007 | Handholes - (HH / Chamb | 6700000 |  |  |  | 6700000
I250377 | I250377008 | Poles | 1720000 |  | 120000 | 120000 | 1600000
I250377 | I250377009 | FDT Foundation | 400000 |  |  |  | 400000
I250377 | I250377010 | Infrastructure Laying - | 47296436 | 20000 | 6650000 | 6670000 | 40626436
I250377 | I250377011 | Cable Hauling - (Aerial | 9665724.57 |  |  |  | 9665724.57
I250377 | I250377012 | Building Attachments - | 1666500 |  |  |  | 1666500
I250377 | I250377013 | Transportation - (Vehic | 4775000 |  |  |  | 4775000
I250377 | I250377014 | Tool Kit - (Access) | 375000 | 344214.98 |  | 344214.98 | 30785.02
I250377 | I250377015 | Tool Kit - (Dev.) | 150000 |  |  |  | 150000
I250377 | I250377016 | Cable preparation Tools | 450000 | 3124.98 |  | 3124.98 | 446875.02
I250377 | I250377017 | Splice Machine | 2400000 | 3585.05 |  | 3585.05 | 2396414.95
I250377 | I250377018 | Cleavers | 400000 | 57000 |  | 57000 | 343000
I250377 | I250377019 | VFLs | 160000 |  |  |  | 160000
I250377 | I250377020 | OTDR - For Core / FTTH bo | 750000 | 365000 |  | 365000 | 385000
I250377 | I250377021 | PON Power Mtr. | 960000 |  |  |  | 960000
I250377 | I250377022 | CATV Transmission Equipmen | 3141400 | 920190.14 |  | 920190.14 | 2221209.86
I250377 | I250377023 | PON Cards | 4170000 |  |  |  | 4170000
I250377 | I250377024 | Carry | 6000000 |  |  |  | 6000000
I250377 | I250377025 | Bolan | 5000000 |  |  |  | 5000000
I250377 | I250378001 | Cabinets & Accessories - | 10610000 | 2106106.21 |  | 2106106.21 | 8503893.79
I250378 | I250378002 | Consumable & Accessories | 2184500 |  |  |  | 2184500
I250378 | I250378003 | Cables - (Feeder Access | 18405651.92 | 3881631.69 |  | 3881631.69 | 14524020.23
I250378 | I250378004 | Enclosures - (Feeder Ac | 1227800 |  |  |  | 1227800
I250378 | I250378005 | Splitters - (Access & Dis | 1575600 |  |  |  | 1575600
I250378 | I250378006 | Duct - (HDPE / GI with | 31695408.9 | 8207480.23 |  | 8207480.23 | 23487928.67
I250378 | I250378007 | Handholes - (HH / Chamb | 4680000 |  |  |  | 4680000
I250378 | I250378008 | FDT Foundation | 200000 | 116702.26 |  | 116702.26 | 83297.74
I250378 | I250378009 | Infrastructure Laying - | 32354991.37 | 2250000 |  | 2250000 | 30104991.37
I250378 | I250378010 | Cable Hauling - (Aerial | 3451847.36 | 22200 |  | 22200 | 3429647.36
I250378 | I250378011 | Building Attachments - | 980000 |  |  |  | 980000
I250378 | I250378012 | Transportation - (Vehic | 750000 |  |  |  | 750000
I250378 | I250378013 | Tool Kit - (Access) | 375000 | 317120 |  | 317120 | 57880
I250378 | I250378014 | Tool Kit - (Dev.) | 160000 |  |  |  | 160000
I250378 | I250378015 | Cable preparation Tools | 300000 |  |  |  | 300000
I250378 | I250378016 | Splice Machine | 1600000 |  |  |  | 1600000
I250378 | I250378017 | Cleavers | 480000 | 40187.49 |  | 40187.49 | 439812.51
I250378 | I250378018 | VFLs | 120000 |  |  |  | 120000
I250378 | I250378019 | OTDR - For Core / FTTH bo | 750000 | 365000 |  | 365000 | 385000
I250378 | I250378020 | PON Power Mtr. | 960000 |  |  |  | 960000
I250378 | I250378021 | CATV Transmission Equipmen | 3141400 |  |  |  | 3141400
I250378 | I250378022 | PON Cards | 4170000 |  |  |  | 4170000
I250378 | I250378023 | Carry | 6000000 |  |  |  | 6000000
I250378 | I250378024 | Bolan | 5000000 |  |  |  | 5000000
I250378 | I250379001 | Cabinets & Accessories - | 3866000 |  |  |  | 3866000
I250379 | I250379002 | Consumable & Accessories | 728850 |  |  |  | 728850
I250379 | I250379003 | Cables - (Feeder Access | 7640501.82 |  |  |  | 7640501.82
I250379 | I250379004 | Enclosures - (Feeder Ac | 557900 |  |  |  | 557900
I250379 | I250379005 | Splitters - (Access & Dis | 1361520 |  |  |  | 1361520
I250379 | I250379006 | Duct - (HDPE / GI with | 13704594.88 |  |  |  | 13704594.88
I250379 | I250379007 | Handholes - (HH / Chamb | 5456000 |  |  |  | 5456000
I250379 | I250379008 | FDT Foundation | 60000 |  |  |  | 60000
I250379 | I250379009 | Infrastructure Laying - | 9142403.1 |  |  |  | 9142403.1
I250379 | I250379010 | Cable Hauling - (Aerial | 1654271.04 |  |  |  | 1654271.04
I250379 | I250379011 | Building Attachments - | 2457000 |  |  |  | 2457000
I250379 | I250379012 | Transportation - (Vehic | 600000 |  |  |  | 600000
I250379 | I250379013 | Tool Kit - (Access) | 150000 |  |  |  | 150000
I250379 | I250379014 | Tool Kit - (Dev.) | 80000 |  |  |  | 80000
I250379 | I250379015 | Cable preparation Tools | 150000 |  |  |  | 150000
I250379 | I250379016 | Splice Machine | 800000 |  |  |  | 800000
I250379 | I250379017 | Cleavers | 160000 |  |  |  | 160000
I250379 | I250379018 | VFLs | 60000 |  |  |  | 60000
I250379 | I250379019 | PON Power Mtr. | 360000 |  |  |  | 360000
I250379 | I250379020 | CATV Transmission Equipmen | 945200 |  |  |  | 945200
I250379 | I250379021 | PON Cards | 834000 |  |  |  | 834000
I250379 | I250379022 | Bolan | 2500000 |  |  |  | 2500000
I250379 | I250380000 | StormFiber Expansion – Gul | 115955842.07 | 115955842.06 |  | 115955842.06 | 0.01
I250380 | I250380001 | Cabinets & Accessories - | 10838243.57 | 2257877 | 1192500 | 3450377 | 7387866.57
I250380 | I250380002 | Consumable & Accessories | 2832591.14 | 323443.19 |  | 323443.19 | 2509147.95
I250380 | I250380003 | Cables - (Feeder Access | 18980263.31 | 4804040.86 |  | 4804040.86 | 14176222.45
I250380 | I250380004 | Enclosures - (Feeder Ac | 2173975.35 | 236463.37 |  | 236463.37 | 1937511.98
I250380 | I250380005 | Splitters - (Access & Dis | 5297368.45 | 126648.48 |  | 126648.48 | 5170719.97
I250380 | I250380006 | Duct - (HDPE / GI with | 26696808.79 |  |  |  | 26696808.79
I250380 | I250380007 | FDT Foundation | 217672.16 |  |  |  | 217672.16
I250380 | I250380008 | Infrastructure Laying - | 90435693.32 |  | 17650000 | 17650000 | 72785693.32
I250380 | I250380009 | Cable Hauling - (Aerial | 6690707.79 | 162250 | 2087750 | 2250000 | 4440707.79
I250380 | I250380010 | Building Attachments - | 3658100 | 36000 |  | 36000 | 3622100
I250380 | I250380011 | Tool Kit - (Access) | 675000 | 219295.38 |  | 219295.38 | 455704.62
I250380 | I250380012 | Tool Kit - (Dev.) | 189758.86 | 106224.85 |  | 106224.85 | 83534.01
I250380 | I250380013 | Cable prepartion Tools - | 596270.19 |  |  |  | 596270.19
I250380 | I250380014 | Splice Machine | 3200000 |  |  |  | 3200000
I250380 | I250380015 | Cleavers | 720000 | 99000 |  | 99000 | 621000
I250380 | I250380016 | VFLs | 280000 |  |  |  | 280000
I250380 | I250380017 | OTDR - For Core / FTTH b | 1900000 |  |  |  | 1900000
I250380 | I250380018 | PON Power Mtr. | 1680000 |  |  |  | 1680000
I250380 | I250380019 | CATV Transmission Equipmen | 3141400 | 1789511.2 |  | 1789511.2 | 1351888.8
I250380 | I250380020 | PON Cards | 5004000 |  |  |  | 5004000
I250380 | I250380021 | Bolan | 15000000 |  |  |  | 15000000
I250380 | I250681001 | Cabinets & Accessories - | 6495000 | 1728145.82 |  | 1728145.82 | 4766854.18
I250681 | I250681002 | Consumable & Accessories | 1116750 | 725703.41 |  | 725703.41 | 391046.59
I250681 | I250681003 | Cables - (Feeder Access | 13784561.01 | 4569827.31 |  | 4569827.31 | 9214733.7
I250681 | I250681004 | Enclosures - (Feeder Ac | 898199.68 | 252198.36 |  | 252198.36 | 646001.32
I250681 | I250681005 | Splitters - (Access & Dis | 2453027.22 | 412102.3 |  | 412102.3 | 2040924.92
I250681 | I250681006 | Duct - (HDPE / GI with | 19198376.12 | 3203482.83 |  | 3203482.83 | 15994893.29
I250681 | I250681007 | Handholes - (HH / Chamb | 4444000 |  |  |  | 4444000
I250681 | I250681008 | Poles | 270000 |  |  |  | 270000
I250681 | I250681009 | FDT Foundation | 120000 |  |  |  | 120000
I250681 | I250681010 | Infrastructure Laying - | 31332348.04 | 1500000 |  | 1500000 | 29832348.04
I250681 | I250681011 | Cable Hauling - (Aerial | 2541870 |  |  |  | 2541870
I250681 | I250681012 | Transportation - (Vehic | 540000 |  |  |  | 540000
I250681 | I250681013 | Tool Kit - (Access) | 150000 | 144000 |  | 144000 | 6000
I250681 | I250681014 | Tool Kit - (Dev.) | 64000 |  |  |  | 64000
I250681 | I250681015 | Cable prepartion Tools | 150000 |  |  |  | 150000
I250681 | I250681016 | Splice Machine | 800000 |  |  |  | 800000
I250681 | I250681017 | Cleavers | 160000 |  |  |  | 160000
I250681 | I250681018 | VFLs | 60000 |  |  |  | 60000
I250681 | I250681019 | PON Power Mtr. | 360000 |  |  |  | 360000
I250681 | I250681020 | CATV Transmission Equipme | 952170 |  |  |  | 952170
I250681 | I250681021 | PON Cards | 4200750 |  |  |  | 4200750
I250681 | I250681022 | Carry | 5000000 |  |  |  | 5000000
I250681 | I250734001 | Cabinets & Accessories - | 38912000 | 275229.22 |  | 275229.22 | 38636770.78
I250734 | I250734002 | Consumable & Accessories | 5263450 | 271877.11 |  | 271877.11 | 4991572.89
I250734 | I250734003 | Cables - (Feeder Access | 35882683.62 | 4328229.08 |  | 4328229.08 | 31554454.54
I250734 | I250734004 | Enclosures - (Feeder Ac | 4984508.49 | 267066.32 |  | 267066.32 | 4717442.17
I250734 | I250734005 | Splitters - (Access & Dis | 14033389.92 | 476932.64 |  | 476932.64 | 13556457.28
I250734 | I250734006 | Duct - (HDPE / GI with | 33519464.4 | 9438694.21 |  | 9438694.21 | 24080770.19
I250734 | I250734007 | Handholes - (HH / Chamb | 8404000 |  |  |  | 8404000
I250734 | I250734008 | FDT Foundation | 700000 | 128715.65 |  | 128715.65 | 571284.35
I250734 | I250734009 | Infrastructure Laying - | 52774994.49 |  |  |  | 52774994.49
I250734 | I250734010 | Cable Hauling - (Aerial | 11737570.5 |  |  |  | 11737570.5
I250734 | I250734011 | Building Attachments - | 4752013.98 |  |  |  | 4752013.98
I250734 | I250734012 | Transportation - (Vehic | 4025000 |  |  |  | 4025000
I250734 | I250734013 | Tool Kit - (Access) | 600000 | 264000 |  | 264000 | 336000
I250734 | I250734014 | Tool Kit - (Dev.) | 320000 |  |  |  | 320000
I250734 | I250734015 | Cable prepartion Tools - | 600000 |  |  |  | 600000
I250734 | I250734016 | Splice Machine | 3200000 |  |  |  | 3200000
I250734 | I250734017 | Cleavers | 720000 |  |  |  | 720000
I250734 | I250734018 | VFLs | 240000 |  |  |  | 240000
I250734 | I250734019 | OTDR - For Core / FTTH b | 750000 |  |  |  | 750000
I250734 | I250734020 | PON Power Mtr. | 1440000 |  |  |  | 1440000
I250734 | I250734021 | CATV Transmission Equipmen | 2978331.75 |  |  |  | 2978331.75
I250734 | I250734022 | OLT | 2240400 |  |  |  | 2240400
I250734 | I250734023 | PON Cards | 9801750 |  |  |  | 9801750
I250734 | I250734024 | Switch | 840150 |  |  |  | 840150
I250734 | I250734025 | Cdarry with ladder | 12000000 | 5868066 | 6912000 | 12780066 | 780066.00-
I250734 | I250734026 | Bolan | 5000000 |  |  |  | 5000000
I250734 | I250737001 | Cabinets & Accessories - | 19730000 | 54587.34 |  | 54587.34 | 19675412.66
I250737 | I250737002 | Consumable & Accessories | 3039620 |  |  |  | 3039620
I250737 | I250737003 | Cables - (Feeder Access | 31713706.02 |  |  |  | 31713706.02
I250737 | I250737004 | Enclosures - (Feeder Ac | 2939101.2 |  |  |  | 2939101.2
I250737 | I250737005 | Splitters - (Access & Dis | 7217064.8 |  |  |  | 7217064.8
I250737 | I250737006 | Duct - (HDPE / GI with | 64945432.56 | 9866906.79 |  | 9866906.79 | 55078525.77
I250737 | I250737007 | Handholes - (HH / Chamb | 26158000 |  |  |  | 26158000
I250737 | I250737008 | FDT Foundation | 300000 |  |  |  | 300000
I250737 | I250737009 | Infrastructure Laying - | 205420087.5 | 14884375 | 21250000 | 36134375 | 169285712.5
I250737 | I250737010 | Cable Hauling - (Aerial | 7694939.6 |  |  |  | 7694939.6
I250737 | I250737011 | Building Attachments - | 5630000 |  |  |  | 5630000
I250737 | I250737012 | Transportation - (Vehic | 1620000 |  |  |  | 1620000
I250737 | I250737013 | Tool Kit - (Access) | 450000 | 201220 |  | 201220 | 248780
I250737 | I250737014 | Tool Kit - (Dev.) | 220000 |  |  |  | 220000
I250737 | I250737015 | Cable prepartion Tools - | 300000 |  |  |  | 300000
I250737 | I250737016 | Splice Machine | 1600000 |  |  |  | 1600000
I250737 | I250737017 | Cleavers | 480000 |  |  |  | 480000
I250737 | I250737018 | VFLs | 200000 |  |  |  | 200000
I250737 | I250737019 | OTDR - For Core / FTTH b | 1725000 |  |  |  | 1725000
I250737 | I250737020 | PON Power Mtr. | 1200000 |  |  |  | 1200000
I250737 | I250737021 | CATV Transmission Equipmen | 1904340 |  |  |  | 1904340
I250737 | I250737022 | OLT | 2240400 |  |  |  | 2240400
I250737 | I250737023 | PON Cards | 5601000 |  |  |  | 5601000
I250737 | I250737024 | Bolan | 10000000 |  |  |  | 10000000
I250737 | I260060001 | Cabinets & Accessories - | 1087000 |  |  |  | 1087000
I260060 | I260060002 | Consumable & Accessories | 184200 |  |  |  | 184200
I260060 | I260060003 | Cables - (Feeder Access | 6009356.25 |  |  |  | 6009356.25
I260060 | I260060004 | Enclosures - (Feeder Ac | 207400 |  |  |  | 207400
I260060 | I260060005 | Splitters - (Access & Dis | 396450 |  |  |  | 396450
I260060 | I260060006 | Duct - (HDPE / GI with | 4167352 | 4579223.52 |  | 4579223.52 | 411871.52-
I260060 | I260060007 | Handholes - (HH / Chamb | 1936000 |  |  |  | 1936000
I260060 | I260060008 | FDT Foundation | 25000 |  |  |  | 25000
I260060 | I260060009 | Infrastructure Laying - | 1217360 | 1200000 |  | 1200000 | 17360
I260060 | I260060010 | Cable Hauling - (Aerial | 627900 |  |  |  | 627900
I260060 | I260060011 | Building Attachments - | 144000 |  |  |  | 144000
I260060 | I260060012 | Transportation - (Vehic | 90000 |  |  |  | 90000
I260060 | I260060013 | EDFA | 970190 |  |  |  | 970190
I260060 | I260060014 | PON Cards | 2140125 |  |  |  | 2140125
I260060 | I260060015 | Switch | 856050 |  |  |  | 856050
I260060 | I260060016 | Optical Switch Transmitte | 1155667.5 |  |  |  | 1155667.5
I260060 | I260060017 | Tool Kits Clever Power | 590000 |  |  |  | 590000
I260060 | I260060018 | DEV: Tool Kits Cable pre | 1175000 |  |  |  | 1175000
I260060 | I260061001 | Cabinets & Accessories - | 7097000 | 839140.82 |  | 839140.82 | 6257859.18
I260061 | I260061002 | Consumable & Accessories | 1314950 | 122338.05 |  | 122338.05 | 1192611.95
I260061 | I260061003 | Cables - (Feeder Access | 11526644.72 | 2262946.67 |  | 2262946.67 | 9263698.05
I260061 | I260061004 | Enclosures - (Feeder Ac | 1134000 | 83915.27 |  | 83915.27 | 1050084.73
I260061 | I260061005 | Splitters - (Access & Dis | 4707644.71 | 200756.74 |  | 200756.74 | 4506887.97
I260061 | I260061006 | Duct - (HDPE / GI with | 24755935.74 | 12474042.61 |  | 12474042.61 | 12281893.13
I260061 | I260061007 | Handholes - (HH / Chamb | 4026000 |  |  |  | 4026000
I260061 | I260061008 | Poles | 1830000 |  |  |  | 1830000
I260061 | I260061009 | FDT Foundation | 450000 |  |  |  | 450000
I260061 | I260061010 | Infrastructure Laying - | 33122884.34 | 1647400 |  | 1647400 | 31475484.34
I260061 | I260061011 | Cable Hauling - (Aerial | 6584588.26 |  |  |  | 6584588.26
I260061 | I260061012 | Transportation - (Vehic | 1300000 | 5820 |  | 5820 | 1294180
I260061 | I260061013 | Tool Kit - (Access) | 300000 | 41820 |  | 41820 | 258180
I260061 | I260061014 | Tool Kit - (Dev.) | 160000 |  |  |  | 160000
I260061 | I260061015 | Cable prepartion Tools - | 300000 | 134276.54 |  | 134276.54 | 165723.46
I260061 | I260061016 | Splice Machine | 1600000 |  |  |  | 1600000
I260061 | I260061017 | Cleavers | 320000 |  |  |  | 320000
I260061 | I260061018 | VFLs | 120000 |  |  |  | 120000
I260061 | I260061019 | PON Power Mtr. | 720000 |  |  |  | 720000
I260061 | I260061020 | CATV Transmission Equipmen | 970190 |  |  |  | 970190
I260061 | I260061021 | Bolan | 3200000 | 399048.00- | 3145485 | 2746437 | 453563
I260061 | I260061022 | Carry with ladder | 6000000 |  |  |  | 6000000
I260061 | I260061023 | PON Cards | 3566875 |  |  |  | 3566875
I260061 | I260068000 | GPON Infra Storm DHA Dev. | 122623933.02 | 122623933.02 |  | 122623933.02
I260068 | I260068001 | Cabinets & Accessories - | 66020875.64 |  |  |  | 66020875.64
I260068 | I260068002 | Consumable & Accessories | 13031011.53 | 83103.22 |  | 83103.22 | 12947908.31
I260068 | I260068003 | Cables - (Feeder Access | 125580515.42 | 2317240.39 |  | 2317240.39 | 123263275.03
I260068 | I260068004 | Enclosures - (Feeder Ac | 11743510.39 | 25483.09 |  | 25483.09 | 11718027.3
I260068 | I260068005 | Splitters - (Access & Dis | 30438774.1 | 1232983.25- |  | 1232983.25- | 31671757.35
I260068 | I260068006 | Duct - (HDPE / GI with | 92101459.18 | 14718092.47 |  | 14718092.47 | 77383366.71
I260068 | I260068007 | Handholes - (HH / Chamb | 138495874.65 |  |  |  | 138495874.65
I260068 | I260068008 | FDT Foundation | 680000 |  |  |  | 680000
I260068 | I260068009 | Infrastructure Laying - | 1076003802.33 | 11604773 | 67338000 | 78942773 | 997061029.33
I260068 | I260068010 | Cable Hauling - (Aerial | 46316472.5 |  |  |  | 46316472.5
I260068 | I260068011 | Building Attachments - | 47277544.59 |  |  |  | 47277544.59
I260068 | I260068012 | Transportation - (Vehic | 18725000 | 15000 |  | 15000 | 18710000
I260068 | I260068013 | Tool Kit - (Access) | 900000 | 123420 |  | 123420 | 776580
I260068 | I260068014 | Tool Kit - (Dev.) | 560000 |  |  |  | 560000
I260068 | I260068015 | Cable prepartion Tools - | 1050000 |  |  |  | 1050000
I260068 | I260068016 | Splice Machine | 4800000 |  |  |  | 4800000
I260068 | I260068017 | Cleavers | 960000 |  |  |  | 960000
I260068 | I260068018 | VFLs | 380000 |  |  |  | 380000
I260068 | I260068019 | OTDR - For Core / FTTH b | 2700000 |  |  |  | 2700000
I260068 | I260068020 | PON Power Mtr. | 2280000 |  |  |  | 2280000
I260068 | I260068021 | CATV Transmission Equipmen | 7162285 |  |  |  | 7162285
I260068 | I260068022 | Bolan | 22500000 |  | 19786410 | 19786410 | 2713590
I260068 | I260068023 | OLT | 2282800 |  |  |  | 2282800
I260068 | I260068024 | PON Cards | 14267500 |  |  |  | 14267500
I260068 | I260068025 | Switch | 856050 |  |  |  | 856050
I260068 | I260068026 | OLT connectivity SFPs Mult | 33100.6 |  |  |  | 33100.6
I260068 | I260068027 | Uplink SFPs for POP connec | 99301.8 |  |  |  | 99301.8
I260068 | I260105001 | Cabinets & Accessories - | 9524000 |  |  |  | 9524000
I260105 | I260105002 | Consumable & Accessories | 1629900 |  |  |  | 1629900
I260105 | I260105003 | Cables - (Feeder Access | 9866484.34 |  |  |  | 9866484.34
I260105 | I260105004 | Enclosures - (Feeder Ac | 1462600.36 |  |  |  | 1462600.36
I260105 | I260105005 | Splitters - (Access & Dis | 3895533.9 |  |  |  | 3895533.9
I260105 | I260105006 | Duct - (HDPE / GI with | 21439862.72 |  |  |  | 21439862.72
I260105 | I260105007 | Handholes - (HH / Chamb | 12320000 |  |  |  | 12320000
I260105 | I260105008 | FDT Foundation | 150000 |  |  |  | 150000
I260105 | I260105009 | Infrastructure Laying - | 54150094.46 |  |  |  | 54150094.46
I260105 | I260105010 | Cable Hauling - (Aerial | 2886984 |  |  |  | 2886984
I260105 | I260105011 | Building Attachments - | 1338000 |  |  |  | 1338000
I260105 | I260105012 | Transportation - (Vehic | 1260000 |  |  |  | 1260000
I260105 | I260105013 | Tool Kit - (Access) | 75000 |  |  |  | 75000
I260105 | I260105014 | Tool Kit - (Dev.) | 80000 |  |  |  | 80000
I260105 | I260105015 | Cable prepartion Tools - | 150000 |  |  |  | 150000
I260105 | I260105016 | Splice Machine | 800000 |  |  |  | 800000
I260105 | I260105017 | Cleavers | 160000 |  |  |  | 160000
I260105 | I260105018 | VFLs | 40000 |  |  |  | 40000
I260105 | I260105019 | PON Power Mtr | 240000 |  |  |  | 240000
I260105 | I260105020 | CATV Transmission Equipmen | 970190 |  |  |  | 970190
I260105 | I260159001 | Cabinets & Accessories - | 6400000 |  |  |  | 6400000
I260159 | I260159002 | Consumable & Accessories | 864300 | 135.13 |  | 135.13 | 864164.87
I260159 | I260159003 | Cables - (Feeder Access | 6148072.02 | 1127564.08 |  | 1127564.08 | 5020507.94
I260159 | I260159004 | Enclosures - (Feeder Ac | 769599.6 | 18109.32 |  | 18109.32 | 751490.28
I260159 | I260159005 | Splitters - (Access & Dis | 2132039.4 |  |  |  | 2132039.4
I260159 | I260159006 | Duct - (HDPE / GI with | 9359735.04 | 3692667.06 |  | 3692667.06 | 5667067.98
I260159 | I260159007 | Handholes - (HH / Cham | 6028000 |  |  |  | 6028000
I260159 | I260159008 | FDT Foundation | 50000 |  |  |  | 50000
I260159 | I260159009 | Infrastructure Laying - | 23667930 | 5400000 | 14850000 | 20250000 | 3417930
I260159 | I260159010 | Cable Hauling - (Aerial | 2065815 |  |  |  | 2065815
I260159 | I260159011 | Building Attachments - | 8483000 |  |  |  | 8483000
I260159 | I260159012 | Transportation - (Vehic | 960000 |  |  |  | 960000
I260159 | I260159013 | OTDR - For Core / FTTH b | 750000 |  |  |  | 750000
I260159 | I260159014 | CATV Transmission Equipmen | 960330 |  |  |  | 960330
I260159 | I260159015 | PON Cards | 1412250 |  |  |  | 1412250
I260159 | I260159016 | Access Tool Kits | 75000 |  |  |  | 75000
I260159 | I260159017 | Dev Tool Kits | 80000 |  |  |  | 80000
I260159 | I260159018 | PON Meters | 240000 |  |  |  | 240000
I260159 | I260159019 | Clever | 160000 |  |  |  | 160000
I260159 | I260159020 | VFL | 50000 |  |  |  | 50000
I260159 | I260159021 | Cable prepration Tools (Ca | 150000 |  |  |  | 150000
I260159 | I260159022 | Splicing Machine | 1600000 |  |  |  | 1600000
I260159 | I260160001 | Cabinets & Accessories | 27221000 |  |  |  | 27221000
I260160 | I260160002 | Consumable & Accessories | 4059550 |  |  |  | 4059550
I260160 | I260160003 | Cables - (Feeder Acces | 27040142.48 |  |  |  | 27040142.48
I260160 | I260160004 | Enclosures - (Feeder A | 3338105.4 |  |  |  | 3338105.4
I260160 | I260160005 | Splitters - (Access & Di | 8439306.84 |  |  |  | 8439306.84
I260160 | I260160006 | Duct - (HDPE / GI with | 51629595.46 | 11660755.37 |  | 11660755.37 | 39968840.09
I260160 | I260160007 | Handholes - (HH / Cham | 36014000 |  |  |  | 36014000
I260160 | I260160008 | Poles | 2820000 | 8800 |  | 8800 | 2811200
I260160 | I260160009 | FDT Foundation | 175000 |  |  |  | 175000
I260160 | I260160010 | Infrastructure Laying | 110334585 | 7135294 | 15556000 | 22691294 | 87643291
I260160 | I260160011 | Cable Hauling - (Aeria | 10156685 |  |  |  | 10156685
I260160 | I260160012 | Building Attachments - | 6412993.44 |  |  |  | 6412993.44
I260160 | I260160013 | Transportation - (Vehi | 1620000 |  |  |  | 1620000
I260160 | I260160014 | Tool Kit - (Access) | 375000 |  |  |  | 375000
I260160 | I260160015 | Tool Kit - (Dev.) | 240000 |  |  |  | 240000
I260160 | I260160016 | Cable prepartion Tools | 450000 |  |  |  | 450000
I260160 | I260160017 | Splice Machine | 2400000 |  |  |  | 2400000
I260160 | I260160018 | Cleavers | 400000 |  |  |  | 400000
I260160 | I260160019 | VFLs | 200000 |  |  |  | 200000
I260160 | I260160020 | PON Power Mtr. | 960000 |  |  |  | 960000
I260160 | I260160021 | CATV Transmission Equipme | 2880990 |  |  |  | 2880990
I260160 | I260160022 | OTDR A | 1500000 |  |  |  | 1500000
I260160 | I260160023 | OTDR B | 950000 |  |  |  | 950000
I260160 | I260160024 | Bolan | 10000000 |  |  |  | 10000000
I260160 | I260160025 | Carry with ladder | 3000000 |  |  |  | 3000000
I260160 | I260160026 | PON Cards | 7061250 |  |  |  | 7061250
I260160 | I260179001 | Cabinets & Accessories | 1595000 |  |  |  | 1595000
I260179 | I260179002 | Consumable & Accessories | 351650 |  |  |  | 351650
I260179 | I260179003 | Cables - (Feeder Acces | 4155729.5 |  |  |  | 4155729.5
I260179 | I260179004 | Enclosures - (Feeder A | 288000 |  |  |  | 288000
I260179 | I260179005 | Splitters - (Access & Di | 556320 |  |  |  | 556320
I260179 | I260179006 | Duct - (HDPE / GI with | 1014000 | 175384.52 |  | 175384.52 | 838615.48
I260179 | I260179007 | Handholes - (HH / Cham | 1774000 |  |  |  | 1774000
I260179 | I260179008 | FDT Foundation | 25000 |  |  |  | 25000
I260179 | I260179009 | Infrastructure Laying | 1692187.5 | 70000 |  | 70000 | 1622187.5
I260179 | I260179010 | Cable Hauling - (Aeria | 1381047.5 |  |  |  | 1381047.5
I260179 | I260179011 | Building Attachments - | 426000 |  |  |  | 426000
I260179 | I260180001 | Cabinets & Accessories | 16784000 |  |  |  | 16784000
I260180 | I260180002 | Consumable & Accessories | 2562450 |  |  |  | 2562450
I260180 | I260180003 | Cables - (Feeder Acces | 29648578.5 |  |  |  | 29648578.5
I260180 | I260180004 | Enclosures - (Feeder A | 2337600 |  |  |  | 2337600
I260180 | I260180005 | Splitters - (Access & Di | 6502950 |  |  |  | 6502950
I260180 | I260180006 | Duct - (HDPE / GI with | 17492743.03 | 5734786.98 |  | 5734786.98 | 11757956.05
I260180 | I260180007 | Handholes - (HH / Cham | 3014000 |  |  |  | 3014000
I260180 | I260180008 | Poles | 300000 |  |  |  | 300000
I260180 | I260180009 | FDT Foundation | 150000 |  |  |  | 150000
I260180 | I260180010 | Infrastructure Laying | 26601040 | 500000 |  | 500000 | 26101040
I260180 | I260180011 | Cable Hauling - (Aeria | 8320005 |  |  |  | 8320005
I260180 | I260180012 | Building Attachments - | 775500 |  |  |  | 775500
I260180 | I260180013 | Transportation - (Vehi | 2640000 |  |  |  | 2640000
I260180 | I260180014 | Tool Kit - (Access) | 375000 |  |  |  | 375000
I260180 | I260180015 | Tool Kit - (Dev.) | 240000 |  |  |  | 240000
I260180 | I260180016 | Cable prepartion Tools | 450000 |  |  |  | 450000
I260180 | I260180017 | Splice Machine | 2400000 |  |  |  | 2400000
I260180 | I260180018 | Cleavers | 400000 |  |  |  | 400000
I260180 | I260180019 | VFLs | 160000 |  |  |  | 160000
I260180 | I260180020 | PON Power Mtr. | 960000 |  |  |  | 960000
I260180 | I260180021 | CATV Transmission Equipme | 2880990 |  |  |  | 2880990
I260180 | I260180022 | OTDR A | 1500000 |  |  |  | 1500000
I260180 | I260180023 | OTDR B | 950000 |  |  |  | 950000
I260180 | I260180024 | PON Cards | 7061250 |  |  |  | 7061250
I260180 | I260180025 | carry with ladder | 9000000 |  |  |  | 9000000
I260180 | I260180026 | Bolan | 5000000 |  |  |  | 5000000
I260180 | I260180027 | Vehicles Transportation | 750000 |  |  |  | 750000
I260180 | I260208001 | Cabinets & Accessories | 17320000 |  |  |  | 17320000
I260208 | I260208002 | Consumable & Accessories | 2515040 |  |  |  | 2515040
I260208 | I260208003 | Cables - (Feeder Acces | 13720734.69 |  |  |  | 13720734.69
I260208 | I260208004 | Enclosures - (Feeder A | 2430000 |  |  |  | 2430000
I260208 | I260208005 | Splitters - (Access & Di | 5416020 |  |  |  | 5416020
I260208 | I260208006 | Duct - (HDPE / GI with | 34979480.78 |  |  |  | 34979480.78
I260208 | I260208007 | Handholes - (HH / Cham | 19668000 |  |  |  | 19668000
I260208 | I260208008 | FDT Foundation | 150000 |  |  |  | 150000
I260208 | I260208009 | Infrastructure Laying | 74639494.34 |  |  |  | 74639494.34
I260208 | I260208010 | Cable Hauling - (Aeria | 5979017.19 |  |  |  | 5979017.19
I260208 | I260208011 | Building Attachments - | 7850000 |  |  |  | 7850000
I260208 | I260208012 | Transportation - (Vehi | 2725000 |  |  |  | 2725000
I260208 | I260208013 | Tool Kit - (Access) | 225000 | 107220 |  | 107220 | 117780
I260208 | I260208014 | Tool Kit - (Dev.) | 320000 |  |  |  | 320000
I260208 | I260208015 | Cable prepartion Tools | 150000 |  |  |  | 150000
I260208 | I260208016 | Splice Machine | 2400000 |  |  |  | 2400000
I260208 | I260208017 | Cleavers | 320000 |  |  |  | 320000
I260208 | I260208018 | VFLs | 75000 |  |  |  | 75000
I260208 | I260208019 | OTDR - For Core / FTTH | 950000 |  |  |  | 950000
I260208 | I260208020 | PON Power Mtr. | 840000 |  |  |  | 840000
I260208 | I260208021 | CATV Transmission Equipme | 1920660 |  |  |  | 1920660
I260208 | I260208022 | PON Cards | 2824500 |  |  |  | 2824500
I260208 | I260208023 | Bolan | 5000000 |  |  |  | 5000000
I260208 | I260208024 | Car Transportation | 300000 |  |  |  | 300000
I260208 | I260294001 | Cabinets & Accessories | 4895000 |  |  |  | 4895000
I260294 | I260294002 | Consumable & Accessories | 850000 |  |  |  | 850000
I260294 | I260294003 | Cables - (Feeder Acces | 5164351.73 |  |  |  | 5164351.73
I260294 | I260294004 | Enclosures - (Feeder A | 797100 |  |  |  | 797100
I260294 | I260294005 | Splitters - (Access & Di | 1973625.54 |  |  |  | 1973625.54
I260294 | I260294006 | Duct - (HDPE / GI with | 7276642.24 |  |  |  | 7276642.24
I260294 | I260294007 | Handholes - (HH / Cham | 1364000 |  |  |  | 1364000
I260294 | I260294008 | Poles | 270000 |  |  |  | 270000
I260294 | I260294009 | FDT Foundation | 75000 |  |  |  | 75000
I260294 | I260294010 | Infrastructure Laying | 13826260.43 |  |  |  | 13826260.43
I260294 | I260294011 | Cable Hauling - (Aeria | 1687609.69 |  |  |  | 1687609.69
I260294 | I260294012 | Building Attachments - | 2920000 |  |  |  | 2920000
I260294 | I260294013 | Transportation - (Vehi | 510000 |  |  |  | 510000
I260294 | I260294014 | Tool Kit - (Access) | 225000 | 204000 |  | 204000 | 21000
I260294 | I260294015 | Tool Kit - (Dev.) | 80000 |  |  |  | 80000
I260294 | I260294016 | Cable prepartion Tools | 150000 |  |  |  | 150000
I260294 | I260294017 | Splice Machine | 800000 |  |  |  | 800000
I260294 | I260294018 | Cleavers | 240000 |  |  |  | 240000
I260294 | I260294019 | VFLs | 80000 |  |  |  | 80000
I260294 | I260294020 | PON Power Mtr. | 480000 |  |  |  | 480000
I260294 | I260294021 | CATV Transmission Equipme | 960330 |  |  |  | 960330
I260294 | I260294022 | PON Cards | 1412250 |  |  |  | 1412250
I260294 | I260294023 | Carry with ladder | 3000000 |  |  |  | 3000000
I260294 | I260295001 | Cabinets & Accessories | 52927000 | 84024.22 |  | 84024.22 | 52842975.78
I260295 | I260295002 | Consumable & Accessories | 8621700 |  |  |  | 8621700
I260295 | I260295003 | Cables - (Feeder Acces | 59123947.12 | 494771.4 |  | 494771.4 | 58629175.72
I260295 | I260295004 | Enclosures - (Feeder A | 7570592.82 |  |  |  | 7570592.82
I260295 | I260295005 | Splitters - (Access & Di | 20111436 |  |  |  | 20111436
I260295 | I260295006 | Duct - (HDPE / GI with | 77174097.11 |  |  |  | 77174097.11
I260295 | I260295007 | Handholes - (HH / Cham | 18260000 |  |  |  | 18260000
I260295 | I260295008 | Poles | 2820000 |  |  |  | 2820000
I260295 | I260295009 | FDT Foundation | 875000 |  | 25000 | 25000 | 850000
I260295 | I260295010 | Infrastructure Laying - | 146658744.34 | 301600 |  | 301600 | 146357144.34
I260295 | I260295011 | Cable Hauling - (Aerial | 17919324.62 |  |  |  | 17919324.62
I260295 | I260295012 | Building Attachments - | 9996000 |  |  |  | 9996000
I260295 | I260295013 | Transportation - (Vehic | 4315000 |  |  |  | 4315000
I260295 | I260295014 | Tool Kit - (Access) | 900000 | 81840 |  | 81840 | 818160
I260295 | I260295015 | Tool Kit - (Dev.) | 560000 |  |  |  | 560000
I260295 | I260295016 | Cable prepartion Tools | 1050000 |  |  |  | 1050000
I260295 | I260295017 | Splice Machine | 5600000 |  |  |  | 5600000
I260295 | I260295018 | Cleavers | 960000 |  |  |  | 960000
I260295 | I260295019 | VFLs | 360000 |  |  |  | 360000
I260295 | I260295020 | OTDR - For Core / FTTH | 3399999.99 |  |  |  | 3399999.99
I260295 | I260295021 | PON Power Mtr. | 2160000 |  |  |  | 2160000
I260295 | I260295022 | CATV Transmission Equipme | 4024912.5 |  |  |  | 4024912.5
I260295 | I260295023 | OLT | 2259600 |  |  |  | 2259600
I260295 | I260295024 | PON Cards | 11298000 |  |  |  | 11298000
I260295 | I260295025 | Switch | 847350 |  |  |  | 847350
I260295 | I260295026 | OLT connectivity SFPs Mult | 32764.2 |  |  |  | 32764.2
I260295 | I260295027 | Uplink SFPs for POP connec | 98292.6 |  |  |  | 98292.6
I260295 | I260295028 | carry with ladder | 24000000 |  |  |  | 24000000
I260295 | I260295029 | Bolan | 12500000 |  |  |  | 12500000
I260295 | I260296001 | Cabinets & Accessories - | 32652000 |  |  |  | 32652000
I260296 | I260296002 | Consumable & Accessories | 5350350 |  |  |  | 5350350
I260296 | I260296003 | Cables - (Feeder Access | 46966809.57 |  |  |  | 46966809.57
I260296 | I260296004 | Enclosures - (Feeder Ac | 4929398.15 |  |  |  | 4929398.15
I260296 | I260296005 | Splitters - (Access & Dis | 11548971.06 |  |  |  | 11548971.06
I260296 | I260296006 | Duct - (HDPE / GI with | 49528536.77 | 10878217.86 |  | 10878217.86 | 38650318.91
I260296 | I260296007 | Handholes - (HH / Chamb | 8382000 |  |  |  | 8382000
I260296 | I260296008 | Poles | 2250000 |  |  |  | 2250000
I260296 | I260296009 | FDT Foundation | 550000 |  |  |  | 550000
I260296 | I260296010 | Infrastructure Laying - | 84036880 | 9000 |  | 9000 | 84027880
I260296 | I260296011 | Cable Hauling - (Aerial | 16486524 |  |  |  | 16486524
I260296 | I260296012 | Building Attachments - | 4267999.23 |  |  |  | 4267999.23
I260296 | I260296013 | Transportation - (Vehic | 5400000 | 162321 |  | 162321 | 5237679
I260296 | I260296014 | Tool Kit - (Access) | 750000 |  |  |  | 750000
I260296 | I260296015 | Tool Kit - (Dev.) | 320000 |  |  |  | 320000
I260296 | I260296016 | Cable prepartion Tools - | 600000 |  |  |  | 600000
I260296 | I260296017 | Splice Machine | 3200000 |  |  |  | 3200000
I260296 | I260296018 | Cleavers | 800000 |  |  |  | 800000
I260296 | I260296019 | VFLs | 280000 |  |  |  | 280000
I260296 | I260296020 | OTDR - For Core / FTTH b | 3399999.99 |  |  |  | 3399999.99
I260296 | I260296021 | PON Power Mtr. | 1680000 |  |  |  | 1680000
I260296 | I260296022 | CATV Transmission Equipmen | 5055855 |  |  |  | 5055855
I260296 | I260296023 | OLT | 2259600 |  |  |  | 2259600
I260296 | I260296024 | PON Cards | 7061250 |  |  |  | 7061250
I260296 | I260296025 | Switch | 847350 |  |  |  | 847350
I260296 | I260296026 | OLT connectivity SFPs Mult | 32764.2 |  |  |  | 32764.2
I260296 | I260296027 | Uplink SFPs for POP connec | 98292.6 |  |  |  | 98292.6
I260296 | I260296028 | Carry with Ladder | 12000000 |  |  |  | 12000000
I260296 | I260296029 | Bolan | 5000000 |  |  |  | 5000000
I260296 | I260298000 | GPON Infra Storm Petaro Ga | 6183042.98 | 6183042.98 |  | 6183042.98
I260298 | I260298001 | Cabinets & Accessories | 982266.73 | 305277.15 |  | 305277.15 | 676989.58
I260298 | I260298002 | Consumable & Accessories | 209300 | 141795.9 |  | 141795.9 | 67504.1
I260298 | I260298003 | Cables - (Feeder Acces | 503031.56 | 406429.55 |  | 406429.55 | 96602.01
I260298 | I260298004 | Enclosures - (Feeder A | 147966.69 | 20590.1 |  | 20590.1 | 127376.59
I260298 | I260298005 | Splitters - (Access & Di | 211260.15 | 24528.81 |  | 24528.81 | 186731.34
I260298 | I260298006 | Duct - (HDPE / GI with | 1.12 | 2640.78- |  | 2640.78- | 2641.9
I260298 | I260298007 | Handholes - (HH / Cham | 1012000 |  |  |  | 1012000
I260298 | I260298008 | Poles | 210000 |  |  |  | 210000
I260298 | I260298009 | FDT Foundation | 25000 |  |  |  | 25000
I260298 | I260298010 | Infrastructure Laying | 1 |  |  |  | 1
I260298 | I260298011 | Cable Hauling - (Aeria | 594192.09 | 352020 |  | 352020 | 242172.09
I260298 | I260298012 | Building Attachments - | 684000 |  |  |  | 684000
I260298 | I260298013 | Transportation - (Vehi | 175000 | 3600 |  | 3600 | 171400
I260298 | I260361001 | Cabinets & Accessories - | 21353000 |  |  |  | 21353000
I260361 | I260361002 | Consumable & Accessories | 2583050 |  |  |  | 2583050
I260361 | I260361003 | Cables - (Feeder Access | 26007927.86 |  |  |  | 26007927.86
I260361 | I260361004 | Enclosures - (Feeder Ac | 2382000.29 |  |  |  | 2382000.29
I260361 | I260361005 | Splitters - (Access & Dis | 9789928.66 |  |  |  | 9789928.66
I260361 | I260361006 | Duct - (HDPE / GI with | 39503873.99 | 2583860.51 |  | 2583860.51 | 36920013.48
I260361 | I260361007 | Handholes - (HH / Chamb | 29326000 |  |  |  | 29326000
I260361 | I260361008 | FDT Foundation | 375000 |  |  |  | 375000
I260361 | I260361009 | Infrastructure Laying - | 138860279.55 | 2700000 |  | 2700000 | 136160279.55
I260361 | I260361010 | Cable Hauling - (Aerial | 9391110 |  |  |  | 9391110
I260361 | I260361011 | Building Attachments - | 11339002.72 |  |  |  | 11339002.72
I260361 | I260361012 | Transportation - (Vehic | 3600000 |  |  |  | 3600000
I260361 | I260361013 | Tool Kit - (Access) | 375000 |  |  |  | 375000
I260361 | I260361014 | Tool Kit - (Dev.) | 240000 |  |  |  | 240000
I260361 | I260361015 | Cable preparation Tools | 450000 |  |  |  | 450000
I260361 | I260361016 | Splice Machine | 2400000 |  |  |  | 2400000
I260361 | I260361017 | Cleavers | 400000 |  |  |  | 400000
I260361 | I260361018 | VFLs | 160000 |  |  |  | 160000
I260361 | I260361019 | OTDR - For Core / FTTH b | 1500000 |  |  |  | 1500000
I260361 | I260361020 | PON Power Mtr. | 960000 |  |  |  | 960000
I260361 | I260361021 | CATV Transmission Equipmen | 1920660 |  |  |  | 1920660
I260361 | I260361022 | OLT | 2259600 |  |  |  | 2259600
I260361 | I260361023 | PON Cards | 4236750 |  |  |  | 4236750
I260361 | I260361024 | OLT connectivity SFPs Mult | 32764.2 |  |  |  | 32764.2
I260361 | I260361025 | Uplink SFPs for POP connec | 98292.6 |  |  |  | 98292.6
I260361 | I260361026 | Carry with ladder | 3000000 |  |  |  | 3000000
I260361 | I260361027 | Bolan | 9600000 |  |  |  | 9600000
I260361 | I260361028 | Transportation | 600000 |  |  |  | 600000
INT-21-00315 | INT-21-00315 | StormFiber Expansion - G | 736015039 | 283234406.96 | 20434080 | 303668486.96 | 432346552.04
INT-23-00435 | INT-23-00435 | Local-New-StormFiber Exp | 118313906 | 77881903.39 | 1788500 | 79670403.39 | 38643502.61
INT-23-00436 | INT-23-00436 | Local-New-StormFiber Exp | 51381436 | 17417582.61 | 582780 | 18000362.61 | 33381073.39
INT-23-00437 | INT-23-00437 | Local-New-StormFiber Exp | 198839603 | 42295320.28 | 4063200 | 46358520.28 | 152481082.72
INT-23-00438 | INT-23-00438 | Local-New-StormFiber Exp | 13320912 | 121795.99 |  | 121795.99 | 13199116.01
INT-23-00439 | INT-23-00439 | Local-New-StormFiber Exp | 482055980 | 190240587.93 | 7085900 | 197326487.93 | 284729492.07
INT-23-00440 | INT-23-00440 | Local-New-StormFiber Exp | 53663375 | 4688155.21 |  | 4688155.21 | 48975219.79
INT-23-00441 | INT-23-00441 | Local-New-StormFiber Ex | 124440455 | 20306046.74 |  | 20306046.74 | 104134408.26
INT-23-00442 | INT-23-00442 | Local-New-StormFiber Exp | 42564738 | 2854816.24 |  | 2854816.24 | 39709921.76
INT-23-00444 | INT-23-00444 | Local-New-StormFiber Exp | 181805960 | 195619264.95 | 3094390 | 198713654.95 | 16907694.95-
INT-23-00445 | INT-23-00445 | Local-New-StormFiber Exp | 39164547 | 40582736.6 | 389524 | 40972260.6 | 1807713.60-
INT-23-00446 | INT-23-00446 | Local-New-StormFiber Exp | 165172421 |  |  |  | 165172421
INT-23-00447 | INT-23-00447 | Local-New-StormFiber Exp | 213934297 | 112052637.19 | 3139540 | 115192177.19 | 98742119.81
INT-23-00764 | INT-23-00764 | StormFiber Expansion- As | 395693727 | 57769975.94 | 3301960 | 61071935.94 | 334621791.06
Row Labels | Sum of Allocated Budget | Sum of Revised Budget | Sum of Difference |  |  | Row Labels | Sum of Allocated Budget | Sum of Revised Budget | Sum of Difference
100 | 415670312.3488 | 415670312.3488 |  |  |  | 100 | 518998173.5488 | 518998173.5488
102 | 252576804.9885 | 252576804.9885 |  |  |  | 102 | 320950492.9885 | 320950492.9885
103 | 190914712.4087 | 190914712.4087 |  |  |  | 103 | 264880241.6587 | 264880241.6587
104 | 189189403.5922 | 108783907.0655 |  |  |  | 104 | 201467753.5922 | 121062257.0655
105 | 277182368.4801 | 276278195.9401 |  |  |  | 105 | 469213284.4801 | 468309111.9401
106 | 528922932.5858 | 528922932.5858 |  |  |  | 106 | 537922932.5858 | 537922932.5858
107 | 151789539.3189 | 151789539.3189 |  |  |  | 107 | 207441341.7189 | 207441341.7189
108 | 303045745.7902 | 303045745.7902 |  |  |  | 108 | 399657325.7902 | 399657325.7902
109 | 324998966.7491 | 297374054.5754 |  |  |  | 109 | 324998966.7491 | 297374054.5754
110 | 274744690.9635 | 274744690.9635 |  |  |  | 110 | 299162106.9635 | 299162106.9635
111 | 16500000 | 16500000 |  |  |  | 111 | 16500000 | 16500000
112 | 350433922.1714 | 350433922.1714 |  |  |  | 112 | 419021550.1714 | 419021550.1714
I240188 | 92903745.7859 | 3870942.5486 | 89032803.2373 |  |  | I240188 | 108159630.7859 | 11498885.0486 | 96660745.7373
I240189 | 122769785.1659 | 18415467.7749 | 104354317.3911 |  |  | I240189 | 128620785.1659 | 21340967.7749 | 107279817.3911
I240190 | 116050375.6403 | 17407556.346 | 98642819.2943 |  |  | I240190 | 133827375.6403 | 26296056.346 | 107531319.2943
I240435 | 216855243.0449 | 32528286.4567 | 184326956.5881 |  |  | I240435 | 248499863.0449 | 48350596.4567 | 200149266.5881
I240437 | 235442928.2027 | 159700152.5387 | 114897352.4517 |  |  | I240437 | 285986428.2027 | 184971902.5387 | 140169102.4517
I240438 | 166199842.5434 | 88968610.5573 | 77231231.9861 |  |  | I240438 | 197850142.5434 | 104793760.5573 | 93056381.9861
I240440 | 329748933.5319 | 134246297.0109 | 195502636.521 |  |  | I240440 | 380747283.5319 | 159745472.0109 | 221001811.521
I240442 | 107457482.0098 | 69955211.3372 | 37502270.6725 |  |  | I240442 | 120824652.0098 | 76638796.3372 | 44185855.6725
I240459 | 11499005.0092 | 1724850.7514 | 9774154.2578 |  |  | I240459 | 12138005.0092 | 2044350.7514 | 10093654.2578
I240518 | 95923257.2667 | 13709710.3528 | 82213546.9139 |  |  | I240518 | 112050607.2667 | 21773385.3528 | 90277221.9139
I240519 | 279383829.3071 | 279383829.3071 | 0 |  |  | I240519 | 297581509.3071 | 288482669.3071 | 9098840
I240537 | 19408588.4126 | 2911288.2619 | 16497300.1507 |  |  | I240537 | 23356438.4126 | 4885213.2619 | 18471225.1507
I240538 | 142727305.6595 | 24658382.0622 | 118068923.5973 |  |  | I240538 | 202480325.6595 | 54534892.0622 | 147945433.5973
I240539 | 233756231.296 | 43231139.8485 | 182603915.4689 |  |  | I240539 | 262661971.296 | 57684009.8485 | 197056785.4689
I240540 | 161143296.2584 | 23242927.5914 | 137900368.667 |  |  | I240540 | 199830616.2584 | 42586587.5914 | 157244028.667
I240557 | 18684458.866 | 2802668.8299 | 15881790.0361 |  |  | I240557 | 20127458.866 | 3524168.8299 | 16603290.0361
I240678 | 355735547.8042 | 122741586.948 | 232993960.8563 |  |  | I240678 | 414713991.8042 | 152230808.948 | 262483182.8563
I240679 | 10311892.5 | 1546783.875 | 8765108.625 |  |  | I240679 | 10311892.5 | 1546783.875 | 8765108.625
I240680 | 111071445.702 | 14964640.4864 | 96106805.2156 |  |  | I240680 | 133968445.702 | 26413140.4864 | 107555305.2156
I240681 | 12569175 | 3940750.625 | 8628424.375 |  |  | I240681 | 12569175 | 3940750.625 | 8628424.375
I240682 | 537412507.4316 | 64740771.7964 | 472671735.6351 |  |  | I240682 | 626675307.4316 | 109372171.7964 | 517303135.6351
I240683 | 57392829.4625 | 8608924.4194 | 48783905.0431 |  |  | I240683 | 79640275.4625 | 19732647.4194 | 59907628.0431
I240684 | 57875688.609 | 5614364.1964 | 52261324.4126 |  |  | I240684 | 69792468.609 | 11572754.1965 | 58219714.4126
I240700 | 552717264.2608 | 128556497.7914 | 424160766.4694 |  |  | I240700 | 672588564.2608 | 188492147.7914 | 484096416.4694
I240701 | 11665905 | 1749885.75 | 9916019.25 |  |  | I240701 | 15078455 | 3456160.75 | 11622294.25
I240702 | 201783051.7853 | 54371906.0468 | 147411145.7384 |  |  | I240702 | 233184378.5853 | 70072569.4468 | 163111809.1384
I240703 | 768605468.5102 | 129129300.4926 | 639476168.0176 |  |  | I240703 | 861306256.5102 | 175479694.4926 | 685826562.0176
I240704 | 507998709.3732 | 73714951.2711 | 434283758.1021 |  |  | I240704 | 640727539.3732 | 140079366.2711 | 500648173.1021
I240705 | 445686125.3829 | 229125642.1079 | 216560483.275 |  |  | I240705 | 526845585.3829 | 269705372.1079 | 257140213.275
I240782 | 125214350 | 18782152.5 | 106432197.5 |  |  | I240782 | 125214350 | 18782152.5 | 106432197.5
I250114 | 36812251.6233 | 5521837.7435 | 31290413.8798 |  |  | I250114 | 38144251.6233 | 6187837.7435 | 31956413.8798
I250201 | 42698611.2205 | 2833775.325 | 39864835.8955 |  |  | I250201 | 47592961.2205 | 5280950.325 | 42312010.8955
I250202 | 23458996.9509 | 12571577.7588 | 10887419.1921 |  |  | I250202 | 27034446.9509 | 14359302.7588 | 12675144.1921
I250203 | 9236314.051 | 2170533.802 | 7065780.2491 |  |  | I250203 | 13662314.051 | 4383533.802 | 9278780.2491
I250205 | 98131628.0112 | 62922484.6087 | 35209143.4025 |  |  | I250205 | 115636928.0112 | 71675134.6087 | 43961793.4025
I250206 | 238190943.4392 | 150040448.3198 | 88150495.1195 |  |  | I250206 | 348988241.8392 | 205439097.5198 | 143549144.3195
I250207 | 27226772.7085 | 2021974.4197 | 25204798.2888 |  |  | I250207 | 31957072.7085 | 4387124.4197 | 27569948.2888
I250208 | 40848462.1145 | 2852461.4782 | 37996000.6364 |  |  | I250208 | 52865210.1145 | 8860835.4782 | 44004374.6364
I250209 | 83070900.7051 | 22015569.2533 | 61055331.4518 |  |  | I250209 | 130681950.7051 | 45821094.2533 | 84860856.4518
I250210 | 148493354.984 | 44027999.8521 | 104465355.1319 |  |  | I250210 | 192623788.984 | 66093216.8521 | 126530572.1319
I250211 | 45065968.9 | 6759895.335 | 38306073.565 |  |  | I250211 | 49430718.9 | 8942270.335 | 40488448.565
I250212 | 220504163.0685 | 48731434.6257 | 171772728.4427 |  |  | I250212 | 285944485.0685 | 81451595.6257 | 204492889.4427
I250213 | 37620029.3976 | 4080094.1246 | 33539935.273 |  |  | I250213 | 49354039.3976 | 9947099.1246 | 39406940.273
I250298 | 76622670.7877 | 14438907.4254 | 62183763.3623 |  |  | I250298 | 88120170.7877 | 20187657.4254 | 67932513.3623
I250307 | 517994073.7885 | 77699111.0683 | 440294962.7202 |  |  | I250307 | 517994073.7885 | 77699111.0683 | 440294962.7202
I250326 | 23074220.3052 | 3461133.0458 | 19613087.2594 |  |  | I250326 | 26408470.3052 | 5128258.0458 | 21280212.2594
I250327 | 446507712.3593 | 369238484.31 | 77269228.0494 |  |  | I250327 | 531867730.3593 | 411918493.31 | 119949237.0494
I250374 | 1724390 | 258658.5 | 1465731.5 |  |  | I250374 | 1724390 | 258658.5 | 1465731.5
I250375 | 45089308.4162 | 6763396.2624 | 38325912.1538 |  |  | I250375 | 57537758.4162 | 12987621.2624 | 44550137.1538
I250376 | 429014710.9296 | 57647914.2974 | 366250619.948 |  |  | I250376 | 557042160.9296 | 121661639.2974 | 430264344.948
I250377 | 139812094.6044 | 68795330.861 | 71016763.7434 |  |  | I250377 | 210835494.6044 | 104307030.861 | 106528463.7434
I250378 | 66122759.5419 | 39250453.5707 | 23191951.0201 |  |  | I250378 | 111427799.5419 | 61902973.5707 | 45844471.0201
I250379 | 26011896.0433 | 16617397.41 | 9394498.6333 |  |  | I250379 | 47229040.8433 | 27225969.81 | 20003071.0333
I250380 | 264276103.9974 | 47891941.0487 | 216384162.9487 |  |  | I250380 | 283707294.9974 | 57607536.5487 | 226099758.4487
I250681 | 26064968.0335 | 7806588.1068 | 18258379.9267 |  |  | I250681 | 95594354.869 | 42571281.5245 | 53023073.3444
I250734 | 177365323.0045 | 69464773.9243 |  |  |  | I250734 | 214988457.4045 | 107087908.3243
I250737 | 357297930.2508 | 332221547.7819 | 25076382.469 |  |  | I250737 | 376403670.2508 | 341774417.7819 | 34629252.469
I260060 | 12342069.5 | 1851310.425 |  |  |  | I260060 | 25004869.5 | 14514110.425
I260061 | 56110698.1709 | 5943039.4122 |  |  |  | I260061 | 107159247.7709 | 56991589.0122
I260068 | 1568646315.7955 | 376256056.7508 | 1192390259.0447 |  |  | I260068 | 1635462937.7955 | 409664367.7508 | 1239161894.4447
I260105 | 115899688.284 | 53677995.0842 |  |  |  | I260105 | 119641188.284 | 57419495.0842
I260159 | 65790324.28 | 9868548.642 |  |  |  | I260159 | 67815324.28 | 11893548.642
I260160 | 290026668.2352 | 221291824.6428 |  |  |  | I260160 | 321563528.2352 | 252828684.6428
I260179 | 13587284.5 | 2038092.675 |  |  |  | I260179 | 17688934.5 | 6139742.675
I260180 | 74086466.5312 | 17410319.6348 |  |  |  | I260180 | 122128866.5312 | 65452719.6348
I260208 | 180535787.0047 | 180535787.0047 |  |  |  | I260208 | 187392787.0047 | 187392787.0047
I260294 | 37880389.6381 | 26375396.5174 |  |  |  | I260294 | 41609589.6381 | 30104596.5174
I260295 | 284896561.6578 | 284896561.6578 |  |  |  | I260295 | 433500061.6578 | 433500061.6578
I260296 | 184540160.0914 | 121568245.515 |  |  |  | I260296 | 272350044.0914 | 209378129.515
I260298 | 7276483.8012 | 1091472.5702 |  |  |  | I260298 | 10770638.8012 | 4585627.5702
I260361 | 297374857.408 | 275791312.6166 |  |  |  | I260361 | 307110957.408 | 285527412.6165
INT-21-00315 | 715213941.5258 | 162366704.4326 | 584590260.3362 |  |  | INT-21-00315 | 761753116.5258 | 185636291.9326 | 607859847.8362
INT-23-00435 | 86670915.9045 | 30941786.1468 | 55729129.7576 |  |  | INT-23-00435 | 108087915.9045 | 41650286.1468 | 66437629.7576
INT-23-00436 | 38125384.4933 | 6544037.2545 | 31581347.2388 |  |  | INT-23-00436 | 51381436.4933 | 13172063.2545 | 38209373.2388
INT-23-00437 | 166094035.1767 | 24914105.2765 | 141179929.9002 |  |  | INT-23-00437 | 200389603.1767 | 42061889.2765 | 158327713.9002
INT-23-00438 | 12265711.807 | 1839856.771 | 10425855.0359 |  |  | INT-23-00438 | 13329311.807 | 2371656.771 | 10957655.0359
INT-23-00439 | 421676787.8032 | 69473964.4531 | 352202823.3501 |  |  | INT-23-00439 | 484250707.8032 | 100760924.4531 | 383489783.3501
INT-23-00440 | 34497804.8325 | 5174670.7249 | 29323134.1076 |  |  | INT-23-00440 | 53663374.8325 | 14757455.7249 | 38905919.1076
INT-23-00441 | 110203835.3157 | 16530575.2974 | 93673260.0183 |  |  | INT-23-00441 | 124440455.3157 | 23648885.2974 | 100791570.0183
INT-23-00442 | 19658577.5882 | 2948786.6382 | 16709790.95 |  |  | INT-23-00442 | 42564737.5882 | 14401866.6382 | 28162870.95
INT-23-00444 | 141455045.6184 | 27256069.3334 | 114198976.285 |  |  | INT-23-00444 | 175798350.6184 | 44427721.8334 | 131370628.785
INT-23-00445 | 19830973.56 | 2974646.034 | 16856327.526 |  |  | INT-23-00445 | 36865953.56 | 11492136.034 | 25373817.526
INT-23-00446 | 143930927.722 | 0 | 143930927.722 |  |  | INT-23-00446 | 167455820.522 | 11762446.4 | 155693374.122
INT-23-00447 | 167263875.1936 | 30826968.8827 | 136436906.3109 |  |  | INT-23-00447 | 214116397.2736 | 54253229.9227 | 159863167.3509
INT-23-00764 | 284852412.1435 | 100776886.5379 | 184075525.6056 |  |  | INT-23-00764 | 350042372.1435 | 133371866.5379 | 216670505.6056
Grand Total | 18581034211.0381 | 8480651043.2293 | 9519720397.1999 |  |  | Grand Total | 22095709754.6035 | 10815617066.937 | 10712793241.4577

## TBD (hidden)
Gantt Chart | Monitoring the timeline |  |  | Jan | Feb | Mar | Apr | May | Jun
Reason?
| Area 1 | 2026-01-01 | 2026-03-01
Add the data - to be invoiced file by Waqas bhai |  |  | book 2
NOT ASSIGNED - USE JUST ACTUAL |  |  | exp

## Live or Not Live
Live/Not Live Count |  | Live/Not Live %
Row Labels | Count of Area / Section / Pocket / Society (Original Name) | Row Labels | Count of Area / Section / Pocket / Society (Original Name)
LIVE | 525 | LIVE | 45.65%
NOT LIVE | 625 | NOT LIVE | 54.35%
Grand Total | 1150 | Grand Total | 100%

## Areas
Number of Total Areas | 1150
Row Labels | Count of Area / Section / Pocket / Society (Original Name)
Between Fizaghat & Sangota | 1
1-4L | 1
18_P1 | 1
18_P2 | 1
3 Marla Scheme | 1
Abdul Khaliq Colony | 1
Abdullah City | 1
Abdullah Colony & Nawa Killy | 1
Abdullah Sports Tower Ext | 1
Abid Colony | 1
Abid Market | 1
AbrazulMinal_KingsBridgeView | 1
Adam Housing | 1
Adam Housing-P1 | 1
Adam Housing-P2 | 1
Additional Cost | 1
AFOHS PK-1 | 1
AFOHS PK-2 | 1
AFOHS PK-3 | 1
Afzal Town Expansion(Aerial) | 1
Airport (Ghanshal village) P01 | 2
Ajmal Town,Faisal Town | 1
Ajnianwala | 1
Ajwa City_P1 | 1
Ajwa City_P2 | 1
Akari-1 | 1
Akari-2 | 1
Akari-3 | 1
Akbar Town & Laghari Colony | 1
Akhtar Town & Tarrar Road | 1
Al Barkat Villas | 1
Al Freed Garden Phase 1 | 1
Al Freed Garden Phase 2 | 1
Al Hamra | 1
Al Haram City, Hamza City Overs | 1
Al Hassan, Jamal City, Al Noor | 1
Al Hussain Garden | 1
Al Inam Gardens | 1
Al Jalil Housing P2 | 1
Al Jalil Housing P3 | 1
Al Jalil Housing P4 | 1
Al Kabeer Ph-2-Pk1 | 1
Al Kabeer Ph-2-Pk2 | 1
Al Kabeer Ph-2-Pk3 | 1
Al Kabeer Town Ph-1 | 1
Al Karam City Phase 1 | 1
Al Kareem City | 1
Al Khalil Housing Scheme | 1
Al Mansoor Town Ext. | 1
Al mansoorah colony | 1
Al Nawab Rehman Villas AlKareem | 1
Al Rahim City Ph-1 | 1
Al Rahim City Ph-2 | 1
Al Rasool Town | 1
Al Rehmat Villa | 1
Al-Hamd Society | 1
Al-Hamra City | 1
ALi + Fort + Madina | 1
Ali Ahmed Shah Colony | 1
Ali Park & Nadirabad P1 | 1
Ali Park & Nadirabad P2 | 1
Ali Tiown & New Ali Town | 1
Ali Town | 2
Alibad_Colony | 1
Alipur Chatta Road Pocket 1 | 1
Alipur Chatta Road Pocket 2 | 1
Al-Kareem Garden | 1
Allabad, AliTown & IslamPura | 1
Allama Iqbal Town, Aslam Town, | 1
Al-Majeed Housing Scheme | 1
AlNoor Exct-Haram-Garden Ph-4 | 1
AlQuresh Phase 1 | 1
AlQuresh Phase 2 | 1
Al-Rafeh Garden | 1
Al-Raheem Residencia | 1
Al-Raheems Homes | 1
Al-Rahim Garden & Crystal Homes | 1
Al-Reheem Garden | 1
Al-Rehman, Eiffel, Sultan Town | 1
Al-Rehmanpura and Zafarwal Road | 1
Aman kot | 1
Aman Society | 1
Amir Canal View, Canal Residenc | 1
Amir Street Cap Rd & Model Town | 1
Amynabad | 1
Anarkali Bazar | 1
Anwarabad Colony | 1
Arif Town, Shahzad Colony | 1
Arshad Town and Model Town | 1
Asif & Hassan Town | 1
Askari | 1
Askari 01 | 1
Askari 02 | 1
Askari 03 | 1
Askari 04 | 1
Askari 05 | 1
Askari-1 | 2
Askari-10 | 1
Askari-10 P1 | 1
Askari-10 P2 | 1
Askari-10 Sec-S | 1
Askari-11 P1 | 1
Askari-11 P2 | 1
Askari-11 P3 | 1
Askari-2 | 2
Askari-3 | 1
Askari-4 | 2
Askari-5 | 1
Askari-5 P1 | 1
Askari-5 P2 | 1
Askari-5G | 1
Askari-5H | 1
Askari-5J | 1
Askari-6 Sec 01 | 1
Askari-6 Sec 02 | 1
Askari-6 Sec 03 | 1
Askari-6 Sec 04 | 1
Askari-6 Sec 05 | 1
Askari-6 Sec 06 | 1
Askari-6 Sec 07 | 1
Askari-6 Sec 08 | 1
Askari-6 Sec 09 | 1
Askari-6 Sec 10 | 1
Askari-6 Sec 11 | 1
Askari-7 P1 | 1
Askari-7 P2 | 1
Askari-9 | 1
Askari-I | 1
Askari-II | 1
Aslam, Mujtuba & Canal Colony | 1
Atta Housing + Canal + Paradise | 1
Atta Muhammad Coloy HH To 47 Ch | 1
Aurangzaib Town | 1
Awan Chowk To Gulberg City | 1
Awan Housing Society | 1
Ayan Garden | 1
Ayub Park | 1
Ayub Park | 1
Azam Garden | 1
Azhar Colony Khara Road and Bas | 1
Aziz,Imran,Nawab,Gondl,Fjr,Srwr | 1
Azizabad | 1
B-17 Blk-D extn | 1
B-17 BlockD | 1
B-17 BlockF-P1 | 1
B-17 BlockF-P2 | 1
Bagh Mohalla & Naya Mohallla | 1
Bahadurabad & Sharfabad | 1
Bahadurpur | 1
Bahria P10 | 1
Bahria P25 | 1
Bahria P26 | 1
Bahria P3 | 1
Bahria P6 | 1
Bahria P8 | 1
Bahria P9 | 1
Bahrrian Wala | 1
Bajwa Colony | 1
Bajwa Colony, Samad Pura Road,S | 1
Bakarabad & Jughoor | 1
Bala Gujjran | 1
Band Road Extension & Makhdumpu | 1
Bangali Town | 1
Bari Chum | 1
Barkat Town | 1
Barrage Colony | 2
Barrage Officer Colony | 1
Bashir,Chuna Bhati,Jamil | 1
Bast Shor Kot | 1
Bhatti Colony | 1
Bhutta Colony | 1
Bhutto Colony | 1
Bicket Gunj | 1
Bilal City | 1
Bilal Colony & Mukhtyar Town | 1
Bismillah City & Ext | 1
Bismillah Town | 1
Bismilllah Society | 1
Block M | 1
Block N & O New City Ph2 | 1
Block P New City Ph2 | 1
Block Q | 1
Block Q New City Ph2 | 1
Block R | 1
Block R & S New City Ph2 | 1
Block U & V New City Ph2 | 1
Block W & Y New City Ph2 | 1
Block Y & Z New City Ph2 | 1
Block-A | 1
Block-B | 1
Block-C | 1
Block-D | 1
Bodla Town | 1
Bograh Ext | 1
Bonkan | 1
BOR | 1
Buch Villas Extn. | 1
Bukhari Villas | 1
C-18 | 1
Callachi Society | 1
Camp Gujran | 1
Canal & Officer & Faisal | 1
Canal Burg | 1
Canal Cantt Views | 1
Canal Garden_Canal Rd | 1
Canal Park | 1
Canal View | 3
Canal View Multan | 1
Cantt | 1
Cantt Commercial | 1
Cantt.P_1 | 1
Cantt.P_2 | 1
Cantt.P_3 | 1
Cantt_P1 | 1
Cantt_P2 | 1
Capital Rd & Model Town Ext | 1
Cavalry Ext Aerial | 1
Cavalry Ext Hybrid | 1
Center Colony | 1
Central Park Housing-P1 | 1
Central Park Housing-P2 | 1
Central Park Housing-P3 | 1
Chah Hadi Wala | 1
Chak 43 NB,Ali & Yousuf Park | 1
Chak 89 | 1
Chal Jamal | 1
Chalk no.12 | 1
Chandni Chowk | 1
Charkhana P01 | 1
Charkhana P02 | 1
Charkhana P03 | 1
Chaudary Colony | 1
Cheema Town Ph-2 | 1
Cheema Town, Permi Town | 1
Chief Residencia Housing Societ | 1
Chinar_Bagh_P01 | 1
Chinar_Bagh_P02 | 1
Chinar_Bagh_P03 | 1
Chitral City | 1
Christian Town & Muslim Town | 1
Circular Road | 2
Citi Housing Block D_E_F Extn. | 1
CITI Housing D Block | 1
CITI Housing E_F_G | 1
Citi Housing Jinnah Block-P1 | 1
Citi Housing Jinnah Block-P2 | 1
CITI Housing PH-2_Main | 1
Citi Housing Sec-A_Sectn-1 | 1
Citi Housing Sector A | 1
Citi Housing Sector B | 1
Citi Housing Sector C | 1
Citi Housing Sector D | 1
City Side P01 | 1
City Side P02 | 1
City Side P03 | 1
Civil Line Area BOQ | 1
Civil Lines | 4
Civil lines Lower End | 1
Commercial Area, Kothi Mohallah | 1
CPC Colony | 1
CTD_ANF_Police Lines_H11 | 1
Custom Preventive CHS | 1
Daman & Kilo Town | 1
Darbari, Qureshi Muhallah,Shad | 1
Darvesh P1 | 1
Darvesh P2 | 1
Dastgeer Colony | 1
DC Colony ext.PK_1 | 1
DC Colony ext.PK_2 | 1
Defence Colony | 2
Defence Housing | 1
Defence Housing Society | 1
Defence villas | 1
Derai P1 | 1
Derai P2 | 1
Derai P3 | 1
Dewan ka Bagh | 1
DHA PH-4 KK | 1
DHA Ph-4 P1 | 1
DHA Ph-4 P2 | 1
DHA PH-5 M | 1
DHA Rumanza-P1 | 1
DHA Villas | 1
DHA_Ph-1_P1 | 1
DHA_Ph-1_P2 | 1
DHA_Ph-1_P3 | 1
Dhamah,Lalazar & Railway Colony | 1
Dhorr Kot Road & Kot Fateh Din | 1
Diamond Citi P2 | 1
Diamond City_Wasi Country Park | 1
Disposal Road | 1
District Complex, Complex City | 1
DKTCC (Remaining Areas) | 1
Doctor's Colony | 1
Dream Avenue | 1
Dream City | 1
Dream Valley | 1
Dubai Town | 1
E-16 | 1
E-17 | 1
Eden Lane Villas 2 | 1
Eden Orchards | 1
Eden Villas | 1
Eid Gah, Rehmat Abbas,Kaira Muh | 1
Ejaz Town | 1
Emaar P1 | 1
Emaar P2 | 1
Emaar P3 | 1
Estate Area P2 | 1
Estate Area P3 | 1
Etihad Town | 1
F.B Area Block-21 | 1
Factory_Area | 1
Fahad Town | 1
Faisal Town P2 | 1
Faisal Town P3 | 1
Faisal Town P4 | 1
Faisal_Town | 1
Faiz Colony | 1
Falaknaz Pebbles | 1
Farid Town | 1
Fatehgarh | 1
Fatehger Ext | 1
Fatima Jinnah Town A | 1
Fatima Jinnah Town B | 1
Fatima Jinnah Town C | 1
Fatima Jinnah Town D | 1
Fatima Jinnah Town E | 1
Fatima Jinnah Town F | 1
Fatima Jinnah Town G | 1
Fatima Jinnah Town H | 1
Fatima Jinnah Town J | 1
Fauji Basti | 1
Fazaiya Society P1 | 1
Fazaiya Society P2 | 1
Fazal Sun City | 1
Fazal Town | 1
Fazil Town FDT To Khizar Masjio | 1
FB Area Block-22 | 1
FDA City_P1 | 1
FDA City_P2 | 1
FDA City_P3 | 1
Feroz Wattowan-i | 1
Ferozewala | 1
Ferozpur Road | 1
Fesco Abdullahpur | 1
Fesco Colony 132 KV | 1
FMC_Partial | 1
Fortune Arcade | 1
G magnolia Remaining Part | 1
G-11 P1 | 1
G-11 P2 | 1
G-11 P3 | 1
G-11 P4 | 1
Gaju_Khaksar_Shams Gunj | 1
Garden Town | 3
Garden Town_P1 | 1
Garden Town_P2 | 1
Garden Town_P3 | 1
Garjakh Road | 1
Ghalotian Mor | 1
Ghang | 1
Ghani Park FDT To Steel Welding | 1
Ghaziabad | 1
Ghordor Road P1 | 1
Ghordor Road P2 | 1
Ghordor Road P3 | 1
Ghordor Road P4 | 1
Ghorrdo Road | 1
Gillani Town,Tariqabad,Sufipura | 1
Gohaddpur to Ghaniabad | 1
Golf City | 1
Govt Central Model School To Th | 1
Green Acres P1 | 1
Green Acres P2 | 1
Green and Al-hafeez Town | 1
Green City Park | 1
Green Fort Housing Society | 1
Green valley | 1
Green Valley Ph-6 | 1
Green Village | 1
GT Rd Pocket 06 | 1
GT Rd Pocket 07 | 1
GT Rd Pocket 08 | 1
GT Rd Pocket 09 | 1
GT Rd Pocket 10 | 1
GT Rd Pocket 11 | 1
GT Rd Pocket 12 | 1
Gul Kada | 1
Gul zameen Colony | 1
Gulberg | 2
Gulberg & New Gulberg | 1
Gulberg City | 1
Gulberg housing Society | 1
Gulberg Town | 2
Gulberg+Ahmed+Air view | 1
Gulfam Town_Mera Muzzafar | 1
Guli Bagh | 1
Gulistan Colony | 1
Gulistan_town | 1
Gulistan-i-Ashar | 1
Gulraiz Town | 1
Gulshan Aziz Colony | 1
Gulshan Block-19 | 1
Gulshan Block-4A | 1
Gulshan Colony | 2
Gulshan e Ali | 1
Gulshan e Anwar T.Buried | 1
Gulshan e Bakhtawar Ext | 1
Gulshan e Faiz | 1
Gulshan e Haram-II | 1
Gulshan e Iqbal | 1
Gulshan e Makkah | 1
Gulshan Town Ph1 | 1
Gulshanabad P01 | 1
Gulshanabad P02 | 1
Gulshanabad P03 | 1
Gulshan-i-Ghafoor | 1
Gulshen e Yousaf & Stadium | 1
Gulshen I Azmat, Maqbool City | 1
Gulshen I Iqbal | 1
Gulshen-i-Sardar | 1
Gulzar Colony & Main Rd | 1
Gunjra Road,Bagh e Syedan & Bud | 1
Gurrah Muhallah | 1
H13_Mainly Hostels | 1
Habib Colony | 1
Habib Garden | 1
Habibpura | 1
Hafizabad Road | 2
Haider Colony | 1
Haji Park Bypass | 1
Haji Park Commercial | 1
Haji Park Phase 1 | 1
Hajipura | 1
Hamza Ali town | 1
Hamza Town | 1
Haneef Garden | 1
Haq Town | 1
Haseeb Town,Fahad Colony & Dila | 1
Hassan Town | 1
Hayat Town | 1
Heaven City | 1
Hostel City | 1
Hostel City_Extn | 1
Hunterpura Ext | 1
Hussainabad & Ghafoorabad | 1
HVTR & MB & POR & JBR | 1
Hyd Cantt P01 | 1
Hyd Cantt P02 | 1
Hyd Cantt P03 | 1
I-10 P1 | 1
I-10 P2 | 1
I-10 P3 | 1
I-10 P4 | 1
I-10 P5 | 1
I-11 Aerial | 1
I-11P1 | 1
I-11P2 | 1
I-14-P1 | 1
I-14-P2 | 1
I-14-P3 | 1
I-14-P4 | 1
I-9 P1 | 1
I-9 P2 | 1
I-9 P3 | 1
I-9 P4 | 1
Ibrahim Garden | 1
Ideal Garden Housing | 1
Ilyas Colony | 1
Inam City | 1
Indus Smart City | 1
Indus Society | 1
Indus Town | 1
Ingaroderai-Takhtaband P01 | 1
Ingaroderai-Takhtaband P02 | 1
Ingaroderai-Takhtaband P03 | 1
Ink City 02 P01 | 1
Ink City 02 P02 | 1
Ink City 02 P03 | 1
Iqbal Garden | 1
Iqbal Stadium Comm.Area | 1
Islamia Colony PK1 | 1
Islamia Colony PK2 | 1
Islamia Colony PK3 | 1
Islampura | 2
Istiqlalabad | 1
Ittehad Garden P1 | 1
Ittehad Garden P2 | 1
Ittehad Town & Other | 1
Izhar Enclave,Unknown1,Unknown2 | 1
Jail Road Bird Wood & Waris Co | 1
Jalil Town | 1
Jallianwala | 1
Jalvi Market | 1
Jandiala Sher Khan | 1
Japan Town | 2
Jatri Kohna | 1
Jhangi Qazian | 1
Jhangi Saeedan Extension | 1
Jhelum Road Buildings | 1
Jinnah City | 1
Jinnah Colony Aerial | 1
Jinnah Road | 1
Jinnah Road 2 | 1
Jinnah Town, Mohallah Islampura | 1
Judicial Colony Ph 2 | 1
K Gaardens | 1
Kabal P01 | 1
Kabal P02 | 1
Kabal P03 | 1
Kabal P04 | 1
Kabal P05 | 1
Kabal P06 | 1
Kabal P07 | 1
Kabal P08 | 1
Kabal P09 | 1
Kachari Road To Awan Colony Dep | 1
Kacheela House To Gujjar House | 1
Kachehri Area | 1
Kaghan Colony Extension | 1
Kala Gujran_P1 | 1
Kala Gujran_P2 | 1
Kala Shah Kaku | 1
Kaleem Shaheed Colony-2 | 1
Kaloke | 1
Kangra Colony P1 | 1
Kangra Colony P2 | 1
Kanju Road P01 | 1
Kanju Road P02 | 1
Kareenpura Extension | 1
Karimpura, Hajipura, SabriMuhal | 1
Karmawala | 1
Kashmir Colony 1 & 2 | 1
Kashmir Rd Jani Shop st | 1
Kassoki Road P1 | 1
Kassoki Road P2 | 1
Kasur Raiwand Road | 1
Katcheri Road | 1
Katchery Road and Allama Iqbal | 1
Kent Housing Ext. | 1
Khadim Ali Rd | 1
Khakwani Colony | 1
Khan Village II | 1
Khara Road | 1
Khara Road and Nafees Colony | 1
Kharala | 1
Khayaban e Kubra | 1
Khayaban e Sarwar | 1
Khayaban i Abid | 1
Khayaban-e-Nawab | 1
Khayaban-e-Patni CHS | 1
Khokar Colony | 1
Khokhar k_BOQ | 1
Khursheed Town | 1
Khwaja abad | 1
Khy-e-Manzoor | 1
Killi Payen | 1
Kings_ASF_ Tower_P01 | 1
Kings_ASF_ Tower_P02 | 1
Kokan CHS | 1
KOT Abdul Malik | 1
Kot Hashmat 1 & Kot Hashmat 2 | 1
Kot Sondha | 1
Kurkle Androon | 1
Labour Colony | 1
Lahore Jaranwala Road | 1
Lalazar Colony | 1
Landikas_Rang Mohalla | 1
Lasani Colony | 1
Latifabad No 04 | 1
Latifabad No 09 | 1
Latifabad No 10 | 1
Lawarance Road & China Road | 1
Layllpur Garden | 1
LC_P1 | 1
LC_P2 | 1
LC_P3 | 1
LC_P4 | 1
LC_P5 | 1
LC_P6 | 1
LC_P7 | 1
LDA_Ph-1 | 1
LDA_Ph-2 | 1
LDA_Ph-3 | 1
Liaquat Colony | 1
M3-Ind.Estate_P1 | 1
M3-Ind.Estate_P2 | 1
Madina Colony | 1
Madina Town | 3
Madras CHS | 1
Main Area P1 | 1
Main Area P2 | 1
Main Area P3 | 1
Main Bazar Mingora | 1
Main Kasur P-1 | 1
Main Kasur P-2 | 1
Main Kasur P-3 | 1
Main Kasur P-4 | 1
Main Kasur P-5 | 1
Main KKH & Lari Adda | 1
Makan Bagh | 1
Makhan_Malikyar_Kalas | 1
Makhdoomabad | 1
Makkah Town & Ali Town | 1
Malikpura | 1
Mall Road | 1
Manik Road Mohala Hussainabad | 1
Mansoora | 1
Manzoorabad | 1
Maqam Mandi | 1
Maqbool Town | 1
Marala Road & Muradpur | 1
Marhaba Canal View | 1
Marvi Town & Marvi Garden | 1
Master Citi Pk-1 | 1
Master Citi Pk-2 | 1
Master Citi Pk-3 | 1
MB Shora Colony | 1
MBCHS | 1
Meadows_I | 1
Medical Colony | 1
Mehar Farid Colony | 1
Mehar Muhallah,Weraowala,Sadiqa | 1
Metro Homes | 1
Milatabad | 1
Mirza Virkan | 1
Misc. Areas | 1
Misc.Areas Warsak | 1
Model Avenue | 1
Model City Housing | 1
Model Colony | 2
Model Town | 3
Model Town C Extension | 1
Model Town, Arfat Town | 1
MOh Bijli Ghar | 1
Moh Meera Shah Hussain | 1
Mohabatabad P1 | 1
Mohabatabad P2 | 1
Mohala Hajver Nagar Open Area | 1
Mohallah Aam Khass and Noor Sha | 1
Mohsin Town & Rasheed Avenue | 1
Montgomery Society | 1
Muhajir Colony, Old Sadiqabad | 1
Muhall Noor & Park Salamat Park | 1
Mujahid Colony, Tipu Sultan | 1
Mujahid Town_Ali Town | 1
Multan Golf City | 1
Mumtaz City P1 | 1
Mumtaz City P2 | 1
Muncipal Town, Illyas Colony, | 1
Munir Shaheed Colony | 1
Muradey Kalan | 1
Muridke | 1
Mushtaq Town | 1
Muslim Khatri CHS | 1
Muslim Town | 1
Muslimabad | 1
Mustafa , Zafar, Bismillah, Kar | 1
Mustafa Park | 1
N LHR City P1 | 1
N LHR City P2 | 1
N.Blue Ar. & Other Buildings | 1
Nadeem Park | 1
Naimat Colony | 1
Narowal Bypass to Nawab Town (C | 1
Naval ANchorage | 1
Nawab Bhatta Colony | 1
Nawab City | 1
NAYAB Colony Directors Residencies | 1
Nayab Grace City | 1
Nayyab City & Extension | 1
Nazeer Apt. | 1
Nazri Lubana | 1
New Bagh Colony | 1
New City | 1
New Defence | 1
New Model Town | 1
New Naqshband Colony | 1
New Raza Garden | 1
New Surkh Dheri | 1
New Wahdat Colony | 1
New_Muslim town | 1
Niazi Colony | 1
Nihalchand & Greenwood St | 1
NIPA Society | 1
Nisari Muhallah & Muslim Town S | 1
NMC Colony 1 | 1
Nokhar | 1
Noor Colony | 1
Noor Colony,Zamindara Housing | 1
Nowshehra Road | 1
Nowshehra Sansi Road | 1
Oasis Park Residencia | 1
Odigram P01 | 1
Odigram P02 | 1
Odigram P03 | 1
Odigram P04 | 1
Odigram P05 | 1
Odigram P06 | 1
Officer & Professor Colony_PU | 1
Officer Colony | 1
Officers Colony | 1
Officers Colony Canal Road | 1
OPF Colony | 2
Orchird Villas | 1
P1 | 4
P1 muslim town | 1
P2 | 4
P2 muslim town | 1
P3 | 4
P4 | 3
P5 | 3
P6 | 2
P9 | 1
PAEC T.Buried | 1
PAF Base Chaklala | 1
PAF Tarnol-P1 | 1
PAF Tarnol-P2 | 1
Pak China Phosphate Colony | 1
Pak Ideal CHS P1 | 1
Pak Ideal CHS P2 | 1
Palm Village | 1
Pan peer Road Societies | 1
Paradise City | 1
Paradise Complex | 1
Paragon Ideal Homes | 1
Parao Road | 1
Park View_Hybrid_P1 | 1
Park View_T.B_P2 | 1
Park View_T.B_P3 | 1
Park View_T.B_P4 | 1
Part of New Defence | 1
Pasrur Bypass , City Commercial | 1
Pasrur Rd & Skt Bypass | 1
Peeru wala Road | 1
Peerwali | 1
Peoples & Bitholdi Colony | 1
Ph-1 G & H Block | 1
Ph-1 K Block | 1
Ph-2 Q Block | 1
Ph-2 T Block | 1
Ph-3 XX Block | 1
Ph-3 Y & Z Block | 1
Ph-4 K Commercial | 1
Ph-5 K Commercial | 1
PH-7-P1 | 1
PH-7-P2 | 1
PH-7-P3 | 1
PH-7-P5 | 1
Ph-8-IVY-P1 | 1
Ph-8-IVY-P2 | 1
PH-8-P1 | 1
PH-8-P2 | 1
PH-8-P3 | 1
PH-8-P4 | 1
PH-8-P5 | 1
PH-8-P6 | 1
PH-8-P7 | 1
PH-8-P8 | 1
PHA G-11 & I12 | 1
PIB Colony | 1
PiliBheet Society | 1
Pioneer Fountain_KHI UNI | 1
Pohan Colony | 1
Posh AVenue | 1
PSW to Torkham Border | 1
Public Colony & Commercial Area | 1
Punjab Housing & NPS | 1
Punjab Small Ind. Estate | 1
Qadirabad , NoorShah Wali and K | 1
Qaiserabad | 1
Qasim Pur Colony | 1
Qasim Town | 1
Qasim Villas & Shams Colony | 1
Qazi Town | 1
Qazipura_Qadirabad Srndg Area | 1
Qila Gujjran, Rehmanpura | 1
Rahimabad_Qambar | 1
Railway Civil Lines P1 | 1
Railway Civil Lines P2 | 1
Rakh Hiran Minara | 1
Rana Shami Town & Satellite Tow | 1
Ranger Colony | 1
Rangpura Road | 1
Rao Town | 1
Raza Gardan Phase 1 & 2 | 1
Razaq Royal Ph-3_P1 | 1
Razaq Royal Ph-3_P2 | 1
Redline | 1
Rehan Gardens Ph 1&2 | 1
Rehman Avenue | 1
Rehman Colony | 1
Rehman Garden-2 Pk-1 | 1
Rehman Garden-2 Pk-2 | 1
Rehman Garden-2 Pk-3 | 1
Rehman Garden-2 Pk-4 | 1
Rehman Garden-2 Pk-5 | 1
Rehman Garden-2 Pk-6 | 1
Rehman Garden-2 Pk-7 | 1
Rehman Garden-2 Pk-8 | 1
Rehmanpura | 2
Rehmat Colony | 1
Remount Depot | 1
Ring Road P01 | 1
River Area_Hayatabad | 1
Rizwan Colony Deen Pura | 1
Road Kot | 1
Roras Road | 1
Roshan Pakistan | 1
Roshan_Noor ext._Madina_Uni | 1
Roshanabad | 1
Royal city | 1
Royal Palm City | 1
Royal Pearl Enclave | 1
Royal Residencia | 1
Royal Villas EXT. | 1
RPO Office TO Session Court Roa | 1
Rustam Colony & Mohallah | 1
Sabar Wall Colony | 1
Sabzal Road | 1
Sadabad Society | 1
Sadeeqpura | 1
Sadiqabad latifabad Wahidabad | 2
Saeedabad | 1
Safari Garden Phase 1 | 1
Safari Garden Phase 2 | 1
Safdarabad | 1
Saidu Ext | 1
Saidu Sharif P1 | 1
Saidu Sharif P2 | 1
Saif City | 1
Saima Down Town | 1
Saima Villas | 1
Saleem Town Ph-1 | 1
Salhad | 1
Salman Pura - Saleem Park | 1
Samanabad | 2
Samanabad-College Area | 1
Samarzar Housing Society | 1
Sambrial_Road | 1
Sana Valley | 1
Sanobar City | 1
Sarai Saleh | 1
Sarfaraz Colony | 1
Satellite Town | 1
Satellite Town, Aziz Town, Gill | 1
Satellite Town_PK1 | 1
Satellite Town_PK2 | 1
Satellite Town_PK3 | 1
Sattelite Town | 1
Sattellite Town | 1
Sayyam City | 1
Scheme33_MalirCantt_MDU_P01 | 1
Scheme33_MalirCantt_MDU_P02 | 1
Scheme33_MalirCantt_MDU_P03 | 1
Scheme33_MalirCantt_MDU_P04 | 1
Sector P, U, V & SPECHS | 1
Sector Q | 1
Sector R | 1
Sector S | 1
Sector T | 1
Sector W, ZA & Colonies | 1
Sector X | 1
Sector Y | 1
Sector Z | 1
SGD Bhalwal Road TO Fatima Jinn | 1
Shadab Colony | 1
Shagai & Akhon Baba P01 | 1
Shagai & Akhon Baba P02 | 1
Shah Block | 1
Shah Nawaz Grand City | 1
Shahabpura | 1
Shahabpura Main Rd | 1
Shahdara & Habib Colony | 1
Shahdara Town | 1
Shalimar City | 1
Shalimar Town | 1
Shalimar_Al Hamra Town | 1
Shamas Pur | 1
Shamsi Colony | 1
Shamsi Rd | 1
Sharifabad | 1
Shehzad Colony | 1
Sher Rabbani Town & Ghaziabad | 1
Sherwani_Shadab Hsng Scty | 1
Sialkot By Pass | 1
Sialkot Road | 1
Siraj Colony,Sukh Chain Housing | 1
Sitara City | 1
Site Area & Shanghai Tower | 1
SKT Rd Pocket 01 | 1
SKT Rd Pocket 02 | 1
SKT Rd Pocket 03 | 1
SKT Rd Pocket 04 | 1
SKT Rd Pocket 05 | 1
Small Industrial Estate | 1
Soomra Society | 1
SSGC Housing | 1
State and Middle Town | 1
Sufi City Housing Scheme PK-1 | 1
Sufi City Housing Scheme PK-2 | 1
Sui Gas Road | 1
Sui Gas Road Pk1 | 1
Sui Gas Road Pk2 | 1
Sukheke Hafizabad Road | 1
Sultan Colony | 1
Sultan Residencia Park | 1
Sultan Town | 1
Sum Sum Tower | 1
Sunny Garden | 1
Syda Gol,Faisalpur,Jogi&Qasbah& | 1
T & T Colony | 1
Taha Town | 1
Tajabad P01 | 1
Tajabad P02 | 1
Tajpura, Shalimar & Amin Twn | 1
Tameer e Hayat Colony | 1
Tanveer Town & Ratta Rd | 1
Tariq Colony | 1
Tariq Garden & Makki Road Area | 1
Thirkian,Asghar Town,Ahmad Town | 1
Tibba Qadirabad | 1
TIP Housing | 1
Towards Chitti Sheikh | 1
Towards Ugoki Mor | 1
Township_A2_P01 | 1
Township_A2_P02 | 1
Township_B1_P01 | 1
Township_B1_P02 | 1
Township_B1_P03 | 1
Township_B1_P04 | 1
Township_B2_P01 | 1
Township_B2_P02 | 1
Township_C1_BL03 | 1
Township_C2_BL03 | 1
Tulip City | 1
University Town | 1
University Town P1 | 1
University Town P2 | 1
Unknown 01 | 1
Unknown Society _ 4 | 1
Unknown Society _ 5 | 1
Unknown Society _3 | 1
Unknown Society 10 | 1
Unknown Society 13 | 1
Unknown Society 14-P1 | 1
Unknown Society 14-P2 | 1
Unknown Society 14-P3 | 1
Unknown Society 14-P4 | 1
Unknown Society 2 & Iqbal Town | 1
Unknown Society 20 | 1
Unknown Society 21 | 1
Unknown Society 3 | 1
Unknown Society 5 | 1
Unknown Society 9 | 1
Unknown Society_11 | 1
Unknown Society_12 | 1
Unknown Society_22 | 1
Unknown Society_23 | 1
Unknown-1 | 1
Unknown-2 | 1
Unkown Area 2 | 1
Unkown Area 3 | 1
Unkown Area 4 | 1
Unkown Area 6 | 1
Unkown Society 1 | 1
Unkown Society 15 | 1
Unkown Society 16 | 1
Unkown Society 17 | 1
Unkown Society 18 | 1
Unkown Society 19 | 1
Unkown Society 2 | 1
Unkown Society 24 | 1
Unkown Society 6 | 1
Unkown Society 7 | 1
Unkown Society 8 | 1
Usman Trade City | 1
Usmania Village | 1
Village garden | 1
VIP Housing | 1
Wafaqi Colony | 1
Wafay Citi GG Block | 1
Waffay Block Rem.Area | 1
Wapda Colony | 1
Wapda Town | 1
Warriach Town & Arian Colony | 1
Warsak Rd Ext. P1 | 1
Warsak Rd Ext. P2 | 1
Warsak Rd Ext. P3 | 1
Warsak Rd Ext. P4 | 1
Warsak Rd Ext. P5 | 1
Warsak Rd Ext. P6 | 1
Warsak Rd Ext. P7 | 1
Water Board Society | 1
Western Fort | 1
Willoughby Road appartments | 1
Wocland | 1
Writers Colony | 1
Ya Rehman Society | 1
Younas Town | 1
Z Block NST & Services Colony | 1
Zafar Colony | 1
Zafarwal | 1
Zahoor Elahi Road | 1
Zahoor Orchard | 1
Zahoor Orchard Town | 1
Zakariya Villas | 1
Zakria Garden,Unknown 3-4, | 1
Zam Zam City | 1
Zamzam Garden,Jeevan City | 1
Zuabir Colony | 1
DHA Sector A ( Villas ) | 1
Bagga | 1
Chitan | 1
Eid Gah | 1
Gharmala | 1
Gujjar pur | 1
Kantrila | 1
Kantrili | 1
Kotli Allahyar | 1
Saeela | 1
Gharmala Monan | 1
Jahangir | 1
Jhakkarr | 1
Chak Hafizan | 1
Chak Doulat | 1
Ranjha Mahira | 1
Muftian | 1
Chak Akka | 1
Thatti Gujran & Mughlan | 1
Al Hafeez Garden Ph-5 | 1
Al Hafeez Gdn Ph-2 | 1
Al Raheem Gdn Ph-2 Extn. | 1
Tariq Garden | 1
P4-Citi Housing | 1
P1, Extended Part | 1
PK01 | 1
PK02 | 1
PK03 | 1
PK04 | 1
PK05 | 1
High Court Society | 1
Al Rehman Garden 4 | 1
Palm City | 1
PK-01 | 1
PK-02 | 1
Rahbr-Sec-1-P1 | 1
Rahbr-Sec-1-P2 | 1
Rahbr-Sec-2-P1 | 1
Rahbr-Sec-2-P2 | 1
Darussalam Society | 1
Lucknow Society | 1
Dadabhoy Town | 1
SHFT Pocket-1 | 1
SHFT Pocket-2 | 1
SHFT Pocket-3 | 1
SHFT Pocket-4 | 1
SHFT Pocket-5 | 1
TariqBinZayed | 1
Gulshan-e-Rafi | 1
Salman Gardens | 1
Anwar-e-Ibrahim | 1
Rafi Gardens_Gulshan e Muneer | 1
M.Ali Shaheed Society_Maaz Town | 1
Punjabi Sodagran Society | 1
Shamsi Society | 1
Bilal Town | 1
Alfalah Society | 1
Rafah-e-Aam Society | 1
Hansabad | 1
Bagh-e-Malir | 1
Gulshan-e-Tayyaba | 1
Gohar Green | 1
Kazimabad | 1
Surti_Humaira_Jami | 1
Alamgir&Jannat ul Barkat | 1
Pak Kausar Town | 1
Darakhshan Society PK1 | 1
Darakhshan Society PK2 | 1
Millat Garden | 1
NewSukkurCityTownship | 1
Unknown 11 | 1
Sukkur Township Pocket 1 | 1
Sukkur Township P-2_KingCrystl2 | 1
Golimar Area | 1
Sachal Township_Kings Crystal | 1
Shikarpur Rd | 1
100 Feet Rd P1 | 1
100 Feet Rd P2 | 1
Sukkur Ind Area | 1
Unknonwn_1 | 1
Unknown 03 | 1
Main City P1 | 1
Main City P2 | 1
Petaro | 1
Pocket-1 | 1
Pocket-2 | 1
Pocket-3 | 1
Pocket-4 | 1
Pocket-5 | 1
Pocket-6 | 1
Pocket-7 | 1
Al Hafeez Garden Ph-1 | 1
Shia Bagh & BUH Qambar P01 | 1
Shia Bagh & BUH Qambar P02 | 1
Grand Total | 1150

## Feasibilities
Number of CEMs | 97
Row Labels | Count of Fesibility Name | CEM Number
100 | 31 | 100
102 | 28 | 102
103 | 21 | 103
104 | 12 | 104
105 | 35 | 105
106 | 22 | 106
107 | 8 | 107
108 | 25 | 108
109 | 6 | 109
110 | 30 | 110
111 | 1 | 111
112 | 44 | 112
I240188 | 3 | I240188 | Row Labels | Sum of Allocated Budget
I240189 | 2 | I240189 | 100 | 415670312.3488
I240190 | 4 | I240190 | 102 | 252576804.9885
I240435 | 4 | I240435 | 103 | 190914712.4087
I240437 | 10 | I240437 | 104 | 189189403.5922
I240438 | 12 | I240438 | 105 | 277182368.4801
I240440 | 11 | I240440 | 106 | 528922932.5858
I240442 | 2 | I240442 | 107 | 151789539.3189
I240459 | 2 | I240459 | 108 | 303045745.7902
I240518 | 5 | I240518 | 109 | 324998966.7491
I240519 | 5 | I240519 | 110 | 274744690.9635
I240537 | 5 | I240537 | 111 | 16500000
I240538 | 12 | I240538 | 112 | 350433922.1714
I240539 | 12 | I240539 | I240188 | 92903745.7859 | Actual Incurred | Required Budget to Complete the Remaining Work | Net Savings
I240540 | 21 | I240540 | I240189 | 122769785.1659 | 6167069.33 | #N/A | #N/A
I240557 | 2 | I240557 | I240190 | 116050375.6403 | 26612784.95 | #N/A | #N/A
I240678 | 30 | I240678 | I240435 | 216855243.0449 | 4752709.86 | #N/A | #N/A
I240679 | 5 | I240679 | I240437 | 235442928.2027 | 5720633.14 | 5280950.325 | 41485727.7555
I240680 | 10 | I240680 | I240438 | 166199842.5434 | 23696324.88 | 20187657.4254 | 55733688.4823
I240681 | 2 | I240681 | I240440 | 329748933.5319 | 58998585.84 | 411918493.31 | 146310669.2094
I240682 | 33 | I240682 | I240442 | 107457482.0098 | 34791383.43 | 126777815.9816 | 523500411.518
I240683 | 4 | I240683 | I240459 | 11499005.0092 | 46257089.13 | 341774417.7819 | 7477903.339
I240684 | 6 | I240684 | I240518 | 95923257.2667 | 198713654.95 | 44427721.8334 | -35199721.165
I240700 | 28 | I240700 | I240519 | 279383829.3071
I240701 | 4 | I240701 | I240537 | 19408588.4126
I240702 | 24 | I240702 | I240538 | 142727305.6595
I240703 | 37 | I240703 | I240539 | 233756231.296
I240704 | 34 | I240704 | I240540 | 161143296.2584
I240705 | 34 | I240705 | I240557 | 18684458.866
I240782 | 1 | I240782 | I240678 | 355735547.8042
I250114 | 1 | I250114 | I240679 | 10311892.5
I250201 | 2 | I250201 | I240680 | 111071445.702
I250202 | 3 | I250202 | I240681 | 12569175
I250203 | 1 | I250203 | I240682 | 537412507.4316
I250205 | 7 | I250205 | I240683 | 57392829.4625
I250206 | 43 | I250206 | I240684 | 57875688.609
I250207 | 3 | I250207 | I240700 | 552717264.2608
I250208 | 3 | I250208 | I240701 | 11665905
I250209 | 7 | I250209 | I240702 | 201783051.7853
I250210 | 16 | I250210 | I240703 | 768605468.5102
I250211 | 3 | I250211 | I240704 | 507998709.3732
I250212 | 25 | I250212 | I240705 | 445686125.3829
I250213 | 6 | I250213 | I240782 | 125214350
I250298 | 5 | I250298 | I250114 | 36812251.6233
I250307 | 1 | I250307 | I250201 | 42698611.2205
I250326 | 3 | I250326 | I250202 | 23458996.9509
I250327 | 13 | I250327 | I250203 | 9236314.051
I250374 | 4 | I250374 | I250205 | 98131628.0112
I250375 | 4 | I250375 | I250206 | 238190943.4392
I250376 | 17 | I250376 | I250207 | 27226772.7085
I250377 | 12 | I250377 | I250208 | 40848462.1145
I250378 | 7 | I250378 | I250209 | 83070900.7051
I250379 | 2 | I250379 | I250210 | 148493354.984
I250380 | 9 | I250380 | I250211 | 45065968.9
I250681 | 3 | I250681 | I250212 | 220504163.0685
I250734 | 25 | I250734 | I250213 | 37620029.3976
I250737 | 7 | I250737 | I250298 | 76622670.7877
I260060 | 1 | I260060 | I250307 | 517994073.7885
I260061 | 18 | I260061 | I250326 | 23074220.3052
I260068 | 24 | I260068 | I250327 | 446507712.3593
I260105 | 4 | I260105 | I250374 | 1724390
I260159 | 2 | I260159 | I250375 | 45089308.4162
I260160 | 7 | I260160 | I250376 | 429014710.9296
I260179 | 1 | I260179 | I250377 | 139812094.6044
I260180 | 2 | I260180 | I250378 | 66122759.5419
I260208 | 4 | I260208 | I250379 | 26011896.0433
I260294 | 3 | I260294 | I250380 | 264276103.9974
I260295 | 28 | I260295 | I250681 | 26064968.0335
I260296 | 15 | I260296 | I250734 | 177365323.0045
I260298 | 1 | I260298 | I250737 | 357297930.2508
I260361 | 8 | I260361 | I260060 | 12342069.5
INT-21-00315 | 35 | INT-21-00315 | I260061 | 56110698.1709
INT-23-00435 | 8 | INT-23-00435 | I260068 | 1568646315.7955
INT-23-00436 | 4 | INT-23-00436 | I260105 | 115899688.284
INT-23-00437 | 14 | INT-23-00437 | I260159 | 65790324.28
INT-23-00438 | 1 | INT-23-00438 | I260160 | 290026668.2352
INT-23-00439 | 40 | INT-23-00439 | I260179 | 13587284.5
INT-23-00440 | 9 | INT-23-00440 | I260180 | 74086466.5312
INT-23-00441 | 3 | INT-23-00441 | I260208 | 180535787.0047
INT-23-00442 | 2 | INT-23-00442 | I260294 | 37880389.6381
INT-23-00444 | 15 | INT-23-00444 | I260295 | 284896561.6578
INT-23-00445 | 2 | INT-23-00445 | I260296 | 184540160.0914
INT-23-00446 | 7 | INT-23-00446 | I260298 | 7276483.8012
INT-23-00447 | 13 | INT-23-00447 | I260361 | 297374857.408
INT-23-00764 | 20 | INT-23-00764 | INT-21-00315 | 715213941.5258
Grand Total | 1150 |  | INT-23-00435 | 86670915.9045
|  |  | INT-23-00436 | 38125384.4933
|  |  | INT-23-00437 | 166094035.1767
|  |  | INT-23-00438 | 12265711.807
|  |  | INT-23-00439 | 421676787.8032
|  |  | INT-23-00440 | 34497804.8325
|  |  | INT-23-00441 | 110203835.3157
|  |  | INT-23-00442 | 19658577.5882
|  |  | INT-23-00444 | 141455045.6184
|  |  | INT-23-00445 | 19830973.56
|  |  | INT-23-00446 | 143930927.722
|  |  | INT-23-00447 | 167263875.1936
|  |  | INT-23-00764 | 284852412.1435
|  |  | Grand Total | 18581034211.0381

## ODN Remarks Grouped (hidden)
Row Labels | Count of Fesibility Name
Feeders/Trans | 223
Permenant Budget Removal | 43
Swap Cases | 33
Live - As per Plan | 513
Not Live - Permission Issues | 27
Not Live - Others Reasons | 18
Temporary Budget Removal | 19
Live - Permission Awaited | 13
Not Live - Work in Progress (WIP) | 100
Not Live - Work to be initiated | 384
Grand Total | 1373

## Actuals (W) (hidden)
| CEM | 12 | [5 empty] | Upper Limit | Lower Limit
CEM Number not generated | 100 | INT-21-00315 | I240188 | I240188 | 9 | 9 | 9 | I240188001 | I240188999 | 1
CEM Number not generated | 102 | INT-23-00435 | I240189 | I240189 | 9 | 9 | 9 | I240189001 | I240189999 | 2
CEM Number not generated | 103 | INT-23-00436 | I240190 | I240190 | 9 | 9 | 9 | I240190001 | I240190999 | 3
CEM Number not generated | 104 | INT-23-00437 | I240435 | I240435 | 9 | 9 | 9 | I240435001 | I240435999 | 4
CEM Number not generated | 105 | INT-23-00438 | I240437 | I240437 | 9 | 9 | 9 | I240437001 | I240437999 | 5
CEM Number not generated | 106 | INT-23-00439 | I240438 | I240438 | 9 | 9 | 9 | I240438001 | I240438999 | 6
CEM Number not generated | 107 | INT-23-00440 | I240440 | I240440 | 9 | 9 | 9 | I240440001 | I240440999 | 7
CEM Number not generated | 108 | INT-23-00441 | I240442 | I240442 | 9 | 9 | 9 | I240442001 | I240442999 | 8
CEM Number not generated | 109 | INT-23-00442 | I240459 | I240459 | 9 | 9 | 9 | I240459001 | I240459999 | 9
CEM Number not generated | 110 | INT-23-00444 | I240518 | I240518 | 9 | 9 | 9 | I240518001 | I240518999 | 10
CEM Number not generated | 111 | INT-23-00445 | I240519 | I240519 | 9 | 9 | 9 | I240519001 | I240519999 | 11
CEM Number not generated | 112 | INT-23-00446 | I240537 | I240537 | 9 | 9 | 9 | I240537001 | I240537999 | 12
|  | INT-23-00447 | I240538 | I240538 | 9 | 9 | 9 | I240538001 | I240538999 | 13
|  | INT-23-00764 | I240539 | I240539 | 9 | 9 | 9 | I240539001 | I240539999 | 14
|  |  | I240540 | I240540 | 9 | 9 | 9 | I240540001 | I240540999 | 15
|  |  | I240557 | I240557 | 9 | 9 | 9 | I240557001 | I240557999 | 16
|  |  | I240678 | I240678 | 9 | 9 | 9 | I240678001 | I240678999 | 17
|  |  | I240679 | I240679 | 9 | 9 | 9 | I240679001 | I240679999 | 18
|  |  | I240680 | I240680 | 9 | 9 | 9 | I240680001 | I240680999 | 19
|  |  | I240681 | I240681 | 9 | 9 | 9 | I240681001 | I240681999 | 20
|  |  | I240682 | I240682 | 9 | 9 | 9 | I240682001 | I240682999 | 21
|  |  | I240683 | I240683 | 9 | 9 | 9 | I240683001 | I240683999 | 22
|  |  | I240684 | I240684 | 9 | 9 | 9 | I240684001 | I240684999 | 23
|  |  | I240700 | I240700 | 9 | 9 | 9 | I240700001 | I240700999 | 24
|  |  | I240701 | I240701 | 9 | 9 | 9 | I240701001 | I240701999 | 25
|  |  | I240702 | I240702 | 9 | 9 | 9 | I240702001 | I240702999 | 26
|  |  | I240703 | I240703 | 9 | 9 | 9 | I240703001 | I240703999 | 27
|  |  | I240704 | I240704 | 9 | 9 | 9 | I240704001 | I240704999 | 28
|  |  | I240705 | I240705 | 9 | 9 | 9 | I240705001 | I240705999 | 29
|  |  | I240782 | I240782 | 9 | 9 | 9 | I240782001 | I240782999 | 30
|  |  | I250114 | I250114 | 9 | 9 | 9 | I250114001 | I250114999 | 31
|  |  | I250201 | I250201 | 9 | 9 | 9 | I250201001 | I250201999 | 32
|  |  | I250202 | I250202 | 9 | 9 | 9 | I250202001 | I250202999 | 33
|  |  | I250203 | I250203 | 9 | 9 | 9 | I250203001 | I250203999 | 34
|  |  | I250205 | I250205 | 9 | 9 | 9 | I250205001 | I250205999 | 35
|  |  | I250206 | I250206 | 9 | 9 | 9 | I250206001 | I250206999 | 36
|  |  | I250207 | I250207 | 9 | 9 | 9 | I250207001 | I250207999 | 37
|  |  | I250208 | I250208 | 9 | 9 | 9 | I250208001 | I250208999 | 38
|  |  | I250209 | I250209 | 9 | 9 | 9 | I250209001 | I250209999 | 39
|  |  | I250210 | I250210 | 9 | 9 | 9 | I250210001 | I250210999 | 40
|  |  | I250211 | I250211 | 9 | 9 | 9 | I250211001 | I250211999 | 41
|  |  | I250212 | I250212 | 9 | 9 | 9 | I250212001 | I250212999 | 42
|  |  | I250213 | I250213 | 9 | 9 | 9 | I250213001 | I250213999 | 43
|  |  | I250298 | I250298 | 9 | 9 | 9 | I250298001 | I250298999 | 44
|  |  | I250307 | I250307 | 9 | 9 | 9 | I250307001 | I250307999 | 45
|  |  | I250326 | I250326 | 9 | 9 | 9 | I250326001 | I250326999 | 46
|  |  | I250327 | I250327 | 9 | 9 | 9 | I250327001 | I250327999 | 47
|  |  | I250374 | I250374 | 9 | 9 | 9 | I250374001 | I250374999 | 48
|  |  | I250375 | I250375 | 9 | 9 | 9 | I250375001 | I250375999 | 49
|  |  | I250376 | I250376 | 9 | 9 | 9 | I250376001 | I250376999 | 50
|  |  | I250377 | I250377 | 9 | 9 | 9 | I250377001 | I250377999 | 51
|  |  | I250378 | I250378 | 9 | 9 | 9 | I250378001 | I250378999 | 52
|  |  | I250379 | I250379 | 9 | 9 | 9 | I250379001 | I250379999 | 53
|  |  | I250380 | I250380 | 9 | 9 | 9 | I250380001 | I250380999 | 54
|  |  | I250681 | I250681 | 9 | 9 | 9 | I250681001 | I250681999 | 55
|  |  | I250734 | I250734 | 9 | 9 | 9 | I250734001 | I250734999 | 56
|  |  | I250737 | I250737 | 9 | 9 | 9 | I250737001 | I250737999 | 57
|  |  | I260060 | I260060 | 9 | 9 | 9 | I260060001 | I260060999 | 58
|  |  | I260061 | I260061 | 9 | 9 | 9 | I260061001 | I260061999 | 59
|  |  | I260068 | I260068 | 9 | 9 | 9 | I260068001 | I260068999 | 60
|  |  | I260105 | I260105 | 9 | 9 | 9 | I260105001 | I260105999 | 61
|  |  | I260159 | I260159 | 9 | 9 | 9 | I260159001 | I260159999 | 62
|  |  | I260160 | I260160 | 9 | 9 | 9 | I260160001 | I260160999 | 63
|  |  | I260179 | I260179 | 9 | 9 | 9 | I260179001 | I260179999 | 64
|  |  | I260180 | I260180 | 9 | 9 | 9 | I260180001 | I260180999 | 65
|  |  | I260208 | I260208 | 9 | 9 | 9 | I260208001 | I260208999 | 66
|  |  | I260294 | I260294 | 9 | 9 | 9 | I260294001 | I260294999 | 67
|  |  | I260295 | I260295 | 9 | 9 | 9 | I260295001 | I260295999 | 68
|  |  | I260296 | I260296 | 9 | 9 | 9 | I260296001 | I260296999 | 69
|  |  | I260298 | I260298 | 9 | 9 | 9 | I260298001 | I260298999 | 70
|  |  | I260361 | I260361 | 9 | 9 | 9 | I260361001 | I260361999 | 71

## Allocated Budget Check (hidden)
Row Labels | Sum of Allocated Budget |  |  | Row Labels | Sum of Allocated Budget | Data Bank | Var | Row Labels | Sum of Allocated Budget (Fig in Rs.)
100 | 518998173.5488 | 100 | 518998173.5488 | I240188 | 108159630.7859 | 108159630.7859 | 0 | I250734 | 214988457.4045
102 | 320950492.9885 | 102 | 320950492.9885 | I240189 | 128620785.1659 | 128620785.1659 | 0 | I260060 | 25004869.5
103 | 264880241.6587 | 103 | 264880241.6587 | I240190 | 133827375.6403 | 133827375.6403 | 0 | I260061 | 107159247.7709
104 | 201467753.5922 | 104 | 201467753.5922 | I240435 | 248499863.0449 | 248499863.0449 | 0 | I260105 | 119641188.284
105 | 469213284.4801 | 105 | 469213284.4801 | I240437 | 285986428.2027 | 285986428.2027 | 0 | I260159 | 67815324.28
106 | 537922932.5858 | 106 | 537922932.5858 | I240438 | 197850142.5434 | 197850142.5434 | 0 | I260160 | 321563528.2352
107 | 207441341.7189 | 107 | 207441341.7189 | I240440 | 380747283.5319 | 380747283.5319 | 0 | I260179 | 17688934.5
108 | 399657325.7902 | 108 | 399657325.7902 | I240442 | 120824652.0098 | 120824652.0098 | 0 | I260180 | 122128866.5312
109 | 324998966.7491 | 109 | 324998966.7491 | I240459 | 12138005.0092 | 12138005.0092 | 0 | I260208 | 187392787.0047
110 | 299162106.9635 | 110 | 299162106.9635 | I240518 | 112050607.2667 | 112050607.2667 | 0 | I260294 | 41609589.6381
111 | 16500000 | 111 | 16500000 | I240519 | 297581509.3071 | 297581509.3071 | 0 | I260295 | 433500061.6578
112 | 419021550.1714 | 112 | 419021550.1714 | I240537 | 23356438.4126 | 23356438.4126 | 0 | I260296 | 272350044.0914
I240188 | 108159630.7859 |  |  | I240538 | 202480325.6595 | 202480325.6595 | 0 | I260298 | 10770638.8012
I240189 | 128620785.1659 |  | 3980214170.2472 | I240539 | 262661971.296 | 262661971.296 | 0 | I260361 | 307110957.408
I240190 | 133827375.6403 |  | 18115495584.3563 | I240540 | 199830616.2584 | 199830616.2584 | 0 | N/A | 448372018.5452
I240435 | 248499863.0449 |  | 22095709754.6035 | I240557 | 20127458.866 | 20127458.866 | 0 | I240188 | 108159630.7859
I240437 | 285986428.2027 |  |  | I240678 | 414713991.8042 | 414713991.8042 | 0 | I240189 | 128620785.1659
I240438 | 197850142.5434 |  |  | I240679 | 10311892.5 | 10311892.5 | 0 | I240190 | 133827375.6403
I240440 | 380747283.5319 |  |  | I240680 | 133968445.702 | 133968445.702 | 0 | I240435 | 248499863.0449
I240442 | 120824652.0098 |  | 18566058037.9015 | I240681 | 12569175 | 12569175 | 0 | I240437 | 285986428.2027
I240459 | 12138005.0092 |  |  | I240682 | 626675307.4316 | 626675307.4316 | 0 | I240438 | 197850142.5434
I240518 | 112050607.2667 |  |  | I240683 | 79640275.4625 | 79640275.4625 | 0 | I240440 | 380747283.5319
I240519 | 297581509.3071 |  |  | I240684 | 69792468.609 | 69792468.609 | 0 | I240442 | 120824652.0098
I240537 | 23356438.4126 |  |  | I240700 | 672588564.2608 | 672588564.2608 | 0 | I240459 | 12138005.0092
I240538 | 202480325.6595 |  |  | I240701 | 15078455 | 15078455 | 0 | I240518 | 112050607.2667
I240539 | 262661971.296 |  |  | I240702 | 233184378.5853 | 233184378.5853 | 0 | I240519 | 297581509.3071
I240540 | 199830616.2584 |  |  | I240703 | 861306256.5102 | 861306256.5102 | 0 | I240537 | 23356438.4126
I240557 | 20127458.866 |  |  | I240704 | 640727539.3732 | 640727539.3732 | 0 | I240538 | 202480325.6595
I240678 | 414713991.8042 |  |  | I240705 | 526845585.3829 | 526845585.3829 | 0 | I240539 | 262661971.296
I240679 | 10311892.5 |  |  | I240782 | 125214350 | 125214350 | 0 | I240540 | 199830616.2584
I240680 | 133968445.702 |  |  | I250114 | 38144251.6233 | 38144251.6233 | 0 | I240557 | 20127458.866
I240681 | 12569175 |  |  | I250201 | 47592961.2205 | 47592961.2205 | 0 | I240678 | 414713991.8042
I240682 | 626675307.4316 |  |  | I250202 | 27034446.9509 | 27034446.9509 | 4.8429e-08 | I240679 | 10311892.5
I240683 | 79640275.4625 |  |  | I250203 | 13662314.051 | 13662314.051 | 0 | I240680 | 133968445.702
I240684 | 69792468.609 |  |  | I250205 | 115636928.0112 | 115636928.0112 | 0 | I240681 | 12569175
I240700 | 672588564.2608 |  |  | I250206 | 348988241.8392 | 351178676.8392 | 0 | I240682 | 626675307.4316
I240701 | 15078455 |  |  | I250207 | 31957072.7085 | 31957072.7085 | 0 | I240683 | 79640275.4625
I240702 | 233184378.5853 |  |  | I250208 | 52865210.1145 | 52865210.1145 | 0 | I240684 | 69792468.609
I240703 | 861306256.5102 |  |  | I250209 | 130681950.7051 | 130681950.7051 | 0 | I240700 | 672588564.2608
I240704 | 640727539.3732 |  |  | I250210 | 192623788.984 | 192623788.984 | 0 | I240701 | 15078455
I240705 | 526845585.3829 |  |  | I250211 | 49430718.9 | 49430718.9 | 0 | I240702 | 233184378.5853
I240782 | 125214350 |  |  | I250212 | 285944485.0685 | 285944485.0685 | 0 | I240703 | 861306256.5102
I250114 | 38144251.6233 |  |  | I250213 | 49354039.3976 | 49354039.3976 | 0 | I240704 | 640727539.3732
I250201 | 47592961.2205 |  |  | I250298 | 88120170.7877 | 88120170.7877 | 0 | I240705 | 526845585.3829
I250202 | 27034446.9509 |  |  | I250307 | 517994073.7885 | 517994073.7885 | 4.7684e-07 | I240782 | 125214350
I250203 | 13662314.051 |  |  | I250326 | 26408470.3052 | 26408470.3052 | 0 | I250114 | 38144251.6233
I250205 | 115636928.0112 |  |  | I250327 | 531867730.3593 | 531867730.3593 | 0 | I250201 | 47592961.2205
I250206 | 348988241.8392 |  |  | I250374 | 1724390 | 1724390 | 0 | I250202 | 27034446.9509
I250207 | 31957072.7085 |  |  | I250375 | 57537758.4162 | 57537758.4162 | 0 | I250203 | 13662314.051
I250208 | 52865210.1145 |  |  | I250376 | 557042160.9296 | 557042160.9296 | 0 | I250205 | 115636928.0112
I250209 | 130681950.7051 |  |  | I250377 | 210835494.6044 | 210835494.6044 | 0 | I250206 | 351178676.8392
I250210 | 192623788.984 |  |  | I250378 | 111427799.5419 | 111427799.5419 | 0 | I250207 | 31957072.7085
I250211 | 49430718.9 |  |  | I250379 | 47229040.8433 | 47229040.8433 | 0 | I250208 | 52865210.1145
I250212 | 285944485.0685 |  |  | I250380 | 283707294.9974 | 283707294.9974 | 0 | I250209 | 130681950.7051
I250213 | 49354039.3976 |  |  | I250681 | 95594354.869 | 95594354.869 | 0 | I250210 | 192623788.984
I250298 | 88120170.7877 |  |  | I250734 | 214988457.4045 | 214988457.4045 | 0 | I250211 | 49430718.9
I250307 | 517994073.7885 |  |  | I250737 | 376403670.2508 | 376403670.2508 | 0 | I250212 | 285944485.0685
I250326 | 26408470.3052 |  |  | I260060 | 25004869.5 | 25004869.5 | 0 | I250213 | 49354039.3976
I250327 | 531867730.3593 |  |  | I260061 | 107159247.7709 | 107159247.7709 | 0 | I250298 | 88120170.7877
I250374 | 1724390 |  |  | I260068 | 1635462937.7955 | 1635462937.7955 | 0 | I250307 | 517994073.7885
I250375 | 57537758.4162 |  |  | I260105 | 119641188.284 | 119641188.284 | 0 | I250326 | 26408470.3052
I250376 | 557042160.9296 |  |  | I260159 | 67815324.28 | 67815324.28 | 0 | I250327 | 531867730.3593
I250377 | 210835494.6044 |  |  | I260160 | 321563528.2352 | 321563528.2352 | 0 | I250374 | 1724390
I250378 | 111427799.5419 |  |  | I260179 | 17688934.5 | 17688934.5 | 0 | I250375 | 57537758.4162
I250379 | 47229040.8433 |  |  | I260180 | 122128866.5312 | 122128866.5312 | 0 | I250376 | 557042160.9296
I250380 | 283707294.9974 |  |  | I260208 | 187392787.0047 | 187392787.0047 | 0 | I250377 | 210835494.6044
I250681 | 95594354.869 |  |  | I260294 | 41609589.6381 | 41609589.6381 | 0 | I250378 | 111427799.5419
I250734 | 214988457.4045 |  |  | I260295 | 433500061.6578 | 433500061.6578 | 0 | I250379 | 47229040.8433
I250737 | 376403670.2508 |  |  | I260296 | 272350044.0914 | 272350044.0914 | 0 | I250380 | 283707294.9974
I260060 | 25004869.5 |  |  | I260298 | 10770638.8012 | 10770638.8012 | 0 | I250681 | 95594354.869
I260061 | 107159247.7709 |  |  | I260361 | 307110957.408 | 307110957.408 | 0 | I250737 | 376403670.2508
I260068 | 1635462937.7955 |  |  | INT-21-00315 | 761753116.5258 | 761753116.5258 | 0 | I260068 | 1635462937.7955
I260105 | 119641188.284 |  |  | INT-23-00435 | 108087915.9045 | 108087915.9045 | 0 | INT-21-00315 | 761753116.5258
I260159 | 67815324.28 |  |  | INT-23-00436 | 51381436.4933 | 51381436.4933 | 0 | INT-23-00435 | 108087915.9045
I260160 | 321563528.2352 |  |  | INT-23-00437 | 200389603.1767 | 200389603.1767 | 0 | INT-23-00436 | 51381436.4933
I260179 | 17688934.5 |  |  | INT-23-00438 | 13329311.807 | 13329311.807 | -2.0489e-08 | INT-23-00437 | 200389603.1767
I260180 | 122128866.5312 |  |  | INT-23-00439 | 484250707.8032 | 484250707.8032 | 0 | INT-23-00438 | 13329311.807
I260208 | 187392787.0047 |  |  | INT-23-00440 | 53663374.8325 | 53663374.8325 | 0 | INT-23-00439 | 484250707.8032
I260294 | 41609589.6381 |  |  | INT-23-00441 | 124440455.3157 | 124440455.3157 | 0 | INT-23-00440 | 53663374.8325
I260295 | 433500061.6578 |  |  | INT-23-00442 | 42564737.5882 | 42564737.5882 | 0 | INT-23-00441 | 124440455.3157
I260296 | 272350044.0914 |  |  | INT-23-00444 | 175798350.6184 | 175798350.6184 | 0 | INT-23-00442 | 42564737.5882
I260298 | 10770638.8012 |  |  | INT-23-00445 | 36865953.56 | 36865953.56 | 0 | INT-23-00444 | 175798350.6184
I260361 | 307110957.408 |  |  | INT-23-00446 | 167455820.522 | 167455820.522 | 0 | INT-23-00445 | 36865953.56
INT-21-00315 | 761753116.5258 |  |  | INT-23-00447 | 214116397.2736 | 214116397.2736 | 0 | INT-23-00446 | 167455820.522
INT-23-00435 | 108087915.9045 |  |  | INT-23-00764 | 350042372.1435 | 350042372.1435 | 0 | INT-23-00447 | 214116397.2736
INT-23-00436 | 51381436.4933 | [6 empty] | INT-23-00764 | 350042372.1435
INT-23-00437 | 200389603.1767
INT-23-00438 | 13329311.807
INT-23-00439 | 484250707.8032
INT-23-00440 | 53663374.8325
INT-23-00441 | 124440455.3157
INT-23-00442 | 42564737.5882
INT-23-00444 | 175798350.6184
INT-23-00445 | 36865953.56
INT-23-00446 | 167455820.522
INT-23-00447 | 214116397.2736
INT-23-00764 | 350042372.1435
Grand Total | 22095709754.6035

## Timeline Tracking (hidden)
Total Cases | 1373
Completed | 530
In Progress | 98
Not Started | 745

## Heatmap (hidden)
| 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01
100 Feet Rd P1 | bar: 2026-03-01 to 2026-04-01
100 Feet Rd P2 | bar: 2026-03-01 to 2026-04-01
1-4L | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
18_P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
18_P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24F Cable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 Marla Scheme | bar: 2026-03-01 to 2026-04-01
Adam Housing-P1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Adam Housing-P2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Abdullah Colony & Nawa Killy | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Abdullah Sports Tower Ext | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2
Al Hussain Garden | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Abid Market | bar: 2026-03-01
AbrazulMinal_KingsBridgeView | bar: 2026-03-01 to 2026-04-01
Adam Housing | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al Inam Gardens | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Canal View | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
AFOHS PK-1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
AFOHS PK-2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
AFOHS PK-3 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Afzal Town Expansion(Aerial) | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Airport (Ghanshal village) P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Airport (Ghanshal village) P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
CPC Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Dream City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Ajwa City_P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ajwa City_P2 | bar: 2026-03-01 to 2026-04-01
Etihad Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ferozpur Road | bar: 2026-03-01 to 2026-04-01
Ejaz Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Al Barkat Villas | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Al Freed Garden Phase 1 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2
Al Freed Garden Phase 2 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2
Al Hafeez Garden Ph-1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
Al Hafeez Garden Ph-5 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Al Hafeez Gdn Ph-2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al Hamra | bar: 2026-03-01 to 2026-04-01
Garden Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Gul zameen Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Gulberg housing Society | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Indus Smart City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Al Jalil Housing P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al Jalil Housing P3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al Jalil Housing P4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Al Kabeer Ph-2-Pk1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al Kabeer Ph-2-Pk2 | bar: 2026-03-01 to 2026-04-01
Al Kabeer Ph-2-Pk3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
K Gaardens | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Khayaban e Sarwar | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Al Khalil Housing Scheme | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al Mansoor Town Ext. | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al mansoorah colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al Nawab Rehman Villas AlKareem | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al Raheem Gdn Ph-2 Extn. | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Al Rahim City Ph-1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al Rahim City Ph-2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Khayaban i Abid | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Al Rehman Garden 4 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2
Alamgir&Jannat ul Barkat | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Alfalah Society | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Al-Hamd Society | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Main Area P1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
ALi + Fort + Madina | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Main Area P2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Ali Park & Nadirabad P1 | bar: 2026-03-01
Ali Park & Nadirabad P2 | bar: 2026-03-01
Main Area P3 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Model Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Ali Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Alibad_Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
New Defence | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
New Model Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
NMC Colony 1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Part of New Defence | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Railway Civil Lines P1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
AlNoor Exct-Haram-Garden Ph-4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
AlQuresh Phase 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
AlQuresh Phase 2 | bar: 2026-03-01
Railway Civil Lines P2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Royal city | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Al-Rahim Garden & Crystal Homes | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sana Valley | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Aman kot | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
Amir Street Cap Rd & Model Town | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Zam Zam City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Akhtar Town & Tarrar Road | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Al Kareem City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Asif & Hassan Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari 01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari 02 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari 03 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari 04 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari-1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari-1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari-10 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari-10 P1 | bar: 2026-03-01 to 2026-04-01
Askari-10 P2 | bar: 2026-03-01 to 2026-04-01
Askari-10 Sec-S | bar: 2026-03-01 to 2026-04-01
Askari-11 P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Askari-11 P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Askari-11 P3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Askari-2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari-2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari-3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ilyas Colony | bar: 2026-03-01
Askari-4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari-5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Jail Road Bird Wood & Waris Co | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
Jinnah Colony Aerial | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Lawarance Road & China Road | bar: 2026-03-01 to 2026-04-01
LC_P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
LC_P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
LC_P3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
LC_P4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Alipur Chatta Road Pocket 1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Alipur Chatta Road Pocket 2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Anarkali Bazar | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
LDA_Ph-1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
LDA_Ph-3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Mall Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
N LHR City P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
N LHR City P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari-7 P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Askari-7 P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Askari-9 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari-I | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari-II | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Aslam, Mujtuba & Canal Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Atta Muhammad Coloy HH To 47 Ch | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Aurangzaib Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Awan Chowk To Gulberg City | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Azam Garden | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Ayan Garden | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ayub Park | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ayub Park | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Canal & Officer & Faisal | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Defence Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Aziz,Imran,Nawab,Gondl,Fjr,Srwr | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B-17 Blk-D extn | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
B-17 BlockF-P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bagga | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bagh Mohalla & Naya Mohallla | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bagh-e-Malir | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Bahadurabad & Sharfabad | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bahadurpur | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bahria P10 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Bahria P25 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Bahria P6 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Bahria P8 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Bahria P9 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Gulberg | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Bajwa Colony | bar: 2026-03-01 to 2026-04-01
Bajwa Colony, Samad Pura Road,S | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bakarabad & Jughoor | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
Bala Gujjran | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Band Road Extension & Makhdumpu | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Hassan Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Bari Chum | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Barkat Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Barrage Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Barrage Colony | bar: 2026-03-01 to 2026-04-01
Bashir,Chuna Bhati,Jamil | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bast Shor Kot | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bhatti Colony | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bhutta Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bhutto Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bicket Gunj | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bilal City | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bilal Colony & Mukhtyar Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bilal Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Bismillah City & Ext | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bismillah Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Block U & V New City Ph2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block W & Y New City Ph2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block-A | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Block-B | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Block-C | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Block-D | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bodla Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bograh Ext | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bonkan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
BOR | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Buch Villas Extn. | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bukhari Villas | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
C-18 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Cable Stringing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Callachi Society | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2; 2026-08-01: 2; 2026-09-01: 2; 2026-10-01: 2
Camp Gujran | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kot Hashmat 1 & Kot Hashmat 2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Canal Burg | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Canal Cantt Views | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Canal Garden_Canal Rd | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Canal Park | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Madina Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Canal View | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Makkah Town & Ali Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Canal View Multan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Cantt | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Cantt.P_1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Cantt.P_2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Cantt.P_3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Cantt_P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Cantt_P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Center Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Central Park Housing-P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central Park Housing-P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central Park Housing-P3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chah Hadi Wala | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Chak 43 NB,Ali & Yousuf Park | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Chak 89 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Chak Akka | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chak Doulat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chak Hafizan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chal Jamal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Qazipura_Qadirabad Srndg Area | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Chandni Chowk | bar: 2026-03-01 to 2026-04-01
Charkhana P02 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Charkhana P03 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sattellite Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Cheema Town Ph-2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Shalimar_Al Hamra Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sukheke Hafizabad Road | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Chinar_Bagh_P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Chinar_Bagh_P02 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Chinar_Bagh_P03 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Chitan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Chitral City | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
Christian Town & Muslim Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sultan Residencia Park | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Circular Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Citi Housing Block D_E_F Extn. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CITI Housing D Block | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
CITI Housing E_F_G | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Citi Housing Jinnah Block-P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Citi Housing Jinnah Block-P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
CITI Housing PH-2_Main | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Citi Housing Sec-A_Sectn-1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Citi Housing Sector A | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Citi Housing Sector B | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Citi Housing Sector C | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Citi Housing Sector D | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
City Side P01 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
City Side P02 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
City Side P03 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Civil Line Area BOQ | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Civil lines | bar: 2026-03-01 to 2026-04-01
Civil Lines | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sunny Garden | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tulip City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Unknown Society 2 & Iqbal Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Dadabhoy Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Daman & Kilo Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Zahoor Orchard Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Defence Housing | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Defence Housing Society | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Derai P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Dewan ka Bagh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
DHA PH-4 KK | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Diamond Citi P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Diamond City_Wasi Country Park | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
Dream Avenue | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dream Valley | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Drop Cable Installation till Premises Wall | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dubai Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Eden Villas | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshan Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Emaar P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Emaar P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Emaar P3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fahad Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Falaknaz Pebbles | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fatima Jinnah Town C | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fatima Jinnah Town E | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fatima Jinnah Town F | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fatima Jinnah Town G | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fatima Jinnah Town H | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fatima Jinnah Town J | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fazil Town FDT To Khizar Masjio | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
FDA City_P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Satellite Town_PK3 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Shah Block | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Park View_T.B_P3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fortune Arcade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G-11 P1 | bar: 2026-03-01 to 2026-04-01
Garden Town_P3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Garjakh Road | bar: 2026-03-01
Gohaddpur to Ghaniabad | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
P3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
P5 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Gulshan e Anwar T.Buried | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshanabad P03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Habib Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Habibpura | bar: 2026-03-01
Hafizabad Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hostel City | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Hyd Cantt P02 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-10 P4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-10 P5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-14-P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ibrahim Garden | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Kasur P-1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Ittehad Garden P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kabal P04 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kabal P08 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kaleem Shaheed Colony-2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kangra Colony P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kantrili | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Peeru wala Road | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Kashmir Rd Jani Shop st | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Saif City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Kent Housing Ext. | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Khakwani Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kharala | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ajnianwala | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Khursheed Town | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kokan CHS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feroz Wattowan-i | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Ferozewala | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Layllpur Garden | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Township_B1_P04 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Township_B2_P02 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Liaquat Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
M3-Ind.Estate_P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kala Shah Kaku | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Madina Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kaloke | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Main Bazar Mingora | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Main City P1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Main City P2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mirza Virkan | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Muradey Kalan | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Muridke | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Nazri Lubana | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Makan Bagh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Makhan_Malikyar_Kalas | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Rakh Hiran Minara | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Akari-1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Shahdara Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Maqam Mandi | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marala Road & Muradpur | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Marhaba Canal View | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marvi Town & Marvi Garden | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Medical Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Misc.Areas Warsak | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Mohabatabad P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arshad Town and Model Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
District Complex, Complex City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Gulberg Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Naimat Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Naval ANchorage | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Nawab City | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Nayab Grace City | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Nazeer Apt. | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
New Naqshband Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
New Raza Garden | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2
Shalimar City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Nowshehra Road | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
DKTCC (Remaining Areas) | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Oasis Park Residencia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Odigram P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Odigram P02 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Odigram P03 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Odigram P04 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Odigram P05 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Block M | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
DHA Rumanza-P1 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
DHA Villas | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
High Court Society | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Pak China Phosphate Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Pak Ideal CHS P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Palm Village | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Paragon Ideal Homes | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Parao Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sialkot By Pass | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sialkot Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al-Rafeh Garden | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Pasrur Rd & Skt Bypass | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ph-1 G & H Block | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
PH-7-P3 | bar: 2026-03-01 to 2026-04-01
Ph-8-IVY-P2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Pioneer Fountain_KHI UNI | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
PK01 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2
Pocket-1 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2
Pohan Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari-4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al-Reheem Garden | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Punjab Small Ind. Estate | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Punjabi Sodagran Society | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Bismilllah Society | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Qaiserabad | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Qasim Pur Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Qasim Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Qazi Town | bar: 2026-03-01
Circular Road | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Civil Lines | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Rahbr-Sec-2-P1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Rahbr-Sec-2-P2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Green City Park | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Habib Garden | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Rangpura Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ranjha Mahira | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Razaq Royal Ph-3_P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Razaq Royal Ph-3_P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Askari-5 P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari-5 P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Katchery Road and Allama Iqbal | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Rehman Garden-2 Pk-7 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Rehman Garden-2 Pk-8 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
River Area_Hayatabad | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Roras Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Roshan Pakistan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Roshan_Noor ext._Madina_Uni | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Roshanabad | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Manik Road Mohala Hussainabad | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Moh Meera Shah Hussain | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Royal Residencia | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Royal Villas EXT. | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
RPO Office TO Session Court Roa | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Mohala Hajver Nagar Open Area | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sachal Township_Kings Crystal | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2
Mushtaq Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sadiqabad latifabad Wahidabad | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Pan peer Road Societies | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Saima Down Town | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2; 2026-08-01: 2; 2026-09-01: 2; 2026-10-01: 2
Askari-5G | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Salman Gardens | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sarai Saleh | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2
Sarfaraz Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Satellite Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Samanabad-College Area | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scheme33_MalirCantt_MDU_P03 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Scheme33_MalirCantt_MDU_P04 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sector P, U, V & SPECHS | bar: 2026-03-01 to 2026-04-01
Sector Q | bar: 2026-03-01 to 2026-04-01
Sector R | bar: 2026-03-01 to 2026-04-01
Sector S | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sector T | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sector W, ZA & Colonies | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sector X | bar: 2026-03-01 to 2026-04-01
Sector Y | bar: 2026-03-01 to 2026-04-01
Sector Z | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
SGD Bhalwal Road TO Fatima Jinn | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Abid Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Shagai & Akhon Baba P01 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Shagai & Akhon Baba P02 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
Ajmal Town,Faisal Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Shah Nawaz Grand City | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Shahabpura | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
Shahabpura Main Rd | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Shahdara & Habib Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Akbar Town & Laghari Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Al Haram City, Hamza City Overs | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Shalimar Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al Hassan, Jamal City, Al Noor | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Shamas Pur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shamsi Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Shamsi Society | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sharifabad | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SHFT Pocket-1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
SHFT Pocket-2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Shia Bagh & BUH Qambar P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Shia Bagh & BUH Qambar P02 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari-5J | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
SKT Rd Pocket 05 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Small Industrial Estate | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Soomra Society | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
SSGC Housing | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Amir Canal View, Canal Residenc | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sui Gas Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Arif Town, Shahzad Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sukkur Township P-2_KingCrystl2 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2
Sultan Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
T & T Colony | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tajabad P02 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
Tameer e Hayat Colony | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commercial Area, Kothi Mohallah | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Tariq Garden & Makki Road Area | bar: 2026-03-01
Thatti Gujran & Mughlan | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TIP Housing | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Towards Ugoki Mor | bar: 2026-03-01
Askari-6 Sec 03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Askari-6 Sec 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gulshen I Azmat, Maqbool City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Gulshen I Iqbal | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Mehar Farid Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Model Avenue | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unknown Society _ 5 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
Unknown Society_12 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
Unknown Society_22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unknown Society_23 | bar: 2026-03-01
Noor Colony,Zamindara Housing | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Public Colony & Commercial Area | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Rao Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Rehman Avenue | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Unkown Society 15 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Unkown Society 16 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Unkown Society 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unkown Society 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unkown Society 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unkown Society 6 | bar: 2026-03-01 to 2026-04-01
Wafay Citi GG Block | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Warsak Rd Ext. P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Warsak Rd Ext. P3 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Writers Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ya Rehman Society | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Younas Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Z Block NST & Services Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Zafar Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Zafarwal | bar: 2026-03-01
Zahoor Elahi Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Tibba Qadirabad | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Warriach Town & Arian Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Zakria Garden,Unknown 3-4, | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Ali Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Disposal Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gulraiz Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
P5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshanabad P01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hafizabad Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Hansabad | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Iqbal Stadium Comm.Area | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Islampura | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Jhelum Road Buildings | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Khadim Ali Rd | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Tariq Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Latifabad No 09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lucknow Society | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
M.Ali Shaheed Society_Maaz Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
M3-Ind.Estate_P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KOT Abdul Malik | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Madras CHS | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kurkle Androon | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Al-Hamra City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
PH-8-P2 | bar: 2026-03-01
PH-8-P3 | bar: 2026-03-01
PH-8-P4 | bar: 2026-03-01
Rehman Garden-2 Pk-6 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Rehmanpura | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rehmanpura | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Rehmat Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Ring Road P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Cheema Town, Permi Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Al-Raheems Homes | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Royal Pearl Enclave | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Aman Society | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Amynabad | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Anwarabad Colony | bar: 2026-03-01 to 2026-04-01
LDA_Ph-2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
HVTR & MB & POR & JBR | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Iqbal Garden | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Block N & O New City Ph2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block P New City Ph2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kassoki Road P1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Block Q New City Ph2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil lines Lower End | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
CTD_ANF_Police Lines_H11 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2
Custom Preventive CHS | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2
Darakhshan Society PK1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Darakhshan Society PK2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Unknown Society 5 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Darussalam Society | bar: 2026-03-01 to 2026-04-01
Dastgeer Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
DC Colony ext.PK_1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
DC Colony ext.PK_2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Zahoor Orchard | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Defence villas | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Derai P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
DHA Ph-4 P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
DHA Ph-4 P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DHA PH-5 M | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
LC_P6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
DHA_Ph-1_P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Chaudary Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
LC_P7 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Civil Lines | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
E-17 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Eden Lane Villas 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Eid Gah | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ghaziabad | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Estate Area P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Estate Area P3 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
Factory_Area | bar: 2026-03-01 to 2026-04-01
Faisal_Town | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Khokar Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Farid Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fatehgarh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fatima Jinnah Town A | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fatima Jinnah Town B | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fazaiya Society P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fazal Sun City | bar: 2026-03-01
Fazal Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
FB Area Block-22 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
FDA City_P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Lalazar Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Madina Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Officers Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Paradise City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Samanabad | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Satellite Town_PK1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Satellite Town_PK2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Shadab Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sultan Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Park View_Hybrid_P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Park View_T.B_P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder From PoP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unknown Society 3 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Fesco Abdullahpur | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fesco Colony 132 KV | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
FMC_Partial | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G magnolia Remaining Part | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G-11 P3 | bar: 2026-03-01 to 2026-04-01
G-11 P4 | bar: 2026-03-01 to 2026-04-01
Unknown-2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Garden Town_P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Garden Town_P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ghalotian Mor | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
P1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Ghani Park FDT To Steel Welding | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gharmala | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gharmala Monan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ghordor Road P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ghordor Road P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ghordor Road P3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ghordor Road P4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ghorrdo Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
P2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Gohar Green | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Golf City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Golimar Area | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2
Govt Central Model School To Th | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Green Acres P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Green Acres P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Green and Al-hafeez Town | bar: 2026-03-01 to 2026-04-01
Green Fort Housing Society | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Green valley | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2
Green Valley Ph-6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Green Village | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
GT Rd Pocket 06 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
GT Rd Pocket 07 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
GT Rd Pocket 08 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
GT Rd Pocket 09 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
GT Rd Pocket 11 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
GT Rd Pocket 12 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
Gujjar pur | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2
Gul Kada | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2
P4 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Gulberg & New Gulberg | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
P4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulberg Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Guli Bagh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulistan Colony | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gulistan_town | bar: 2026-03-01
Gulistan-i-Ashar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gulshan Aziz Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshan Block-19 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshan Block-4A | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshan Colony | bar: 2026-03-01
Gulshan e Ali | bar: 2026-03-01
Gulshan e Bakhtawar Ext | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshan e Faiz | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshan e Haram-II | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshan e Iqbal | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshan e Makkah | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshan Town Ph1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshan-e-Rafi | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Gulshan-e-Tayyaba | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Gulshan-i-Ghafoor | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshen e Yousaf & Stadium | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
P6 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
P6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshen-i-Sardar | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulzar Colony & Main Rd | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Abdul Khaliq Colony | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2; 2026-08-01: 2; 2026-09-01: 2; 2026-10-01: 2
Ali Ahmed Shah Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
H13_Mainly Hostels | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al-Kareem Garden | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Azhar Colony Khara Road and Bas | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Defence Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Dhorr Kot Road & Kot Fateh Din | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Gulberg | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Haji Park Bypass | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Haneef Garden | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Haji Park Commercial | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Haseeb Town,Fahad Colony & Dila | bar: 2026-03-01 to 2026-04-01
Haji Park Phase 1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Hamza Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Ideal Garden Housing | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Redline | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2
Hunterpura Ext | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kasur Raiwand Road | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Khara Road | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Hyd Cantt P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Hyd Cantt P03 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-10 P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-10 P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-11 Aerial | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-11P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-11P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-14-P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-14-P3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-14-P4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-9 P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-9 P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-9 P3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-9 P4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Khara Road and Nafees Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Park View_T.B_P4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inam City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Madina Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Indus Society | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ingaroderai-Takhtaband P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ingaroderai-Takhtaband P03 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ink City 02 P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ink City 02 P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ink City 02 P03 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Installation / Termination of Cables & Testing of Man ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Kasur P-2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Islamia Colony PK1 | bar: 2026-03-01 to 2026-04-01
Islamia Colony PK2 | bar: 2026-03-01 to 2026-04-01
Islamia Colony PK3 | bar: 2026-03-01 to 2026-04-01
Islampura | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Istiqlalabad | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ittehad Garden P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ittehad Town & Other | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Jahangir | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rehan Gardens Ph 1&2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jalil Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Jallianwala | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Jalvi Market | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Main Kasur P-4 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Japan Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Japan Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Main Kasur P-5 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Jhakkarr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jhangi Qazian | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Jhangi Saeedan Extension | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Maqbool Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sherwani_Shadab Hsng Scty | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Jinnah Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Saima Villas | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Munir Shaheed Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Judicial Colony Ph 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Mustafa Park | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Kabal P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kabal P02 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kabal P03 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kabal P05 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kabal P06 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kabal P07 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kachari Road To Awan Colony Dep | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kacheela House To Gujjar House | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Nadeem Park | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Kaghan Colony Extension | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kala Gujran_P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kala Gujran_P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Officer Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Kangra Colony P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kanju Road P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kanju Road P02 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kantrila | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kareenpura Extension | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Karmawala | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kashmir Colony 1 & 2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Qadirabad , NoorShah Wali and K | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Road Kot | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Katcheri Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kazimabad | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Khan Village II | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Saleem Town Ph-1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Khayaban e Kubra | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bahrrian Wala | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Khayaban-e-Patni CHS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chalk no.12 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Khokhar k_BOQ | bar: 2026-03-01
Khwaja abad | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2
Khy-e-Manzoor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kings_ASF_ Tower_P02 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Kotli Allahyar | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Jandiala Sher Khan | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Jatri Kohna | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Landikas_Rang Mohalla | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Township_B1_P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Township_B1_P02 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Township_B1_P03 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Township_B2_P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kot Sondha | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Main CO ODF Rack | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Nokhar | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Main KKH & Lari Adda | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Makhdoomabad | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Master Citi Pk-1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
MBCHS | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Meadows_I | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Darbari, Qureshi Muhallah,Shad | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Dhamah,Lalazar & Railway Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Metro Homes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milatabad | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2
Millat Garden | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Eid Gah, Rehmat Abbas,Kaira Muh | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Misc. Areas | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gunjra Road,Bagh e Syedan & Bud | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Model Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Model Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Karimpura, Hajipura, SabriMuhal | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Model Town C Extension | bar: 2026-03-01 to 2026-04-01
Mehar Muhallah,Weraowala,Sadiqa | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Syda Gol,Faisalpur,Jogi&Qasbah& | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mohallah Aam Khass and Noor Sha | bar: 2026-03-01 to 2026-04-01
Mohsin Town & Rasheed Avenue | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Montgomery Society | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Muftian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Al-Rehman, Eiffel, Sultan Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Muhall Noor & Park Salamat Park | bar: 2026-03-01
Mujahid Town_Ali Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Multan Golf City | bar: 2026-03-01
Mumtaz City P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PSW to Torkham Border | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bangali Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gillani Town,Tariqabad,Sufipura | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Muslim Khatri CHS | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Muslim Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Muslimabad | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gurrah Muhallah | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Hajipura | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Akari-2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Akari-3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
N.Blue Ar. & Other Buildings | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Hamza Ali town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Jinnah City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Nawab Bhatta Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
NAYAB Colony Directors Residencies | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Nayyab City & Extension | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kachehri Area | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
New Bagh Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Manzoorabad | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Paradise Complex | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Qila Gujjran, Rehmanpura | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
New Surkh Dheri | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
NewSukkurCityTownship | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Niazi Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
NIPA Society | bar: 2026-03-01
Sattelite Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Noor Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Odigram P06 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Officer & Professor Colony_PU | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sufi City Housing Scheme PK-2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Officers Colony Canal Road | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
OPF Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
OPF Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Tajpura, Shalimar & Amin Twn | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
P1 muslim town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
P1, Extended Part | bar: 2026-03-01 to 2026-04-01
Unkown Area 2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Unkown Area 3 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
P2 muslim town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
P3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Unkown Area 4 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Unkown Area 6 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
P4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Additional Cost | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
P4-Citi Housing | bar: 2026-03-01 to 2026-04-01
P5 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
Block Q | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
Block R | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
Mumtaz City P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PAF Tarnol-P1 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
PAF Tarnol-P2 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
Pak Ideal CHS P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Pak Kausar Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Palm City | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2
Abdullah City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Nowshehra Sansi Road | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
Al-Raheem Residencia | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Ph-1 K Block | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Ph-2 T Block | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Ph-3 XX Block | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Ph-3 Y & Z Block | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Ph-4 K Commercial | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Ph-5 K Commercial | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
PH-7-P1 | bar: 2026-03-01 to 2026-04-01
PH-7-P2 | bar: 2026-03-01 to 2026-04-01
PH-7-P5 | bar: 2026-03-01 to 2026-04-01
Ph-8-IVY-P1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
PH-8-P7 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
PH-8-P8 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
PHA G-11 & I12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PIB Colony | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PiliBheet Society | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
PK-01 | bar: 2026-03-01 to 2026-04-01
PK02 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
PK-02 | bar: 2026-03-01 to 2026-04-01
PK03 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
PK04 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
PK05 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
Pocket-2 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
Pocket-3 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
Pocket-4 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
Pocket-5 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
Pocket-6 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
Pocket-7 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
Al-Rehmanpura and Zafarwal Road | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Qasim Villas & Shams Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Rafi Gardens_Gulshan e Muneer | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Rahimabad_Qambar | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Doctor's Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Garden Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Hayat Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Raza Gardan Phase 1 & 2 | bar: 2026-03-01 to 2026-04-01
Rehman Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Rehman Garden-2 Pk-2 | bar: 2026-03-01
Rehman Garden-2 Pk-3 | bar: 2026-03-01 to 2026-04-01
Rehman Garden-2 Pk-4 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
Rehman Garden-2 Pk-5 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
Rizwan Colony Deen Pura | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Khayaban-e-Nawab | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sadabad Society | bar: 2026-03-01 to 2026-04-01
Safari Garden Phase 2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Nisari Muhallah & Muslim Town S | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Saidu Sharif P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Salhad | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Salman Pura - Saleem Park | bar: 2026-03-01 to 2026-04-01
Punjab Housing & NPS | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sambrial_Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sadeeqpura | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
PAF Base Chaklala | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sher Rabbani Town & Ghaziabad | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Askari-6 Sec 01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
SHFT Pocket-3 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
SHFT Pocket-4 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
SHFT Pocket-5 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Shikarpur Rd | bar: 2026-03-01 to 2026-04-01
Askari-5H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sitara City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Site Area & Shanghai Tower | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
SKT Rd Pocket 01 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2
SKT Rd Pocket 02 | bar: 2026-03-01
State and Middle Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Allama Iqbal Town, Aslam Town, | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sukkur Ind Area | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Sukkur Township Pocket 1 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2
Azizabad | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sum Sum Tower | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0
Canal View | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Surti_Humaira_Jami | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Taha Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Tajabad P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Chief Residencia Housing Societ | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Tanveer Town & Ratta Rd | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Tariq Garden | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TariqBinZayed | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Faiz Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Towards Chitti Sheikh | bar: 2026-03-01
Askari-6 Sec 02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Askari-6 Sec 04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Askari-6 Sec 06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Askari-6 Sec 07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Askari-6 Sec 08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Askari-6 Sec 09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Haider Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Haq Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Heaven City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Hussainabad & Ghafoorabad | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Indus Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Izhar Enclave,Unknown1,Unknown2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Jinnah Town, Mohallah Islampura | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Model City Housing | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Unknonwn_1 | bar: 2026-03-01 to 2026-04-01
Unknown 01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unknown Society _ 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unknown Society _3 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
Unknown Society 10 | bar: 2026-03-01
Unknown Society 13 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Unknown Society 14-P1 | bar: 2026-03-01
Unknown Society 14-P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unknown Society 14-P3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unknown Society 14-P4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Model Town, Arfat Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Unknown Society 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unknown Society 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Muhajir Colony, Old Sadiqabad | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Mujahid Colony, Tipu Sultan | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Unknown Society 9 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
Unknown Society_11 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Muncipal Town, Illyas Colony, | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Mustafa , Zafar, Bismillah, Kar | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Unkown Society 7 | bar: 2026-03-01
Unkown Society 8 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
Rustam Colony & Mohallah | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Satellite Town, Aziz Town, Gill | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Village garden | bar: 2026-03-01
VIP Housing | bar: 2026-03-01 to 2026-04-01
Wafaqi Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Waffay Block Rem.Area | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Wapda Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Wapda Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Siraj Colony,Sukh Chain Housing | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Warsak Rd Ext. P1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Warsak Rd Ext. P5 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Warsak Rd Ext. P6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Warsak Rd Ext. P7 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Water Board Society | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Western Fort | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Willoughby Road appartments | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Wocland | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Zakariya Villas | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Zamzam Garden,Jeevan City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Between Fizaghat & Sangota | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Al Rasool Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Al Kabeer Town Ph-1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Al Rehmat Villa | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Allabad, AliTown & IslamPura | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Usmania Village | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Anwar-e-Ibrahim | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Askari 05 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
Atta Housing + Canal + Paradise | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2
B-17 BlockD | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
B-17 BlockF-P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bahria P26 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Bahria P3 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2; 2026-07-01: 2
Barrage Officer Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kassoki Road P2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Block R & S New City Ph2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block Y & Z New City Ph2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cantt Commercial | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Capital Rd & Model Town Ext | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Cavalry Ext Aerial | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Cavalry Ext Hybrid | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Charkhana P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Darvesh P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Darvesh P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Derai P3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
LC_P5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
DHA Sector A ( Villas ) | bar: 2026-03-01 to 2026-04-01
DHA_Ph-1_P2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
DHA_Ph-1_P3 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Al Karam City Phase 1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
E-16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Eden Orchards | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
PAEC T.Buried | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
F.B Area Block-21 | bar: 2026-03-01 to 2026-04-01
Faisal Town P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Faisal Town P3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Faisal Town P4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fatehger Ext | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fatima Jinnah Town D | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Fauji Basti | bar: 2026-03-01 to 2026-04-01
Fazaiya Society P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
FDA City_P3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unknown-1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
G-11 P2 | bar: 2026-03-01 to 2026-04-01
Gaju_Khaksar_Shams Gunj | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Garden Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
Feeder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
GT Rd Pocket 10 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
P3 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Gulberg City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gulberg+Ahmed+Air view | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulfam Town_Mera Muzzafar | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Gulshanabad P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Al-Majeed Housing Scheme | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Hostel City_Extn | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
I-10 P3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ingaroderai-Takhtaband P02 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Main Kasur P-3 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Kabal P09 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
New City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Saeedabad | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Killi Payen | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Kings_ASF_ Tower_P01 | bar: 2026-03-01
Ghang | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Labour Colony | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lasani Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Latifabad No 04 | bar: 2026-03-01 to 2026-04-01
Latifabad No 10 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Township_A2_P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Township_A2_P02 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Township_C1_BL03 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Township_C2_BL03 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lahore Jaranwala Road | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Malikpura | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Safdarabad | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Mansoora | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Master Citi Pk-2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Master Citi Pk-3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
MB Shora Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Model Town | bar: 2026-03-01 to 2026-04-01
Model Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Thirkian,Asghar Town,Ahmad Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Mohabatabad P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Wahdat Colony | bar: 2026-03-01
New_Muslim town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Nihalchand & Greenwood St | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ranger Colony | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Royal Palm City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sufi City Housing Scheme PK-1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Orchird Villas | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
P9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jinnah Road 2 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2
Peerwali | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Peoples & Bitholdi Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Petaro | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ph-2 Q Block | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
PH-8-P1 | bar: 2026-03-01
PH-8-P5 | bar: 2026-03-01
PH-8-P6 | bar: 2026-03-01 to 2026-04-01
Posh AVenue | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Rafah-e-Aam Society | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Rahbr-Sec-1-P1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Rahbr-Sec-1-P2 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Rehman Garden-2 Pk-1 | bar: 2026-03-01
Remount Depot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MOh Bijli Ghar | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sabar Wall Colony | bar: 2026-03-01 to 2026-04-01
Sabzal Road | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2; 2026-06-01: 2
Sadiqabad latifabad Wahidabad | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Narowal Bypass to Nawab Town (C | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Saeela | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Safari Garden Phase 1 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Saidu Ext | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Saidu Sharif P1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Pasrur Bypass , City Commercial | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Samanabad | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Rana Shami Town & Satellite Tow | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Samarzar Housing Society | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sanobar City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Usman Trade City | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Sayyam City | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Scheme33_MalirCantt_MDU_P01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Scheme33_MalirCantt_MDU_P02 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Shamsi Rd | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Shehzad Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ali Tiown & New Ali Town | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
SKT Rd Pocket 03 | 2026-03-01: 2; 2026-04-01: 2; 2026-05-01: 2
SKT Rd Pocket 04 | bar: 2026-03-01
Sui Gas Road Pk1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sui Gas Road Pk2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Awan Housing Society | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0
Askari-6 Sec 05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Askari-6 Sec 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
University Town | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
University Town P1 | bar: 2026-03-01 to 2026-04-01
University Town P2 | bar: 2026-03-01 to 2026-04-01
Unknown 03 | bar: 2026-03-01 to 2026-04-01
Unknown 11 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Unkown Society 1 | bar: 2026-03-01
Unkown Society 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unkown Society 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Warsak Rd Ext. P4 | 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0
Zuabir Colony | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2

## 71 CEMs (hidden)
AAA
I240700
I240684
I240702
I240705
I240683
I240678
I240682
I240681
I240680
I240679
I240701
I240704
I240540
I240459
I240435
I240189
I240437
INT-23-00764
I250298
I240537
I240538
INT-23-00438
INT-23-00435
INT-23-00436
I240557
I240438
I240440
I240518
INT-23-00437
INT-23-00440
INT-23-00441
INT-23-00442
INT-23-00444
INT-23-00445
INT-23-00446
INT-23-00447
I240519
I240539
I240442
I240782
I250114
INT-21-00315
INT-23-00439
I250207
I250206
I250203
I250202
I250201
I250205
I250213
I250212
I250211
I250210
I250208
I240190
I240703
I250209
I250326
I250327
I250375
I250380
I250379
I250378
I250376
I250377
I260068
I250737
I250374
I250307
I250681
I240188

## Faraz (hidden)
CEM Number | CEM Initiation Date | City Name | Fesibility Name | Area / Section / Pocket / Society (Original Name) | Total H.P | Customers According to % (Market Share) | Customers based on completion | HP% based on Live % | HP Based on completion - Realistic | Allocated Budget | Revised Budget | Difference | Costing Efficiency | Area / Section / Pocket / Society (Revised Name) | Customers Take up %age (Key Factor) | Total Civil works (Meters) | Originally Approved on: Arial, Buried, Hybrid | Allocation Percentage | Current Status (Live/Not Live) | Live on (Arial,Buried, Hybrid) | % of Completion of Work Done | Timeline | Timeline - Monthwise | Remarks by ODN
I240539 | 2024-02-28 | Swat | Swat Ph2 | Gul Kada | 816 | 326.4 | LIVE - 80% Completed | 80% | 261.12 | 12199624.6265 | 3903879.8805 | 8295744.746 | -1 |  | 0.4 | 1936.6 | Hybrid |  | LIVE | Arial | 80% |  |  | Civil work is on going
I240702 | 2024-05-15 | Hyderabad | Hyderabad | Gulshan e Bakhtawar Ext | 502 | 200.8 | LIVE - 25% Completed | 25% | 50.2 | 6132597.0046 | 4829420.1411 | 1303176.8635 | 0 |  | 0.4 | 1063.865 | Hybrid |  | LIVE | Arial | 25% |  |  | Due to permission constraints, some sections are live on buried, and the remaining pockets are live on aerial
I240702 | 2024-05-15 | Hyderabad | Hyderabad | MB Shora Colony | 902 | 360.8 | LIVE - 80% Completed | 80% | 288.64 | 10416857.7484 | 3333394.4795 | 7083463.2689 | -1 |  | 0.4 | 1525.59 | Hybrid |  | LIVE | Hybrid | 80% |  |  | Due to permission issue some part Live on Aerial
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | B-17 BlockD | 1124 | 449.6 | LIVE - 95% Completed | 95% | 427.12 | 23877998.0164 | 4596514.6181 | 19281483.3982 | -0.85 |  | 0.4 | 12386.0512 | Buried |  | LIVE | Buried | 95%
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | B-17 BlockF-P1 | 1978 | 791.2 | LIVE - 95% Completed | 95% | 751.64 | 50643660.5822 | 9748904.6621 | 40894755.9201 | -1 |  | 0.4 | 23860.8856 | Buried |  | LIVE | Buried | 95%
I250376 | 2024-11-25 | Islamabad | Islamabad Ph3 (P2) | B-17 BlockF-P2 | 2512 | 1004.8 | LIVE - 95% Completed | 95% | 954.56 | 45858969.2637 | 8827851.5833 | 37031117.6804 | -0.85 |  | 0.4 | 21030.9924 | Buried |  | LIVE | Buried | 95%

## Sheet13 (hidden)
DG Khan
DG Khan
Hafizabad
Jhang
Buffer Zone Khi
Kasur
Muridky, Kalasha Kako, Shadra
Lalamusa
Mandi Bahauddin
DHA Multan
Narowal
Rawalpindi
Sadiqabad
Islamabad DHA Ph1
Quetta Cantt
Sialkot Cantt
Top City Islamabad
Askari Lahore
Chinar Bagh Lahore
Al Jalil & Al khalil LHE
Chitral Ph1
Askari Sialkot
Naval Anchorage and other Areas (ISB)
Royal Palm & Canal View
Abbottabad Ph2
Haripur Ph2
Swat Ph2
Mardan Ph2
Jhelum- Kala Gojran
Sialkot
Sargodha
RahimYar Khan Ph2
Quetta
Faisalabad Ph4
Okara
Askari RWP (4-7-10)
Gujranwala Ph3
Swat
Hyderabad
Lahore Ph5
Multan Ph3
Karachi Ph5
Torkhan Border
ISB DHA Ph4
Haripur Hazara
Gujranwala
Jhelum Ph2
Daska
Abbottabad
Wah Cantt
Mingora
Mardan
ISB DHA Ph-5
DHA KHI - Common Corridor Project
Askari Multan
Islamabad
Faisalabad
Islamabad Ph3 (P2)
Peshawar (P2)
Sahiwal (P2)
Wahh Estate
Gulshan-e-Maymar
CTC Lahore
Bahwalpur (P2)-B
ISB-BT-Ph-8
DHA Gujranwala
Jhelum (P4)
DHA PH 1-5
DHA PH 7-8
Al Hafeez Garden & Tariq Garden
Faisalabad Citi Hosuing Extension
Khyban-e-Amin, High court & Al Rehman PH4
Palm City Lahore
Gujranwala Makki Road
LHE - DHA Phase 6, EME, Rahbar
Darussalam_LucknowSociety_DadabhoyTown
Model Town_Sh Faisal_Faisal Cant
Sukkur
Petaro Garrison, Hyderabad
Lhr MW City & Al Hafeez Ph-1
Gujranwala Ph2
Karachi Misc Areas
Hyderabad Misc Areas
Lahore Misc Areas
Multan Misc. Areas
Faisalabad Misc Areas
Sahiwal Misc Areas
Islamabad Misc Areas
Rawalpindi Misc Areas
Wah Cant Misc Ares
Peshawar Misc Areas
Askari (1-6) Karachi

## Sheet15 (hidden)
S. No | CEM Number | Fesibility Name | Area / Section / Pocket / Society | Total H.P | Customers Take up %age (Key Factor) | Customers According to %age | Allocated Budget (Fig in Rs.) | Total Civil works (Meters) | Current Status | % of Completion of Work Done | Timeline | Remarks (if any) | Originally Approved on: Arial, Buried, Hybrid
28 | I260061 | Jhelum (P4) | Bagga | 228 | 40% | 91.2 | 3869211.6667 | 1184.5
29 | I260061 | Jhelum (P4) | Chitan | 294 | 40% | 117.6 | 4559364.7847 | 1496.15
30 | I260061 | Jhelum (P4) | Eid Gah | 206 | 40% | 82.4 | 3357905.5377 | 1068.35
31 | I260061 | Jhelum (P4) | Gharmala | 202 | 40% | 80.8 | 2178203.0417 | 541.65
32 | I260061 | Jhelum (P4) | Gujjar pur | 126 | 40% | 50.4 | 2275726.5417 | 672.1
33 | I260061 | Jhelum (P4) | Kantrila | 238 | 40% | 95.2 | 3129442.0417 | 917.7
34 | I260061 | Jhelum (P4) | Kantrili | 208 | 40% | 83.2 | 2162403.1667 | 541.65
35 | I260061 | Jhelum (P4) | Kotli Allahyar | 266 | 40% | 106.4 | 2708058.2917 | 677.35
36 | I260061 | Jhelum (P4) | Saeela | 694 | 40% | 277.6 | 4676213.2837 | 917.7
37 | I260061 | Jhelum (P4) | Gharmala Monan | 132 | 40% | 52.8 | 1417650.1014 | 320.7808
38 | I260061 | Jhelum (P4) | Jahangir | 214 | 40% | 85.6 | 2604761.892 | 674.822
39 | I260061 | Jhelum (P4) | Jhakkarr | 448 | 40% | 179.2 | 2988945.0352 | 521.9526
40 | I260061 | Jhelum (P4) | Chak Hafizan | 168 | 40% | 67.2 | 1785086.5201 | 418.6
41 | I260061 | Jhelum (P4) | Chak Doulat | 154 | 40% | 61.6 | 1603424.197 | 328.9
42 | I260061 | Jhelum (P4) | Ranjha Mahira | 532 | 40% | 212.8 | 5161699.6917 | 1303.0549
43 | I260061 | Jhelum (P4) | Muftian | 130 | 40% | 52 | 1700283.8209 | 418.6
44 | I260061 | Jhelum (P4) | Chak Akka | 1976 | 40% | 790.4 | 8306728.6407 | 0
45 | I260061 | Jhelum (P4) | Thatti Gujran & Mughlan | 448 | 40% | 179.2 | 1625589.9159 | 0
46 | I260061 | Jhelum (P4) | Feeder |  |  |  | 49748549.6 | 18975
47 | I260061 | Jhelum (P4) | Transportation |  |  |  | 1300000 | 0
48 | I260060 | DHA Gujranwala | DHA Sector A ( Villas ) | 528 | 50% | 264 | 12342069.5 | 6621.7
49 | I260060 | DHA Gujranwala | Feeder |  |  |  | 12572800 | 3850
50 | I260060 | DHA Gujranwala | Transportation |  |  |  | 90000 | 0
51 | I260105 | Al Hafeez Garden & Tariq Garden | Al Hafeez Garden Ph-5 | 1450 | 40% | 580 | 26639854.6273 | 14837.408
52 | I260105 | Al Hafeez Garden & Tariq Garden | Al Hafeez Gdn Ph-2 | 1404 | 40% | 561.6 | 29240431.6706 | 14059.4256
53 | I260105 | Al Hafeez Garden & Tariq Garden | Al Raheem Gdn Ph-2 Extn. | 1150 | 40% | 460 | 22652075.7062 | 11108.95
54 | I260105 | Al Hafeez Garden & Tariq Garden | Feeder |  |  |  | 1756000 | 600
55 | I260105 | Al Hafeez Garden & Tariq Garden | Transportation |  |  |  | 900000 | 0
56 | I260105 | Al Hafeez Garden & Tariq Garden | Tariq Garden | 1498 | 40% | 599.2 | 37367326.2798 | 18395
57 | I260105 | Al Hafeez Garden & Tariq Garden | Feeder |  |  |  | 365500 | 0
58 | I260105 | Al Hafeez Garden & Tariq Garden | Transportation |  |  |  | 720000 | 0
59 | I260159 | Faisalabad Citi Hosuing Extension | P4-Citi Housing | 2926 | 60% | 1755.6 | 57161538.184 | 24765.6
60 | I260159 | Faisalabad Citi Hosuing Extension | P1, Extended Part | 386 | 60% | 231.6 | 8628786.096 | 3922.8
61 | I260159 | Faisalabad Citi Hosuing Extension | Feeder |  |  |  | 1065000 | 0
62 | I260159 | Faisalabad Citi Hosuing Extension | Transportation |  |  |  | 960000 | 0
63 | I260160 | Khyban-e-Amin, High court & Al Rehman PH4 | PK01 | 4706 | 40% | 1882.4 | 86408046.75 | 47548.65
64 | I260160 | Khyban-e-Amin, High court & Al Rehman PH4 | PK02 | 938 | 40% | 375.2 | 15310091.5 | 8152.95
65 | I260160 | Khyban-e-Amin, High court & Al Rehman PH4 | PK03 | 2990 | 40% | 1196 | 60220180.5 | 34483.9
66 | I260160 | Khyban-e-Amin, High court & Al Rehman PH4 | PK04 | 2590 | 40% | 1036 | 52810322 | 30341.65
67 | I260160 | Khyban-e-Amin, High court & Al Rehman PH4 | PK05 | 1756 | 40% | 702.4 | 44141308.5 | 25962.85
68 | I260160 | Khyban-e-Amin, High court & Al Rehman PH4 | High Court Society | 776 | 40% | 310.4 | 9966467.3674 | 1668.41
69 | I260160 | Khyban-e-Amin, High court & Al Rehman PH4 | Al Rehman Garden 4 | 978 | 40% | 391.2 | 21170251.6177 | 10028
70 | I260160 | Khyban-e-Amin, High court & Al Rehman PH4 | Feeder |  |  |  | 29916860 | 7637
71 | I260160 | Khyban-e-Amin, High court & Al Rehman PH4 | Transportation |  |  |  | 1620000 | 0
72 | I260179 | Palm City Lahore | Palm City | 732 | 40% | 292.8 | 13587284.5 | 1541.25
73 | I260179 | Palm City Lahore | Feeder |  |  |  | 4101650 | 715
74 | I260180 | Gujranwala Makki Road | PK-01 | 5402 | 40% | 2160.8 | 36230431.9062 | 4771.35
75 | I260180 | Gujranwala Makki Road | PK-02 | 7946 | 40% | 3178.4 | 37856034.625 | 2417.3
76 | I260180 | Gujranwala Makki Road | Feeder |  |  |  | 45402400 | 12562
77 | I260180 | Gujranwala Makki Road | Transportation |  |  |  | 2640000 | 0
78 | I260208 | LHE - DHA Phase 6, EME, Rahbar | Rahbr-Sec-1-P1 | 1190 | 40% | 476 | 36151846.5 | 21861.6
79 | I260208 | LHE - DHA Phase 6, EME, Rahbar | Rahbr-Sec-1-P2 | 952 | 40% | 380.8 | 24294953.8888 | 14717.181
80 | I260208 | LHE - DHA Phase 6, EME, Rahbar | Rahbr-Sec-2-P1 | 2848 | 40% | 1139.2 | 61787735.75 | 34024.8
81 | I260208 | LHE - DHA Phase 6, EME, Rahbar | Rahbr-Sec-2-P2 | 2836 | 40% | 1134.4 | 58301250.8659 | 35524.2681
82 | I260208 | LHE - DHA Phase 6, EME, Rahbar | Feeder |  |  |  | 4132000 | 500
83 | I260208 | LHE - DHA Phase 6, EME, Rahbar | Transportation |  |  |  | 2725000 | 0
84 | I260294 | Darussalam_LucknowSociety_DadabhoyTown | Darussalam Society | 1074 | 40% | 429.6 | 18047048.0325 | 3990
85 | I260294 | Darussalam_LucknowSociety_DadabhoyTown | Lucknow Society | 1322 | 40% | 528.8 | 16195392.3801 | 3096
86 | I260294 | Darussalam_LucknowSociety_DadabhoyTown | Dadabhoy Town | 662 | 40% | 264.8 | 3637949.2255 | 496
87 | I260294 | Darussalam_LucknowSociety_DadabhoyTown | Feeder |  |  |  | 3219200 | 105
88 | I260294 | Darussalam_LucknowSociety_DadabhoyTown | Transportation |  |  |  | 510000 | 0
89 | I260295 | Model Town_Sh Faisal_Faisal Cant | SHFT Pocket-1 | 658 | 40% | 263.2 | 6004577.2636 | 915.7447
90 | I260295 | Model Town_Sh Faisal_Faisal Cant | SHFT Pocket-2 | 1814 | 40% | 725.6 | 15570489.25 | 2498.1
91 | I260295 | Model Town_Sh Faisal_Faisal Cant | SHFT Pocket-3 | 1438 | 40% | 575.2 | 13171602.75 | 1886.5
92 | I260295 | Model Town_Sh Faisal_Faisal Cant | SHFT Pocket-4 | 810 | 40% | 324 | 11834428.25 | 2531.1
93 | I260295 | Model Town_Sh Faisal_Faisal Cant | SHFT Pocket-5 | 1628 | 40% | 651.2 | 12786389.5 | 1995.4
94 | I260295 | Model Town_Sh Faisal_Faisal Cant | TariqBinZayed | 1156 | 40% | 462.4 | 11984167.1091 | 2006.3986
95 | I260295 | Model Town_Sh Faisal_Faisal Cant | Gulshan-e-Rafi | 712 | 40% | 284.8 | 7181085.395 | 1326.6
96 | I260295 | Model Town_Sh Faisal_Faisal Cant | Salman Gardens | 382 | 40% | 152.8 | 3373988.4876 | 541.5
97 | I260295 | Model Town_Sh Faisal_Faisal Cant | Anwar-e-Ibrahim | 558 | 40% | 223.2 | 5089046.74 | 865.7
98 | I260295 | Model Town_Sh Faisal_Faisal Cant | Rafi Gardens_Gulshan e Muneer | 890 | 40% | 356 | 7641320.7956 | 1239.7
99 | I260295 | Model Town_Sh Faisal_Faisal Cant | M.Ali Shaheed Society_Maaz Town | 596 | 40% | 238.4 | 6445888.8368 | 1278
100 | I260295 | Model Town_Sh Faisal_Faisal Cant | Punjabi Sodagran Society | 450 | 40% | 180 | 6586551.8239 | 1291.7697
101 | I260295 | Model Town_Sh Faisal_Faisal Cant | Shamsi Society | 1744 | 40% | 697.6 | 17108465.7763 | 3376.23
102 | I260295 | Model Town_Sh Faisal_Faisal Cant | Bilal Town | 2212 | 40% | 884.8 | 19560927.9296 | 3424.19
103 | I260295 | Model Town_Sh Faisal_Faisal Cant | Alfalah Society | 1330 | 40% | 532 | 9706625.8913 | 1495.12
104 | I260295 | Model Town_Sh Faisal_Faisal Cant | Rafah-e-Aam Society | 834 | 40% | 333.6 | 8920240.4115 | 1590.6
105 | I260295 | Model Town_Sh Faisal_Faisal Cant | Hansabad | 528 | 40% | 211.2 | 5393428.6324 | 994.4
106 | I260295 | Model Town_Sh Faisal_Faisal Cant | Bagh-e-Malir | 792 | 40% | 316.8 | 7735109.7626 | 1471.8
107 | I260295 | Model Town_Sh Faisal_Faisal Cant | Gulshan-e-Tayyaba | 488 | 40% | 195.2 | 5401796.4313 | 1072.5
108 | I260295 | Model Town_Sh Faisal_Faisal Cant | Gohar Green | 1906 | 40% | 762.4 | 29290908.987 | 10847.4088
109 | I260295 | Model Town_Sh Faisal_Faisal Cant | Model Colony | 1302 | 40% | 520.8 | 12104452.8181 | 2178
110 | I260295 | Model Town_Sh Faisal_Faisal Cant | Kazimabad | 1154 | 40% | 461.6 | 10519705.22 | 1940.4
111 | I260295 | Model Town_Sh Faisal_Faisal Cant | Surti_Humaira_Jami | 1516 | 40% | 606.4 | 12216807.595 | 1971.42
112 | I260295 | Model Town_Sh Faisal_Faisal Cant | Alamgir&Jannat ul Barkat | 1020 | 40% | 408 | 7583418.9193 | 1115.291
113 | I260295 | Model Town_Sh Faisal_Faisal Cant | Pak Kausar Town | 1034 | 40% | 413.6 | 6765403.0162 | 1049.4
114 | I260295 | Model Town_Sh Faisal_Faisal Cant | Darakhshan Society PK1 | 222 | 40% | 88.8 | 3979448.6124 | 895.0324
115 | I260295 | Model Town_Sh Faisal_Faisal Cant | Darakhshan Society PK2 | 2078 | 40% | 831.2 | 15803943.4835 | 2554.8738
116 | I260295 | Model Town_Sh Faisal_Faisal Cant | Millat Garden | 610 | 40% | 244 | 5136341.9697 | 816.2
117 | I260295 | Model Town_Sh Faisal_Faisal Cant | Feeder |  |  |  | 144288500 | 42940
118 | I260295 | Model Town_Sh Faisal_Faisal Cant | Transportation |  |  |  | 4315000 | 0
119 | I260296 | Sukkur | NewSukkurCityTownship | 762 | 40% | 304.8 | 7542578.1916 | 1284.665
120 | I260296 | Sukkur | Unknown 11 | 670 | 40% | 268 | 11492216.9454 | 2551.85
121 | I260296 | Sukkur | Sukkur Township Pocket 1 | 2046 | 40% | 818.4 | 12123929.355 | 789.935
122 | I260296 | Sukkur | Sukkur Township P-2_KingCrystl2 | 1516 | 40% | 606.4 | 7990896.3184 | 667.7
123 | I260296 | Sukkur | Golimar Area | 292 | 40% | 116.8 | 3389734.3987 | 0
124 | I260296 | Sukkur | Sachal Township_Kings Crystal | 1864 | 40% | 745.6 | 12254249.1767 | 1459.35
125 | I260296 | Sukkur | Shikarpur Rd | 1058 | 40% | 423.2 | 16261340.1708 | 3277.2
126 | I260296 | Sukkur | 100 Feet Rd P1 | 1472 | 40% | 588.8 | 22129453.0529 | 5111.75
127 | I260296 | Sukkur | 100 Feet Rd P2 | 2416 | 40% | 966.4 | 26522963.7375 | 4135.4
128 | I260296 | Sukkur | Sukkur Ind Area | 350 | 40% | 140 | 11770055.9292 | 2834.75
129 | I260296 | Sukkur | Unknonwn_1 | 402 | 40% | 160.8 | 2664905.7008 | 0
130 | I260296 | Sukkur | Unknown 03 | 180 | 40% | 72 | 1604977.2113 | 0
131 | I260296 | Sukkur | Barrage Colony | 964 | 40% | 385.6 | 10509049.2072 | 1430
132 | I260296 | Sukkur | Main City P1 | 2372 | 40% | 948.8 | 17722825.1654 | 2280.45
133 | I260296 | Sukkur | Main City P2 | 2494 | 40% | 997.6 | 20560985.5305 | 2596.7
134 | I260296 | Sukkur | Feeder |  |  |  | 82409884 | 24103.3
135 | I260296 | Sukkur | Transportation |  |  |  | 5400000 | 0
136 | I260298 | Petaro Garrison, Hyderabad | Petaro | 740 | 40% | 296 | 7276483.8012 | 2118
137 | I260298 | Petaro Garrison, Hyderabad | Feeder |  |  |  | 3319155 | 2600
138 | I260298 | Petaro Garrison, Hyderabad | Transportation |  |  |  | 175000 | 0
139 | I260361 | Lhr MW City & Al Hafeez Ph-1 | Pocket-1 | 1948 | 40% | 779.2 | 30287495.44 | 16031.455
140 | I260361 | Lhr MW City & Al Hafeez Ph-1 | Pocket-2 | 828 | 40% | 331.2 | 27941058.86 | 16931.805
141 | I260361 | Lhr MW City & Al Hafeez Ph-1 | Pocket-3 | 2042 | 40% | 816.8 | 45803599.988 | 28458.1
142 | I260361 | Lhr MW City & Al Hafeez Ph-1 | Pocket-4 | 2728 | 40% | 1091.2 | 49809689.072 | 26927.89
143 | I260361 | Lhr MW City & Al Hafeez Ph-1 | Pocket-5 | 2654 | 40% | 1061.6 | 51751094.568 | 28172.705
144 | I260361 | Lhr MW City & Al Hafeez Ph-1 | Pocket-6 | 986 | 40% | 394.4 | 22463919.244 | 12747.9
145 | I260361 | Lhr MW City & Al Hafeez Ph-1 | Pocket-7 | 1778 | 40% | 711.2 | 45344853.868 | 27073.695
146 | I260361 | Lhr MW City & Al Hafeez Ph-1 | Al Hafeez Garden Ph-1 | 1406 | 40% | 562.4 | 23973146.368 | 10945.7
147 | I260361 | Lhr MW City & Al Hafeez Ph-1 | Feeder |  |  |  | 6136100 | 600
148 | I260361 | Lhr MW City & Al Hafeez Ph-1 | Transportation |  |  |  | 3600000 | 0

## Financials Data Bank- 18th Mar (hidden)
| * Total |  | 19228004048.84 | 3364041920.48 | 616853823.33 | 3978468675.8 | 13218303540.52
CEMz | Orders | Details | Budget | Actual | Commitment | Assigned | Available
I240188 | I240188000 | StormFiber Expansion – DHA | 6606972.94 | 6606972.94 |  | 6606972.94
I240188 | I240188001 | Cabinets & Accessories - | 8597643.82 | 52195.56 |  | 52195.56 | 8545448.26
I240188 | I240188002 | Consumable & Accessories | 2553619.57 | 23156.47 |  | 23156.47 | 2530463.1
I240188 | I240188003 | Cables - (Feeder Access | 4367822.49 | 741397.52 |  | 741397.52 | 3626424.97
I240188 | I240188004 | Enclosures - (Feeder Ac | 1011367.55 | 1269.94 |  | 1269.94 | 1010097.61
I240188 | I240188005 | Splitters - (Access & Dis | 1628109.57 | 18464.24 |  | 18464.24 | 1609645.33
I240188 | I240188006 | Duct - (HDPE / GI with | 3795143.99 |  |  |  | 3795143.99
I240188 | I240188007 | Handholes - (HH / Chamb | 8004000 |  |  |  | 8004000
I240188 | I240188008 | FDT Foundation | 40000 |  |  |  | 40000
I240188 | I240188009 | Infrastructure Laying - | 5764812.02 | 212290 | 4102970 | 4315260 | 1449552.02
I240188 | I240188010 | Cable Hauling - (Aerial | 2679920.4 | 10770 |  | 10770 | 2669150.4
I240188 | I240188011 | Building Attachments - | 990000 |  |  |  | 990000
I240188 | I240188012 | Transportation - (Vehic | 900000 |  |  |  | 900000
I240188 | I240188013 | Tool Kit - (Access) | 150000 | 109800 |  | 109800 | 40200
I240188 | I240188014 | Tool Kit - (Dev.) | 80000 |  |  |  | 80000
I240188 | I240188015 | Cable prepartion Tools - | 150000 |  |  |  | 150000
I240188 | I240188016 | Splice Machine | 800000 |  |  |  | 800000
I240188 | I240188017 | Cleavers | 400000 |  |  |  | 400000
I240188 | I240188018 | VFLS | 100000 |  |  |  | 100000
I240188 | I240188019 | PON Power Meters. | 600000 |  |  |  | 600000
I240188 | I240188020 | CATV Transmission Equipmen | 2094400 | 894755.6 |  | 894755.6 | 1199644.4
I240188 | I240188021 | PON cards | 2156000 |  |  |  | 2156000
I240188 | I240188022 | Bolan | 3600000 |  |  |  | 3600000
I240188 | I240189000 | StormFiber Expansion – Que | 23632807.92 | 23632807.92 |  | 23632807.92
I240189 | I240189001 | Cabinets & Accessories - | 3498481.35 | 416841.66 |  | 416841.66 | 3081639.69
I240189 | I240189002 | Consumable & Accessories | 2357620.89 | 1822312.18 |  | 1822312.18 | 535308.71
I240189 | I240189003 | Cables - (Feeder Access | 21840678.17 | 3295504.31 |  | 3295504.31 | 18545173.86
I240189 | I240189004 | Enclosures - (Feeder Ac | 913937.53 | 51921.69 |  | 51921.69 | 862015.84
I240189 | I240189005 | Splitters - (Access & Dis | 972582.45 | 127163.68 |  | 127163.68 | 845418.77
I240189 | I240189006 | Duct - (HDPE / GI with | 24188045.12 |  |  |  | 24188045.12
I240189 | I240189007 | Handholes - (HH / Chamb | 4112000 |  |  |  | 4112000
I240189 | I240189008 | Poles | 168000 |  |  |  | 168000
I240189 | I240189009 | FDT Foundation | 100000 |  |  |  | 100000
I240189 | I240189010 | Infrastructure Laying - | 26376051.33 |  |  |  | 26376051.33
I240189 | I240189011 | Cable Hauling - (Aerial | 3384838.5 |  |  |  | 3384838.5
I240189 | I240189012 | Building Attachments - | 1844500 |  |  |  | 1844500
I240189 | I240189013 | Transportation - (Vehic | 3050000 | 233720 |  | 233720 | 2816280
I240189 | I240189014 | Tool Kit - (Access) | 150000 | 126830 |  | 126830 | 23170
I240189 | I240189015 | Tool Kit - (Dev.) | 120000 |  |  |  | 120000
I240189 | I240189016 | Cable prepartion Tools - | 450000 | 2499.99 |  | 2499.99 | 447500.01
I240189 | I240189017 | Splice Machine | 1400000 | 737898.01 |  | 737898.01 | 662101.99
I240189 | I240189018 | Cleavers | 240000 | 190000 |  | 190000 | 50000
I240189 | I240189019 | VFLs | 120000 |  |  |  | 120000
I240189 | I240189020 | OTDR - For Core / FTTH b | 1075000 |  |  |  | 1075000
I240189 | I240189021 | PON Power Meters. | 480000 | 192174.13 |  | 192174.13 | 287825.87
I240189 | I240189022 | CATV Transmission Equipmen | 2372402.25 | 894755.6 |  | 894755.6 | 1477646.65
I240189 | I240189023 | PON Cards | 3407400 |  |  |  | 3407400
I240189 | I240189024 | Bolan | 4335120.73 | 16386.78 |  | 16386.78 | 4318733.95
I240189 | I240190000 | StormFiber Expansion – Sia | 40527705.86 | 40527705.86 |  | 40527705.86
I240190 | I240190001 | Cabinets & Accessories - | 4326752.64 | 253812.83 |  | 253812.83 | 4072939.81
I240190 | I240190002 | Consumable & Accessories | 1657151.4 | 1354458.88 |  | 1354458.88 | 302692.52
I240190 | I240190003 | Cables - (Feeder Access | 12392349.47 | 4056681.19 |  | 4056681.19 | 8335668.28
I240190 | I240190004 | Enclosures - (Feeder Ac | 653599.8 | 111050.93 |  | 111050.93 | 542548.87
I240190 | I240190005 | Splitters - (Access & Dis | 789646.42 | 34641.72 |  | 34641.72 | 755004.7
I240190 | I240190006 | Duct - (HDPE / GI with | 39249550.46 | 18541.86 |  | 18541.86 | 39231008.6
I240190 | I240190007 | Handholes - (HH / Chamb | 7293500 |  |  |  | 7293500
I240190 | I240190008 | Poles | 560000 |  |  |  | 560000
I240190 | I240190009 | FDT Foundation | 100000 |  |  |  | 100000
I240190 | I240190010 | Infrastructure Laying - | 15558347.5 |  |  |  | 15558347.5
I240190 | I240190011 | Cable Hauling - (Aerial | 4713513.6 |  |  |  | 4713513.6
I240190 | I240190012 | Building Attachments - | 782998.68 |  |  |  | 782998.68
I240190 | I240190013 | Transportation - (Vehic | 6000000 | 171050 |  | 171050 | 5828950
I240190 | I240190014 | Tool Kit - (Access) | 300000 | 308400 |  | 308400 | 8400.00-
I240190 | I240190015 | Tool Kit - (Dev.) | 80000 |  |  |  | 80000
I240190 | I240190016 | Cable prepartion Tools - | 150000 | 152480.62 |  | 152480.62 | 2480.62-
I240190 | I240190017 | Splice Machine | 792000 |  |  |  | 792000
I240190 | I240190018 | Cleavers | 400000 |  |  |  | 400000
I240190 | I240190019 | VFLs | 100000 |  |  |  | 100000
I240190 | I240190020 | PON Power Meters. | 600000 | 96045.46 |  | 96045.46 | 503954.54
I240190 | I240190021 | CATV Transmission Equipmen | 2094400 | 1802598.63 |  | 1802598.63 | 291801.37
I240190 | I240190022 | PON Cards | 5390000 |  |  |  | 5390000
I240190 | I240190023 | Bolan | 5240900.6 | 288005.86 |  | 288005.86 | 4952894.74
I240190 | I240435000 | StormFiber Expansion – Top | 14573649.93 | 14573649.93 |  | 14573649.93
I240435 | I240435001 | Cabinets & Accessories - | 11966911.04 | 716514.71 |  | 716514.71 | 11250396.33
I240435 | I240435002 | Consumable & Accessories | 2779361.65 | 1363192.39 |  | 1363192.39 | 1416169.26
I240435 | I240435003 | Cables - (Feeder Access | 29970939.44 | 3979863.61 |  | 3979863.61 | 25991075.83
I240435 | I240435004 | Enclosures - (Feeder Ac | 679142.77 | 159447.21 |  | 159447.21 | 519695.56
I240435 | I240435005 | Splitters - (Access & Dis | 4753039.41 | 180325.15 |  | 180325.15 | 4572714.26
I240435 | I240435006 | Duct - (HDPE / GI with | 2255374.9 | 775037.36 |  | 775037.36 | 1480337.54
I240435 | I240435007 | Handholes - (HH / Chamb | 620000 |  |  |  | 620000
I240435 | I240435008 | FDT Foundation | 90000 |  | 60000 | 60000 | 30000
I240435 | I240435009 | Infrastructure Laying - | 1387875.99 | 26499.99 | 768700 | 795199.99 | 592676
I240435 | I240435010 | Cable Hauling - (Aerial | 6644239 | 875000 | 1437875 | 2312875 | 4331364
I240435 | I240435011 | Building Attachments - | 1796855 |  |  |  | 1796855
I240435 | I240435012 | Transportation - (Vehic | 3740000 |  |  |  | 3740000
I240435 | I240435013 | Tool Kit - (Access) | 240000 | 190700 |  | 190700 | 49300
I240435 | I240435014 | Tool Kit - (Dev.) | 200000 |  |  |  | 200000
I240435 | I240435015 | Cable prepartion Tools - | 480000 | 232090.13 |  | 232090.13 | 247909.87
I240435 | I240435016 | Splice Machine | 2800000 | 401479.67 |  | 401479.67 | 2398520.33
I240435 | I240435017 | Cleavers | 320000 |  |  |  | 320000
I240435 | I240435018 | VFLs | 160000 |  |  |  | 160000
I240435 | I240435019 | OTDR - For Core / FTTH b | 700000 |  |  |  | 700000
I240435 | I240435020 | PON Power Mtr. | 640000 | 96087.07 |  | 96087.07 | 543912.93
I240435 | I240435021 | CATV Transmission Equipmen | 3407400 |  |  |  | 3407400
I240435 | I240435022 | OLT | 2697525 |  |  |  | 2697525
I240435 | I240435023 | PON Cards | 5111100 |  |  |  | 5111100
I240435 | I240435024 | Bolan | 17930875 | 1995240.00- | 17677125 | 15681885 | 2248990
I240435 | I240435025 | Switch | 851850 |  |  |  | 851850
I240435 | I240435026 | OLT connectivity SFPs Mult | 32938.2 |  |  |  | 32938.2
I240435 | I240435027 | Uplink SFPs for POP connec | 13814.6 | 13087.66 |  | 13087.66 | 726.94
I240435 | I240437000 | StormFiber Expansion – Ask | 58643039.61 | 58643039.61 |  | 58643039.61
I240437 | I240437001 | Cabinets & Accessories - | 16674157.71 | 790087.3 |  | 790087.3 | 15884070.41
I240437 | I240437002 | Consumable & Accessories | 3288517.68 | 637970.8 |  | 637970.8 | 2650546.88
I240437 | I240437003 | Cables - (Feeder Access | 29851148.54 | 2099045.05 |  | 2099045.05 | 27752103.49
I240437 | I240437004 | Enclosures - (Feeder Ac | 2247971.97 | 234476.25 |  | 234476.25 | 2013495.72
I240437 | I240437005 | Splitters - (Access & Dis | 7023232.87 | 165950.97 |  | 165950.97 | 6857281.9
I240437 | I240437006 | Duct - (HDPE / GI with | 44976229.59 | 2300795.08 |  | 2300795.08 | 42675434.51
I240437 | I240437007 | Handholes - (HH / Chamb | 15720000 |  |  |  | 15720000
I240437 | I240437008 | FDT Foundation | 60000 |  |  |  | 60000
I240437 | I240437009 | Infrastructure Laying - | 73804037.72 |  | 10400000 | 10400000 | 63404037.72
I240437 | I240437010 | Cable Hauling - (Aerial | 14222806.37 |  |  |  | 14222806.37
I240437 | I240437011 | Building Attachments - | 13985509.56 |  |  |  | 13985509.56
I240437 | I240437012 | Transportation - (Vehic | 4350000 |  |  |  | 4350000
I240437 | I240437013 | Tool Kit - (Access) | 360000 | 375660 |  | 375660 | 15660.00-
I240437 | I240437014 | Tool Kit - (Dev.) | 150000 |  |  |  | 150000
I240437 | I240437015 | Cable prepartion Tools - | 318332.3 | 15438.5 |  | 15438.5 | 302893.8
I240437 | I240437016 | Splice Machine | 2100000 |  |  |  | 2100000
I240437 | I240437017 | Cleavers | 480000 | 92658.18 |  | 92658.18 | 387341.82
I240437 | I240437018 | VFLs | 180000 |  |  |  | 180000
I240437 | I240437019 | OTDR - For Core / FTTH b | 700000 |  |  |  | 700000
I240437 | I240437020 | PON Power Mtr. | 720000 |  |  |  | 720000
I240437 | I240437021 | CATV Transmission Equipmen | 1945057.5 | 1802598.64 |  | 1802598.64 | 142458.86
I240437 | I240437022 | OLT | 2697525 |  |  |  | 2697525
I240437 | I240437023 | PON Cards | 5962950 |  |  |  | 5962950
I240437 | I240437024 | Bolan | 6561957.32 | 100446.24 |  | 100446.24 | 6461511.08
I240437 | I240438000 | StormFiber Expansion – Chi | 23399064.34 | 23399064.34 |  | 23399064.34
I240438 | I240438001 | Cabinets & Accessories - | 20184693.22 | 158984.29 |  | 158984.29 | 20025708.93
I240438 | I240438002 | Consumable & Accessories | 5081433.68 | 893424.2 |  | 893424.2 | 4188009.48
I240438 | I240438003 | Cables - (Feeder Access | 41821723.39 | 753944.01 |  | 753944.01 | 41067779.38
I240438 | I240438004 | Enclosures - (Feeder Ac | 3150138.58 | 761.99 |  | 761.99 | 3149376.59
I240438 | I240438005 | Splitters - (Access & Dis | 8875705.23 | 18673.35 |  | 18673.35 | 8857031.88
I240438 | I240438006 | Duct - (HDPE / GI with | 46781981.36 | 9500000.00- |  | 9500000.00- | 56281981.36
I240438 | I240438007 | Handholes - (HH / Chamb | 7936500 |  |  |  | 7936500
I240438 | I240438008 | Poles | 570000 |  |  |  | 570000
I240438 | I240438009 | FDT Foundation | 310000 |  |  |  | 310000
I240438 | I240438010 | Infrastructure Laying - | 22229016.9 | 23927324 |  | 23927324 | 1698307.10-
I240438 | I240438011 | Cable Hauling - (Aerial | 11667317 |  |  |  | 11667317
I240438 | I240438012 | Building Attachments - | 812000 |  |  |  | 812000
I240438 | I240438013 | Transportation - (Vehic | 3280000 |  |  |  | 3280000
I240438 | I240438014 | Tool Kit - (Access) | 300000 | 276400 |  | 276400 | 23600
I240438 | I240438015 | Tool Kit - (Dev.) | 100000 |  |  |  | 100000
I240438 | I240438016 | Cable prepartion Tools - | 240000 |  |  |  | 240000
I240438 | I240438017 | Splice Machine | 1400000 |  |  |  | 1400000
I240438 | I240438018 | Cleavers | 400000 |  |  |  | 400000
I240438 | I240438019 | VFLs | 160000 |  |  |  | 160000
I240438 | I240438020 | OTDR - For Core / FTTH b | 675000 |  |  |  | 675000
I240438 | I240438021 | PON Power Mtr. | 560000 |  |  |  | 560000
I240438 | I240438022 | CATV Transmission Equipmen | 1817280 | 1802598.64 |  | 1802598.64 | 14681.36
I240438 | I240438023 | PON Cards | 8518500 |  |  |  | 8518500
I240438 | I240438024 | Carry with Ladder | 5000000 |  | 2179000 | 2179000 | 2821000
I240438 | I240438025 | Bolan | 1800000 |  |  |  | 1800000
I240438 | I240440000 | StormFiber Expansion – Lah | 53404413.16 | 53404413.16 |  | 53404413.16
I240440 | I240440001 | Cabinets & Accessories - | 31966433.41 | 745233.67 |  | 745233.67 | 31221199.74
I240440 | I240440002 | Consumable & Accessories | 5807873.75 | 613571.9 |  | 613571.9 | 5194301.85
I240440 | I240440003 | Cables - (Feeder Access | 50046994.2 | 1325259.2 |  | 1325259.2 | 48721735
I240440 | I240440004 | Enclosures - (Feeder Ac | 2499128.73 | 106529.8 |  | 106529.8 | 2392598.93
I240440 | I240440005 | Splitters - (Access & Dis | 10305147.05 | 51837.81 |  | 51837.81 | 10253309.24
I240440 | I240440006 | Duct - (HDPE / GI with | 66749136.4 | 5471840.14 |  | 5471840.14 | 61277296.26
I240440 | I240440007 | Handholes - (HH / Chamb | 31767000 | 2893500 | 3161000 | 6054500 | 25712500
I240440 | I240440008 | FDT Foundation | 250137.91 | 49499.56 |  | 49499.56 | 200638.35
I240440 | I240440009 | Infrastructure Laying - | 92504854.79 | 32780.00- | 9856125 | 9823345 | 82681509.79
I240440 | I240440010 | Cable Hauling - (Aerial | 10058474.58 |  |  |  | 10058474.58
I240440 | I240440011 | Building Attachments - | 2287998.12 |  |  |  | 2287998.12
I240440 | I240440012 | Transportation - (Vehic | 3340000 |  |  |  | 3340000
I240440 | I240440013 | Tool Kit - (Access) | 375000 | 345000 |  | 345000 | 30000
I240440 | I240440014 | Tool Kit - (Dev.) | 300000 |  |  |  | 300000
I240440 | I240440015 | Cable prepartion Tools - | 900000 |  |  |  | 900000
I240440 | I240440016 | Splice Machine | 4800000 | 1164174.57 |  | 1164174.57 | 3635825.43
I240440 | I240440017 | Cleavers | 400000 |  |  |  | 400000
I240440 | I240440018 | VFLs | 220000 |  |  |  | 220000
I240440 | I240440019 | OTDR - For Core / FTTH b | 1400000 |  |  |  | 1400000
I240440 | I240440020 | PON Power Mtr. | 1320000 | 48043.54 |  | 48043.54 | 1271956.46
I240440 | I240440021 | CATV Transmission Equipmen | 4784557.5 | 4506496.55 |  | 4506496.55 | 278060.95
I240440 | I240440022 | PON Cards | 10222200 |  |  |  | 10222200
I240440 | I240440023 | Carry with ladder | 5000000 |  | 2179000 | 2179000 | 2821000
I240440 | I240440024 | Bolan | 3600000 |  |  |  | 3600000
I240440 | I240442000 | StormFiber Expansion – Chi | 8728453.36 | 8728453.36 |  | 8728453.36
I240442 | I240442001 | Cabinets & Accessories - | 6623469.65 | 200451.49 |  | 200451.49 | 6423018.16
I240442 | I240442002 | Consumable & Accessories | 1591400 | 1192701.02 |  | 1192701.02 | 398698.98
I240442 | I240442003 | Cables - (Feeder Access | 25537960.93 | 4378626.7 |  | 4378626.7 | 21159334.23
I240442 | I240442004 | Enclosures - (Feeder Ac | 608686.44 | 114283.33 |  | 114283.33 | 494403.11
I240442 | I240442005 | Splitters - (Access & Dis | 532123.63 | 77130.52 |  | 77130.52 | 454993.11
I240442 | I240442006 | Duct - (HDPE / GI with | 27293801.75 |  |  |  | 27293801.75
I240442 | I240442007 | Handholes - (HH / Cham | 3088500 |  |  |  | 3088500
I240442 | I240442008 | Poles | 1344000 |  | 112000 | 112000 | 1232000
I240442 | I240442009 | FDT Foundation | 80000 |  | 40000 | 40000 | 40000
I240442 | I240442010 | Infrastructure Laying - | 35424288 | 555000 |  | 555000 | 34869288
I240442 | I240442011 | Cable Hauling - (Aerial | 5721245.1 | 1515640 | 794760 | 2310400 | 3410845.1
I240442 | I240442012 | Transportation - (Vehic | 4250000 | 257000 |  | 257000 | 3993000
I240442 | I240442013 | Tool Kit - (Access) | 180000 | 103250 |  | 103250 | 76750
I240442 | I240442014 | Tool Kit - (Dev.) | 50000 | 50000 |  | 50000
I240442 | I240442015 | Cable prepartion Tools - | 120000 |  |  |  | 120000
I240442 | I240442016 | Splice Machine | 700000 | 525000 |  | 525000 | 175000
I240442 | I240442017 | Cleavers | 240000 |  |  |  | 240000
I240442 | I240442018 | VFLs | 120000 |  |  |  | 120000
I240442 | I240442019 | OTDR - For Core / FTTH b | 675000 | 365000 |  | 365000 | 310000
I240442 | I240442020 | PON Power Mtr. | 250000 | 96087.06 |  | 96087.06 | 153912.94
I240442 | I240442021 | CATV Transmission Equipmen | 3080857.5 |  |  |  | 3080857.5
I240442 | I240442022 | Bolan | 3600000 | 935.3 |  | 935.3 | 3599064.7
I240442 | I240442023 | Carry with ladder | 1800000 |  |  |  | 1800000
I240442 | I240442024 | OLT | 2697525 |  |  |  | 2697525
I240442 | I240442025 | PON cards | 2555550 |  |  |  | 2555550
I240442 | I240442026 | Switch | 851850 |  |  |  | 851850
I240442 | I240459000 | STORMFIBER EXPANSION – ASK | 3240589.35 | 3240589.35 |  | 3240589.35
I240459 | I240459001 | Cabinets & Accessories - | 1082081.97 | 1366.53 |  | 1366.53 | 1080715.44
I240459 | I240459002 | Consumable & Accessories | 240174.35 | 121723.47 |  | 121723.47 | 118450.88
I240459 | I240459003 | Cables - (Feeder Access | 1305899.39 | 38696.11 |  | 38696.11 | 1267203.28
I240459 | I240459004 | Enclosures - (Feeder Ac | 179889.04 | 499.37 |  | 499.37 | 179389.67
I240459 | I240459005 | Splitters - (Access & Dis | 538311.13 |  |  |  | 538311.13
I240459 | I240459006 | Duct - (HDPE / GI with | 3035121.56 |  |  |  | 3035121.56
I240459 | I240459007 | Handholes - (HH / Chamb | 657000 |  |  |  | 657000
I240459 | I240459008 | FDT Foundation | 50000 |  |  |  | 50000
I240459 | I240459009 | Infrastructure Laying - | 1176342.4 |  |  |  | 1176342.4
I240459 | I240459010 | Cable Hauling - (Aerial | 561858.4 |  |  |  | 561858.4
I240459 | I240459011 | Tool Kit - (Access) | 150000 | 84030 |  | 84030 | 65970
I240459 | I240459012 | Tool Kit - (Dev.) | 160000 |  |  |  | 160000
I240459 | I240459013 | Cable preparation Tools | 300000 |  |  |  | 300000
I240459 | I240459015 | Cleavers | 160000 | 57000 |  | 57000 | 103000
I240459 | I240459016 | VFLs | 80000 |  |  |  | 80000
I240459 | I240459017 | OTDR - For Core / FTTH b | 700000 |  |  |  | 700000
I240459 | I240459018 | PON Power Mtr. | 320000 |  |  |  | 320000
I240459 | I240459019 | CATV Transmission Equipmen | 2129625 | 1802598.64 |  | 1802598.64 | 327026.36
I240459 | I240459020 | PON Cards | 851850 |  |  |  | 851850
I240459 | I240518000 | StormFiber Expansion – Mis | 46221961.23 | 46221961.23 |  | 46221961.23
I240518 | I240518001 | Cabinets & Accessories - | 7758642.19 | 277271.48 |  | 277271.48 | 7481370.71
I240518 | I240518002 | Consumable & Accessories | 1752844.96 | 86255.61 |  | 86255.61 | 1666589.35
I240518 | I240518003 | Cables - (Feeder Access | 6214392.81 | 2304511.27 |  | 2304511.27 | 3909881.54
I240518 | I240518004 | Enclosures - (Feeder Ac | 985071.12 | 20716.73 |  | 20716.73 | 964354.39
I240518 | I240518005 | Splitters - (Access & Dis | 3801893.17 | 79354.62 |  | 79354.62 | 3722538.55
I240518 | I240518006 | Duct - (HDPE / GI with | 17220507.85 |  |  |  | 17220507.85
I240518 | I240518007 | Handholes - (HH / Chamb | 10027500 |  |  |  | 10027500
I240518 | I240518008 | FDT Foundation | 68615.78 |  |  |  | 68615.78
I240518 | I240518009 | Infrastructure Laying - | 8356874.55 |  | 24145 | 24145 | 8332729.55
I240518 | I240518010 | Cable Hauling - (Aerial | 3542940.4 |  |  |  | 3542940.4
I240518 | I240518011 | Building Attachments - | 1937502 |  |  |  | 1937502
I240518 | I240518012 | Transportation - (Vehic | 1590000 |  |  |  | 1590000
I240518 | I240518013 | Tool Kit - (Access) | 150000 |  |  |  | 150000
I240518 | I240518014 | Tool Kit - (Dev.) | 160000 |  |  |  | 160000
I240518 | I240518015 | Cable preparation Tools | 300000 |  |  |  | 300000
I240518 | I240518016 | Splice Machine | 1600000 | 10755.16 |  | 10755.16 | 1589244.84
I240518 | I240518017 | Cleavers | 480000 |  |  |  | 480000
I240518 | I240518018 | VFLs | 120000 |  |  |  | 120000
I240518 | I240518019 | OTDR - For Core / FTTH b | 1400000 |  |  |  | 1400000
I240518 | I240518020 | PON Power Mtr. | 720000 |  |  |  | 720000
I240518 | I240518021 | CATV Transmission Equipeme | 1064812.5 |  |  |  | 1064812.5
I240518 | I240518022 | PON Cards | 1703700 |  |  |  | 1703700
I240518 | I240518023 | Bolan | 3599429.56 | 0.01- | 1949700 | 1949699.99 | 1649729.57
I240518 | I240519001 | Cabinets & Accessories - | 13373000 |  |  |  | 13373000
I240519 | I240519002 | Consumable & Accessories | 2738100 |  |  |  | 2738100
I240519 | I240519003 | Cables - (Feeder Access | 32864149.71 |  |  |  | 32864149.71
I240519 | I240519004 | Enclosures - (Feeder Ac | 1971797.46 |  |  |  | 1971797.46
I240519 | I240519005 | Splitters - (Access & Dis | 6030985.48 |  |  |  | 6030985.48
I240519 | I240519006 | Duct - (HDPE / GI with | 54747638.94 |  |  |  | 54747638.94
I240519 | I240519007 | Handholes - (HH / Chamb | 21660000 |  |  |  | 21660000
I240519 | I240519008 | FDT Foundation | 225000 |  |  |  | 225000
I240519 | I240519009 | Infrastructure Laying - | 102021741.43 |  |  |  | 102021741.43
I240519 | I240519010 | Cable Hauling - (Aerial | 8911103.5 |  |  |  | 8911103.5
I240519 | I240519011 | Building Attachments - | 49363491.54 |  |  |  | 49363491.54
I240519 | I240519012 | Transportation - (Vehic | 3675000 |  |  |  | 3675000
I240519 | I240519013 | Tool Kit - (Access) | 450000 |  |  |  | 450000
I240519 | I240519014 | Tool Kit - (Dev.) | 400000 |  |  |  | 400000
I240519 | I240519015 | Cable preparation Tools | 750000 |  |  |  | 750000
I240519 | I240519016 | Splice Machine | 4000000 |  |  |  | 4000000
I240519 | I240519017 | Cleavers | 480000 |  |  |  | 480000
I240519 | I240519018 | VFLs | 200000 |  |  |  | 200000
I240519 | I240519019 | OTDR - For Core / FTTH b | 1400000 |  |  |  | 1400000
I240519 | I240519020 | PON Power Mtr. | 1200000 |  |  |  | 1200000
I240519 | I240519021 | CATV Transmission Equipeme | 8348130 |  |  |  | 8348130
I240519 | I240519022 | PON Cards | 5111100 |  |  |  | 5111100
I240519 | I240519023 | OLT | 2697525 |  |  |  | 2697525
I240519 | I240519024 | Switch | 851850 |  |  |  | 851850
I240519 | I240519025 | OLT connectivity SFPs Mult | 32938.2 |  |  |  | 32938.2
I240519 | I240519026 | Uplink SFPs for POP connec | 98814.6 |  |  |  | 98814.6
I240519 | I240519027 | Bolan | 9000000 |  |  |  | 9000000
I240519 | I240537000 | StormFiber Expansion – Abb | 5337898.44 | 5337898.44 |  | 5337898.44
I240537 | I240537001 | Cabinets & Accessories - | 3701341.05 | 463518.8 |  | 463518.8 | 3237822.25
I240537 | I240537002 | Consumable & Accessories | 938337.48 | 769486.74 |  | 769486.74 | 168850.74
I240537 | I240537003 | Cables - (Feeder Access | 6084143.95 | 3209255.47 |  | 3209255.47 | 2874888.48
I240537 | I240537004 | Enclosures - (Feeder Ac | 257101.69 | 243196.38 |  | 243196.38 | 13905.31
I240537 | I240537005 | Splitters - (Access & Dis | 757776.9 | 19188.75 |  | 19188.75 | 738588.15
I240537 | I240537006 | Duct - (HDPE / GI with | 1329172.72 |  |  |  | 1329172.72
I240537 | I240537007 | Handholes - (HH / Chamb | 154000 |  |  |  | 154000
I240537 | I240537008 | Poles | 840000 |  |  |  | 840000
I240537 | I240537009 | FDT Foundation | 30000 |  |  |  | 30000
I240537 | I240537010 | Infrastructure Laying - | 46519.3 |  |  |  | 46519.3
I240537 | I240537011 | Cable Hauling - (Aerial | 2318548 | 2222860 | 77140 | 2300000 | 18548
I240537 | I240537012 | Building Attachments - | 1046460 |  |  |  | 1046460
I240537 | I240537013 | Transportation - (Vehic | 540000 |  |  |  | 540000
I240537 | I240537014 | Tool Kit - (Access) | 150000 | 148850 |  | 148850 | 1150
I240537 | I240537015 | Tool Kit - (Dev.) | 80000 | 25000 |  | 25000 | 55000
I240537 | I240537016 | Cable preparation Tools | 150000 |  |  |  | 150000
I240537 | I240537017 | Splice Machine | 796270.19 | 766499.86 |  | 766499.86 | 29770.33
I240537 | I240537018 | Cleavers | 240000 | 19000 |  | 19000 | 221000
I240537 | I240537019 | VFLs | 60000 |  |  |  | 60000
I240537 | I240537020 | PON Power Mtr. | 360000 | 48043.53 |  | 48043.53 | 311956.47
I240537 | I240537021 | CATV Transmission Equipmen | 965430 | 901299.31 |  | 901299.31 | 64130.69
I240537 | I240537022 | PON Cards | 1703700 |  |  |  | 1703700
I240537 | I240537023 | Bolan | 3900000 |  | 1949700 | 1949700 | 1950300
I240537 | I240538000 | StormFiber Expansion – Har | 13069988.05 | 13069988.05 |  | 13069988.05
I240538 | I240538001 | Cabinets & Accessories - | 14585209.98 | 590561.85 |  | 590561.85 | 13994648.13
I240538 | I240538002 | Consumable & Accessories | 3390190.61 | 739274.79 |  | 739274.79 | 2650915.82
I240538 | I240538003 | Cables - (Feeder Access | 31444645.43 | 5324914.09 |  | 5324914.09 | 26119731.34
I240538 | I240538004 | Enclosures - (Feeder Ac | 2172672.05 | 285110.54 |  | 285110.54 | 1887561.51
I240538 | I240538005 | Splitters - (Access & Dis | 5183772.95 | 535788.77 |  | 535788.77 | 4647984.18
I240538 | I240538006 | Duct - (HDPE / GI with | 44451537.66 | 16025.23 |  | 16025.23 | 44435512.43
I240538 | I240538007 | Handholes - (HH / Chamb | 4834000 | 187000 |  | 187000 | 4647000
I240538 | I240538008 | Poles | 3300000 |  |  |  | 3300000
I240538 | I240538009 | FDT Foundation | 360000 | 14000 |  | 14000 | 346000
I240538 | I240538010 | Infrastructure Laying - | 34774340 | 471250 |  | 471250 | 34303090
I240538 | I240538011 | Cable Hauling - (Aerial | 7952802.5 | 2124580 | 1872460 | 3997040 | 3955762.5
I240538 | I240538012 | Building Attachments - | 32767000 |  |  |  | 32767000
I240538 | I240538013 | Transportation - (Vehic | 3960000 |  |  |  | 3960000
I240538 | I240538014 | Tool Kit - (Access) | 225000 | 24251.42 |  | 24251.42 | 200748.58
I240538 | I240538015 | Tool Kit - (Dev.) | 160000 |  |  |  | 160000
I240538 | I240538016 | Cable preparation Tools | 300000 | 6732.85 |  | 6732.85 | 293267.15
I240538 | I240538017 | Splice Machine | 1600000 |  |  |  | 1600000
I240538 | I240538018 | Cleavers | 240000 |  |  |  | 240000
I240538 | I240538019 | VFLs | 100000 |  |  |  | 100000
I240538 | I240538020 | OTDR - For Core / FTTH b | 675000 |  |  |  | 675000
I240538 | I240538021 | PON Power Mtr. | 600000 |  |  |  | 600000
I240538 | I240538022 | CATV Transmission Equipmen | 2058637.5 |  |  |  | 2058637.5
I240538 | I240538023 | PON cards | 4259250 |  |  |  | 4259250
I240538 | I240538024 | Carry with ladder | 2500000 | 205000 | 2254000 | 2459000 | 41000
I240538 | I240538025 | Bolan | 3900000 |  |  |  | 3900000
I240538 | I240539000 | StormFiber Expansion – Swa | 19700450.35 | 19700450.35 |  | 19700450.35
I240539 | I240539001 | Cabinets & Accessories - | 26228265.86 | 3991826.99 |  | 3991826.99 | 22236438.87
I240539 | I240539002 | Consumable & Accessories | 7066994.71 | 5405693.08 |  | 5405693.08 | 1661301.63
I240539 | I240539003 | Cables - (Feeder Access | 55327638.71 | 11686421.75 |  | 11686421.75 | 43641216.96
I240539 | I240539004 | Enclosures - (Feeder Ac | 3435692.42 | 972295.99 |  | 972295.99 | 2463396.43
I240539 | I240539005 | Splitters - (Access & Dis | 8847995.54 | 1740268.07 |  | 1740268.07 | 7107727.47
I240539 | I240539006 | Duct - (HDPE / GI with | 39540802.63 | 1109527.02 |  | 1109527.02 | 38431275.61
I240539 | I240539007 | Handholes - (HH / Chamb | 3608000 |  |  |  | 3608000
I240539 | I240539008 | Poles | 4710000 |  |  |  | 4710000
I240539 | I240539009 | FDT Foundation | 540000 |  |  |  | 540000
I240539 | I240539010 | Infrastructure Laying - | 40151148 |  |  |  | 40151148
I240539 | I240539011 | Cable Hauling - (Aerial | 15900781 |  |  |  | 15900781
I240539 | I240539012 | Building Attachments - | 36715452 |  |  |  | 36715452
I240539 | I240539013 | Transportation - (Vehic | 810000 | 143000 |  | 143000 | 667000
I240539 | I240539014 | Tool Kit - (Access) | 450000 | 163250 |  | 163250 | 286750
I240539 | I240539015 | Tool Kit - (Dev.) | 320000 | 25000 |  | 25000 | 295000
I240539 | I240539016 | Cable preparation Tools | 556182.98 | 43217.28 |  | 43217.28 | 512965.7
I240539 | I240539017 | Splice Machine | 3200000 | 698788.47 |  | 698788.47 | 2501211.53
I240539 | I240539018 | Cleavers | 480000 | 91735.68 |  | 91735.68 | 388264.32
I240539 | I240539019 | VFLs | 200000 | 2686.81 |  | 2686.81 | 197313.19
I240539 | I240539020 | OTDR - For Core / FTTH b | 675000 |  |  |  | 675000
I240539 | I240539021 | PON Power Mtr. | 1200000 | 93043.53 |  | 93043.53 | 1106956.47
I240539 | I240539022 | CATV Transmission Equipmen | 3308017.5 |  |  |  | 3308017.5
I240539 | I240539023 | PON Cards | 8518500 |  |  |  | 8518500
I240539 | I240539024 | Bolan | 7200000 |  |  |  | 7200000
I240539 | I240539025 | Carry with Ladder | 2500000 |  |  |  | 2500000
I240539 | I240540000 | StormFiber Expansion – Mar | 24383593.99 | 24383593.99 |  | 24383593.99
I240540 | I240540001 | Cabinets & Accessories - | 22163060.61 | 1553128.2 |  | 1553128.2 | 20609932.41
I240540 | I240540002 | Consumable & Accessories | 8587251.35 | 2379826.99 |  | 2379826.99 | 6207424.36
I240540 | I240540003 | Cables - (Feeder Access | 54650932.71 | 6587884.69 |  | 6587884.69 | 48063048.02
I240540 | I240540004 | Enclosures - (Feeder Ac | 2814859.14 | 594313.2 |  | 594313.2 | 2220545.94
I240540 | I240540005 | Splitters - (Access & Dis | 7666707.98 | 775387.89 |  | 775387.89 | 6891320.09
I240540 | I240540006 | Duct - (HDPE / GI with | 26938132.71 |  | 48400 | 48400 | 26889732.71
I240540 | I240540007 | Handholes - (HH / Chamb | 4222000 |  |  |  | 4222000
I240540 | I240540008 | Poles | 3320000 | 20000 | 280000 | 300000 | 3020000
I240540 | I240540009 | FDT Foundation | 660000 |  | 200000 | 200000 | 460000
I240540 | I240540010 | Infrastructure Laying - | 23772456.35 | 2519000 | 3030075 | 5549075 | 18223381.35
I240540 | I240540011 | Cable Hauling - (Aerial | 16463355 | 1455120 | 1488880 | 2944000 | 13519355
I240540 | I240540012 | Building Attachments - | 306000 |  |  |  | 306000
I240540 | I240540013 | Transportation - (Vehic | 3900000 |  |  |  | 3900000
I240540 | I240540014 | Tool Kit - (Access) | 375000 | 106860 |  | 106860 | 268140
I240540 | I240540015 | Tool Kit - (Dev.) | 224000 | 2686.85 |  | 2686.85 | 221313.15
I240540 | I240540016 | Cable preparation Tools | 450000 |  |  |  | 450000
I240540 | I240540017 | Splice Machine | 2400000 | 7459.61 |  | 7459.61 | 2392540.39
I240540 | I240540018 | Cleavers | 400000 |  |  |  | 400000
I240540 | I240540019 | VFLs | 160000 |  |  |  | 160000
I240540 | I240540020 | OTDR - For Core / FTTH b | 675000 |  |  |  | 675000
I240540 | I240540021 | PON Power Mtr. | 960000 | 48022.73 |  | 48022.73 | 911977.27
I240540 | I240540022 | CATV Transmission Equipmen | 3024067.5 | 894755.6 |  | 894755.6 | 2129311.9
I240540 | I240540023 | PON Cards | 6814800 |  |  |  | 6814800
I240540 | I240540024 | Bolan | 5400000 |  |  |  | 5400000
I240540 | I240540025 | Carry with Ladder | 2500000 |  |  |  | 2500000
I240540 | I240557000 | StormFiber Expansion – Kal | 3210324.26 | 3210324.26 |  | 3210324.26
I240557 | I240557001 | Cabinets & Accessories - | 1678992.86 | 19567.78 |  | 19567.78 | 1659425.08
I240557 | I240557002 | Consumable & Accessories | 397800 | 12412.56 |  | 12412.56 | 385387.44
I240557 | I240557003 | Cables - (Feeder Access | 4627848.8 | 90981.87 |  | 90981.87 | 4536866.93
I240557 | I240557004 | Enclosures - (Feeder Ac | 295462 | 10314.99 |  | 10314.99 | 285147.01
I240557 | I240557005 | Splitters - (Access & Dis | 682656.45 | 32135.79 |  | 32135.79 | 650520.66
I240557 | I240557006 | Duct - (HDPE / GI with | 4334773.33 |  |  |  | 4334773.33
I240557 | I240557007 | Handholes - (HH / Chamb | 726000 |  |  |  | 726000
I240557 | I240557008 | Poles | 300000 |  |  |  | 300000
I240557 | I240557009 | FDT Foundation | 40000 |  |  |  | 40000
I240557 | I240557010 | Infrastructure Laying - | 770400 |  |  |  | 770400
I240557 | I240557011 | Cable Hauling - (Aerial | 1701415 |  |  |  | 1701415
I240557 | I240557012 | Building Attachments - | 669500 |  |  |  | 669500
I240557 | I240557013 | Transportation - (Vehic | 685000 |  |  |  | 685000
I240557 | I240557014 | Tool Kit - (Access) | 75000 | 27660 |  | 27660 | 47340
I240557 | I240557015 | Tool Kit - (Dev.) | 50000 |  |  |  | 50000
I240557 | I240557016 | Cable prepartion Tools - | 150000 | 360 |  | 360 | 149640
I240557 | I240557017 | Cleavers | 80000 | 45464.73 |  | 45464.73 | 34535.27
I240557 | I240557018 | VFLs | 20000 |  |  |  | 20000
I240557 | I240557019 | PON Power Mtr. | 240000 | 211161.39 |  | 211161.39 | 28838.61
I240557 | I240678000 | StormFiber Expansion – Dev | 47815770.8 | 47815770.8 |  | 47815770.8
I240678 | I240678001 | Cabinets & Accessories - | 37183752.84 | 3575414.79 |  | 3575414.79 | 33608338.05
I240678 | I240678002 | Consumable & Accessories | 8085881.63 | 2515398.83 |  | 2515398.83 | 5570482.8
I240678 | I240678003 | Cables - (Feeder Access | 67180622.96 | 6491792.46 |  | 6491792.46 | 60688830.5
I240678 | I240678004 | Enclosures - (Feeder Ac | 3828548.51 | 441610.69 |  | 441610.69 | 3386937.82
I240678 | I240678005 | Splitters - (Access & Dis | 13750628.63 | 1389015.3 |  | 1389015.3 | 12361613.33
I240678 | I240678006 | Duct - (HDPE / GI with | 83407258.87 | 2004456.7 |  | 2004456.7 | 81402802.17
I240678 | I240678007 | Handholes - (HH / Chamb | 21128500 | 198000 | 33000 | 231000 | 20897500
I240678 | I240678008 | Poles | 3450000 |  |  |  | 3450000
I240678 | I240678009 | FDT Foundation | 775000 | 34000 |  | 34000 | 741000
I240678 | I240678010 | Infrastructure Laying - | 95860589.3 | 435625 | 744600 | 1180225 | 94680364.3
I240678 | I240678011 | Cable Hauling - (Aerial | 18579414.35 | 7775370 | 1320720 | 9096090 | 9483324.35
I240678 | I240678012 | Building Attachments - ( | 5040000 |  |  |  | 5040000
I240678 | I240678013 | Transportation - (Vehic | 7000000 |  |  |  | 7000000
I240678 | I240678014 | Tool Kit - (Access) | 525000 | 520810 |  | 520810 | 4190
I240678 | I240678015 | Tool Kit - (Dev.) | 800000 |  |  |  | 800000
I240678 | I240678016 | Cable prepartion Tools - | 750000 | 113032.78 |  | 113032.78 | 636967.22
I240678 | I240678017 | Splice Machine | 3972270.19 | 749191.22 |  | 749191.22 | 3223078.97
I240678 | I240678018 | Cleavers | 1120000 | 76000 |  | 76000 | 1044000
I240678 | I240678019 | VFLs | 380000 |  |  |  | 380000
I240678 | I240678020 | OTDR - For Core / FTTH b | 1750000 |  |  |  | 1750000
I240678 | I240678021 | PON Power Mtr. | 2280000 | 192338.98 |  | 192338.98 | 2087661.02
I240678 | I240678022 | CATV Transmission Equipmen | 1930860 | 1789511.2 |  | 1789511.2 | 141348.8
I240678 | I240678023 | PON Cards | 7666650 | 3531787.99 |  | 3531787.99 | 4134862.01
I240678 | I240678024 | OLT | 2697525 | 1803964.62 |  | 1803964.62 | 893560.38
I240678 | I240678025 | OLT connectivity SFPs Mult | 16469.1 |  |  |  | 16469.1
I240678 | I240678026 | Uplink SFPs for POP connec | 49407.3 | 32163.49 |  | 32163.49 | 17243.81
I240678 | I240678027 | Bolan | 6906205.97 | 465755.97 | 6457700 | 6923455.97 | 17250.00-
I240678 | I240678028 | Carry | 7500000 | 205000 | 6612000 | 6817000 | 683000
I240678 | I240679000 | StormFiber Expansion – Dev | 546545.29 | 546545.29 |  | 546545.29
I240679 | I240679001 | Cabinets & Accessories - | 2989446.12 | 181712.03 |  | 181712.03 | 2807734.09
I240679 | I240679002 | Consumable & Accessories | 628165.42 | 124111.08 |  | 124111.08 | 504054.34
I240679 | I240679003 | Cables - (Feeder Access | 4618605.71 | 297815.21 |  | 297815.21 | 4320790.5
I240679 | I240679004 | Enclosures - (Feeder Ac | 19051.64 | 18236.9 |  | 18236.9 | 814.74
I240679 | I240679005 | Splitters - (Access & Dis | 1440955.86 | 58563.68 |  | 58563.68 | 1382392.18
I240679 | I240679006 | CATV Transmission Equipmen | 3265425 | 894755.6 |  | 894755.6 | 2370669.4
I240679 | I240679007 | PON Cards | 4259250 |  |  |  | 4259250
I240679 | I240679008 | Carry | 5000000 |  |  |  | 5000000
I240679 | I240679009 | Bolan | 3600000 |  |  |  | 3600000
I240679 | I240679010 | Access tool kits | 375000 | 19000 |  | 19000 | 356000
I240679 | I240679011 | Clever | 400000 |  |  |  | 400000
I240679 | I240679012 | PON Meters | 960000 |  |  |  | 960000
I240679 | I240679013 | VFL | 160000 |  |  |  | 160000
I240679 | I240679014 | DEV Tool Kits and Cable pr | 600000 |  |  |  | 600000
I240679 | I240679015 | OTDR | 975000 |  |  |  | 975000
I240679 | I240679016 | Splicing Machines | 2400000 |  |  |  | 2400000
I240679 | I240680000 | StormFiber Expansion – Dev | 11280616.03 | 11280616.03 |  | 11280616.03
I240680 | I240680001 | Cabinets & Accessories - | 14998426.84 | 32797.6 |  | 32797.6 | 14965629.24
I240680 | I240680002 | Consumable & Accessories | 3134578.96 | 345001.25 |  | 345001.25 | 2789577.71
I240680 | I240680003 | Cables - (Feeder Access | 15702401.45 | 4477907.44 |  | 4477907.44 | 11224494.01
I240680 | I240680004 | Enclosures - (Feeder Ac | 2011153.03 | 43616.83 |  | 43616.83 | 1967536.2
I240680 | I240680005 | Splitters - (Access & Dis | 5403288.6 | 47033.22 |  | 47033.22 | 5356255.38
I240680 | I240680006 | Duct - (HDPE / GI with | 24367006.63 | 108332.7 |  | 108332.7 | 24258673.93
I240680 | I240680007 | Handholes - (HH / Chamb | 6597980 |  |  |  | 6597980
I240680 | I240680008 | FDT Foundation | 360000 |  |  |  | 360000
I240680 | I240680009 | Infrastructure Laying - | 38789036.21 |  | 4850000 | 4850000 | 33939036.21
I240680 | I240680010 | Cable Hauling - (Aerial | 6164985 |  |  |  | 6164985
I240680 | I240680011 | Building Attachments - | 2819654 |  |  |  | 2819654
I240680 | I240680012 | Transportation - (Vehic | 2200000 | 458900 |  | 458900 | 1741100
I240680 | I240680013 | Tool Kit - (Access) | 375000 | 250560 |  | 250560 | 124440
I240680 | I240680014 | Tool Kit - (Dev.) | 160000 |  |  |  | 160000
I240680 | I240680015 | Cable prepartion Tools - | 300000 |  |  |  | 300000
I240680 | I240680016 | Splice Machine | 1600000 | 422322.78 |  | 422322.78 | 1177677.22
I240680 | I240680017 | Cleavers | 400000 |  |  |  | 400000
I240680 | I240680018 | VFLs | 160000 |  |  |  | 160000
I240680 | I240680019 | OTDR - For Core / FTTH b | 1350000 |  |  |  | 1350000
I240680 | I240680020 | PON Power Mtr. | 600000 |  |  |  | 600000
I240680 | I240680021 | CATV Transmission Equipmen | 3208635 | 894755.6 |  | 894755.6 | 2313879.4
I240680 | I240680022 | PON Cards | 4259250 |  |  |  | 4259250
I240680 | I240680023 | Bolan | 3900000 |  | 1949700 | 1949700 | 1950300
I240680 | I240680024 | Carry | 5000000 | 410000 | 4508000 | 4918000 | 82000
I240680 | I240681000 | StormFiber Expansion – Dev | 3750661.42 | 3750661.42 |  | 3750661.42
I240681 | I240681001 | Cables - (Feeder Access | 1430095 | 74445.45 |  | 74445.45 | 1355649.55
I240681 | I240681002 | Enclosures - (Feeder Ac | 44000 |  |  |  | 44000
I240681 | I240681003 | Duct - (HDPE / GI with | 1797702.58 | 183332.6 |  | 183332.6 | 1614369.98
I240681 | I240681004 | Handholes - (HH / Chamb | 880000 |  | 480000 | 480000 | 400000
I240681 | I240681005 | Infrastructure Laying - | 960000 | 20080 |  | 20080 | 939920
I240681 | I240681006 | PON cards | 851850 |  |  |  | 851850
I240681 | I240681007 | Access tool Kits | 75000 | 71040 |  | 71040 | 3960
I240681 | I240681008 | PON Meter | 120000 |  |  |  | 120000
I240681 | I240681009 | VFL | 25000 |  |  |  | 25000
I240681 | I240681010 | Splice Machine | 800000 |  |  |  | 800000
I240681 | I240681011 | Dev Tool / Cable Prep Kit | 225000 |  |  |  | 225000
I240681 | I240682000 | StormFiber Expansion – Dev | 108487352.27 | 108494352.27 |  | 108494352.27 | 7000.00-
I240682 | I240682001 | Cabinets & Accessories - | 47659285.97 | 1915814.15 |  | 1915814.15 | 45743471.82
I240682 | I240682002 | Consumable & Accessories | 11566992.44 | 2835867.54 |  | 2835867.54 | 8731124.9
I240682 | I240682003 | Cables - (Feeder Access | 101449885.88 | 14005849.2 |  | 14005849.2 | 87444036.68
I240682 | I240682004 | Enclosures - (Feeder Ac | 6296601.23 | 301972.35 |  | 301972.35 | 5994628.88
I240682 | I240682005 | Splitters - (Access & Dis | 14967539.69 | 1167052.22 |  | 1167052.22 | 13800487.47
I240682 | I240682006 | Duct - (HDPE / GI with | 137383079.4 | 1407413.9 |  | 1407413.9 | 135975665.5
I240682 | I240682007 | Handholes - (HH / Chamb | 20083000 |  |  |  | 20083000
I240682 | I240682008 | Poles | 1740000 |  |  |  | 1740000
I240682 | I240682009 | FDT Foundation | 975000 | 2049.79 |  | 2049.79 | 972950.21
I240682 | I240682010 | Infrastructure Laying - | 81717210.1 | 237700 | 15775000 | 16012700 | 65704510.1
I240682 | I240682011 | Cable Hauling - (Aerial | 30772482 | 3767505 | 1544775 | 5312280 | 25460202
I240682 | I240682012 | Building Attachments - | 31215600 |  |  |  | 31215600
I240682 | I240682013 | Transportation - (Vehic | 13515000 |  |  |  | 13515000
I240682 | I240682014 | Tool Kit - (Access) | 1050000 | 636620 |  | 636620 | 413380
I240682 | I240682015 | Tool Kit - (Dev.) | 250000 |  |  |  | 250000
I240682 | I240682016 | Cable prepartion Tools - | 883330 | 2955.23 |  | 2955.23 | 880374.77
I240682 | I240682017 | Splice Machine | 3996046.22 |  |  |  | 3996046.22
I240682 | I240682018 | Cleavers | 1120000 | 76856 |  | 76856 | 1043144
I240682 | I240682019 | VFLs | 400000 |  |  |  | 400000
I240682 | I240682020 | OTDR - For Core / FTTH b | 1750000 |  |  |  | 1750000
I240682 | I240682021 | PON Power Mtr. | 2280000 |  |  |  | 2280000
I240682 | I240682022 | CATV Transmission Equipmen | 4174065 |  |  |  | 4174065
I240682 | I240682023 | OLT | 2697525 |  |  |  | 2697525
I240682 | I240682024 | PON Cards | 12777750 | 10218403.39 |  | 10218403.39 | 2559346.61
I240682 | I240682025 | Bolan | 11700000 |  | 5849100 | 5849100 | 5850900
I240682 | I240682026 | Carry | 5000000 | 205000 | 4433000 | 4638000 | 362000
I240682 | I240682027 | OLT connectivity SFPs Mult | 32938.2 | 30773.25 |  | 30773.25 | 2164.95
I240682 | I240682028 | Uplink SFPs for POP connec | 98814.6 |  |  |  | 98814.6
I240682 | I240683000 | StormFiber Expansion – Dev | 7533819.25 | 7533819.25 |  | 7533819.25
I240683 | I240683001 | Cabinets & Accessories - | 8229032.22 | 2060399.54 |  | 2060399.54 | 6168632.68
I240683 | I240683002 | Consumable & Accessories | 1645427.72 | 296981.68 |  | 296981.68 | 1348446.04
I240683 | I240683003 | Cables - (Feeder Access | 9749703.98 | 2872124.95 |  | 2872124.95 | 6877579.03
I240683 | I240683004 | Enclosures - (Feeder Ac | 1173936.01 | 260835.76 |  | 260835.76 | 913100.25
I240683 | I240683005 | Splitters - (Access & Dis | 2083311.61 | 1427843.93 |  | 1427843.93 | 655467.68
I240683 | I240683006 | Duct - (HDPE / GI with | 18436995.56 | 23366 |  | 23366 | 18413629.56
I240683 | I240683007 | Handholes - (HH / Chamb | 2728000 |  |  |  | 2728000
I240683 | I240683008 | FDT Foundation | 120000 |  |  |  | 120000
I240683 | I240683009 | Infrastructure Laying - | 22575861 |  |  |  | 22575861
I240683 | I240683010 | Cable Hauling - (Aerial | 4084643.5 |  |  |  | 4084643.5
I240683 | I240683011 | Transportation - (Vehic | 1200000 |  |  |  | 1200000
I240683 | I240683012 | Tool Kit - (Access) | 225000 | 240550 |  | 240550 | 15550.00-
I240683 | I240683013 | Tool Kit - (Dev.) | 100000 |  |  |  | 100000
I240683 | I240683014 | Cable prepartion Tools - | 300000 |  |  |  | 300000
I240683 | I240683015 | Splice Machine | 1600000 |  |  |  | 1600000
I240683 | I240683016 | Cleavers | 240000 | 19937.49 |  | 19937.49 | 220062.51
I240683 | I240683017 | VFLs | 100000 |  |  |  | 100000
I240683 | I240683019 | PON Power Mtr. | 600000 | 144130.6 |  | 144130.6 | 455869.4
I240683 | I240683020 | CATV Transmission Equipmen | 2115427.5 |  |  |  | 2115427.5
I240683 | I240683021 | PON Cards | 3407400 |  |  |  | 3407400
I240683 | I240683022 | Bolan | 3900000 |  | 1949700 | 1949700 | 1950300
I240683 | I240684000 | StormFiber Expansion – Dev | 9116409.03 | 9116409.03 |  | 9116409.03
I240684 | I240684001 | Cabinets & Accessories - | 4921637.15 | 345760.87 |  | 345760.87 | 4575876.28
I240684 | I240684002 | Consumable & Accessories | 950950 | 16635.36 |  | 16635.36 | 934314.64
I240684 | I240684003 | Cables - (Feeder Access | 7116138.74 | 739508.68 |  | 739508.68 | 6376630.06
I240684 | I240684004 | Enclosures - (Feeder Ac | 558009.5 | 10073.9 |  | 10073.9 | 547935.6
I240684 | I240684005 | Splitters - (Access & Dis | 1811746.74 | 98657.98 |  | 98657.98 | 1713088.76
I240684 | I240684006 | Duct - (HDPE / GI with | 12344361.37 | 463227.89 |  | 463227.89 | 11881133.48
I240684 | I240684007 | Handholes - (HH / Chamb | 3078000 |  |  |  | 3078000
I240684 | I240684008 | FDT Foundation
I240684 | I240684009 | Infrastructure Laying - | 20036939.44 | 681190 | 1484790 | 2165980 | 17870959.44
I240684 | I240684010 | Cable Hauling - (Aerial | 1469010.8 | 190449.4 | 41100 | 231549.4 | 1237461.4
I240684 | I240684011 | Building Attachments - | 7680276 | 203350 | 508105 | 711455 | 6968821
I240684 | I240684012 | Transportation - (Vehic | 710000 |  |  |  | 710000
I240684 | I240684013 | Tool Kit - (Access) | 8890.32 |  |  |  | 8890.32
I240684 | I240684014 | Tool Kit - (Dev.) | 50000 |  |  |  | 50000
I240684 | I240684015 | Cable prepartion Tools - | 150000 |  |  |  | 150000
I240684 | I240684016 | Splice Machine | 800000 |  |  |  | 800000
I240684 | I240684017 | Cleavers | 80000 |  |  |  | 80000
I240684 | I240684018 | VFLs | 20000 |  |  |  | 20000
I240684 | I240684019 | PON Power Mtr. | 120000 |  |  |  | 120000
I240684 | I240684020 | CATV Transmission Equipmen | 3208635 |  |  |  | 3208635
I240684 | I240684021 | Bolan or Karvan | 1800000 |  |  |  | 1800000
I240684 | I240700000 | StormFiber Expansion – Dev | 45174886.75 | 45174886.75 |  | 45174886.75
I240700 | I240700001 | Cabinets & Accessories - | 71267692.6 | 3186663.05 |  | 3186663.05 | 68081029.55
I240700 | I240700002 | Consumable & Accessories | 15273318.65 | 2033845.8 |  | 2033845.8 | 13239472.85
I240700 | I240700003 | Cables - (Feeder Access | 86906988.2 | 8159778.36 |  | 8159778.36 | 78747209.84
I240700 | I240700004 | Enclosures - (Feeder Ac | 9210100.26 | 462887.93 |  | 462887.93 | 8747212.33
I240700 | I240700005 | Splitters - (Access & Dis | 20061276.8 | 837181.43 |  | 837181.43 | 19224095.37
I240700 | I240700006 | Duct - (HDPE / GI with | 134648607.51 | 3474736.02 |  | 3474736.02 | 131173871.49
I240700 | I240700007 | Handholes - (HH / Chamb | 38478000 |  |  |  | 38478000
I240700 | I240700008 | FDT Foundation | 1260000 | 200000 |  | 200000 | 1060000
I240700 | I240700009 | Infrastructure Laying - | 170146748.4 | 1304800 | 4235000 | 5539800 | 164606948.4
I240700 | I240700010 | Cable Hauling - (Aerial | 26331117.5 | 2352785 | 8897215 | 11250000 | 15081117.5
I240700 | I240700011 | Building Attachments - | 17834752 |  |  |  | 17834752
I240700 | I240700012 | Transportation - (Vehic | 9570000 |  |  |  | 9570000
I240700 | I240700013 | Tool Kit - (Access) | 1350000 | 661590 |  | 661590 | 688410
I240700 | I240700014 | Tool Kit - (Dev.) | 300000 | 75000 |  | 75000 | 225000
I240700 | I240700015 | Cable prepartion Tools - | 900000 |  |  |  | 900000
I240700 | I240700016 | Splice Machine | 4788586.61 | 728825.78 |  | 728825.78 | 4059760.83
I240700 | I240700017 | Cleavers | 1440000 | 212743.15 |  | 212743.15 | 1227256.85
I240700 | I240700018 | VFLs | 480000 | 16120.86 |  | 16120.86 | 463879.14
I240700 | I240700019 | OTDR - For Core / FTTH b | 2425000 | 836000 |  | 836000 | 1589000
I240700 | I240700020 | PON Power Mtr. | 2880000 | 140.17 |  | 140.17 | 2879859.83
I240700 | I240700021 | CATV Transmission Equipmen | 5139495 |  |  |  | 5139495
I240700 | I240700022 | OLT | 2697525 |  |  |  | 2697525
I240700 | I240700023 | PON Cards | 21296250 |  |  |  | 21296250
I240700 | I240700024 | Carry with ladder | 17500000 | 615000 | 15478000 | 16093000 | 1407000
I240700 | I240700025 | Bolan | 7500000 |  | 3899400 | 3899400 | 3600600
I240700 | I240700026 | OLT connectivity SFPs Mult | 32938.2 | 30773.25 |  | 30773.25 | 2164.95
I240700 | I240700027 | Uplink SFPs for POP connec | 98814.6 |  |  |  | 98814.6
I240700 | I240700028 | Switch | 851850 |  |  |  | 851850
I240700 | I240701000 | StormFiber Expansion – Dev | 4920839.77 | 4920839.77 |  | 4920839.77
I240701 | I240701001 | Cabinets & Accessories - | 1593154.89 | 1600801.89 |  | 1600801.89 | 7647.00-
I240701 | I240701002 | Consumable & Accessories | 897591.23 | 405559.91 |  | 405559.91 | 492031.32
I240701 | I240701003 | Cables - (Feeder Access | 6208490.46 | 1909333.56 |  | 1909333.56 | 4299156.9
I240701 | I240701004 | Enclosures - (Feeder Ac | 16072 | 5491.26 |  | 5491.26 | 10580.74
I240701 | I240701005 | Splitters - (Access & Dis | 1590111.85 | 115830.04- |  | 115830.04- | 1705941.89
I240701 | I240701006 | Infrastructure Laying - | 143654.45 |  |  |  | 143654.45
I240701 | I240701007 | PON Cards | 2555550 | 814503.89 |  | 814503.89 | 1741046.11
I240701 | I240701008 | Bolan | 3900000 |  |  |  | 3900000
I240701 | I240701009 | Access Tool Kits | 150000 | 99200 |  | 99200 | 50800
I240701 | I240701010 | PON Meter | 360000 |  |  |  | 360000
I240701 | I240701011 | Clevers | 160000 |  |  |  | 160000
I240701 | I240701012 | Splicing Machine | 800000 |  |  |  | 800000
I240701 | I240701013 | Cable prepration Tools (Ca | 150000 |  |  |  | 150000
I240701 | I240701014 | Dev Tool Kit | 50000 |  |  |  | 50000
I240701 | I240701015 | VFL | 60000 |  |  |  | 60000
I240701 | I240701016 | EDFA | 965430 |  |  |  | 965430
I240701 | I240702000 | StormFiber Expansion – Dev | 37124490.55 | 37124490.53 |  | 37124490.53 | 0.02
I240702 | I240702001 | Cabinets & Accessories - | 28614505.46 | 476292.33 |  | 476292.33 | 28138213.13
I240702 | I240702002 | Consumable & Accessories | 6064600 | 708034.34 |  | 708034.34 | 5356565.66
I240702 | I240702003 | Cables - (Feeder Access | 32211448.1 | 5934485.25 |  | 5934485.25 | 26276962.85
I240702 | I240702004 | Enclosures - (Feeder Ac | 1621585.98 | 121260.72 |  | 121260.72 | 1500325.26
I240702 | I240702005 | Splitters - (Access & Dis | 7850771.94 | 151971.03 |  | 151971.03 | 7698800.91
I240702 | I240702006 | Duct - (HDPE / GI with | 47554277.84 | 2041984.17 |  | 2041984.17 | 45512293.67
I240702 | I240702007 | Handholes - (HH / Chamb | 4792305 | 724950 | 982399 | 1707349 | 3084956
I240702 | I240702008 | Poles | 3360000 |  |  |  | 3360000
I240702 | I240702009 | FDT Foundation | 780000 |  |  |  | 780000
I240702 | I240702010 | Infrastructure Laying - | 32173833.6 | 7515010 | 3274850 | 10789860 | 21383973.6
I240702 | I240702011 | Cable Hauling - (Aerial | 11075544.56 |  | 2282790 | 2282790 | 8792754.56
I240702 | I240702012 | Building Attachments - | 15663516 |  |  |  | 15663516
I240702 | I240702013 | Transportation - (Vehic | 3880000 |  |  |  | 3880000
I240702 | I240702014 | Tool Kit - (Access) | 375000 | 233690 |  | 233690 | 141310
I240702 | I240702015 | Tool Kit - (Dev.) | 150000 |  |  |  | 150000
I240702 | I240702016 | Cable prepartion Tools - | 450000 | 164286.71 |  | 164286.71 | 285713.29
I240702 | I240702017 | Splice Machine | 2400000 | 637069.22 |  | 637069.22 | 1762930.78
I240702 | I240702018 | Cleavers | 400000 | 38000 |  | 38000 | 362000
I240702 | I240702019 | VFLs | 160000 |  |  |  | 160000
I240702 | I240702020 | OTDR - For Core / FTTH b | 1350000 |  |  |  | 1350000
I240702 | I240702021 | PON Power Mtr. | 960000 |  |  |  | 960000
I240702 | I240702022 | CATV Transmission Equipmen | 3024067.5 |  |  |  | 3024067.5
I240702 | I240702023 | PON Cards | 8518500 | 705871.29 |  | 705871.29 | 7812628.71
I240702 | I240702024 | Carry with ladder | 7500000 |  | 6537000 | 6537000 | 963000
I240702 | I240702025 | Bolan | 3900000 |  | 1949700 | 1949700 | 1950300
I240702 | I240703000 | StormFiber Expansion – Dev | 115713566.96 | 115713566.96 |  | 115713566.96
I240703 | I240703001 | Cabinets & Accessories - | 88562225.64 | 5264183.85 |  | 5264183.85 | 83298041.79
I240703 | I240703002 | Consumable & Accessories | 17154771.21 | 4588972.2 |  | 4588972.2 | 12565799.01
I240703 | I240703003 | Cables - (Feeder Access | 102651091.64 | 14983086.97 |  | 14983086.97 | 87668004.67
I240703 | I240703004 | Enclosures - (Feeder Ac | 7445340.67 | 964117.03 |  | 964117.03 | 6481223.64
I240703 | I240703005 | Splitters - (Access & Dis | 24403340.36 | 1460671.9 |  | 1460671.9 | 22942668.46
I240703 | I240703006 | Duct - (HDPE / GI with | 113718233.09 | 1622640.33 |  | 1622640.33 | 112095592.76
I240703 | I240703007 | Handholes - (HH / Chamb | 47802000 |  | 5949500 | 5949500 | 41852500
I240703 | I240703008 | Poles | 480000 |  |  |  | 480000
I240703 | I240703009 | FDT Foundation | 1140000 | 20000 | 90000 | 110000 | 1030000
I240703 | I240703010 | Infrastructure Laying - | 195171841.36 | 79600 | 22262800 | 22342400 | 172829441.36
I240703 | I240703011 | Cable Hauling - (Aerial | 36101113.5 | 448450 |  | 448450 | 35652663.5
I240703 | I240703012 | Building Attachments - | 48795828 | 66640 |  | 66640 | 48729188
I240703 | I240703013 | Transportation - (Vehic | 9350000 | 268500 |  | 268500 | 9081500
I240703 | I240703014 | Tool Kit - (Access) | 900000 | 893610 |  | 893610 | 6390
I240703 | I240703015 | Tool Kit - (Dev.) | 500000 | 50000 |  | 50000 | 450000
I240703 | I240703016 | Cable prepartion Tools - | 1500000 | 106331.14 |  | 106331.14 | 1393668.86
I240703 | I240703017 | Splice Machine | 3996046.22 | 815448.06 |  | 815448.06 | 3180598.16
I240703 | I240703018 | Cleavers | 960000 |  |  |  | 960000
I240703 | I240703019 | VFLs | 440000 |  |  |  | 440000
I240703 | I240703020 | OTDR - For Core / FTTH b | 4175000 | 402000 |  | 402000 | 3773000
I240703 | I240703021 | PON Power Mtr. | 2280000 | 288261.24 |  | 288261.24 | 1991738.76
I240703 | I240703022 | CATV Transmission Equipmen | 8646277.5 | 894755.6 |  | 894755.6 | 7751521.9
I240703 | I240703023 | OLT | 2697525 | 1803964.63 |  | 1803964.63 | 893560.37
I240703 | I240703024 | PON Cards | 17037000 | 17126221.76 |  | 17126221.76 | 89221.76-
I240703 | I240703025 | Switch | 851850 |  |  |  | 851850
I240703 | I240703026 | Carry with ladder | 10000000 | 270000 | 6687000 | 6957000 | 3043000
I240703 | I240703027 | Bolan | 16200000 | 412254.12 | 16206200 | 16618454.12 | 418454.12-
I240703 | I240704000 | StormFiber Expansion – Dev | 57704515.61 | 57704515.63 |  | 57704515.63 | 0.02-
I240704 | I240704001 | Cabinets & Accessories - | 59097303.75 | 1796696.11 |  | 1796696.11 | 57300607.64
I240704 | I240704002 | Consumable & Accessories | 11787481.21 | 2242803.52 |  | 2242803.52 | 9544677.69
I240704 | I240704003 | Cables - (Feeder Access | 86201126.02 | 4742594 |  | 4742594 | 81458532.02
I240704 | I240704004 | Enclosures - (Feeder Ac | 6478111.25 | 508241.97 |  | 508241.97 | 5969869.28
I240704 | I240704005 | Splitters - (Access & Dis | 20780571.03 | 701423.72 |  | 701423.72 | 20079147.31
I240704 | I240704006 | Duct - (HDPE / GI with | 166226840.67 | 6297696.25 |  | 6297696.25 | 159929144.42
I240704 | I240704007 | Handholes - (HH / Chamb | 28118000 | 136000 |  | 136000 | 27982000
I240704 | I240704008 | FDT Foundation | 94881.74 |  | 18000 | 18000 | 76881.74
I240704 | I240704009 | Infrastructure Laying - | 133132883.3 | 5650675 | 3780000 | 9430675 | 123702208.3
I240704 | I240704010 | Cable Hauling - (Aerial | 26568246 | 1778300 | 2221700 | 4000000 | 22568246
I240704 | I240704011 | Building Attachments - | 8620640 |  |  |  | 8620640
I240704 | I240704012 | Transportation - (Vehic | 6400000 | 8000 |  | 8000 | 6392000
I240704 | I240704013 | Tool Kit - (Access) | 1050000 | 1123470 |  | 1123470 | 73470.00-
I240704 | I240704014 | Tool Kit - (Dev.) | 300000 |  |  |  | 300000
I240704 | I240704015 | Cable prepartion Tools - | 750000 | 52792.04 |  | 52792.04 | 697207.96
I240704 | I240704016 | Splice Machine | 4800000 | 1681989.59 |  | 1681989.59 | 3118010.41
I240704 | I240704017 | Cleavers | 1112000 | 57000 |  | 57000 | 1055000
I240704 | I240704018 | VFLs | 380000 |  |  |  | 380000
I240704 | I240704019 | OTDR - For Core / FTTH b | 1750000 | 365000 |  | 365000 | 1385000
I240704 | I240704020 | PON Power Mtr. | 2280000 | 144068.19 |  | 144068.19 | 2135931.81
I240704 | I240704021 | CATV Transmission Equipmen | 4174065 | 894755.6 |  | 894755.6 | 3279309.4
I240704 | I240704022 | OLT | 2697525 | 1803964.62 |  | 1803964.62 | 893560.38
I240704 | I240704023 | PON Cards | 11074050 | 9882198.05 |  | 9882198.05 | 1191851.95
I240704 | I240704024 | Switch | 851850 |  |  |  | 851850
I240704 | I240704025 | Carry with Ladder | 12500000 | 270000 | 11045000 | 11315000 | 1185000
I240704 | I240704026 | Bolan | 5850000 |  | 3899400 | 3899400 | 1950600
I240704 | I240705000 | StormFiber Expansion – Dev | 66153410.9 | 66153410.9 |  | 66153410.9
I240705 | I240705001 | Cabinets & Accessories - | 38859485.6 | 1013063.3 |  | 1013063.3 | 37846422.3
I240705 | I240705002 | Consumable & Accessories | 8845136.33 | 283964.07 |  | 283964.07 | 8561172.26
I240705 | I240705003 | Cables - (Feeder Access | 73877986.36 | 1711894.56 |  | 1711894.56 | 72166091.8
I240705 | I240705004 | Enclosures - (Feeder Ac | 6256625.44 | 180827.17 |  | 180827.17 | 6075798.27
I240705 | I240705005 | Splitters - (Access & Dis | 15774882.52 | 70209.75 |  | 70209.75 | 15704672.77
I240705 | I240705006 | Duct - (HDPE / GI with | 98328198.3 | 882579.09 |  | 882579.09 | 97445619.21
I240705 | I240705007 | Handholes - (HH / Chamb | 25802000 | 8020000 | 1396000 | 9416000 | 16386000
I240705 | I240705008 | Poles | 420000 |  |  |  | 420000
I240705 | I240705009 | FDT Foundation | 675000 | 100000 | 275000 | 375000 | 300000
I240705 | I240705010 | Infrastructure Laying - | 129376466.56 | 5837099 | 4341746 | 10178845 | 119197621.56
I240705 | I240705011 | Cable Hauling - (Aerial | 21106153.43 | 83760 | 1050 | 84810 | 21021343.43
I240705 | I240705012 | Building Attachments - | 32405912 |  |  |  | 32405912
I240705 | I240705013 | Transportation - (Vehic | 8080000 | 71500 |  | 71500 | 8008500
I240705 | I240705014 | Tool Kit - (Access) | 420000 | 322950 |  | 322950 | 97050
I240705 | I240705015 | Tool Kit - (Dev.) | 250000 |  |  |  | 250000
I240705 | I240705016 | Cable prepartion Tools - | 600000 |  |  |  | 600000
I240705 | I240705017 | Splice Machine | 2800000 | 481917.17 |  | 481917.17 | 2318082.83
I240705 | I240705018 | Cleavers | 560000 | 38000 |  | 38000 | 522000
I240705 | I240705019 | VFLs | 300000 |  |  |  | 300000
I240705 | I240705020 | OTDR - For Core / FTTH b | 2325000 |  |  |  | 2325000
I240705 | I240705021 | PON Power Mtr. | 1280000 |  |  |  | 1280000
I240705 | I240705022 | CATV Transmission Equipmen | 5139495 | 2684266.81 |  | 2684266.81 | 2455228.19
I240705 | I240705023 | OLT | 2697525 | 1803964.62 |  | 1803964.62 | 893560.38
I240705 | I240705024 | PON Cards | 11925900 | 8512941.77 |  | 8512941.77 | 3412958.23
I240705 | I240705025 | OLT connectivity SFPs Mult | 32938.2 | 30773.26 |  | 30773.26 | 2164.94
I240705 | I240705026 | Uplink SFPs for POP connec | 98814.6 |  |  |  | 98814.6
I240705 | I240705027 | Carry with lader | 12500000 |  | 10895000 | 10895000 | 1605000
I240705 | I240705028 | Bolan | 5400000 |  |  |  | 5400000
I240705 | I240782000 | LH Infrastructure developm | 67399054.37 | 67399054.37 |  | 67399054.37
I240782 | I240782001 | Cabinets & Accessories - | 795954.5 | 70215.49 |  | 70215.49 | 725739.01
I240782 | I240782002 | Cables - (Feeder Access | 10628985.93 | 114746.3 |  | 114746.3 | 10514239.63
I240782 | I240782003 | Enclosures - (Feeder Ac | 229144.67 | 10363.28 |  | 10363.28 | 218781.39
I240782 | I240782004 | Duct - (HDPE / GI with | 16733918.58 | 25342.23 |  | 25342.23 | 16708576.35
I240782 | I240782005 | Infrastructure Laying - | 4497110 | 110000 |  | 110000 | 4387110
I240782 | I240782006 | Admin / Supervision Charge | 2925183.22 | 535974 |  | 535974 | 2389209.22
I240782 | I240782007 | Transportation - (Vehic | 1600000 | 378000 |  | 378000 | 1222000
I240782 | I240782008 | Tool Kit - (Dev.) | 160000 | 25000 |  | 25000 | 135000
I240782 | I240782009 | Cable prepartion Tools - | 300000 |  |  |  | 300000
I240782 | I240782010 | Splice Machine | 1600000 | 721876.21 |  | 721876.21 | 878123.79
I240782 | I240782011 | Cleavers | 160000 |  |  |  | 160000
I240782 | I240782012 | VFLs | 40000 |  |  |  | 40000
I240782 | I240782013 | OTDR - For Core / FTTH b | 3000000 |  |  |  | 3000000
I240782 | I240782014 | Optical Power Mtr & Source | 510000 |  |  |  | 510000
I240782 | I240782015 | Fiber Identifier | 320000 |  |  |  | 320000
I240782 | I240782016 | Others (Blades for Tools) | 40000 |  |  |  | 40000
I240782 | I240782017 | Hilux / Double Cabin | 14000000 | 198 |  | 198 | 13999802
I240782 | I250114000 | StormFiber Expansion – Jin | 4407341.61 | 4407341.61 |  | 4407341.61
I250114 | I250114001 | Cabinets & Accessories - | 3641000 |  |  |  | 3641000
I250114 | I250114002 | Consumable & Accessories | 816110.5 | 28248.13 |  | 28248.13 | 787862.37
I250114 | I250114003 | Cables - (Feeder Access | 12293354.39 | 286483.65 |  | 286483.65 | 12006870.74
I250114 | I250114004 | Enclosures - (Feeder Ac | 594500.03 |  |  |  | 594500.03
I250114 | I250114005 | Splitters - (Access & Dis | 1408991.76 |  |  |  | 1408991.76
I250114 | I250114006 | Duct - (HDPE / GI with | 5826354.25 | 1272786.28 |  | 1272786.28 | 4553567.97
I250114 | I250114007 | Handholes - (HH / Chamb | 645260 |  |  |  | 645260
I250114 | I250114008 | FDT Foundation | 50000 |  |  |  | 50000
I250114 | I250114009 | Infrastructure Laying - | 3481542.98 | 2274000 |  | 2274000 | 1207542.98
I250114 | I250114010 | Cable Hauling - (Aerial | 1607710.5 |  |  |  | 1607710.5
I250114 | I250114011 | Building Attachments - | 2417000.34 |  |  |  | 2417000.34
I250114 | I250114012 | Existing Aerial Cable Cutt | 300000 |  |  |  | 300000
I250114 | I250114013 | Transportation - (Vehic | 655000 | 6500 |  | 6500 | 648500
I250114 | I250201000 | StormFiber Expansion – Dev | 6043398.79 | 6043398.79 |  | 6043398.79
I250201 | I250201001 | Cabinets & Accessories | 5752200.56 | 10651.77 |  | 10651.77 | 5741548.79
I250201 | I250201002 | Consumable & Accessories | 1266539.85 | 722434.3 |  | 722434.3 | 544105.55
I250201 | I250201003 | Cables - (Feeder Access | 3311062.82 | 957700.85 |  | 957700.85 | 2353361.97
I250201 | I250201004 | Enclosures - (Feeder Ac | 631236.49 | 1777.89 |  | 1777.89 | 629458.6
I250201 | I250201005 | Splitters - (Access & Dis | 2515669.22 | 4788.33 |  | 4788.33 | 2510880.89
I250201 | I250201006 | Duct - (HDPE / GI with | 3274348.49 | 14400 |  | 14400 | 3259948.49
I250201 | I250201007 | Handholes - (HH / Chamb | 144000 |  |  |  | 144000
I250201 | I250201008 | FDT Foundation | 75000 |  | 50000 | 50000 | 25000
I250201 | I250201009 | Infrastructure Laying - | 7418190 |  | 1168400 | 1168400 | 6249790
I250201 | I250201010 | Cable Hauling - (Aeria | 813765 |  | 840780 | 840780 | 27015.00-
I250201 | I250201011 | Building Attachments - ( | 12125000 |  |  |  | 12125000
I250201 | I250201012 | Transportation - (Vehic | 525000 |  |  |  | 525000
I250201 | I250201013 | PON Cards | 1419750 |  |  |  | 1419750
I250201 | I250201014 | Carry with Ladder
I250201 | I250201015 | Tool Kits Access | 150000 |  |  |  | 150000
I250201 | I250201016 | Clevers | 160000 |  |  |  | 160000
I250201 | I250201017 | PON Metres | 360000 |  |  |  | 360000
I250201 | I250201018 | VFL | 60000 |  |  |  | 60000
I250201 | I250201019 | Tool Kit - Dev | 75000 |  |  |  | 75000
I250201 | I250201020 | Splicing Machine | 800000 |  |  |  | 800000
I250201 | I250201021 | Bolan | 1949700 |  | 1949700 | 1949700
I250201 | I250202000 | StormFiber Expansion – Dev | 1202573.79 | 1202573.79 |  | 1202573.79
I250202 | I250202001 | Cabinets & Accessories | 3940084.52 | 29997.96 |  | 29997.96 | 3910086.56
I250202 | I250202002 | Consumable & Accessories | 958100 | 211837.17 |  | 211837.17 | 746262.83
I250202 | I250202003 | Cables - (Feeder Access | 5821006.37 | 1947579.72 |  | 1947579.72 | 3873426.65
I250202 | I250202004 | Enclosures - (Feeder Ac | 487432.47 | 89355.6 |  | 89355.6 | 398076.87
I250202 | I250202005 | Splitters - (Access & Dis | 1282154.12 | 137902.64 |  | 137902.64 | 1144251.48
I250202 | I250202006 | Duct - (HDPE / GI with | 3601748.68 |  |  |  | 3601748.68
I250202 | I250202007 | Handholes - (HH / Chamb | 712000 |  | 17000 | 17000 | 695000
I250202 | I250202008 | Poles | 600000 |  |  |  | 600000
I250202 | I250202009 | FDT Foundation | 76000 |  |  |  | 76000
I250202 | I250202010 | Infrastructure Laying - | 5284890.26 |  |  |  | 5284890.26
I250202 | I250202011 | Cable Hauling - (Aeria | 2291559.38 | 2109540 | 242220 | 2351760 | 60200.62-
I250202 | I250202012 | Transportation - (Vehic | 810000 |  |  |  | 810000
I250202 | I250202013 | Tool Kit - (Access) | 75000 | 59900 |  | 59900 | 15100
I250202 | I250202014 | Tool Kit - (Dev.) | 80000 | 25000 |  | 25000 | 55000
I250202 | I250202015 | Cable prepartion Tools - | 116897.37 | 26134.27 |  | 26134.27 | 90763.1
I250202 | I250202016 | Splice Machine | 800000 | 721876.2 |  | 721876.2 | 78123.8
I250202 | I250202017 | Cleavers | 160000 |  |  |  | 160000
I250202 | I250202018 | VFLs | 40000 | 2687 |  | 2687 | 37313
I250202 | I250202019 | OTDR - For Core / FTTH bo | 950000 |  |  |  | 950000
I250202 | I250202020 | PON Power Mtr. | 240000 | 48022.73 |  | 48022.73 | 191977.27
I250202 | I250202021 | CATV Transmission Equipmen | 3208635 |  |  |  | 3208635
I250202 | I250202022 | PON Cards | 709875 |  |  |  | 709875
I250202 | I250202023 | Carry with Ladder | 2500000 | 205000 | 2254000 | 2459000 | 41000
I250202 | I250202024 | PON Cards | 709875 |  |  |  | 709875
I250202 | I250203000 | StormFiber Expansion – Dev | 450000 | 450000 |  | 450000
I250203 | I250203001 | Cabinets & Accessories | 1695000 |  |  |  | 1695000
I250203 | I250203002 | Consumable & Accessories | 362000 |  |  |  | 362000
I250203 | I250203003 | Cables - (Feeder Access | 2768692.85 |  |  |  | 2768692.85
I250203 | I250203004 | Enclosures - (Feeder Ac | 229500 |  |  |  | 229500
I250203 | I250203005 | Splitters - (Access & Dis | 645237.85 |  |  |  | 645237.85
I250203 | I250203006 | Duct - (HDPE / GI with | 2229390.8 |  |  |  | 2229390.8
I250203 | I250203007 | Handholes - (HH / Chamb | 440000 |  |  |  | 440000
I250203 | I250203008 | Poles | 150000 |  |  |  | 150000
I250203 | I250203009 | FDT Foundation | 30000 |  |  |  | 30000
I250203 | I250203010 | Infrastructure Laying - | 3049500 |  |  |  | 3049500
I250203 | I250203011 | Cable Hauling - (Aeria | 1162992.55 |  |  |  | 1162992.55
I250203 | I250203012 | Transportation - (Vehic | 450000 |  |  |  | 450000
I250203 | I250205000 | StormFiber Expansion – Dev | 10830900 | 10830900 |  | 10830900
I250205 | I250205001 | Cabinets & Accessories | 8529000 |  |  |  | 8529000
I250205 | I250205002 | Consumable & Accessories | 1930050 |  |  |  | 1930050
I250205 | I250205003 | Cables - (Feeder Access | 17276463.74 |  |  |  | 17276463.74
I250205 | I250205004 | Enclosures - (Feeder Ac | 1256400 |  |  |  | 1256400
I250205 | I250205005 | Splitters - (Access & Dis | 3529012.07 |  |  |  | 3529012.07
I250205 | I250205006 | Duct - (HDPE / GI with | 28667662.5 |  |  |  | 28667662.5
I250205 | I250205007 | Handholes - (HH / Chamb | 7182000 | 16500 |  | 16500 | 7165500
I250205 | I250205008 | FDT Foundation | 200000 |  |  |  | 200000
I250205 | I250205009 | Infrastructure Laying - | 26065313.04 |  | 2100000 | 2100000 | 23965313.04
I250205 | I250205010 | Cable Hauling - (Aeria | 4570126.66 |  |  |  | 4570126.66
I250205 | I250205011 | Building Attachments - ( | 304000 |  |  |  | 304000
I250205 | I250205012 | Transportation - (Vehic | 2100000 |  |  |  | 2100000
I250205 | I250205013 | Tool Kit - (Access) | 150000 | 140435 |  | 140435 | 9565
I250205 | I250205014 | Tool Kit - (Dev.) | 72000 |  |  |  | 72000
I250205 | I250205015 | Cable preparation Tools | 150000 |  |  |  | 150000
I250205 | I250205016 | Splice Machine | 800000 |  |  |  | 800000
I250205 | I250205017 | Cleavers | 160000 |  |  |  | 160000
I250205 | I250205018 | VFLs | 60000 |  |  |  | 60000
I250205 | I250205019 | OTDR - For Core / FTTH b | 950000 |  |  |  | 950000
I250205 | I250205020 | PON Power Mtr. | 360000 |  |  |  | 360000
I250205 | I250205021 | CATV Transmission Equipmen | 3208635 |  |  |  | 3208635
I250205 | I250205022 | PON Cards | 1419750 |  |  |  | 1419750
I250205 | I250205023 | Carry with ladder | 2500000 | 205000 | 2254000 | 2459000 | 41000
I250205 | I250205024 | Bolan | 1950000 |  | 1949700 | 1949700 | 300
I250205 | I250206000 | StormFiber Expansion – Dev | 9288952.11 | 9288952.11 |  | 9288952.11
I250206 | I250206001 | Cabinets & Accessories | 43253000 | 655194.81 |  | 655194.81 | 42597805.19
I250206 | I250206002 | Consumable & Accessories | 8706550 | 707135.96 |  | 707135.96 | 7999414.04
I250206 | I250206003 | Cables - (Feeder Access | 66041515.58 | 17108501.53 |  | 17108501.53 | 48933014.05
I250206 | I250206004 | Enclosures - (Feeder Ac | 5425800 | 881225.15 |  | 881225.15 | 4544574.85
I250206 | I250206005 | Splitters - (Access & Dis | 15632654.71 | 384624.05 |  | 384624.05 | 15248030.66
I250206 | I250206006 | Duct - (HDPE / GI with | 74618061.81 | 8363009.05 |  | 8363009.05 | 66255052.76
I250206 | I250206007 | Handholes - (HH / Chamb | 12298000 | 1983000 | 264000 | 2247000 | 10051000
I250206 | I250206008 | Poles | 6600000 |  |  |  | 6600000
I250206 | I250206009 | FDT Foundation | 1100000 | 60000 | 20000 | 80000 | 1020000
I250206 | I250206010 | Infrastructure Laying - | 32107395.79 | 5084131 | 171000 | 5255131 | 26852264.79
I250206 | I250206011 | Cable Hauling - (Aeria | 18557639.63 | 191500 |  | 191500 | 18366139.63
I250206 | I250206012 | Transportation - (Vehic | 7110000 |  |  |  | 7110000
I250206 | I250206013 | Tool Kit - (Access) | 600000 | 261230 |  | 261230 | 338770
I250206 | I250206014 | Tool Kit - (Dev.) | 186666 |  |  |  | 186666
I250206 | I250206015 | Cable preparation Tools | 450000 |  |  |  | 450000
I250206 | I250206016 | Splice Machine | 2400000 | 959501.19 |  | 959501.19 | 1440498.81
I250206 | I250206017 | Cleavers | 640000 |  |  |  | 640000
I250206 | I250206018 | VFLs | 60000 |  |  |  | 60000
I250206 | I250206019 | OTDR - For Core / FTTH b | 1225000 | 365000 |  | 365000 | 860000
I250206 | I250206020 | PON Power Mtr. | 1320000 | 48043.54 |  | 48043.54 | 1271956.46
I250206 | I250206021 | CATV Transmission Equipmen | 6232702.5 |  |  |  | 6232702.5
I250206 | I250206022 | OLT | 1987650 |  |  |  | 1987650
I250206 | I250206023 | PON Cards | 7098750 |  |  |  | 7098750
I250206 | I250206024 | Switch | 851850 |  |  |  | 851850
I250206 | I250206025 | OLT connectivity SFPs Mult | 32938.2 | 30773.25 |  | 30773.25 | 2164.95
I250206 | I250206026 | Uplink SFPs for POP connec | 98814.6 |  |  |  | 98814.6
I250206 | I250206027 | Carry with Ladder | 10000000 | 410000 | 4508000 | 4918000 | 5082000
I250206 | I250206028 | Bolan | 3900000 | 1500 | 1949700 | 1951200 | 1948800
I250206 | I250207001 | Cabinets & Accessories | 4097000 | 160400 |  | 160400 | 3936600
I250207 | I250207002 | Consumable & Accessories | 921200 |  |  |  | 921200
I250207 | I250207003 | Cables - (Feeder Access | 6706225.22 |  |  |  | 6706225.22
I250207 | I250207004 | Enclosures - (Feeder Ac | 574500.62 |  |  |  | 574500.62
I250207 | I250207005 | Splitters - (Access & Dis | 1532826.72 |  |  |  | 1532826.72
I250207 | I250207006 | Duct - (HDPE / GI with | 5064560.56 |  |  |  | 5064560.56
I250207 | I250207007 | Handholes - (HH / Chamb | 792000 | 117500 |  | 117500 | 674500
I250207 | I250207008 | Poles | 600000 |  |  |  | 600000
I250207 | I250207009 | FDT Foundation | 90000 |  |  |  | 90000
I250207 | I250207010 | Infrastructure Laying - | 7778175 | 5857280 |  | 5857280 | 1920895
I250207 | I250207011 | Cable Hauling - (Aeria | 2810656 | 87000 | 1313000 | 1400000 | 1410656
I250207 | I250207012 | Transportation - (Vehic | 990000 |  |  |  | 990000
I250207 | I250207013 | Tool Kit - (Access) | 75000 | 74710 |  | 74710 | 290
I250207 | I250207014 | Tool Kit - (Dev.) | 80000 |  |  |  | 80000
I250207 | I250207015 | Cable preparation Tools | 150000 |  |  |  | 150000
I250207 | I250207016 | Splice Machine | 1600000 |  |  |  | 1600000
I250207 | I250207017 | Cleavers | 160000 |  |  |  | 160000
I250207 | I250207018 | VFLs | 20000 |  |  |  | 20000
I250207 | I250207019 | OTDR - For Core / FTTH b | 950000 |  |  |  | 950000
I250207 | I250207020 | PON Power Mtr. | 240000 |  |  |  | 240000
I250207 | I250207021 | CATV Transmission Equipmen | 3208635 |  |  |  | 3208635
I250207 | I250207022 | PON Cards | 709875 |  |  |  | 709875
I250207 | I250207023 | Carry with Ladder | 2500000 | 274000 | 2254000 | 2528000 | 28000.00-
I250207 | I250208000 | StormFiber Expansion – Dev | 2465971.53 | 2465971.53 |  | 2465971.53
I250208 | I250208001 | Cabinets & Accessories | 3365028.47 | 84490.02 |  | 84490.02 | 3280538.45
I250208 | I250208002 | Consumable & Accessories | 1186100 | 11730.31 |  | 11730.31 | 1174369.69
I250208 | I250208003 | Cables - (Feeder Access | 7108035.17 | 302841.58 |  | 302841.58 | 6805193.59
I250208 | I250208004 | Enclosures - (Feeder Ac | 679800 | 49203.66 |  | 49203.66 | 630596.34
I250208 | I250208005 | Splitters - (Access & Dis | 2227497.85 | 46072.03 |  | 46072.03 | 2181425.82
I250208 | I250208006 | Duct - (HDPE / GI with | 9609646.27 | 3156968.31 |  | 3156968.31 | 6452677.96
I250208 | I250208007 | Handholes - (HH / Chamb | 2750000 |  |  |  | 2750000
I250208 | I250208008 | Poles | 600000 |  |  |  | 600000
I250208 | I250208009 | FDT Foundation | 120000 |  |  |  | 120000
I250208 | I250208010 | Infrastructure Laying - | 14828375.39 | 7876879 | 618000 | 8494879 | 6333496.39
I250208 | I250208011 | Cable Hauling - (Aeria | 2214755.43 |  |  |  | 2214755.43
I250208 | I250208012 | Building Attachments - ( | 1830000 |  |  |  | 1830000
I250208 | I250208013 | Transportation - (Vehic | 1080000 |  |  |  | 1080000
I250208 | I250208014 | Tool Kit - (Access) | 150000 |  |  |  | 150000
I250208 | I250208015 | Tool Kit - (Dev.) | 75000 |  |  |  | 75000
I250208 | I250208016 | Cable prepartion Tools - | 150000 |  |  |  | 150000
I250208 | I250208017 | Splice Machine | 800000 |  |  |  | 800000
I250208 | I250208018 | Cleavers | 160000 |  |  |  | 160000
I250208 | I250208019 | VFLs | 60000 |  |  |  | 60000
I250208 | I250208020 | OTDR - For Core / FTTH bo | 950000 |  |  |  | 950000
I250208 | I250208021 | PON Power Mtr. | 600000 |  |  |  | 600000
I250208 | I250208022 | CATV Transmission Equipmen | 4301842.5 |  |  |  | 4301842.5
I250208 | I250208023 | PON Cards | 1419750 |  |  |  | 1419750
I250208 | I250208024 | Carry with ladder | 5000000 | 205000 | 2254000 | 2459000 | 2541000
I250208 | I250209001 | Cabinets & Accessories | 15970000 | 643055.42 |  | 643055.42 | 15326944.58
I250209 | I250209002 | Consumable & Accessories | 3267750 |  |  |  | 3267750
I250209 | I250209003 | Cables - (Feeder Access | 24601656.08 | 9574770.31 |  | 9574770.31 | 15026885.77
I250209 | I250209004 | Enclosures - (Feeder Ac | 1949400 |  |  |  | 1949400
I250209 | I250209005 | Splitters - (Access & Dis | 6156930.17 |  |  |  | 6156930.17
I250209 | I250209006 | Duct - (HDPE / GI with | 23285017 | 11184083.07 |  | 11184083.07 | 12100933.93
I250209 | I250209007 | Handholes - (HH / Chamb | 4774000 | 132000 | 92500 | 224500 | 4549500
I250209 | I250209008 | Poles | 1800000 |  |  |  | 1800000
I250209 | I250209009 | FDT Foundation | 330000 |  | 125000 | 125000 | 205000
I250209 | I250209010 | Infrastructure Laying - | 38858250 | 12022300 | 7362000 | 19384300 | 19473950
I250209 | I250209011 | Cable Hauling - (Aeria | 6135947.46 | 5100 | 409770 | 414870 | 5721077.46
I250209 | I250209012 | Building Attachments - ( | 943000 |  |  |  | 943000
I250209 | I250209013 | Transportation - (Vehic | 2610000 |  |  |  | 2610000
I250209 | I250209014 | Tool Kit - (Access) | 450000 |  |  |  | 450000
I250209 | I250209015 | Tool Kit - (Dev.) | 320000 |  |  |  | 320000
I250209 | I250209016 | Cable prepartion Tools - | 450000 |  |  |  | 450000
I250209 | I250209017 | Splice Machine | 2400000 |  |  |  | 2400000
I250209 | I250209018 | Cleavers | 720000 |  |  |  | 720000
I250209 | I250209019 | VFLs | 180000 |  |  |  | 180000
I250209 | I250209020 | OTDR - For Core / FTTH bo | 1900000 |  |  |  | 1900000
I250209 | I250209021 | PON Power Mtr. | 1080000 |  |  |  | 1080000
I250209 | I250209022 | CATV Transmission Equipmen | 5267272.5 |  |  |  | 5267272.5
I250209 | I250209023 | PON Cards | 4259250 |  |  |  | 4259250
I250209 | I250209024 | Carry with ladder | 7500000 | 2441022 | 4558000 | 6999022 | 500978
I250209 | I250209025 | Bolan | 11700000 |  | 1949700 | 1949700 | 9750300
I250209 | I250209026 | OLT | 1987650 |  |  |  | 1987650
I250209 | I250209027 | Switch | 851850 |  |  |  | 851850
I250209 | I250209028 | OLT connectivity SFPs Mult | 32938.2 |  |  |  | 32938.2
I250209 | I250209029 | Uplink SFPs for POP connec | 98814.6 |  |  |  | 98814.6
I250209 | I250210000 | StormFiber Expansion – Dev | 19275228.09 | 19275228.09 |  | 19275228.09
I250210 | I250210001 | Cabinets & Accessories | 20546212.72 | 1144655.53 |  | 1144655.53 | 19401557.19
I250210 | I250210002 | Consumable & Accessories | 4629078.18 | 1211456.39 |  | 1211456.39 | 3417621.79
I250210 | I250210003 | Cables - (Feeder Access | 37622625.5 | 8266509.66 |  | 8266509.66 | 29356115.84
I250210 | I250210004 | Enclosures - (Feeder Ac | 2741064.91 | 195871.06 |  | 195871.06 | 2545193.85
I250210 | I250210005 | Splitters - (Access & Dis | 8648521.66 | 246958.5 |  | 246958.5 | 8401563.16
I250210 | I250210006 | Duct - (HDPE / GI with | 29887327.68 | 4338057.48 |  | 4338057.48 | 25549270.2
I250210 | I250210007 | Handholes - (HH / Chamb | 7326000 |  | 105000 | 105000 | 7221000
I250210 | I250210008 | Poles | 780000 |  |  |  | 780000
I250210 | I250210009 | FDT Foundation | 425000 |  |  |  | 425000
I250210 | I250210010 | Infrastructure Laying - | 31159920.45 | 750000 | 1826200 | 2576200 | 28583720.45
I250210 | I250210011 | Cable Hauling - (Aeria | 9878373.86 |  |  |  | 9878373.86
I250210 | I250210012 | Building Attachments - ( | 830000 |  |  |  | 830000
I250210 | I250210013 | Transportation - (Vehic | 3980000 |  |  |  | 3980000
I250210 | I250210014 | Tool Kit - (Access) | 300000 | 253650 | 34400 | 288050 | 11950
I250210 | I250210015 | Tool Kit - (Dev.) | 300000 |  |  |  | 300000
I250210 | I250210016 | Cable prepartion Tools - | 600000 |  |  |  | 600000
I250210 | I250210017 | Splice Machine | 3200000 | 3585.06 |  | 3585.06 | 3196414.94
I250210 | I250210018 | Cleavers | 320000 | 38000 |  | 38000 | 282000
I250210 | I250210019 | VFLs | 160000 |  |  |  | 160000
I250210 | I250210020 | OTDR - For Core / FTTH b | 950000 |  |  |  | 950000
I250210 | I250210021 | PON Power Mtr. | 1440000 |  |  |  | 1440000
I250210 | I250210022 | CATV Transmission Equipmen | 5267272.5 |  |  |  | 5267272.5
I250210 | I250210023 | OLT | 1987650 |  |  |  | 1987650
I250210 | I250210024 | PON Cards | 4259250 |  |  |  | 4259250
I250210 | I250210025 | Switch | 851850 |  |  |  | 851850
I250210 | I250210026 | OLT connectivity SFPs Mult | 32938.2 |  |  |  | 32938.2
I250210 | I250210027 | Uplink SFPs for POP connec | 98814.6 |  |  |  | 98814.6
I250210 | I250210028 | Carry with Ladder | 4731635.93 | 410000 | 4508000 | 4918000 | 186364.07-
I250210 | I250210029 | Bolan | 3900000 |  | 1949700 | 1949700 | 1950300
I250210 | I250211001 | Cabinets & Accessories | 8931000 | 1698413.39 |  | 1698413.39 | 7232586.61
I250211 | I250211002 | Consumable & Accessories | 1960600 | 682837.88 |  | 682837.88 | 1277762.12
I250211 | I250211003 | Cables - (Feeder Access | 8611849.5 | 2668132.3 |  | 2668132.3 | 5943717.2
I250211 | I250211004 | Enclosures - (Feeder Ac | 1139100 | 189766.89 |  | 189766.89 | 949333.11
I250211 | I250211005 | Splitters - (Access & Dis | 3579600 | 1024520.66 |  | 1024520.66 | 2555079.34
I250211 | I250211006 | Duct - (HDPE / GI with | 7757104.4 | 2162686.29 |  | 2162686.29 | 5594418.11
I250211 | I250211007 | Handholes - (HH / Chamb | 1628000 |  |  |  | 1628000
I250211 | I250211008 | Poles | 450000 |  |  |  | 450000
I250211 | I250211009 | FDT Foundation | 150000 |  |  |  | 150000
I250211 | I250211010 | Infrastructure Laying - | 5742250 | 2262000 | 3450000 | 5712000 | 30250
I250211 | I250211011 | Cable Hauling - (Aeria | 3181215 | 459900 | 1540100 | 2000000 | 1181215
I250211 | I250211012 | Transportation - (Vehic | 1170000 |  |  |  | 1170000
I250211 | I250211013 | Tool Kit - (Access) | 150000 | 149740 |  | 149740 | 260
I250211 | I250211014 | Tool Kit - (Dev.) | 75000 |  |  |  | 75000
I250211 | I250211015 | Cable prepartion Tools - | 150000 |  |  |  | 150000
I250211 | I250211016 | Splice Machine | 800000 |  |  |  | 800000
I250211 | I250211017 | Cleavers | 160000 | 19000 |  | 19000 | 141000
I250211 | I250211018 | VFLs | 60000 |  |  |  | 60000
I250211 | I250211019 | PON Power Mtr. | 360000 |  |  |  | 360000
I250211 | I250211020 | CATV Transmission Equipmen | 3208635 |  |  |  | 3208635
I250211 | I250211021 | PON Cards | 2129625 |  |  |  | 2129625
I250211 | I250211022 | Carry with Ladder | 5000000 | 205000 | 2254000 | 2459000 | 2541000
I250211 | I250212000 | StormFiber Expansion – Dev | 27505715.19 | 27505715.19 |  | 27505715.19
I250212 | I250212001 | Cabinets & Accessories | 34555196.47 | 941180.2 |  | 941180.2 | 33614016.27
I250212 | I250212002 | Consumable & Accessories | 7810450 | 1663404.32 |  | 1663404.32 | 6147045.68
I250212 | I250212003 | Cables - (Feeder Access | 48236629.33 | 5843760.82 |  | 5843760.82 | 42392868.51
I250212 | I250212004 | Enclosures - (Feeder Ac | 5448457.69 | 364394.32 |  | 364394.32 | 5084063.37
I250212 | I250212005 | Splitters - (Access & Dis | 11563085.75 | 295572.4 |  | 295572.4 | 11267513.35
I250212 | I250212006 | Duct - (HDPE / GI with | 40537242.42 | 8415162.19 |  | 8415162.19 | 32122080.23
I250212 | I250212007 | Handholes - (HH / Chamb | 10384000 |  |  |  | 10384000
I250212 | I250212008 | Poles | 7500000 |  |  |  | 7500000
I250212 | I250212009 | FDT Foundation | 810000 | 80000 |  | 80000 | 730000
I250212 | I250212010 | Infrastructure Laying - | 62850175 | 2174500 | 6772500 | 8947000 | 53903175
I250212 | I250212011 | Cable Hauling - (Aeria | 19938867.85 |  | 271344 | 271344 | 19667523.85
I250212 | I250212012 | Transportation - (Vehic | 6120000 | 143200 |  | 143200 | 5976800
I250212 | I250212013 | Tool Kit - (Access) | 300000 |  |  |  | 300000
I250212 | I250212014 | Tool Kit - (Dev.) | 225000 |  |  |  | 225000
I250212 | I250212015 | Cable prepartion Tools - | 450000 |  |  |  | 450000
I250212 | I250212016 | Splice Machine | 2384665.37 | 769746.94 |  | 769746.94 | 1614918.43
I250212 | I250212017 | Cleavers | 320000 |  |  |  | 320000
I250212 | I250212018 | VFLs | 140000 |  |  |  | 140000
I250212 | I250212019 | OTDR - For Core / FTTH b | 975000 |  |  |  | 975000
I250212 | I250212020 | PON Power Mtr. | 840000 |  |  |  | 840000
I250212 | I250212021 | CATV Transmission Equipmen | 4174065 |  |  |  | 4174065
I250212 | I250212022 | PON Cards | 4969125 |  |  |  | 4969125
I250212 | I250212023 | carry with ladder | 5000000 | 205000 | 2254000 | 2459000 | 2541000
I250212 | I250212024 | Bolan | 3900000 |  | 1949700 | 1949700 | 1950300
I250212 | I250213000 | StormFiber Expansion – Dev | 728861.3 | 728861.3 |  | 728861.3
I250213 | I250213001 | Cabinets & Accessories - | 5055036.58 | 625323.62 |  | 625323.62 | 4429712.96
I250213 | I250213002 | Consumable & Accessories | 1094730.85 | 238791.12 |  | 238791.12 | 855939.73
I250213 | I250213003 | Cables - (Feeder Access | 7144328.21 | 1484713.16 |  | 1484713.16 | 5659615.05
I250213 | I250213004 | Enclosures - (Feeder Ac | 617403.19 | 89501.36 |  | 89501.36 | 527901.83
I250213 | I250213005 | Splitters - (Access & Dis | 1709959.95 | 175183.77 |  | 175183.77 | 1534776.18
I250213 | I250213006 | Duct - (HDPE / GI with | 11399813.48 | 15413.11 |  | 15413.11 | 11384400.37
I250213 | I250213007 | Handholes - (HH / Chamb | 1892000 |  |  |  | 1892000
I250213 | I250213008 | Poles | 540000 |  |  |  | 540000
I250213 | I250213009 | FDT Foundation | 150000 |  |  |  | 150000
I250213 | I250213010 | Infrastructure Laying - | 14821023.99 | 20000 |  | 20000 | 14801023.99
I250213 | I250213011 | Cable Hauling - (Aerial | 2671082 |  |  |  | 2671082
I250213 | I250213012 | Building Attachments - | 30000 |  |  |  | 30000
I250213 | I250213013 | Transportation - (Vehic | 1500000 |  |  |  | 1500000
I250213 | I250213014 | Tool Kit - (Access) | 150000 | 46470 |  | 46470 | 103530
I250213 | I250213015 | Tool Kit - (Dev.) | 133333.34 |  |  |  | 133333.34
I250213 | I250213016 | Cable prepartion Tools - | 300000 |  |  |  | 300000
I250213 | I250213017 | Splice Machine | 1600000 |  |  |  | 1600000
I250213 | I250213018 | Cleavers | 160000 |  |  |  | 160000
I250213 | I250213019 | VFLs | 80000 |  |  |  | 80000
I250213 | I250213020 | OTDR - For Core / FTTH b | 950000 |  |  |  | 950000
I250213 | I250213021 | PON Power Mtr. | 480000 |  |  |  | 480000
I250213 | I250213022 | CATV Transmission Equipmen | 3208635 |  |  |  | 3208635
I250213 | I250213023 | PON Card | 709875 |  |  |  | 709875
I250213 | I250213024 | Carry with Ladder | 2500000 | 274000 | 2254000 | 2528000 | 28000.00-
I250213 | I250298000 | StormFiber Expansion – Dev | 12515292.49 | 12515292.49 |  | 12515292.49
I250298 | I250298001 | Cabinets & Accessories - | 10712833.2 | 214336.58 |  | 214336.58 | 10498496.62
I250298 | I250298002 | Consumable & Accessories | 1658850 | 1408196.09 |  | 1408196.09 | 250653.91
I250298 | I250298003 | Cables - (Feeder Access | 17353741.92 | 3689615.09 |  | 3689615.09 | 13664126.83
I250298 | I250298004 | Enclosures - (Feeder Ac | 1237933.36 | 33775.12 |  | 33775.12 | 1204158.24
I250298 | I250298005 | Splitters - (Access & Dis | 3383603.4 | 23998.36 |  | 23998.36 | 3359605.04
I250298 | I250298006 | Duct - (HDPE / GI with | 6093027.3 | 36403.64 |  | 36403.64 | 6056623.66
I250298 | I250298007 | Handholes - (HH / Chamb | 1496000 |  |  |  | 1496000
I250298 | I250298008 | FDT Foundation | 63853.57 | 40000 |  | 40000 | 23853.57
I250298 | I250298009 | Infrastructure Laying - | 16450000 |  | 16450000 | 16450000
I250298 | I250298010 | Cable Hauling - (Aerial | 5498043 |  | 1800000 | 1800000 | 3698043
I250298 | I250298011 | Building Attachments - | 5605999.76 |  |  |  | 5605999.76
I250298 | I250298012 | Transportation - (Vehic | 1125000 |  |  |  | 1125000
I250298 | I250307000 | StormFiber Expansion-DKTCC | 75387481.45 | 75387481.45 |  | 75387481.45
I250307 | I250307001 | Cabinets & Accessories - | 78629750 |  |  |  | 78629750
I250307 | I250307002 | Consumable & Accessories | 18531525 |  |  |  | 18531525
I250307 | I250307003 | Cables - (Feeder Access | 62868432.88 |  |  |  | 62868432.88
I250307 | I250307004 | Enclosures - (Feeder Ac | 15541942.2 |  |  |  | 15541942.2
I250307 | I250307005 | Splitters - (Access & Dis | 16866196 |  |  |  | 16866196
I250307 | I250307006 | Duct - (HDPE / GI with | 108775007.54 | 11913725.39 | 68977.48 | 11982702.87 | 96792304.67
I250307 | I250307007 | Handholes - (HH / Chamb | 3210999.21 |  | 82333.16 | 82333.16 | 3128666.05
I250307 | I250307008 | FDT Foundation | 225000 |  |  |  | 225000
I250307 | I250307009 | Infrastructure Laying - | 42874175.36 | 23306777.62 | 4037466.86 | 27344244.48 | 15529930.88
I250307 | I250307010 | Cable Hauling - (Aerial | 23740711.08 | 1773480 |  | 1773480 | 21967231.08
I250307 | I250307011 | Building Attachments - | 71344696.8 | 311642 |  | 311642 | 71033054.8
I250307 | I250307012 | Tool Kit - (Access) | 375000 | 254080 |  | 254080 | 120920
I250307 | I250307013 | Tool Kit - (Dev.) | 240000 |  |  |  | 240000
I250307 | I250307014 | Cable prepartion Tools - | 450000 |  |  |  | 450000
I250307 | I250307015 | Splice Machine | 2400000 |  |  |  | 2400000
I250307 | I250307016 | Cleavers | 640000 |  |  |  | 640000
I250307 | I250307017 | VFLs | 160000 |  |  |  | 160000
I250307 | I250307018 | OTDR - For Core / FTTH b | 5524999.97 |  |  |  | 5524999.97
I250307 | I250307019 | PON Power Mtr. | 960000 |  |  |  | 960000
I250307 | I250307020 | CATV Transmission Equipmen | 2885000 |  |  |  | 2885000
I250307 | I250326000 | StormFiber Expansion – Ask | 12898820.18 | 12944820.18 |  | 12944820.18 | 46000.00-
I250326 | I250326001 | Cabinets & Accessories - | 2162444.23 | 40763.5 |  | 40763.5 | 2121680.73
I250326 | I250326002 | Consumable & Accessories | 402150 | 123906.62 |  | 123906.62 | 278243.38
I250326 | I250326003 | Cables - (Feeder Access | 2312990.01 | 363906.79 |  | 363906.79 | 1949083.22
I250326 | I250326004 | Enclosures - (Feeder Acc | 78263.38 | 19832.1 |  | 19832.1 | 58431.28
I250326 | I250326005 | Splitters - (Access & Dist | 557576.4 | 10090.97 |  | 10090.97 | 547485.43
I250326 | I250326006 | Duct - (HDPE / GI with C | 3823847.48 | 4549.26 |  | 4549.26 | 3819298.22
I250326 | I250326007 | Handholes - (HH / Chambe | 1672000 |  |  |  | 1672000
I250326 | I250326008 | FDT Foundation | 75000 |  |  |  | 75000
I250326 | I250326009 | Infrastructure Laying - | 440444.78 |  |  |  | 440444.78
I250326 | I250326010 | Cable Hauling - (Aerial | 971933.85 |  |  |  | 971933.85
I250326 | I250326011 | Building Attachments - ( | 523000 |  |  |  | 523000
I250326 | I250326012 | Transportation - (Vehicl | 540000 |  |  |  | 540000
I250326 | I250326013 | Tool Kit - (Access) | 75000 |  |  |  | 75000
I250326 | I250326014 | Cleavers | 80000 |  |  |  | 80000
I250326 | I250326015 | VFLs | 20000 |  |  |  | 20000
I250326 | I250326016 | PON Power Mtr. | 120000 |  |  |  | 120000
I250326 | I250326017 | PON Card | 695375 |  |  |  | 695375
I250326 | I250326018 | Carry | 2500000 |  |  |  | 2500000
I250326 | I250327000 | StormFiber Expansion – Dev | 29427064.36 | 29427064.36 |  | 29427064.36
I250327 | I250327001 | Cabinets & Accessories - | 39408342.71 | 1149530.83 |  | 1149530.83 | 38258811.88
I250327 | I250327002 | Consumable & Accessories | 7294700 | 21300.92 |  | 21300.92 | 7273399.08
I250327 | I250327003 | Cables - (Feeder Access | 33848033.66 | 2951833.32 |  | 2951833.32 | 30896200.34
I250327 | I250327004 | Enclosures - (Feeder Acc | 4960090.44 | 16277.45 |  | 16277.45 | 4943812.99
I250327 | I250327005 | Splitters - (Access & Dist | 14135870.99 | 156461.71 |  | 156461.71 | 13979409.28
I250327 | I250327006 | Duct - (HDPE / GI with C | 123429636.41 | 2873524.88 |  | 2873524.88 | 120556111.53
I250327 | I250327007 | Handholes - (HH / Chambe | 45228000 | 55500 |  | 55500 | 45172500
I250327 | I250327008 | FDT Foundation | 265275.81 |  |  |  | 265275.81
I250327 | I250327009 | Infrastructure Laying - | 174983237 | 9113250.48 | 40263277.83 | 49376528.31 | 125606708.69
I250327 | I250327010 | Cable Hauling - (Aerial | 8552208.87 | 590000 |  | 590000 | 7962208.87
I250327 | I250327011 | Building Attachments - ( | 40862250 | 1058280 |  | 1058280 | 39803970
I250327 | I250327012 | Transportation - (Vehicl | 8075000 |  |  |  | 8075000
I250327 | I250327013 | Tool Kit - (Access) | 450000 |  |  |  | 450000
I250327 | I250327014 | Tool Kit - (Dev.) | 480000 |  |  |  | 480000
I250327 | I250327015 | Cable prepartion Tools - | 900000 |  |  |  | 900000
I250327 | I250327016 | Splice Machine | 3200000 | 751924.86 |  | 751924.86 | 2448075.14
I250327 | I250327017 | Cleavers | 480000 |  |  |  | 480000
I250327 | I250327018 | VFLs | 240000 |  |  |  | 240000
I250327 | I250327019 | PON Power Mtr. | 1440000 |  |  |  | 1440000
I250327 | I250327020 | CATV Transmission Equipmen | 3908007.5 |  |  |  | 3908007.5
I250327 | I250327021 | OLT | 1947050 |  |  |  | 1947050
I250327 | I250327022 | PON Cards | 9735250 |  |  |  | 9735250
I250327 | I250327023 | Switch | 834450 |  |  |  | 834450
I250327 | I250327024 | Uplink SFPs for POP connec | 72597.15 |  |  |  | 72597.15
I250327 | I250327025 | OLT connectivity SFPs Mult | 24199.05 | 16081.75 |  | 16081.75 | 8117.3
I250327 | I250327026 | Carry | 10000000 |  |  |  | 10000000
I250327 | I250327027 | Bolan | 3600000 |  |  |  | 3600000
I250327 | I250374001 | Cabinets & Accessories - | 243000 |  |  |  | 243000
I250374 | I250374002 | Consumable & Accessories | 20430 |  |  |  | 20430
I250374 | I250374003 | Cables - (Feeder Access | 614999.7 |  |  |  | 614999.7
I250374 | I250374004 | Enclosures - (Feeder Ac | 17500 |  |  |  | 17500
I250374 | I250374005 | Splitters - (Access & Dis | 135000 |  |  |  | 135000
I250374 | I250374006 | Cable Hauling - (Aeria | 434000 |  |  |  | 434000
I250374 | I250375001 | Cabinets & Accessories - | 6827000 |  |  |  | 6827000
I250375 | I250375002 | Consumable & Accessories | 1344100 |  |  |  | 1344100
I250375 | I250375003 | Cables - (Feeder Access | 8369153.6 |  |  |  | 8369153.6
I250375 | I250375004 | Enclosures - (Feeder Ac | 805800 |  |  |  | 805800
I250375 | I250375005 | Splitters - (Access & Dis | 2413432.73 |  |  |  | 2413432.73
I250375 | I250375006 | Duct - (HDPE / GI with | 12879222.65 |  |  |  | 12879222.65
I250375 | I250375007 | Handholes - (HH / Chamb | 2214000 |  |  |  | 2214000
I250375 | I250375008 | FDT Foundation | 125000 |  |  |  | 125000
I250375 | I250375009 | Infrastructure Laying - | 16493059.73 | 11893750 | 640000 | 12533750 | 3959309.73
I250375 | I250375010 | Cable Hauling - (Aerial | 2698989.71 |  |  |  | 2698989.71
I250375 | I250375011 | Building Attachments - | 2618000 |  |  |  | 2618000
I250375 | I250375012 | Transportation - (Vehic | 750000 |  |  |  | 750000
I250375 | I250375013 | Tool Kit - (Access) | 225000 |  |  |  | 225000
I250375 | I250375014 | Tool Kit - (Dev.) | 50000 |  |  |  | 50000
I250375 | I250375015 | Cable preparation Tools | 150000 |  |  |  | 150000
I250375 | I250375016 | Splice Machine | 800000 |  |  |  | 800000
I250375 | I250375017 | Cleavers | 160000 |  |  |  | 160000
I250375 | I250375018 | VFLs | 60000 |  |  |  | 60000
I250375 | I250375019 | PON Power Mtr. | 360000 |  |  |  | 360000
I250375 | I250375020 | EDFA | 945200 | 894755.6 |  | 894755.6 | 50444.4
I250375 | I250375021 | PON Cards | 2502000 |  |  |  | 2502000
I250375 | I250375022 | Bolan | 5000000 |  |  |  | 5000000
I250375 | I250376001 | Cabinets & Accessories - | 35065000 | 1074919.55 |  | 1074919.55 | 33990080.45
I250376 | I250376002 | Consumable & Accessories | 6908300 | 74032.38 |  | 74032.38 | 6834267.62
I250376 | I250376003 | Cables - (Feeder Access | 68660060.35 | 870328.95 |  | 870328.95 | 67789731.4
I250376 | I250376004 | Enclosures - (Feeder Ac | 6240400 | 304636.82 |  | 304636.82 | 5935763.18
I250376 | I250376005 | Splitters - (Access & Dis | 15112710 | 648487.39 |  | 648487.39 | 14464222.61
I250376 | I250376006 | Duct - (HDPE / GI with | 140414796.34 | 53092.08 |  | 53092.08 | 140361704.26
I250376 | I250376007 | Handholes - (HH / Chamb | 31272000 | 374500 | 462500 | 837000 | 30435000
I250376 | I250376008 | FDT Foundation | 450000 |  |  |  | 450000
I250376 | I250376009 | Infrastructure Laying - | 200056203.18 | 28087535 | 1660540 | 29748075 | 170308128.18
I250376 | I250376010 | Cable Hauling - (Aerial | 19360681.06 | 26160 | 9000 | 35160 | 19325521.06
I250376 | I250376011 | Building Attachments - | 17159000 | 44000 | 4200 | 48200 | 17110800
I250376 | I250376012 | Transportation - (Vehic | 2712500 |  |  |  | 2712500
I250376 | I250376013 | Tool Kit - (Access) | 1125000 | 328780 |  | 328780 | 796220
I250376 | I250376014 | Tool Kit - (Dev.) | 300000 |  |  |  | 300000
I250376 | I250376015 | Cable preparation Tools | 900000 |  |  |  | 900000
I250376 | I250376016 | Splice Machine | 4800000 | 737898 |  | 737898 | 4062102
I250376 | I250376017 | Cleavers | 1200000 |  |  |  | 1200000
I250376 | I250376018 | VFLs | 420000 |  |  |  | 420000
I250376 | I250376019 | OTDR - For Core / FTTH b | 4350000 |  |  |  | 4350000
I250376 | I250376020 | PON Power Mtr. | 2520000 |  |  |  | 2520000
I250376 | I250376021 | CATV Transmission Equipmen | 5031800 |  |  |  | 5031800
I250376 | I250376022 | OLT | 1946000 |  |  |  | 1946000
I250376 | I250376023 | PON Cards | 12510000 |  |  |  | 12510000
I250376 | I250376024 | Switch | 834000 |  |  |  | 834000
I250376 | I250376025 | OLT connectivity SFPs Mult | 32248 | 30773.26 |  | 30773.26 | 1474.74
I250376 | I250376026 | Uplink SFPs for POP connec | 96744 |  |  |  | 96744
I250376 | I250376027 | Carry | 6000000 |  |  |  | 6000000
I250376 | I250376028 | Bolan | 10000000 |  |  |  | 10000000
I250376 | I250377000 | StormFiber Expansion – New | 41030648.34 | 41030648.34 |  | 41030648.34
I250377 | I250377001 | Cabinets & Accessories - | 18588920.44 | 542110.93 |  | 542110.93 | 18046809.51
I250377 | I250377002 | Consumable & Accessories | 4130700 | 1598265.73 |  | 1598265.73 | 2532434.27
I250377 | I250377003 | Cables - (Feeder Access | 30413868.4 | 6261087.49 |  | 6261087.49 | 24152780.91
I250377 | I250377004 | Enclosures - (Feeder Ac | 2682938.79 | 62808.53 |  | 62808.53 | 2620130.26
I250377 | I250377005 | Splitters - (Access & Dis | 6789809.71 | 105858.88 |  | 105858.88 | 6683950.83
I250377 | I250377006 | Duct - (HDPE / GI with | 34974948.35 | 372387.37 |  | 372387.37 | 34602560.98
I250377 | I250377007 | Handholes - (HH / Chamb | 6700000 |  |  |  | 6700000
I250377 | I250377008 | Poles | 1720000 |  | 120000 | 120000 | 1600000
I250377 | I250377009 | FDT Foundation | 400000 |  |  |  | 400000
I250377 | I250377010 | Infrastructure Laying - | 47296436 | 20000 | 6650000 | 6670000 | 40626436
I250377 | I250377011 | Cable Hauling - (Aerial | 9665724.57 |  |  |  | 9665724.57
I250377 | I250377012 | Building Attachments - | 1666500 |  |  |  | 1666500
I250377 | I250377013 | Transportation - (Vehic | 4775000 |  |  |  | 4775000
I250377 | I250377014 | Tool Kit - (Access) | 375000 | 344214.98 |  | 344214.98 | 30785.02
I250377 | I250377015 | Tool Kit - (Dev.) | 150000 |  |  |  | 150000
I250377 | I250377016 | Cable preparation Tools | 450000 | 3124.98 |  | 3124.98 | 446875.02
I250377 | I250377017 | Splice Machine | 2400000 | 3585.05 |  | 3585.05 | 2396414.95
I250377 | I250377018 | Cleavers | 400000 | 57000 |  | 57000 | 343000
I250377 | I250377019 | VFLs | 160000 |  |  |  | 160000
I250377 | I250377020 | OTDR - For Core / FTTH bo | 750000 | 365000 |  | 365000 | 385000
I250377 | I250377021 | PON Power Mtr. | 960000 |  |  |  | 960000
I250377 | I250377022 | CATV Transmission Equipmen | 3141400 | 920190.14 |  | 920190.14 | 2221209.86
I250377 | I250377023 | PON Cards | 4170000 |  |  |  | 4170000
I250377 | I250377024 | Carry | 6000000 |  |  |  | 6000000
I250377 | I250377025 | Bolan | 5000000 |  |  |  | 5000000
I250377 | I250378001 | Cabinets & Accessories - | 10610000 | 2106106.21 |  | 2106106.21 | 8503893.79
I250378 | I250378002 | Consumable & Accessories | 2184500 |  |  |  | 2184500
I250378 | I250378003 | Cables - (Feeder Access | 18405651.92 | 3881631.69 |  | 3881631.69 | 14524020.23
I250378 | I250378004 | Enclosures - (Feeder Ac | 1227800 |  |  |  | 1227800
I250378 | I250378005 | Splitters - (Access & Dis | 1575600 |  |  |  | 1575600
I250378 | I250378006 | Duct - (HDPE / GI with | 31695408.9 | 8207480.23 |  | 8207480.23 | 23487928.67
I250378 | I250378007 | Handholes - (HH / Chamb | 4680000 |  |  |  | 4680000
I250378 | I250378008 | FDT Foundation | 200000 | 116702.26 |  | 116702.26 | 83297.74
I250378 | I250378009 | Infrastructure Laying - | 32354991.37 | 2250000 |  | 2250000 | 30104991.37
I250378 | I250378010 | Cable Hauling - (Aerial | 3451847.36 | 22200 |  | 22200 | 3429647.36
I250378 | I250378011 | Building Attachments - | 980000 |  |  |  | 980000
I250378 | I250378012 | Transportation - (Vehic | 750000 |  |  |  | 750000
I250378 | I250378013 | Tool Kit - (Access) | 375000 | 317120 |  | 317120 | 57880
I250378 | I250378014 | Tool Kit - (Dev.) | 160000 |  |  |  | 160000
I250378 | I250378015 | Cable preparation Tools | 300000 |  |  |  | 300000
I250378 | I250378016 | Splice Machine | 1600000 |  |  |  | 1600000
I250378 | I250378017 | Cleavers | 480000 | 40187.49 |  | 40187.49 | 439812.51
I250378 | I250378018 | VFLs | 120000 |  |  |  | 120000
I250378 | I250378019 | OTDR - For Core / FTTH bo | 750000 | 365000 |  | 365000 | 385000
I250378 | I250378020 | PON Power Mtr. | 960000 |  |  |  | 960000
I250378 | I250378021 | CATV Transmission Equipmen | 3141400 |  |  |  | 3141400
I250378 | I250378022 | PON Cards | 4170000 |  |  |  | 4170000
I250378 | I250378023 | Carry | 6000000 |  |  |  | 6000000
I250378 | I250378024 | Bolan | 5000000 |  |  |  | 5000000
I250378 | I250379001 | Cabinets & Accessories - | 3866000 |  |  |  | 3866000
I250379 | I250379002 | Consumable & Accessories | 728850 |  |  |  | 728850
I250379 | I250379003 | Cables - (Feeder Access | 7640501.82 |  |  |  | 7640501.82
I250379 | I250379004 | Enclosures - (Feeder Ac | 557900 |  |  |  | 557900
I250379 | I250379005 | Splitters - (Access & Dis | 1361520 |  |  |  | 1361520
I250379 | I250379006 | Duct - (HDPE / GI with | 13704594.88 |  |  |  | 13704594.88
I250379 | I250379007 | Handholes - (HH / Chamb | 5456000 |  |  |  | 5456000
I250379 | I250379008 | FDT Foundation | 60000 |  |  |  | 60000
I250379 | I250379009 | Infrastructure Laying - | 9142403.1 |  |  |  | 9142403.1
I250379 | I250379010 | Cable Hauling - (Aerial | 1654271.04 |  |  |  | 1654271.04
I250379 | I250379011 | Building Attachments - | 2457000 |  |  |  | 2457000
I250379 | I250379012 | Transportation - (Vehic | 600000 |  |  |  | 600000
I250379 | I250379013 | Tool Kit - (Access) | 150000 |  |  |  | 150000
I250379 | I250379014 | Tool Kit - (Dev.) | 80000 |  |  |  | 80000
I250379 | I250379015 | Cable preparation Tools | 150000 |  |  |  | 150000
I250379 | I250379016 | Splice Machine | 800000 |  |  |  | 800000
I250379 | I250379017 | Cleavers | 160000 |  |  |  | 160000
I250379 | I250379018 | VFLs | 60000 |  |  |  | 60000
I250379 | I250379019 | PON Power Mtr. | 360000 |  |  |  | 360000
I250379 | I250379020 | CATV Transmission Equipmen | 945200 |  |  |  | 945200
I250379 | I250379021 | PON Cards | 834000 |  |  |  | 834000
I250379 | I250379022 | Bolan | 2500000 |  |  |  | 2500000
I250379 | I250380000 | StormFiber Expansion – Gul | 115955842.07 | 115955842.06 |  | 115955842.06 | 0.01
I250380 | I250380001 | Cabinets & Accessories - | 10838243.57 | 2257877 | 1192500 | 3450377 | 7387866.57
I250380 | I250380002 | Consumable & Accessories | 2832591.14 | 323443.19 |  | 323443.19 | 2509147.95
I250380 | I250380003 | Cables - (Feeder Access | 18980263.31 | 4804040.86 |  | 4804040.86 | 14176222.45
I250380 | I250380004 | Enclosures - (Feeder Ac | 2173975.35 | 236463.37 |  | 236463.37 | 1937511.98
I250380 | I250380005 | Splitters - (Access & Dis | 5297368.45 | 126648.48 |  | 126648.48 | 5170719.97
I250380 | I250380006 | Duct - (HDPE / GI with | 26696808.79 |  |  |  | 26696808.79
I250380 | I250380007 | FDT Foundation | 217672.16 |  |  |  | 217672.16
I250380 | I250380008 | Infrastructure Laying - | 90435693.32 |  | 17650000 | 17650000 | 72785693.32
I250380 | I250380009 | Cable Hauling - (Aerial | 6690707.79 | 162250 | 2087750 | 2250000 | 4440707.79
I250380 | I250380010 | Building Attachments - | 3658100 | 36000 |  | 36000 | 3622100
I250380 | I250380011 | Tool Kit - (Access) | 675000 | 219295.38 |  | 219295.38 | 455704.62
I250380 | I250380012 | Tool Kit - (Dev.) | 189758.86 | 106224.85 |  | 106224.85 | 83534.01
I250380 | I250380013 | Cable prepartion Tools - | 596270.19 |  |  |  | 596270.19
I250380 | I250380014 | Splice Machine | 3200000 |  |  |  | 3200000
I250380 | I250380015 | Cleavers | 720000 | 99000 |  | 99000 | 621000
I250380 | I250380016 | VFLs | 280000 |  |  |  | 280000
I250380 | I250380017 | OTDR - For Core / FTTH b | 1900000 |  |  |  | 1900000
I250380 | I250380018 | PON Power Mtr. | 1680000 |  |  |  | 1680000
I250380 | I250380019 | CATV Transmission Equipmen | 3141400 | 1789511.2 |  | 1789511.2 | 1351888.8
I250380 | I250380020 | PON Cards | 5004000 |  |  |  | 5004000
I250380 | I250380021 | Bolan | 15000000 |  |  |  | 15000000
I250380 | I250681001 | Cabinets & Accessories - | 6495000 | 1728145.82 |  | 1728145.82 | 4766854.18
I250681 | I250681002 | Consumable & Accessories | 1116750 | 725703.41 |  | 725703.41 | 391046.59
I250681 | I250681003 | Cables - (Feeder Access | 13784561.01 | 4569827.31 |  | 4569827.31 | 9214733.7
I250681 | I250681004 | Enclosures - (Feeder Ac | 898199.68 | 252198.36 |  | 252198.36 | 646001.32
I250681 | I250681005 | Splitters - (Access & Dis | 2453027.22 | 412102.3 |  | 412102.3 | 2040924.92
I250681 | I250681006 | Duct - (HDPE / GI with | 19198376.12 | 3203482.83 |  | 3203482.83 | 15994893.29
I250681 | I250681007 | Handholes - (HH / Chamb | 4444000 |  |  |  | 4444000
I250681 | I250681008 | Poles | 270000 |  |  |  | 270000
I250681 | I250681009 | FDT Foundation | 120000 |  |  |  | 120000
I250681 | I250681010 | Infrastructure Laying - | 31332348.04 | 1500000 |  | 1500000 | 29832348.04
I250681 | I250681011 | Cable Hauling - (Aerial | 2541870 |  |  |  | 2541870
I250681 | I250681012 | Transportation - (Vehic | 540000 |  |  |  | 540000
I250681 | I250681013 | Tool Kit - (Access) | 150000 | 144000 |  | 144000 | 6000
I250681 | I250681014 | Tool Kit - (Dev.) | 64000 |  |  |  | 64000
I250681 | I250681015 | Cable prepartion Tools | 150000 |  |  |  | 150000
I250681 | I250681016 | Splice Machine | 800000 |  |  |  | 800000
I250681 | I250681017 | Cleavers | 160000 |  |  |  | 160000
I250681 | I250681018 | VFLs | 60000 |  |  |  | 60000
I250681 | I250681019 | PON Power Mtr. | 360000 |  |  |  | 360000
I250681 | I250681020 | CATV Transmission Equipme | 952170 |  |  |  | 952170
I250681 | I250681021 | PON Cards | 4200750 |  |  |  | 4200750
I250681 | I250681022 | Carry | 5000000 |  |  |  | 5000000
I250681 | I250734001 | Cabinets & Accessories - | 38912000 | 275229.22 |  | 275229.22 | 38636770.78
I250734 | I250734002 | Consumable & Accessories | 5263450 | 271877.11 |  | 271877.11 | 4991572.89
I250734 | I250734003 | Cables - (Feeder Access | 35882683.62 | 4328229.08 |  | 4328229.08 | 31554454.54
I250734 | I250734004 | Enclosures - (Feeder Ac | 4984508.49 | 267066.32 |  | 267066.32 | 4717442.17
I250734 | I250734005 | Splitters - (Access & Dis | 14033389.92 | 476932.64 |  | 476932.64 | 13556457.28
I250734 | I250734006 | Duct - (HDPE / GI with | 33519464.4 | 9438694.21 |  | 9438694.21 | 24080770.19
I250734 | I250734007 | Handholes - (HH / Chamb | 8404000 |  |  |  | 8404000
I250734 | I250734008 | FDT Foundation | 700000 | 128715.65 |  | 128715.65 | 571284.35
I250734 | I250734009 | Infrastructure Laying - | 52774994.49 |  |  |  | 52774994.49
I250734 | I250734010 | Cable Hauling - (Aerial | 11737570.5 |  |  |  | 11737570.5
I250734 | I250734011 | Building Attachments - | 4752013.98 |  |  |  | 4752013.98
I250734 | I250734012 | Transportation - (Vehic | 4025000 |  |  |  | 4025000
I250734 | I250734013 | Tool Kit - (Access) | 600000 | 264000 |  | 264000 | 336000
I250734 | I250734014 | Tool Kit - (Dev.) | 320000 |  |  |  | 320000
I250734 | I250734015 | Cable prepartion Tools - | 600000 |  |  |  | 600000
I250734 | I250734016 | Splice Machine | 3200000 |  |  |  | 3200000
I250734 | I250734017 | Cleavers | 720000 |  |  |  | 720000
I250734 | I250734018 | VFLs | 240000 |  |  |  | 240000
I250734 | I250734019 | OTDR - For Core / FTTH b | 750000 |  |  |  | 750000
I250734 | I250734020 | PON Power Mtr. | 1440000 |  |  |  | 1440000
I250734 | I250734021 | CATV Transmission Equipmen | 2978331.75 |  |  |  | 2978331.75
I250734 | I250734022 | OLT | 2240400 |  |  |  | 2240400
I250734 | I250734023 | PON Cards | 9801750 |  |  |  | 9801750
I250734 | I250734024 | Switch | 840150 |  |  |  | 840150
I250734 | I250734025 | Cdarry with ladder | 12000000 | 5868066 | 6912000 | 12780066 | 780066.00-
I250734 | I250734026 | Bolan | 5000000 |  |  |  | 5000000
I250734 | I250737001 | Cabinets & Accessories - | 19730000 | 54587.34 |  | 54587.34 | 19675412.66
I250737 | I250737002 | Consumable & Accessories | 3039620 |  |  |  | 3039620
I250737 | I250737003 | Cables - (Feeder Access | 31713706.02 |  |  |  | 31713706.02
I250737 | I250737004 | Enclosures - (Feeder Ac | 2939101.2 |  |  |  | 2939101.2
I250737 | I250737005 | Splitters - (Access & Dis | 7217064.8 |  |  |  | 7217064.8
I250737 | I250737006 | Duct - (HDPE / GI with | 64945432.56 | 9866906.79 |  | 9866906.79 | 55078525.77
I250737 | I250737007 | Handholes - (HH / Chamb | 26158000 |  |  |  | 26158000
I250737 | I250737008 | FDT Foundation | 300000 |  |  |  | 300000
I250737 | I250737009 | Infrastructure Laying - | 205420087.5 | 14884375 | 21250000 | 36134375 | 169285712.5
I250737 | I250737010 | Cable Hauling - (Aerial | 7694939.6 |  |  |  | 7694939.6
I250737 | I250737011 | Building Attachments - | 5630000 |  |  |  | 5630000
I250737 | I250737012 | Transportation - (Vehic | 1620000 |  |  |  | 1620000
I250737 | I250737013 | Tool Kit - (Access) | 450000 | 201220 |  | 201220 | 248780
I250737 | I250737014 | Tool Kit - (Dev.) | 220000 |  |  |  | 220000
I250737 | I250737015 | Cable prepartion Tools - | 300000 |  |  |  | 300000
I250737 | I250737016 | Splice Machine | 1600000 |  |  |  | 1600000
I250737 | I250737017 | Cleavers | 480000 |  |  |  | 480000
I250737 | I250737018 | VFLs | 200000 |  |  |  | 200000
I250737 | I250737019 | OTDR - For Core / FTTH b | 1725000 |  |  |  | 1725000
I250737 | I250737020 | PON Power Mtr. | 1200000 |  |  |  | 1200000
I250737 | I250737021 | CATV Transmission Equipmen | 1904340 |  |  |  | 1904340
I250737 | I250737022 | OLT | 2240400 |  |  |  | 2240400
I250737 | I250737023 | PON Cards | 5601000 |  |  |  | 5601000
I250737 | I250737024 | Bolan | 10000000 |  |  |  | 10000000
I250737 | I260060001 | Cabinets & Accessories - | 1087000 |  |  |  | 1087000
I260060 | I260060002 | Consumable & Accessories | 184200 |  |  |  | 184200
I260060 | I260060003 | Cables - (Feeder Access | 6009356.25 |  |  |  | 6009356.25
I260060 | I260060004 | Enclosures - (Feeder Ac | 207400 |  |  |  | 207400
I260060 | I260060005 | Splitters - (Access & Dis | 396450 |  |  |  | 396450
I260060 | I260060006 | Duct - (HDPE / GI with | 4167352 | 4579223.52 |  | 4579223.52 | 411871.52-
I260060 | I260060007 | Handholes - (HH / Chamb | 1936000 |  |  |  | 1936000
I260060 | I260060008 | FDT Foundation | 25000 |  |  |  | 25000
I260060 | I260060009 | Infrastructure Laying - | 1217360 | 1200000 |  | 1200000 | 17360
I260060 | I260060010 | Cable Hauling - (Aerial | 627900 |  |  |  | 627900
I260060 | I260060011 | Building Attachments - | 144000 |  |  |  | 144000
I260060 | I260060012 | Transportation - (Vehic | 90000 |  |  |  | 90000
I260060 | I260060013 | EDFA | 970190 |  |  |  | 970190
I260060 | I260060014 | PON Cards | 2140125 |  |  |  | 2140125
I260060 | I260060015 | Switch | 856050 |  |  |  | 856050
I260060 | I260060016 | Optical Switch Transmitte | 1155667.5 |  |  |  | 1155667.5
I260060 | I260060017 | Tool Kits Clever Power | 590000 |  |  |  | 590000
I260060 | I260060018 | DEV: Tool Kits Cable pre | 1175000 |  |  |  | 1175000
I260060 | I260061001 | Cabinets & Accessories - | 7097000 | 839140.82 |  | 839140.82 | 6257859.18
I260061 | I260061002 | Consumable & Accessories | 1314950 | 122338.05 |  | 122338.05 | 1192611.95
I260061 | I260061003 | Cables - (Feeder Access | 11526644.72 | 2262946.67 |  | 2262946.67 | 9263698.05
I260061 | I260061004 | Enclosures - (Feeder Ac | 1134000 | 83915.27 |  | 83915.27 | 1050084.73
I260061 | I260061005 | Splitters - (Access & Dis | 4707644.71 | 200756.74 |  | 200756.74 | 4506887.97
I260061 | I260061006 | Duct - (HDPE / GI with | 24755935.74 | 12474042.61 |  | 12474042.61 | 12281893.13
I260061 | I260061007 | Handholes - (HH / Chamb | 4026000 |  |  |  | 4026000
I260061 | I260061008 | Poles | 1830000 |  |  |  | 1830000
I260061 | I260061009 | FDT Foundation | 450000 |  |  |  | 450000
I260061 | I260061010 | Infrastructure Laying - | 33122884.34 | 1647400 |  | 1647400 | 31475484.34
I260061 | I260061011 | Cable Hauling - (Aerial | 6584588.26 |  |  |  | 6584588.26
I260061 | I260061012 | Transportation - (Vehic | 1300000 | 5820 |  | 5820 | 1294180
I260061 | I260061013 | Tool Kit - (Access) | 300000 | 41820 |  | 41820 | 258180
I260061 | I260061014 | Tool Kit - (Dev.) | 160000 |  |  |  | 160000
I260061 | I260061015 | Cable prepartion Tools - | 300000 | 134276.54 |  | 134276.54 | 165723.46
I260061 | I260061016 | Splice Machine | 1600000 |  |  |  | 1600000
I260061 | I260061017 | Cleavers | 320000 |  |  |  | 320000
I260061 | I260061018 | VFLs | 120000 |  |  |  | 120000
I260061 | I260061019 | PON Power Mtr. | 720000 |  |  |  | 720000
I260061 | I260061020 | CATV Transmission Equipmen | 970190 |  |  |  | 970190
I260061 | I260061021 | Bolan | 3200000 | 399048.00- | 3145485 | 2746437 | 453563
I260061 | I260061022 | Carry with ladder | 6000000 |  |  |  | 6000000
I260061 | I260061023 | PON Cards | 3566875 |  |  |  | 3566875
I260061 | I260068000 | GPON Infra Storm DHA Dev. | 122623933.02 | 122623933.02 |  | 122623933.02
I260068 | I260068001 | Cabinets & Accessories - | 66020875.64 |  |  |  | 66020875.64
I260068 | I260068002 | Consumable & Accessories | 13031011.53 | 83103.22 |  | 83103.22 | 12947908.31
I260068 | I260068003 | Cables - (Feeder Access | 125580515.42 | 2317240.39 |  | 2317240.39 | 123263275.03
I260068 | I260068004 | Enclosures - (Feeder Ac | 11743510.39 | 25483.09 |  | 25483.09 | 11718027.3
I260068 | I260068005 | Splitters - (Access & Dis | 30438774.1 | 1232983.25- |  | 1232983.25- | 31671757.35
I260068 | I260068006 | Duct - (HDPE / GI with | 92101459.18 | 14718092.47 |  | 14718092.47 | 77383366.71
I260068 | I260068007 | Handholes - (HH / Chamb | 138495874.65 |  |  |  | 138495874.65
I260068 | I260068008 | FDT Foundation | 680000 |  |  |  | 680000
I260068 | I260068009 | Infrastructure Laying - | 1076003802.33 | 11604773 | 67338000 | 78942773 | 997061029.33
I260068 | I260068010 | Cable Hauling - (Aerial | 46316472.5 |  |  |  | 46316472.5
I260068 | I260068011 | Building Attachments - | 47277544.59 |  |  |  | 47277544.59
I260068 | I260068012 | Transportation - (Vehic | 18725000 | 15000 |  | 15000 | 18710000
I260068 | I260068013 | Tool Kit - (Access) | 900000 | 123420 |  | 123420 | 776580
I260068 | I260068014 | Tool Kit - (Dev.) | 560000 |  |  |  | 560000
I260068 | I260068015 | Cable prepartion Tools - | 1050000 |  |  |  | 1050000
I260068 | I260068016 | Splice Machine | 4800000 |  |  |  | 4800000
I260068 | I260068017 | Cleavers | 960000 |  |  |  | 960000
I260068 | I260068018 | VFLs | 380000 |  |  |  | 380000
I260068 | I260068019 | OTDR - For Core / FTTH b | 2700000 |  |  |  | 2700000
I260068 | I260068020 | PON Power Mtr. | 2280000 |  |  |  | 2280000
I260068 | I260068021 | CATV Transmission Equipmen | 7162285 |  |  |  | 7162285
I260068 | I260068022 | Bolan | 22500000 |  | 19786410 | 19786410 | 2713590
I260068 | I260068023 | OLT | 2282800 |  |  |  | 2282800
I260068 | I260068024 | PON Cards | 14267500 |  |  |  | 14267500
I260068 | I260068025 | Switch | 856050 |  |  |  | 856050
I260068 | I260068026 | OLT connectivity SFPs Mult | 33100.6 |  |  |  | 33100.6
I260068 | I260068027 | Uplink SFPs for POP connec | 99301.8 |  |  |  | 99301.8
I260068 | I260105001 | Cabinets & Accessories - | 9524000 |  |  |  | 9524000
I260105 | I260105002 | Consumable & Accessories | 1629900 |  |  |  | 1629900
I260105 | I260105003 | Cables - (Feeder Access | 9866484.34 |  |  |  | 9866484.34
I260105 | I260105004 | Enclosures - (Feeder Ac | 1462600.36 |  |  |  | 1462600.36
I260105 | I260105005 | Splitters - (Access & Dis | 3895533.9 |  |  |  | 3895533.9
I260105 | I260105006 | Duct - (HDPE / GI with | 21439862.72 |  |  |  | 21439862.72
I260105 | I260105007 | Handholes - (HH / Chamb | 12320000 |  |  |  | 12320000
I260105 | I260105008 | FDT Foundation | 150000 |  |  |  | 150000
I260105 | I260105009 | Infrastructure Laying - | 54150094.46 |  |  |  | 54150094.46
I260105 | I260105010 | Cable Hauling - (Aerial | 2886984 |  |  |  | 2886984
I260105 | I260105011 | Building Attachments - | 1338000 |  |  |  | 1338000
I260105 | I260105012 | Transportation - (Vehic | 1260000 |  |  |  | 1260000
I260105 | I260105013 | Tool Kit - (Access) | 75000 |  |  |  | 75000
I260105 | I260105014 | Tool Kit - (Dev.) | 80000 |  |  |  | 80000
I260105 | I260105015 | Cable prepartion Tools - | 150000 |  |  |  | 150000
I260105 | I260105016 | Splice Machine | 800000 |  |  |  | 800000
I260105 | I260105017 | Cleavers | 160000 |  |  |  | 160000
I260105 | I260105018 | VFLs | 40000 |  |  |  | 40000
I260105 | I260105019 | PON Power Mtr | 240000 |  |  |  | 240000
I260105 | I260105020 | CATV Transmission Equipmen | 970190 |  |  |  | 970190
I260105 | I260159001 | Cabinets & Accessories - | 6400000 |  |  |  | 6400000
I260159 | I260159002 | Consumable & Accessories | 864300 | 135.13 |  | 135.13 | 864164.87
I260159 | I260159003 | Cables - (Feeder Access | 6148072.02 | 1127564.08 |  | 1127564.08 | 5020507.94
I260159 | I260159004 | Enclosures - (Feeder Ac | 769599.6 | 18109.32 |  | 18109.32 | 751490.28
I260159 | I260159005 | Splitters - (Access & Dis | 2132039.4 |  |  |  | 2132039.4
I260159 | I260159006 | Duct - (HDPE / GI with | 9359735.04 | 3692667.06 |  | 3692667.06 | 5667067.98
I260159 | I260159007 | Handholes - (HH / Cham | 6028000 |  |  |  | 6028000
I260159 | I260159008 | FDT Foundation | 50000 |  |  |  | 50000
I260159 | I260159009 | Infrastructure Laying - | 23667930 | 5400000 | 14850000 | 20250000 | 3417930
I260159 | I260159010 | Cable Hauling - (Aerial | 2065815 |  |  |  | 2065815
I260159 | I260159011 | Building Attachments - | 8483000 |  |  |  | 8483000
I260159 | I260159012 | Transportation - (Vehic | 960000 |  |  |  | 960000
I260159 | I260159013 | OTDR - For Core / FTTH b | 750000 |  |  |  | 750000
I260159 | I260159014 | CATV Transmission Equipmen | 960330 |  |  |  | 960330
I260159 | I260159015 | PON Cards | 1412250 |  |  |  | 1412250
I260159 | I260159016 | Access Tool Kits | 75000 |  |  |  | 75000
I260159 | I260159017 | Dev Tool Kits | 80000 |  |  |  | 80000
I260159 | I260159018 | PON Meters | 240000 |  |  |  | 240000
I260159 | I260159019 | Clever | 160000 |  |  |  | 160000
I260159 | I260159020 | VFL | 50000 |  |  |  | 50000
I260159 | I260159021 | Cable prepration Tools (Ca | 150000 |  |  |  | 150000
I260159 | I260159022 | Splicing Machine | 1600000 |  |  |  | 1600000
I260159 | I260160001 | Cabinets & Accessories | 27221000 |  |  |  | 27221000
I260160 | I260160002 | Consumable & Accessories | 4059550 |  |  |  | 4059550
I260160 | I260160003 | Cables - (Feeder Acces | 27040142.48 |  |  |  | 27040142.48
I260160 | I260160004 | Enclosures - (Feeder A | 3338105.4 |  |  |  | 3338105.4
I260160 | I260160005 | Splitters - (Access & Di | 8439306.84 |  |  |  | 8439306.84
I260160 | I260160006 | Duct - (HDPE / GI with | 51629595.46 | 11660755.37 |  | 11660755.37 | 39968840.09
I260160 | I260160007 | Handholes - (HH / Cham | 36014000 |  |  |  | 36014000
I260160 | I260160008 | Poles | 2820000 | 8800 |  | 8800 | 2811200
I260160 | I260160009 | FDT Foundation | 175000 |  |  |  | 175000
I260160 | I260160010 | Infrastructure Laying | 110334585 | 7135294 | 15556000 | 22691294 | 87643291
I260160 | I260160011 | Cable Hauling - (Aeria | 10156685 |  |  |  | 10156685
I260160 | I260160012 | Building Attachments - | 6412993.44 |  |  |  | 6412993.44
I260160 | I260160013 | Transportation - (Vehi | 1620000 |  |  |  | 1620000
I260160 | I260160014 | Tool Kit - (Access) | 375000 |  |  |  | 375000
I260160 | I260160015 | Tool Kit - (Dev.) | 240000 |  |  |  | 240000
I260160 | I260160016 | Cable prepartion Tools | 450000 |  |  |  | 450000
I260160 | I260160017 | Splice Machine | 2400000 |  |  |  | 2400000
I260160 | I260160018 | Cleavers | 400000 |  |  |  | 400000
I260160 | I260160019 | VFLs | 200000 |  |  |  | 200000
I260160 | I260160020 | PON Power Mtr. | 960000 |  |  |  | 960000
I260160 | I260160021 | CATV Transmission Equipme | 2880990 |  |  |  | 2880990
I260160 | I260160022 | OTDR A | 1500000 |  |  |  | 1500000
I260160 | I260160023 | OTDR B | 950000 |  |  |  | 950000
I260160 | I260160024 | Bolan | 10000000 |  |  |  | 10000000
I260160 | I260160025 | Carry with ladder | 3000000 |  |  |  | 3000000
I260160 | I260160026 | PON Cards | 7061250 |  |  |  | 7061250
I260160 | I260179001 | Cabinets & Accessories | 1595000 |  |  |  | 1595000
I260179 | I260179002 | Consumable & Accessories | 351650 |  |  |  | 351650
I260179 | I260179003 | Cables - (Feeder Acces | 4155729.5 |  |  |  | 4155729.5
I260179 | I260179004 | Enclosures - (Feeder A | 288000 |  |  |  | 288000
I260179 | I260179005 | Splitters - (Access & Di | 556320 |  |  |  | 556320
I260179 | I260179006 | Duct - (HDPE / GI with | 1014000 | 175384.52 |  | 175384.52 | 838615.48
I260179 | I260179007 | Handholes - (HH / Cham | 1774000 |  |  |  | 1774000
I260179 | I260179008 | FDT Foundation | 25000 |  |  |  | 25000
I260179 | I260179009 | Infrastructure Laying | 1692187.5 | 70000 |  | 70000 | 1622187.5
I260179 | I260179010 | Cable Hauling - (Aeria | 1381047.5 |  |  |  | 1381047.5
I260179 | I260179011 | Building Attachments - | 426000 |  |  |  | 426000
I260179 | I260180001 | Cabinets & Accessories | 16784000 |  |  |  | 16784000
I260180 | I260180002 | Consumable & Accessories | 2562450 |  |  |  | 2562450
I260180 | I260180003 | Cables - (Feeder Acces | 29648578.5 |  |  |  | 29648578.5
I260180 | I260180004 | Enclosures - (Feeder A | 2337600 |  |  |  | 2337600
I260180 | I260180005 | Splitters - (Access & Di | 6502950 |  |  |  | 6502950
I260180 | I260180006 | Duct - (HDPE / GI with | 17492743.03 | 5734786.98 |  | 5734786.98 | 11757956.05
I260180 | I260180007 | Handholes - (HH / Cham | 3014000 |  |  |  | 3014000
I260180 | I260180008 | Poles | 300000 |  |  |  | 300000
I260180 | I260180009 | FDT Foundation | 150000 |  |  |  | 150000
I260180 | I260180010 | Infrastructure Laying | 26601040 | 500000 |  | 500000 | 26101040
I260180 | I260180011 | Cable Hauling - (Aeria | 8320005 |  |  |  | 8320005
I260180 | I260180012 | Building Attachments - | 775500 |  |  |  | 775500
I260180 | I260180013 | Transportation - (Vehi | 2640000 |  |  |  | 2640000
I260180 | I260180014 | Tool Kit - (Access) | 375000 |  |  |  | 375000
I260180 | I260180015 | Tool Kit - (Dev.) | 240000 |  |  |  | 240000
I260180 | I260180016 | Cable prepartion Tools | 450000 |  |  |  | 450000
I260180 | I260180017 | Splice Machine | 2400000 |  |  |  | 2400000
I260180 | I260180018 | Cleavers | 400000 |  |  |  | 400000
I260180 | I260180019 | VFLs | 160000 |  |  |  | 160000
I260180 | I260180020 | PON Power Mtr. | 960000 |  |  |  | 960000
I260180 | I260180021 | CATV Transmission Equipme | 2880990 |  |  |  | 2880990
I260180 | I260180022 | OTDR A | 1500000 |  |  |  | 1500000
I260180 | I260180023 | OTDR B | 950000 |  |  |  | 950000
I260180 | I260180024 | PON Cards | 7061250 |  |  |  | 7061250
I260180 | I260180025 | carry with ladder | 9000000 |  |  |  | 9000000
I260180 | I260180026 | Bolan | 5000000 |  |  |  | 5000000
I260180 | I260180027 | Vehicles Transportation | 750000 |  |  |  | 750000
I260180 | I260208001 | Cabinets & Accessories | 17320000 |  |  |  | 17320000
I260208 | I260208002 | Consumable & Accessories | 2515040 |  |  |  | 2515040
I260208 | I260208003 | Cables - (Feeder Acces | 13720734.69 |  |  |  | 13720734.69
I260208 | I260208004 | Enclosures - (Feeder A | 2430000 |  |  |  | 2430000
I260208 | I260208005 | Splitters - (Access & Di | 5416020 |  |  |  | 5416020
I260208 | I260208006 | Duct - (HDPE / GI with | 34979480.78 |  |  |  | 34979480.78
I260208 | I260208007 | Handholes - (HH / Cham | 19668000 |  |  |  | 19668000
I260208 | I260208008 | FDT Foundation | 150000 |  |  |  | 150000
I260208 | I260208009 | Infrastructure Laying | 74639494.34 |  |  |  | 74639494.34
I260208 | I260208010 | Cable Hauling - (Aeria | 5979017.19 |  |  |  | 5979017.19
I260208 | I260208011 | Building Attachments - | 7850000 |  |  |  | 7850000
I260208 | I260208012 | Transportation - (Vehi | 2725000 |  |  |  | 2725000
I260208 | I260208013 | Tool Kit - (Access) | 225000 | 107220 |  | 107220 | 117780
I260208 | I260208014 | Tool Kit - (Dev.) | 320000 |  |  |  | 320000
I260208 | I260208015 | Cable prepartion Tools | 150000 |  |  |  | 150000
I260208 | I260208016 | Splice Machine | 2400000 |  |  |  | 2400000
I260208 | I260208017 | Cleavers | 320000 |  |  |  | 320000
I260208 | I260208018 | VFLs | 75000 |  |  |  | 75000
I260208 | I260208019 | OTDR - For Core / FTTH | 950000 |  |  |  | 950000
I260208 | I260208020 | PON Power Mtr. | 840000 |  |  |  | 840000
I260208 | I260208021 | CATV Transmission Equipme | 1920660 |  |  |  | 1920660
I260208 | I260208022 | PON Cards | 2824500 |  |  |  | 2824500
I260208 | I260208023 | Bolan | 5000000 |  |  |  | 5000000
I260208 | I260208024 | Car Transportation | 300000 |  |  |  | 300000
I260208 | I260294001 | Cabinets & Accessories | 4895000 |  |  |  | 4895000
I260294 | I260294002 | Consumable & Accessories | 850000 |  |  |  | 850000
I260294 | I260294003 | Cables - (Feeder Acces | 5164351.73 |  |  |  | 5164351.73
I260294 | I260294004 | Enclosures - (Feeder A | 797100 |  |  |  | 797100
I260294 | I260294005 | Splitters - (Access & Di | 1973625.54 |  |  |  | 1973625.54
I260294 | I260294006 | Duct - (HDPE / GI with | 7276642.24 |  |  |  | 7276642.24
I260294 | I260294007 | Handholes - (HH / Cham | 1364000 |  |  |  | 1364000
I260294 | I260294008 | Poles | 270000 |  |  |  | 270000
I260294 | I260294009 | FDT Foundation | 75000 |  |  |  | 75000
I260294 | I260294010 | Infrastructure Laying | 13826260.43 |  |  |  | 13826260.43
I260294 | I260294011 | Cable Hauling - (Aeria | 1687609.69 |  |  |  | 1687609.69
I260294 | I260294012 | Building Attachments - | 2920000 |  |  |  | 2920000
I260294 | I260294013 | Transportation - (Vehi | 510000 |  |  |  | 510000
I260294 | I260294014 | Tool Kit - (Access) | 225000 | 204000 |  | 204000 | 21000
I260294 | I260294015 | Tool Kit - (Dev.) | 80000 |  |  |  | 80000
I260294 | I260294016 | Cable prepartion Tools | 150000 |  |  |  | 150000
I260294 | I260294017 | Splice Machine | 800000 |  |  |  | 800000
I260294 | I260294018 | Cleavers | 240000 |  |  |  | 240000
I260294 | I260294019 | VFLs | 80000 |  |  |  | 80000
I260294 | I260294020 | PON Power Mtr. | 480000 |  |  |  | 480000
I260294 | I260294021 | CATV Transmission Equipme | 960330 |  |  |  | 960330
I260294 | I260294022 | PON Cards | 1412250 |  |  |  | 1412250
I260294 | I260294023 | Carry with ladder | 3000000 |  |  |  | 3000000
I260294 | I260295001 | Cabinets & Accessories | 52927000 | 84024.22 |  | 84024.22 | 52842975.78
I260295 | I260295002 | Consumable & Accessories | 8621700 |  |  |  | 8621700
I260295 | I260295003 | Cables - (Feeder Acces | 59123947.12 | 494771.4 |  | 494771.4 | 58629175.72
I260295 | I260295004 | Enclosures - (Feeder A | 7570592.82 |  |  |  | 7570592.82
I260295 | I260295005 | Splitters - (Access & Di | 20111436 |  |  |  | 20111436
I260295 | I260295006 | Duct - (HDPE / GI with | 77174097.11 |  |  |  | 77174097.11
I260295 | I260295007 | Handholes - (HH / Cham | 18260000 |  |  |  | 18260000
I260295 | I260295008 | Poles | 2820000 |  |  |  | 2820000
I260295 | I260295009 | FDT Foundation | 875000 |  | 25000 | 25000 | 850000
I260295 | I260295010 | Infrastructure Laying - | 146658744.34 | 301600 |  | 301600 | 146357144.34
I260295 | I260295011 | Cable Hauling - (Aerial | 17919324.62 |  |  |  | 17919324.62
I260295 | I260295012 | Building Attachments - | 9996000 |  |  |  | 9996000
I260295 | I260295013 | Transportation - (Vehic | 4315000 |  |  |  | 4315000
I260295 | I260295014 | Tool Kit - (Access) | 900000 | 81840 |  | 81840 | 818160
I260295 | I260295015 | Tool Kit - (Dev.) | 560000 |  |  |  | 560000
I260295 | I260295016 | Cable prepartion Tools | 1050000 |  |  |  | 1050000
I260295 | I260295017 | Splice Machine | 5600000 |  |  |  | 5600000
I260295 | I260295018 | Cleavers | 960000 |  |  |  | 960000
I260295 | I260295019 | VFLs | 360000 |  |  |  | 360000
I260295 | I260295020 | OTDR - For Core / FTTH | 3399999.99 |  |  |  | 3399999.99
I260295 | I260295021 | PON Power Mtr. | 2160000 |  |  |  | 2160000
I260295 | I260295022 | CATV Transmission Equipme | 4024912.5 |  |  |  | 4024912.5
I260295 | I260295023 | OLT | 2259600 |  |  |  | 2259600
I260295 | I260295024 | PON Cards | 11298000 |  |  |  | 11298000
I260295 | I260295025 | Switch | 847350 |  |  |  | 847350
I260295 | I260295026 | OLT connectivity SFPs Mult | 32764.2 |  |  |  | 32764.2
I260295 | I260295027 | Uplink SFPs for POP connec | 98292.6 |  |  |  | 98292.6
I260295 | I260295028 | carry with ladder | 24000000 |  |  |  | 24000000
I260295 | I260295029 | Bolan | 12500000 |  |  |  | 12500000
I260295 | I260296001 | Cabinets & Accessories - | 32652000 |  |  |  | 32652000
I260296 | I260296002 | Consumable & Accessories | 5350350 |  |  |  | 5350350
I260296 | I260296003 | Cables - (Feeder Access | 46966809.57 |  |  |  | 46966809.57
I260296 | I260296004 | Enclosures - (Feeder Ac | 4929398.15 |  |  |  | 4929398.15
I260296 | I260296005 | Splitters - (Access & Dis | 11548971.06 |  |  |  | 11548971.06
I260296 | I260296006 | Duct - (HDPE / GI with | 49528536.77 | 10878217.86 |  | 10878217.86 | 38650318.91
I260296 | I260296007 | Handholes - (HH / Chamb | 8382000 |  |  |  | 8382000
I260296 | I260296008 | Poles | 2250000 |  |  |  | 2250000
I260296 | I260296009 | FDT Foundation | 550000 |  |  |  | 550000
I260296 | I260296010 | Infrastructure Laying - | 84036880 | 9000 |  | 9000 | 84027880
I260296 | I260296011 | Cable Hauling - (Aerial | 16486524 |  |  |  | 16486524
I260296 | I260296012 | Building Attachments - | 4267999.23 |  |  |  | 4267999.23
I260296 | I260296013 | Transportation - (Vehic | 5400000 | 162321 |  | 162321 | 5237679
I260296 | I260296014 | Tool Kit - (Access) | 750000 |  |  |  | 750000
I260296 | I260296015 | Tool Kit - (Dev.) | 320000 |  |  |  | 320000
I260296 | I260296016 | Cable prepartion Tools - | 600000 |  |  |  | 600000
I260296 | I260296017 | Splice Machine | 3200000 |  |  |  | 3200000
I260296 | I260296018 | Cleavers | 800000 |  |  |  | 800000
I260296 | I260296019 | VFLs | 280000 |  |  |  | 280000
I260296 | I260296020 | OTDR - For Core / FTTH b | 3399999.99 |  |  |  | 3399999.99
I260296 | I260296021 | PON Power Mtr. | 1680000 |  |  |  | 1680000
I260296 | I260296022 | CATV Transmission Equipmen | 5055855 |  |  |  | 5055855
I260296 | I260296023 | OLT | 2259600 |  |  |  | 2259600
I260296 | I260296024 | PON Cards | 7061250 |  |  |  | 7061250
I260296 | I260296025 | Switch | 847350 |  |  |  | 847350
I260296 | I260296026 | OLT connectivity SFPs Mult | 32764.2 |  |  |  | 32764.2
I260296 | I260296027 | Uplink SFPs for POP connec | 98292.6 |  |  |  | 98292.6
I260296 | I260296028 | Carry with Ladder | 12000000 |  |  |  | 12000000
I260296 | I260296029 | Bolan | 5000000 |  |  |  | 5000000
I260296 | I260298000 | GPON Infra Storm Petaro Ga | 6183042.98 | 6183042.98 |  | 6183042.98
I260298 | I260298001 | Cabinets & Accessories | 982266.73 | 305277.15 |  | 305277.15 | 676989.58
I260298 | I260298002 | Consumable & Accessories | 209300 | 141795.9 |  | 141795.9 | 67504.1
I260298 | I260298003 | Cables - (Feeder Acces | 503031.56 | 406429.55 |  | 406429.55 | 96602.01
I260298 | I260298004 | Enclosures - (Feeder A | 147966.69 | 20590.1 |  | 20590.1 | 127376.59
I260298 | I260298005 | Splitters - (Access & Di | 211260.15 | 24528.81 |  | 24528.81 | 186731.34
I260298 | I260298006 | Duct - (HDPE / GI with | 1.12 | 2640.78- |  | 2640.78- | 2641.9
I260298 | I260298007 | Handholes - (HH / Cham | 1012000 |  |  |  | 1012000
I260298 | I260298008 | Poles | 210000 |  |  |  | 210000
I260298 | I260298009 | FDT Foundation | 25000 |  |  |  | 25000
I260298 | I260298010 | Infrastructure Laying | 1 |  |  |  | 1
I260298 | I260298011 | Cable Hauling - (Aeria | 594192.09 | 352020 |  | 352020 | 242172.09
I260298 | I260298012 | Building Attachments - | 684000 |  |  |  | 684000
I260298 | I260298013 | Transportation - (Vehi | 175000 | 3600 |  | 3600 | 171400
I260298 | I260361001 | Cabinets & Accessories - | 21353000 |  |  |  | 21353000
I260361 | I260361002 | Consumable & Accessories | 2583050 |  |  |  | 2583050
I260361 | I260361003 | Cables - (Feeder Access | 26007927.86 |  |  |  | 26007927.86
I260361 | I260361004 | Enclosures - (Feeder Ac | 2382000.29 |  |  |  | 2382000.29
I260361 | I260361005 | Splitters - (Access & Dis | 9789928.66 |  |  |  | 9789928.66
I260361 | I260361006 | Duct - (HDPE / GI with | 39503873.99 | 2583860.51 |  | 2583860.51 | 36920013.48
I260361 | I260361007 | Handholes - (HH / Chamb | 29326000 |  |  |  | 29326000
I260361 | I260361008 | FDT Foundation | 375000 |  |  |  | 375000
I260361 | I260361009 | Infrastructure Laying - | 138860279.55 | 2700000 |  | 2700000 | 136160279.55
I260361 | I260361010 | Cable Hauling - (Aerial | 9391110 |  |  |  | 9391110
I260361 | I260361011 | Building Attachments - | 11339002.72 |  |  |  | 11339002.72
I260361 | I260361012 | Transportation - (Vehic | 3600000 |  |  |  | 3600000
I260361 | I260361013 | Tool Kit - (Access) | 375000 |  |  |  | 375000
I260361 | I260361014 | Tool Kit - (Dev.) | 240000 |  |  |  | 240000
I260361 | I260361015 | Cable preparation Tools | 450000 |  |  |  | 450000
I260361 | I260361016 | Splice Machine | 2400000 |  |  |  | 2400000
I260361 | I260361017 | Cleavers | 400000 |  |  |  | 400000
I260361 | I260361018 | VFLs | 160000 |  |  |  | 160000
I260361 | I260361019 | OTDR - For Core / FTTH b | 1500000 |  |  |  | 1500000
I260361 | I260361020 | PON Power Mtr. | 960000 |  |  |  | 960000
I260361 | I260361021 | CATV Transmission Equipmen | 1920660 |  |  |  | 1920660
I260361 | I260361022 | OLT | 2259600 |  |  |  | 2259600
I260361 | I260361023 | PON Cards | 4236750 |  |  |  | 4236750
I260361 | I260361024 | OLT connectivity SFPs Mult | 32764.2 |  |  |  | 32764.2
I260361 | I260361025 | Uplink SFPs for POP connec | 98292.6 |  |  |  | 98292.6
I260361 | I260361026 | Carry with ladder | 3000000 |  |  |  | 3000000
I260361 | I260361027 | Bolan | 9600000 |  |  |  | 9600000
I260361 | I260361028 | Transportation | 600000 |  |  |  | 600000
INT-21-00315 | INT-21-00315 | StormFiber Expansion - G | 736015039 | 283234406.96 | 20434080 | 303668486.96 | 432346552.04
INT-23-00435 | INT-23-00435 | Local-New-StormFiber Exp | 118313906 | 77881903.39 | 1788500 | 79670403.39 | 38643502.61
INT-23-00436 | INT-23-00436 | Local-New-StormFiber Exp | 51381436 | 17417582.61 | 582780 | 18000362.61 | 33381073.39
INT-23-00437 | INT-23-00437 | Local-New-StormFiber Exp | 198839603 | 42295320.28 | 4063200 | 46358520.28 | 152481082.72
INT-23-00438 | INT-23-00438 | Local-New-StormFiber Exp | 13320912 | 121795.99 |  | 121795.99 | 13199116.01
INT-23-00439 | INT-23-00439 | Local-New-StormFiber Exp | 482055980 | 190240587.93 | 7085900 | 197326487.93 | 284729492.07
INT-23-00440 | INT-23-00440 | Local-New-StormFiber Exp | 53663375 | 4688155.21 |  | 4688155.21 | 48975219.79
INT-23-00441 | INT-23-00441 | Local-New-StormFiber Ex | 124440455 | 20306046.74 |  | 20306046.74 | 104134408.26
INT-23-00442 | INT-23-00442 | Local-New-StormFiber Exp | 42564738 | 2854816.24 |  | 2854816.24 | 39709921.76
INT-23-00444 | INT-23-00444 | Local-New-StormFiber Exp | 181805960 | 195619264.95 | 3094390 | 198713654.95 | 16907694.95-
INT-23-00445 | INT-23-00445 | Local-New-StormFiber Exp | 39164547 | 40582736.6 | 389524 | 40972260.6 | 1807713.60-
INT-23-00446 | INT-23-00446 | Local-New-StormFiber Exp | 165172421 |  |  |  | 165172421
INT-23-00447 | INT-23-00447 | Local-New-StormFiber Exp | 213934297 | 112052637.19 | 3139540 | 115192177.19 | 98742119.81
INT-23-00764 | INT-23-00764 | StormFiber Expansion- As | 395693727 | 57769975.94 | 3301960 | 61071935.94 | 334621791.06
I240188
I240189
I240190
I240435
I240437
I240438
I240440
I240442
I240459
I240518
I240519
I240537
I240538
I240539
I240540
I240557
I240678
I240679
I240680
I240681
I240682
I240683
I240684
I240700
I240701
I240702
I240703
I240704
I240705
I240782
I250114
I250201
I250202
I250203
I250205
I250206
I250207
I250208
I250209
I250210
I250211
I250212
I250213
I250298
I250307
I250326
I250327
I250374
I250375
I250376
I250377
I250378
I250379
I250380
I250681
I250734
I250737
I260060
I260061
I260068
I260105
I260159
I260160
I260179
I260180
I260208
I260294
I260295
I260296
I260298
I260361
INT-21-00315
INT-23-00435
INT-23-00436
INT-23-00437
INT-23-00438
INT-23-00439
INT-23-00440
INT-23-00441
INT-23-00442
INT-23-00444
INT-23-00445
INT-23-00446
INT-23-00447
INT-23-00764